## Sheet1
N |  |  | 18Jul10:55-12:26 (Robert SPIRIDON) | 1306 | 204 |  |  | Origin File: DCS CELL TRACKER.xls |  |  |  |  | RBS TYPE AND CONFIGURATION | [10 empty] | SITE CONFIGURATION | [5 empty] | SITE TIPOLOGY |  |  |  |  | CW DESIGN AND IMPLEMENTATION |  |  |  | Last time update data from CW to DCS = 18Jul 11:02 |  |  |  | SITE TRACKING | [22 empty] | SITE TESTING/ INTEGRATION |  |  |  | PAC |  | ANTENNAE AND FEEDERS | [29 empty] | TRANSMISSION DESIGN |  |  | NEAR END MW EQ. CONFIGURATION | MIHAELA/ |  |  | MIHAELA/ | MIHAELA/ | MIHAELA/ | MIHAELA/ | MIHAELA/ | MIHAELA/ | MIHAELA/ | MIHAELA/ | MXU DESIGN AND INSTALLATION | MIHAELA/ | MIHAELA/ |  | MIHAELA/ | MIHAELA/ |  | TRAFFIC CONFIGURATION | MIHAELA/ | MIHAELA/ | FAR END MW EQ. CONFIGURATION |  |  | MIHAELA/ |  | Last time update data from DATA BASE to DCS = 13Jul 11:16 | MIHAELA/ | FAR END MW EQ. CONFIGURATION |  | MIHAELA/ |  |  | MIHAELA/ | MW IMPLEMENTATION | MIHAELA/ | MIHAELA/ | MIHAELA/ | [5 empty] | MIHAELA/ |  | MIHAELA/ | MIHAELA/ | E1 CONFIGURATION |  |  | MW AND RF SURVEYORS |  | REPEATER CONFIGURATION | [20 empty] | OLD SITE IMPLEM./TESTING/ INTEGRATION | [8 empty] | OLD PAC RBS | [9 empty] | MW Transfer data: 22th June, 2001, 11.30am!
65 | 1211 |  | 18Jul10:21:25-10:21:58 (Daniela VINCIOTI) | 1306 | 1310 |  | SITE LOCALISATION | [11 empty] | RBS TYPE AND CONFIGURATION-opt./old | [15 empty] | Last time update data from CW to DCS = 18Jul 10:58 | [48 empty] | ANTENNAE AND FEEDERS-OPT. | [17 empty] | DANA | MARIA | DANA | DANA | MONA | DANA | DANA | MONA | MONA | MONA | MONA | MONA | MONA | MONA | MONA | MARIA | MONA | MONA | MARIA | MONA | MONA | MW | DANA | MONA | MONA | MARIA | MARIA | DANA | MONA | DANA | DANA | MONA | MARIA | DANA | MONA | DANA | DANA | MONA | MIHAELA/MONA | MONA | MONA | MONA | WAREHOUSE | ICOM | ICOM | ICOM | ICOM | MONA | MW | MONA | MONA | MARIA | MARIA | MARIA | MARIA | MARIA | ANTENNA AND FEEDER LINK | [7 empty] | ANTENNA AND FEEDERS REMOTE/OPT. | [24 empty] | DANA | DANA | [5 empty] | A) MW Near - Far |  |  | B) MW Far - Near
PHASE | SITE TYPE | SITE CODE | SITE NAME | OBJECTIVE/CITY | CLUSTER NAME | Regions | Design coord-North | Design coord-East | Real coord-North | Real coord-East | SITE ADDRESS | OWNER/CONTACT | RBS1 | M/E1 | ORD. CDU1 | ORD TRUs1 | BBS1 | CHANGED | RBS | M/E | ORD. CDU | ORD. TRUs | BBS2 | S.C.F. | CRANE COSMOROM | CRANE SUB. | OLD S.C.F. | OLD CRANE COSMOROM | OLD CRANE COSMOROM | RBS HEIGHT [m] | TYPE | BUILDING / TOWER HEIGHT | SUPORT TYPE | SHELTER / ROOM | DESIGN | LEASE | CIVIL WORKS | START DAY | END DAY | CW STATUS | PROVISIONAL ACCEPTANCE | CW IMPL. ENGINEER | CW Check-list RECEIVED YRO | PAP RECEIVED YRO | SARF | RARF | CORF | S.Aq. | TRANSM. DESIGN LINK | TRD | P.D. | D.D.E. | Observations | ADD ORDER INSTALL. FAR END MW ANT. | RF CMD NO | RF PO TO SUB | RF INSTALL. VENDOR | RF SUB | SITE ENGINEERING | EQ. TESTED INTRAROM WAREHOUSE | RF EQ. DELIVERED TO SITE | RF INSTALL. BEGINS | RF. INSTALL. FINISHES | RF TEAM LEADER | POWER SUPPLY | INTEGR./ COMISS. ENGINEER | ESTIMATED SITE TESTING/ INTEGRATION | SITE TESTING/ INTEGRATION | SITE ACCEPT. | PAC SENT TO COSMOROM | PAC RETURNED FROM COSMOROM | A antenna | A azim. | A tilt | A magl | B antenna | B azim. | B tilt | B magl | C antenna | C azim. | C tilt | C magl | D antenna | D azim. | D tilt | D magl | Splitter/ tapper | A DX LENGTH [m] | A DX2 LENGTH [m] | A FEEDER TYPE | B DX1 LENGTH [m] | B DX2 LENGTH [m] | B FEEDER TYPE | C DX1 LENGTH [m] | C DX2 LENGTH [m] | C FEEDER TYPE | D DX1 LENGTH [m] | D DX2 LENGTH [m] | D FEEDER TYPE | TOTAL FEEDER LENGTH [m] | PATH NAME | BSC Destination | TRANSMISSION TYPE | AZ. NEAR END | ANT. NEAR END | ANT. HEIGHT NEAR END | RADIO CABLE NEAR END | RAU NEAR END | SMU | MMU NEAR END | AMM1 NEAR END | AMM2 NEAR END | AMM3 NEAR END | POWER SPLITTER | MW RACK | ID MXU1 | MXU1 DELIVERED DATE | MXU1 INVOICED | ID MXU2 | MXU2 DELIVERED DATE | MXU2 INVOICED | MW OBSERVATIONS | TRAFFIC CABLE DESIGN | TRAFFIC CABLE INSTALLED | TRAFFIC CONFIGURATION | SITE CODE FAR END | SITE NAME FAR END | AZ. FAR END | ANT. FAR END | ANT HEIGHT FAR END | RADIO CABLE FAR END | RAU FAR END | ADDITIONAL SITE (CODE) | AZ. ADD. | ANT. ADD. | ANT HEIGHT ADD. | RADIO CABLE ADD. | RAU ADD. | MW PO NO. | MW SUB. | MW PO DATE | MW CMD NO | MW EQ. DELIVERED ON LINK | LINK INSTALL. BEGINS | LINK INSTALL. FINISHES | MW TEAM LEADER | LINK ALIGNEMENT DATE | LINK ACCEPTED | MW OBSERVATIONS | MW FILE SENT TO COSMOROM | MW FILE RETURNED FROM COSMOROM | E1 CONNECTED | OBS | E1 CONNECTION DATE | MW SURVEYOR | RF SURVEYOR | Repeater TYPE | SITE CODE LINK(RF) | ANT. LINK | Azim. LINK | Tilt LINK | Magl. LINK | DX LINK LENGTH [m] | FEEDER TYPE_LINK | ANT. SERVICE_A | Azim. SERVICE_A | Tilt SERVICE_A | Magl. SERVICE_A | ANT. SERVICE_B | Azim. SERVICE_B | Tilt SERVICE_B | Magl. SERVICE_B | DXA LENGTH [m] | FEEDER TYPE_A | DXB LENGTH [m] | FEEDER TYPE_B | SPLITTER TYPE | OLD RF SITE ENGINEERING | OLD RF CMD NO | OLD RF PO TO SUB | OLD RF INSTALL. VENDOR | OLD RF SUB | OLD RF INSTALL. FINISHES | INTEGR./ COMISS. ENGINEER OLD RBS | SITE TESTING/ INTEGRATION OLD RBS | SITE ACCEPT. OLD RBS | PAC SENT TO COSMOROM OLD RBS | PAC RETURNED FROM COSMOROM OLD RBS | Terrain Height [m] | Location | County | MSC | EXTENSION MSC | BSC TRC | REMOTE BSC | EXTENSION BSC | Install | Double | MW in DCS no: | Install | Double | MW in DCS no: | E.O.U.D.
Phase_2 | CS | BA001 | UNIREA | Iasi(11+2) | BA031 Independentei_RTC | Moldova | 47 10 00.2 | 27 34 50.2 | 47 09 55.2 | 27 34 44 | Piata Unirii nr.11 | Asociatia de proprietari Unirea Iasi/Varna Octav - pres. Asoc., Piata Unirii nr.11 Et.4 Ap.27, 032/ 113 031 | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-10-11 | N/A | N/A |  |  |  | 29 | B | 31.8 | Stalpi de arhitectura existenti | Room | PROTELCO | OK | IMSAT | 2000-09-04 | 2000-09-16 | YesV | 2000-10-10 | Doru | 2000-11-22 | 2000-10-13 |  |  |  | 2000-07-24 | 2000-07-10 |  | 2000-07-24 | 2000-08-08 |  |  |  | 2000-09-27 | YRO | TRY | 2000-09-27 | 2000-09-27 | 2000-09-28 | 2000-09-29 | 2000-10-01 |  | Yes | Cristian Croitor | 2001-02-28 | 2001-01-10 | 2001-01-10 | 2001-01-22 | 2001-01-26 | K 739 494 | 80 | 0 | 29.5 | K 739 494 | 200 | 0 | 29.5 | K 739 494 | 320 | 0 | 29.5 |  |  |  |  | N/A | 42 | 42 | 7/8" | 22 | 22 | 7/8" | 42 | 42 | 7/8" |  |  |  | 202 | ML 23 E 1+0 | Baneasa | MW | 345 | 0.6 | 30 | 45 | 23/58 |  |  | 2U-3 |  |  |  | N/A | [9 empty] | 1 | BA031 | INDEPENDENTEI_RTC | 166 | 0.6 | 32.5 | 30 | 23/56 | [6 empty] | 6 | TRYLON | 2000-09-27 | 243 | 2001-09-27 | 2000-09-28 | 2000-10-01 | OK | OK | 2001-01-10 |  | 2001-01-22 | 2001-01-22 | 30N01 Iasi-Baneasa |  | OK | George IFRIM | George IFRIM | [32 empty] | 81 | Iasi | Iasi | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BA002 | HOTEL MOLDOVA | Iasi(11+2) | BA030 Podul Ros_RTC | Moldova | 47 09 32.5 | 27 35 18.1 | 47 09 32.6 | 27 35 17.8 | Str. Anastasie Panu nr.29, Hotel Moldova | Hotel Moldova/Hotel Moldova - 032/ 142 225 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-10-11 | Yes | N/A |  |  |  | 46 | B | 46 | C3.5m+C3.5m+C3.5m | N/A | PROTELCO | OK | IMSAT | 2000-08-01 | 2000-09-15 | YesV | 2000-09-27 | Doru | 2000-10-03 | 2000-09-29 |  |  |  | 2000-06-22 | 2000-06-15 |  | 2000-07-03 | 2000-07-18 |  |  |  | 2000-10-03 | YRO | TRY | 2000-10-03 | 2000-10-03 | 2000-10-04 | 2000-10-06 | 2000-10-07 |  | Yes | Cristian Croitor | 2001-02-28 | 2001-01-10 | 2001-01-10 | 2001-01-16 | 2001-01-26 | K 739 494 | 80 | 0 | 47.3 | K 739 494 | 200 | 0 | 47.3 | K 739 494 | 320 | 0 | 47.3 |  |  |  |  | N/A | 11 | 11 | 7/8" | 20 | 20 | 7/8" | 33 | 33 | 7/8" |  |  |  | 128 | ML 23 E 1+0 | Baneasa | MW | 186 | 0.6 | 47 | 20 | 23/56 |  |  | 2U-3 |  |  |  | RBS | [9 empty] | 1 | BA008 | PODUL ROS | 6 | 0.6 | 33.5 | 14 | 23/58 | [6 empty] | 7 | TRYLON | 2000-10-03 | 252 | 2000-10-03 | 2000-10-04 | 2000-10-07 | OK | OK | 2001-01-10 |  | 2001-01-22 | 2001-01-22 | 30N03 Iasi-Baneasa |  | 2000-12-20 | George IFRIM | George IFRIM | [32 empty] | 58 | Iasi | Iasi | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BA003 | PRIMAVERII | Iasi(11+2) | BA030 Podul Ros_RTC | Moldova | 47 09 10.3 | 27 35 57.1 | 47 09 11.2 | 27 35 57.1 | Splaiul Bahluiului nr.28 Bl.T2 | Asociatie de locatari/Stegaru Iasim - 032/ 136 480 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-10-11 | Yes | N/A |  |  |  | 32 | B | 35.2 | C4m+C4m | N/A | PROTELCO | OK | IMSAT | 2000-08-01 | 2000-09-08 | YesV | 2000-09-14 | Doru | 2000-12-18 | 2000-09-22 |  |  |  | 2000-06-22 | 2000-06-10 |  | 2000-07-03 | 2000-09-04 |  |  |  | 2000-09-27 | YRO | TRY | 2000-09-27 | 2000-09-27 | 2000-09-28 | 2000-09-29 | 2000-10-01 |  | Yes | Cristian Croitor | 2001-02-28 | 2000-12-22 | 2000-12-22 | 2001-03-02 | 2001-04-10 | K 739 494 | 80 | 0 | 37.9 | K 739 494 | 200 | 0 | 37.9 | K 739 494 | 320 | 0 | 36 |  |  |  |  | N/A | 26 | 26 | 7/8" | 26 | 26 | 7/8" | 10.5 | 10.5 | 7/8" |  |  |  | 125 | ML 23 E 1+0 | Baneasa | MW | 242 | 0.6 | 35.5 | 10.5 | 23/56 |  |  | 2U-3 |  |  |  | RBS | [9 empty] | 1 | BA008 | PODUL ROS |  | 0.6 |  |  | 23/58 | [6 empty] | 6 | TRYLON | 2000-09-27 | 242 | 2000-09-27 | 2000-09-28 | 2000-10-01 | OK | OK | 2000-12-22 |  | 2001-02-05 | 2001-02-06 | 30N05 Iasi-Baneasa |  | 2000-12-20 | George IFRIM | George IFRIM | [32 empty] | 40 | Iasi | Iasi | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BA004 | PACURARI | Iasi(11+2) | BA031 Independentei_RTC | Moldova | 47 10 26.4 | 27 32 25.4 | 47 10 30 | 27 32 29.2 | Sos. Pacurari nr.54 Bl.554 Sc.B | Asociatie de locatari/Bursuc Nicolae Et.4 ap.11 - Pres. Maftei C. Et.3 Sc.B Ap.9 | 2102 | M | C+C+C+ | 2/2/2 | N/A | ANTENNA MOVED | [5 empty] | 2000-10-11 | Yes | N/A |  |  |  | 40 | B | 43.4 | C4m+C4m | N/A | PROTELCO | OK | IMSAT | 2000-08-05 | 2000-09-15 | YesV | 2000-09-19 | Doru | 2000-11-22 | 2000-09-22 |  |  | 2001-06-27 | 2000-06-30 | 2000-06-10 |  | 2000-07-21 | 2000-08-02 |  |  |  | 2000-10-03 | YRO | TRY | 2000-10-03 | 2000-10-03 | 2000-10-04 | 2000-10-06 | 2000-10-07 | IVAN | Yes | Ion Soare | 2001-06-06 | 2001-06-06 | 2001-06-06 |  |  | K 739 494 | 70 | 0 | 44.5 | K 739 494 | 170 | 0 | 44.5 | K 739 494 | 280 | 0 | 44.5 |  |  |  |  | N/A | 15 | 15 | 7/8" | 15 | 15 | 7/8'' | 23 | 23 | 7/8'' |  |  |  | 106 | ML 23 E 1+0 | Baneasa | MW | 93 | 0.6 | 43/0.3 | 13.5 | 23/56 | [6 empty] | RBS | [9 empty] | 1 | BA005 | COPOU | 273 | 0.6 | 31.5/0.3 | 29 | 23/58 | [6 empty] | 63* | KEN-KEN | 2001-05-04 | 879 | 2001-05-04 | 2001-05-07 | 2001-05-16 | OK | OK | 2001-06-06 |  | 2001-06-19 | 2001-07-10 | 30N06 Iasi-Baneasa |  | 2001-04-15 | George IFRIM | George IFRIM | [32 empty] | 73 | Iasi | Iasi | [7 empty] | 2 |  |  | 2
Phase_2 | CS | BA005 | COPOU | Iasi(11+2) | BA031 Independentei_RTC | Moldova | 47 10 48.9 | 27 34 04.7 | 47 10 25.7 | 27 34 29.3 | Str. Berthelot nr.16 | Universitatea Alex. Ioan Cuza/Bogdan E. Plescan - Bd. Carol nr.20, 032/ 201 000 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-10-20 | Yes | N/A |  |  |  | 31.2 | B | 33.9 | T3m+T3m | N/A | PROTELCO | OK | KEN-KEN | 2001-02-01 | 2001-05-18 | YesV | 2001-06-21 | Doru |  | 2001-06-26 |  |  |  | 2000-07-20 | 2000-06-10 |  | 2000-07-20 | 2000-08-02 |  |  |  | 2001-05-04 | ICOM | KEN KEN | 2001-05-04 | 2000-11-10 | 2001-05-07 | 2001-05-18 | 2001-06-06 | IVAN | Yes | Ion Soare | 2001-06-06 | 2001-06-06 | 2001-06-06 | 2001-06-19 | 2001-07-11 | K 739 494 | 80 | 0 | 32.5 | K 739 494 | 200 | 0 | 32.5 | K 739 494 | 320 | 0 | 32 |  |  |  |  | N/A | 6 | 6 | 7/8" | 29 | 29 | 7/8" | 29 | 29 | 7/8" |  |  |  | 128 | ML 23 E 1+1* | Baneasa | MW | 160 | 0.6 | 32/0.3 | 6 | 23/58 | [6 empty] | RBS | [9 empty] | 1 | BA031 | INDEPENDENTEI_RTC | 340 | 0.6 | 32.5/0.3 | 30 | 23/56 | [6 empty] | 63* | KEN-KEN | 2001-05-04 | 883 | 2001-05-04 | 2001-05-07 | 2001-05-16 | OK | OK | 2001-06-06 |  | 2001-06-19 | 2001-07-10 | 30N06 Iasi-Baneasa |  | 2001-04-15 | George IFRIM | George IFRIM | [32 empty] | 84 | Iasi | Iasi | [7 empty] | 2 |  |  | 2
Phase_2 | CS | BA006 | ALEXANDRU CEL BUN | Iasi(11+2) | BA031 Independentei_RTC | Moldova | 47 09 40.4 | 27 33 47.5 | 47 09 47.7 | 27 33 46.1 | B-dul. Alexandru Cel Bun nr.29 Bl.X5 | Asociatie de locatari nr.5/Grecu Adam - Ap.24, 259 438 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | Yes | N/A |  |  |  | 35.5 | B | 32 | C4m+C4m+C4m | N/A | PROTELCO | OK | IMSAT | 2000-08-03 | 2000-09-16 | YesV | 2000-09-20 | Doru | 2000-11-22 | 2000-09-22 |  |  |  | 2000-07-04 | 2000-06-10 |  | 2000-07-06 | 2000-07-18 |  |  |  | 2000-09-27 | YRO | TRY | 2000-09-27 | 2000-09-27 | 2000-09-28 | 2000-09-29 | 2000-10-01 |  | Yes | Cristian Croitor | 2001-02-28 | 2001-01-11 | 2001-01-11 | 2001-01-16 | 2001-01-26 | K 739 494 | 80 | 0 | 38 | K 739 494 | 200 | 0 | 38 | K 739 494 | 320 | 0 | 37.1 |  |  |  |  | N/A | 20 | 20 | 7/8" | 14 | 14 | 7/8" | 16 | 16 | 7/8" |  |  |  | 100 | ML 23 E 1+0 | Baneasa | MW | 80 | 0.6 | 36.6 | 16 | 23/56 |  |  | 2U-3 |  |  |  | RBS | [9 empty] | 1 | BA001 | UNIREA | 259 | 0.6 | 30 | 26 | 23/58 | [6 empty] | 6 | TRYLON | 2000-09-27 | 244 | 2000-09-28 | 2000-09-28 | 2000-10-01 | OK | OK | 2001-01-11 |  | 2001-01-22 | 2001-01-22 | 30N01 Iasi-Baneasa |  | OK | George IFRIM | George IFRIM | [32 empty] | 45 | Iasi | Iasi | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BA007 | NICOLINA | Iasi(11+2) | BA030 Podul Ros_RTC | Moldova | 47 08 20.2 | 27 34 44.6 | 47 08 19.4 | 27 34 36 | Sos. Nicolina nr.14 Bl.941 | Asociatia de proprietari/Agapie Niculai - pres., Et.2, Ap.11, 032/ 221 302 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-10-11 | Yes | N/A |  |  |  | 23.8 | B | 24.05 | T4.5m+T4.5m | N/A | PROTELCO | OK | IMSAT | 2000-08-18 | 2000-09-14 | YesV | 2000-09-20 | Doru | 2000-11-22 | 2000-09-22 |  |  |  | 2000-07-20 | 2000-06-10 |  | 2000-07-20 | 2000-08-02 |  |  |  | 2000-09-27 | YRO | TRY | 2000-09-27 | 2000-09-27 | 2000-09-28 | 2000-10-01 | 2000-10-03 |  | Yes | Cristian Croitor | 2001-02-28 | 2001-01-10 | 2001-01-10 | 2001-01-16 | 2001-01-26 | K 739 494 | 80 | 0 | 27.25 | K 739 494 | 200 | 0 | 27 | K 739 494 | 320 | 0 | 27.25 |  |  |  |  | N/A | 19.5 | 19.5 | 7/8" | 6 | 6 | 7/8" | 19.5 | 19.5 | 7/8" |  |  |  | 90 | ML 23 E 1+0 | Baneasa | MW | 33 | 0.6 | 26.75 | 19 | 23/56 |  |  | 2U-3 |  |  |  | RBS | [9 empty] | 1 | BA008 | PODUL ROS | 208 | 0.6 | 33.5 | 27 | 23/58 | [6 empty] | 6 | TRYLON | 2000-09-27 | 240 | 2000-09-27 | 2000-09-28 | 2000-10-03 | IVAN | OK | 2001-01-10 |  | 2001-01-22 | 2001-01-22 | 30N04 Iasi-Baneasa |  | 2000-12-20 | George IFRIM | George IFRIM | [32 empty] | 76 | Iasi | Iasi | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BA008 | PODUL ROS | Iasi(11+2) | BA030 Podul Ros_RTC | Moldova | 47 08 53.4 | 27 35 08.9 | 47 08 53.4 | 27 35 08.9 | Aleea Nicolina nr.10 Bl.G4 | Asociatia de locatari nr.3/Fedco Constantin - parter Ap.3, 032/ 139 054 | 2102 | M/E | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-09-06 | Yes | N/A |  |  |  | 31.5 | B | 34.5 | C3m+C3m+C3m | N/A | PROTELCO | OK | IMSAT | 2000-08-03 | 2000-08-25 | YesV | 2000-08-25 | Doru | 2000-11-22 | 2000-08-30 |  |  |  | 2000-06-22 | 2000-06-10 |  | 2000-07-03 | 2000-07-14 |  |  |  | 2000-09-27 | YRO | TRY | 2000-08-31 | 2000-08-31 | 2000-09-28 | 2000-10-01 | 2000-10-03 |  | Yes | Cristian Croitor | 2001-02-28 | 2000-12-22 | 2000-12-22 | 2001-03-02 | 2001-04-10 | K 739 494 | 80 | 0 | 34 | K 739 494 | 200 | 0 | 34 | K 739 494 | 320 | 0 | 34 |  |  |  |  | N/A | 14 | 14 | 7/8" | 27 | 27 | 7/8" | 11 | 11 | 7/8" |  |  |  | 104 | ML 23 E 1+0 | Baneasa | MW | 338 | 0.6 | 33.5 | 11 | 23/58 |  |  | 4U-1 |  |  |  | RBS | [9 empty] | 1 | BA030 | PODUL ROS_RTC | 159 | 0.6 | 20 | 20 | 23/56 | [6 empty] | 7/6 | TRYLON | 3.10.00-27.09.00 | 241 | 2000-09-27 | 2000-09-28 | 2000-10-03 | IVAN | OK | 2000-12-22 |  | 2001-02-05 | 2001-02-06 | 30N04 Iasi-Baneasa |  | 2000-12-20 | George IFRIM | George IFRIM | [32 empty] | 47 | Iasi | Iasi | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BA009 | FACULTATEA MED. VETERINARA | Iasi(11+2) | BA009 Facultatea de Medicina Veterinara | Moldova | 47 11 33 | 27 33 25.6 | 47 11 38 | 27 33 24.1 | Aleea Sadoveanu nr.8, Facultatea de Medicina Veterinara | Ministerul invatamantului/Prorector Coman Ioan | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-10-13 | Yes | N/A |  |  |  | 21.55 | B | 21.55 | C6m+C6m+C6m | N/A | PROTELCO | OK | IMSAT | 2000-09-05 | 2000-10-05 | YesV | 2000-10-10 | Doru | 2000-10-12 |  |  |  |  | 2000-06-30 | 2000-06-10 |  | 2000-07-03 | 2000-07-21 |  |  |  | 2000-10-20 | ICOM | IMSAT | 2000-10-06 | 2000-10-06 | 2000-10-23 | 2000-10-25 | 2000-10-27 |  | Yes | Cristian Croitor | 2001-02-28 | 2001-01-13 | 2001-01-13 | 2001-01-16 | 2001-01-26 | K 739 494 | 80 | 0 | 26.2 | K 739 494 | 200 | 0 | 26.2 | K 739 494 | 320 | 0 | 26.2 |  |  |  |  | N/A | 17 | 17 | 7/8" | 50 | 50 | 7/8'' | 17 | 17 | 7/8'' |  |  |  | 168 | N/A | Baneasa | HDSL | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | RBS | [7 empty] | 60/2 pairs - outdoor |  |  | BSC21 | BSC BANEASA |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | HDSL+30N02 Iasi-Baneasa |  | 2001-01-08 | George IFRIM | George IFRIM | [32 empty] | 153 | Iasi | Iasi | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | BA010 | TATARASI | Iasi(11+2) | BA030 Podul Ros_RTC | Moldova | 47 09 32.4 | 27 36 30.7 | 47 09 27.9 | 27 36 36.8 | Str. Stroancea nr.30 Bl.D4B | Asociatie de locatari/Andreies Mihai - pres. Asociatie, Et.1, Ap.6, 032/ 272 052 | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-10-13 | N/A | N/A |  |  |  | 26.5 | B | 29.5 | C4m+C4m+C4m | Room | PROTELCO | OK | IMSAT | 2000-09-15 | 2000-10-11 | YesV | 2000-10-26 | Doru | 2000-11-22 | 2000-10-31 |  |  |  | 2000-06-30 | 2000-06-10 |  | 2000-07-03 | 2000-07-20 |  |  |  | 2000-10-20 | ICOM | IMSAT | 2000-10-06 | 2000-10-06 | 2000-10-23 | 2000-10-25 | 2000-10-27 |  | Yes | Cristian Croitor | 2001-02-28 | 2001-01-10 | 2001-01-10 |  |  | K 739 494 | 80 | 0 | 32 | K 739 494 | 210 | 0 | 32 | K 739 494 | 330 | 0 | 32 |  |  |  |  | N/A | 24 | 24 | 7/8" | 8 | 8 | 7/8" | 21 | 21 | 7/8" |  |  |  | 106 | ML 23 E 1+0 | Baneasa | MW | 275 | 0.6 | 31 | 8 | 23/58 |  |  | 4U-1 |  |  |  | N/A | [9 empty] | 1 | BA002 | HOTEL MOLDOVA | 95 | 0.6 | 47 | 11 | 23/56 | [6 empty] | 1 | IMSAT | 2000-10-20 | 275 | 2000-10-13 | 2000-10-14 | 2000-10-18 | RADU | OK | 2001-01-10 |  | 2001-01-22 | 2001-01-22 | 30N03 Iasi-Baneasa |  | 2000-12-20 | George IFRIM | George IFRIM | [32 empty] | 40 | Iasi | Iasi | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BA011 | BUCIUM | Iasi(11+2) | BA030 Podul Ros_RTC | Moldova | 47 08 29.6 | 27 36 01.7 | 47 08 26.4 | 27 35 59.2 | Str. Socola nr.57 Sc.C,B | Asociatie de proprietari/Dl. Sendrea Gh. | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-10-20 | Yes | N/A |  |  |  | 21 | B | 27 | C2m+C2m+C2m | N/A | PROTELCO | OK | IMSAT | 2000-09-07 | 2000-11-30 | YesV | 2001-02-15 | Doru | 2001-01-17 | 2001-02-26 |  |  |  | 2000-06-22 | 2000-06-10 |  | 2000-07-03 | 2000-08-23 |  |  |  | 2000-12-15 | ICOM | IMSAT | 2000-11-13 | 2000-12-15 | 2000-12-19 | 2001-01-16 | 2001-01-25 |  | Yes | Ion Soare | 2001-02-28 | 2001-02-22 | 2001-02-22 |  |  | K 739 494 | 80 | 0 | 25.2 | K 739 494 | 200 | 0 | 29.5 | K 739 494 | 320 | 0 | 28.2 |  |  |  |  | N/A | 15 | 15 | 7/8" | 38 | 38 | 7/8" | 15 | 15 | 7/8" |  |  |  | 136 | ML 23 E 1+0 | Baneasa | MW | 353 | 0.6 | 28.5/0.3 | 15 | 23/58 |  |  | 4U-1 |  |  |  | RBS | [9 empty] | 1 | BA003 | PRIMAVERII | 173 | 0.6 | 37.4/0.3 | 10.5 | 23/56 | [6 empty] | 19* | DIEKAT | 2001-01-24 | 274 | 2001-01-30 | 2001-01-30 | 2001-02-10 | AUREL | OK | 2001-02-22 |  | 2001-03-02 | 2001-04-06 | 30N05 Iasi-Baneasa |  | 2000-12-20 | George IFRIM | George IFRIM | [32 empty] | 54 | Iasi | Iasi | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BA012 | BACAU_RTC | Bacau(5) | BA012 Bacau_RTC | Moldova | 46 33 57.2 | 26 54 43.9 | 46 33 57.4 | 26 54 43.7 | Str. Nicolae Balcescu nr.24 | Romtelecom/Dl. Teodoru Sergiu - 034/ 104 270 | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-09-05 | N/A | N/A |  |  |  | 27 | B | 30 | 15m existing tower | Room | PROTELCO | OK | VECTOR | 2000-07-06 | 2000-07-31 | YesV | 2000-08-02 | Doru | 2000-08-18 | 2000-08-09 |  |  |  | N/A | 2000-07-05 |  | 2000-06-08 | 2000-07-05 |  |  |  | 2000-09-15 | YRO | TRY | 2000-08-22 | 2000-08-22 | 2000-09-18 | 2000-09-19 | 2000-09-21 |  | Yes | Theo Radoi | 2000-12-29 | 2000-12-22 | 2000-12-22 | 2001-02-07 | 2001-04-10 | K 739 494 | 55 | 0 | 43.3 | K 739 494 | 175 | 0 | 43.3 | K 739 494 | 295 | 0 | 43.3 |  |  |  |  | N/A | 22 | 22 | 7/8" | 22 | 22 | 7/8" | 22 | 22 | 7/8" |  |  |  | 132 | N/A | Baneasa | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | [5 empty] | 20012 | 2001-06-25 | [5 empty] | 100/Outdoor |  |  | BSC21 | BSC BANEASA | N/A | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | IVAN | OK | N/A |  | N/A | N/A | 30N01 Bacau-Baneasa |  | 2001-01-29 | George IFRIM | George IFRIM | [32 empty] | 173 | Bacau | Bacau | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | BA013 | CORNISEI | Bacau(5) | BA013 Cornisei_RTC | Moldova | 46 32 51 | 26 54 55 | 46 32 51.4 | 26 54 54.1 | Str. Marasesti nr.187 Bl.E7 | Asociatia de proprietari nr.33/Dl. Barzaghideanu Ion - Et.4, Ap.17, 152 190 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-10-20 | Yes | N/A |  |  |  | 34.3 | B | 34.3 | C2m+C2m | N/A | PROTELCO | OK | VECTOR | 2000-10-16 | 2000-10-25 | YesV | 2000-11-28 | Doru | 2000-11-15 | 2000-12-07 |  |  |  |  | 2000-07-05 |  | 2000-07-11 | 2000-09-18 |  |  |  | 2000-10-24 | ICOM | ISAF | 2000-10-23 | 2000-10-23 | 2000-10-25 | 2000-12-09 | 2000-12-12 |  | Yes | Theo Radoi | 2000-12-29 | 2000-12-23 | 2000-12-23 | 2001-02-07 | 2001-02-16 | K 739 494 | 65 | 0 | 36 | K 739 494 | 160 | 0 | 36 | K 739 494 | 305 | 0 | 36 |  |  |  |  | N/A | 12 | 12 | 7/8" | 18.5 | 18.5 | 7/8" | 12 | 12 | 7/8" |  |  |  | 85 | N/A | Baneasa | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | 4U-1 |  |  |  | RBS | 20013 | 2001-06-25 | [7 empty] | 1 | BSC21 | BSC BANEASA |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | VLAD | OK | N/A |  | N/A | N/A | 30N02 Bacau-Baneasa |  | 2001-01-29 | George IFRIM | George IFRIM | [32 empty] | 163 | Bacau | Bacau | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | BA014 | STEFAN CEL MARE | Bacau(5) | BA014 Stefan Cel Mare_RTC | Moldova | 46 34 54.6 | 26 54 41.4 | 46 34 58.6 | 26 54 43.2 | Str. Stefan cel Mare nr.25, Bl.25, sc.E | Asociatia de locatari 133/Cbucsa Adrian - Et.7, Ap.27, 034/ 182 542 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-10-11 | Yes | N/A |  |  |  | 23.5 | B | 28.5 | T4m+C3m | N/A | PROTELCO | OK | VECTOR | 2000-09-18 | 2000-09-29 | YesV | 2000-10-26 | Doru | 2000-10-05 | 2000-10-31 |  |  |  |  | 2000-07-05 |  | 2000-08-22 | 2000-09-13 |  |  |  | 2000-10-03 | YRO | TRY | 2000-10-03 | 2000-10-03 | 2000-10-04 | 2000-10-06 | 2000-10-20 |  | Yes | Theo Radoi | 2000-12-29 | 2000-12-23 | 2000-12-23 | 2001-02-07 | 2001-02-16 | K 739 494 | 75 | 0 | 27 | K 739 494 | 175 | 0 | 28 | K 739 494 | 345 | 0 | 27 |  |  |  |  | N/A | 21 | 21 | 7/8" | 15 | 15 | 7/8'' | 21 | 21 | 7/8'' |  |  |  | 114 | N/A | Baneasa | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | 4U-1 |  |  |  | RBS | 20014 | 2001-06-25 | [5 empty] | 55/ |  | 1 | BSC21 | BSC BANEASA |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | RADU | OK | N/A |  | N/A | N/A | 30N03 Bacau-Baneasa |  | 2001-01-29 | George IFRIM | George IFRIM | [32 empty] | 168 | Bacau | Bacau | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | BA015 | ENERGIEI | Bacau(5) | BA014 Stefan Cel Mare_RTC | Moldova | 46 34 11 | 26 53 57.3 | 46 34 13.3 | 26 53 48.5 | Str. Energiei nr.34 bl.34 sc.A |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-10-20 | Yes | N/A |  |  |  | 36 | B | 36.6 | C3m+C3m | N/A | PROTELCO | OK | VECTOR | 2000-10-20 | 2000-11-24 | YesV | 2000-11-29 | Doru | 2001-01-19 | 2000-12-07 |  |  |  | 2001-03-21 | 2000-09-01 |  | 2000-09-27 | 2000-10-12 | Old Obs: Old Obs: |  |  | 2000-10-24 | ICOM | ISAF | 2000-10-23 | 2000-10-23 | 2000-10-25 | 2000-12-09 | 2000-12-18 |  | Yes | Theo Radoi | 2000-12-29 | 2000-12-23 | 2000-12-23 |  |  | K 739 494 | 55 | 0 | 38.3 | K 739 494 | 165 | 0 | 38.3 | K 739 494 | 295 | 0 | 38.3 |  |  |  |  | N/A | 9 | 9 | 7/8" | 9 | 9 | 7/8" | 5 | 5 | 7/8" |  |  |  | 46 | ML 23 E 1+0 | Baneasa | MW | 40 | 0.6 | 37.7 | 9 | 23/58 |  |  | 4U-1 |  |  |  | RBS | [9 empty] | 1 | BA014 | STEFAN CEL MARE | 220 | 0.6 | 27 | 20 | 23/56 | [6 empty] | 4 | ISAF | 2000-10-24 | 341 | 2000-10-24 | 2000-10-25 | 2000-12-20 | VLAD | OK | 2000-12-23 | PENDING ITEMS |  |  | 30N03 Bacau-Baneasa |  | 2001-01-29 | Petrica BURGHIU | George IFRIM | [33 empty] | Bacau | Bacau | [7 empty] | 2 |  |  | 2
Phase_2 | CS | BA016 | REPUBLICII | Bacau(5) | BA013 Cornisei_RTC | Moldova | 46 32 01.4 | 26 55 07.5 | 46 32 01.4 | 26 55 07.5 | Str. Republicii nr.74 Bl. 74 Sc.E | Asociatia de locatari nr.88 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-10-20 | Yes | N/A |  |  |  | 23.3 | B | 26.65 | C2m+C2m | N/A | PROTELCO | OK | VECTOR | 2000-10-16 | 2000-10-31 | YesV | 2000-12-06 | Doru | 2001-01-19 | 2000-12-13 |  |  |  | 2001-05-09 | 2000-09-07 |  | 2000-09-08 | 2000-09-27 | Old Obs: Old Obs: |  |  | 2000-10-24 | ICOM | ISAF | 2000-10-23 | 2000-10-23 | 2000-10-25 | 2000-12-09 | 2000-12-18 |  | Yes | Theo Radoi | 2000-12-29 | 2000-12-24 | 2000-12-24 | 2001-01-08 | 2001-01-10 | K 739 494 | 55 | 0 | 27.5 | K 739 494 | 160 | 0 | 27.5 | K 739 494 | 295 | 0 | 28 |  |  |  |  | N/A | 10 | 10 | 7/8" | 10 | 10 | 7/8" | 20 | 20 | 7/8" |  |  |  | 80 | ML 23 E 1+0 | Baneasa | MW | 314 | 0.6 | 27 | 20 | 23/56 |  | N/A | 4U-1 |  |  | N/A | RBS | [9 empty] | 1 | BA013 | CORNISEI | 135 | 0.6 | 35 | 18.5 | 23/58 | [6 empty] | 4 | ISAF | 2000-10-24 | 276 | 2000-10-24 | 2000-10-25 | 2000-12-20 | VLAD | OK | 2000-12-24 | PENDING ITEMS |  |  | 30N02 Bacau-Baneasa |  | 2001-01-29 | Petrica BURGHIU | George IFRIM | [33 empty] | Bacau | Bacau | [7 empty] | 2 |  |  | 2
Phase_2 | CS | BA017 | SUCEAVA_RTC | Suceava(3) | BA017 Suceava_RTC | Moldova | 47 38 44.3 | 26 15 31.1 | 47 38 44.3 | 26 15 31.1 | Str. Nicolae Balcescu nr.6 | Romtelecom/Breaban Stelian - sef logistica adm. 094/ 574 210 | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-09-06 | N/A | N/A |  |  |  | 30.2 | B | 43 | 16m existing tower | Room | PROTELCO | OK | FIBEC | 2000-07-03 | 2000-09-08 | YesV | 2000-09-27 | Doru | 2000-08-18 | 2001-02-07 |  |  |  | N/A | 2000-06-15 |  | 2000-06-14 | 2000-08-23 |  |  |  | 2000-09-15 | YRO | TRY | 2000-08-25 | 2000-08-25 | 2000-09-18 | 2000-09-19 | 2000-09-21 |  | Yes | Cristian Croitor | 2000-12-29 | 2000-12-23 | 2000-12-23 | 2001-02-07 | 2001-04-10 | K 739 494 | 70 | 0 | 40 | K 739 494 | 200 | 0 | 40 | K 739 494 | 300 | 0 | 40 |  |  |  |  | N/A | 13 | 13 | 7/8" | 13 | 13 | 7/8" | 13 | 13 | 7/8" |  |  |  | 78 | N/A | Baneasa | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | 4U-1(TMR9202) |  |  |  | TMR 9202 | 20017 | 2001-06-25 | [5 empty] | 160/Outdoor |  | 1 | BSC21 | BSC BANEASA |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | IVAN | OK | N/A |  | N/A | N/A | 30N01 Suceava-Baneasa |  | 2000-12-20 | George IFRIM | George IFRIM | [32 empty] | 316 | Suceava | Suceava | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | BA018 | OBCINA_RTC | Suceava(3) | BA018 Obcina_RTC | Moldova | 47 38 17.9 | 26 13 31.1 | 47 38 17.6 | 26 13 50.9 | Str. Bistritei F.N., 030/ 204 106 | Romtelecom/Breaban Stelian - sef logistica adm. 094/ 574 210 | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-09-09 | N/A | N/A |  |  |  | 21.9 | B | 21.9 | 9m existing pylon | Room | PROTELCO | OK | FIBEC | 2000-07-10 | 2000-08-24 | YesV | 2000-08-24 | Doru | 2000-08-18 | 2000-08-30 |  |  |  | N/A | 2000-06-10 |  | 2000-06-20 | 2000-08-29 |  |  |  | 2000-09-15 | YRO | TRY | 2000-08-25 | 2000-08-25 | 2000-09-18 | 2000-09-19 | 2000-09-21 |  | Yes | Cristian Croitor | 2001-01-31 | 2001-01-11 | 2001-01-11 | 2001-01-16 | 2001-01-26 | K 739 494 | 45 | 0 | 25 | K 739 494 | 180 | 0 | 25 | K 739 494 | 315 | 0 | 25 |  |  |  |  | N/A | 25 | 25 | 7/8" | 25 | 25 | 7/8" | 25 | 25 | 7/8" |  |  |  | 150 | N/A | Baneasa | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | [5 empty] | N/A | [6 empty] | 100/Indoor |  |  | BSC21 | BSC BANEASA |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | IVAN | OK | N/A |  | N/A | N/A | 30N02 Suceava-Baneasa |  | 2000-12-22 | George IFRIM | George IFRIM | [32 empty] | 375 | Suceava | Suceava | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | BA019 | BURDUJENI | Suceava(3) | BA017 Suceava_RTC | Moldova | 47 40 18.3 | 26 16 45.7 | 47 40 18.3 | 26 16 45.7 | Str. Calea Unirii nr.60 Bl.40A Sc.D | Asociatia de proprietari nr.38/Senciu Ioan - Et.8, Ap.22, 030/ 257 532 | 2102 | M/E | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-09-19 | Yes | N/A |  |  |  | 28 | B | 31.3 | C5m+catarg ancorat pe zid | N/A | PROTELCO | OK | FIBEC | 2000-07-20 | 2000-09-07 | YesV | 2000-10-10 | Doru | 2000-09-08 | 2000-10-13 |  |  |  | 2000-06-22 | 2000-06-10 |  | 2000-06-28 | 2000-08-08 |  |  |  | 2000-09-15 | YRO | TRY | 2000-09-15 | 2000-09-15 | 2000-09-18 | 2000-09-22 | 2000-09-22 |  | Yes | Cristian Croitor | 2001-01-31 | 2001-01-11 | 2001-01-11 | 2001-02-08 | 2001-02-16 | K 739 494 | 45 | 0 | 35 | K 739 494 | 165 | 0 | 32 | K 739 494 | 285 | 0 | 35 |  |  |  |  | N/A | 15 | 15 | 7/8" | 25 | 25 | 7/8" | 15 | 15 | 7/8" |  |  |  | 110 | ML 38 E 1+0 | Baneasa | MW | 208 | 0.6 | 33 | 26 | 38/18 |  |  | 2U-3 |  |  |  | RBS | [9 empty] | 1 | BA017 | SUCEAVA_RTC | 28 | 0.6 | 39.5 | 13 | 38/14 | [6 empty] | 5 | TRYLON | 2000-09-27 | 198 | 2000-09-15 | 2000-09-16 | 2000-09-22 | IVAN | OK | 2001-01-11 |  | 2001-01-22 | 2001-01-22 | 30N01 Suceava-Baneasa |  | 2000-12-20 | George IFRIM | George IFRIM | [32 empty] | 309 | Suceava | Suceava | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BA020 | BOTOSANI_RTC | Botosani(2) | BA020 Botosani_RTC | Moldova | 47 44 38.6 | 26 40 12.1 | 47 44 38.6 | 26 40 12.1 | Str. Calea Nationala nr.5 | Romtelecom Botosani - 031/ 504 103/Aursulesei Cornel - Dir. Tehnic Aurel Grigoreanu, 031/ 504 175, 031/ 512 555 | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-12-11 | N/A |  |  |  |  | 15 | B | 17 | 36m new tower | Room | PROTELCO | OK | FIBEC | 2000-11-14 | 2001-03-05 | YesV | 2001-05-16 | Doru | 2001-03-08 | 2001-05-23 |  |  |  | N/A | 2000-06-12 |  | 2000-10-20 | 2001-03-14 |  |  |  | 2001-03-15 | ICOM | KEN KEN | 2001-03-08 | 2001-03-08 | 2001-03-19 | 2001-03-20 | 2001-03-23 |  | Yes | Ion Soare | 2001-04-07 | 2001-04-07 | 2001-04-07 | 2001-04-17 | 2001-04-23 | K 739 494 | 40 | 0 | 43 | K 739 494 | 160 | 0 | 43 | K 739 494 | 280 | 0 | 43 |  |  |  |  | N/A | 50 | 50 | 7/8" | 50 | 50 | 7/8" | 50 | 50 | 7/8'' |  |  |  | 300 | N/A | Baneasa | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | 4U-1(TMR9202) |  |  |  | TMR 9202 | 20020 | 2001-06-25 | [5 empty] | 45/outdoor |  | 1 | BSC21 | BSC BANEASA | N/A | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | RADU | OK | N/A |  | N/A | N/A | 30N01 Botosani_Baneasa |  | 2000-12-20 | George IFRIM | Petrica BURGHIU | [32 empty] | 160 | Botosani | Botosani | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | BA021 | BOTOSANI_2 | Botosani(2) | BA020 Botosani_RTC | Moldova | 46 44 57.8 | 26 38 38.2 | 47 44 55.1 | 26 38 39.2 | Str. Sucevei nr.7 Bl.7, Sc.C | Asociatia de locatari 20 - Col. Tomoroveanu nr.4, et.2, cam.53/Rotaru Ilie - pres. Asoc, 031/ 581 671 | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-10-20 | N/A | N/A |  |  |  | 33 | B | 33 | T3.5m+T3.5m | Room | PROTELCO | OK | FIBEC | 2000-07-20 | 2000-10-18 | YesV | Respins | Doru | 2000-10-23 | [5 empty] | 2000-06-12 |  | 2000-07-11 | 2000-07-24 |  |  |  | 2000-10-24 | ICOM | ISAF | 2000-10-06 | 2000-10-06 | 2000-10-25 | 2000-10-31 | 2000-11-02 |  | Yes | Ion Soare | 2001-04-07 | 2001-04-07 | 2001-04-07 | 2001-05-08 | 2001-05-15 | K 739 494 | 40 | 0 | 35 | K 739 494 | 160 | 0 | 35 | K 739 494 | 280 | 0 | 35 |  |  |  |  | N/A | 17 | 17 | 7/8" | 17 | 17 | 7/8" | 40 | 40 | 7/8" |  |  |  | 148 | ML 23 E 1+0 | Baneasa | MW | 104 | 0.6 | 34/0.3 | 17 | 23/56 |  |  | 2U-3 | [13 empty] | 1 | BA020 | BOTOSANI_RTC | 284 | 0.6 | 45/0.3 | 52 | 23/58 | [6 empty] | 43* | KEN-KEN | 2001-03-15 | 723 | 2001-03-19 | 2001-03-19 | 2001-03-23 | RADU | OK | 2001-04-07 | PENDING ITEMS |  |  | 30N01 Botosani_Baneasa |  | 2000-12-20 | George IFRIM | Petrica BURGHIU | [32 empty] | 163 | Botosani | Botosani | [7 empty] | 2 |  |  | 2
Phase_2 | CS | BA022 | PIATRA NEAMT 1_RTC | Piatra Neamt(3) | BA022 Piatra Neamt 1_RTC | Moldova | 46 55 55.2 | 26 22 00.7 | 46 55 55.2 | 26 22 00.7 | Bd. Republicii nr.2 | Romtelecom/ | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-09-06 | N/A | N/A |  |  |  | 31 | B | 31 | 3m existed tower | Room | PROTELCO | OK | VECTOR | 2000-07-06 | 2000-07-25 | YesV | 2000-08-02 | Doru | 2000-08-18 | 2000-08-09 |  |  |  | N/A | 2000-05-20 |  | 2000-06-14 | 2000-07-04 |  |  |  | 2000-09-15 | YRO | TRY | 2000-08-22 | 22-08-00 | 2000-09-18 | 2000-09-22 | 2000-09-22 |  | Yes | Theo Radoi | 2000-12-24 | 2000-12-21 | 2000-12-21 | 2001-02-07 | 2001-02-16 | K 739 494 | 80 | 0 | 37.2 | K 739 494 | 200 | 0 | 37.2 | K 739 494 | 320 | 0 | 37.2 |  |  |  |  | N/A | 15 | 15 | 7/8" | 17 | 17 | 7/8" | 19 | 19 | 7/8" |  |  |  | 102 | N/A | Baneasa | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | 4U-1 |  |  |  | N/A | 20022 | 2001-06-25 | [5 empty] | 100/Outdoor |  | 1 | BSC21 | BSC BANEASA | N/A | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | IVAN | OK | N/A |  | N/A | N/A | 30N02 Piatra Neamt-Baneasa |  | 2000-12-22 | George IFRIM | George IFRIM | [32 empty] | 322 | Piatra Neamt | Neamt | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | BA023 | PATRA NEAMT 2_RTC | Piatra Neamt(3) | BA023 Piatra Neamt 2_RTC | Moldova | 46 56 09 | 26 23 01.8 | 46 56 10 | 26 23 01.1 | Str. 1 Decembrie 1918 | Romtelecom/Dl. Gheorgulescu - 033/ 204 191 | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-10-13 | N/A | N/A |  |  |  | 16 | B | 18 | 15m pylon | Room | PROTELCO | OK | VECTOR | 2000-09-06 | 2000-10-06 | YesV | 2000-11-29 | Doru | 2001-01-19 | 2000-12-07 |  |  |  | N/A | 2000-05-20 |  | 2000-07-17 | 2000-08-21 |  |  |  | 2000-10-20 | ICOM | IMSAT | 2000-10-12 | 2000-10-12 | 2000-10-23 | 2000-11-20 | 2000-11-28 |  | Yes | Theo Radoi | 2000-12-24 | 2000-12-21 | 2000-12-21 |  |  | K 739 494 | 0 | 0 | 31 | K 739 494 | 90 | 0 | 31 | K 739 494 | 225 | 0 | 31 |  |  |  |  | N/A | 40 | 40 | 7/8" | 40 | 40 | 7/8" | 40 | 40 | 7/8" |  |  |  | 240 | N/A | Baneasa | FO | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | [7 empty] | 50/Indoor |  |  | BSC21 | BSC BANEASA | N/A | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | VLAD | OK | N/A |  | N/A | N/A | 30N01 Piatra Neamt-Baneasa |  | 2000-12-22 | George IFRIM | George IFRIM | [32 empty] | 360 | Piatra Neamt | Neamt | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | BA024 | PIATRA-NEAMT PIETRICICA | Piatra Neamt(3) | BA022 Piatra Neamt 1_RTC | Moldova | 46 55 43.9 | 26 22 46.3 | 46 55 43.9 | 26 22 46.3 | Ocolul Silvic Gircina-Piatra Neamt | DRTv/DRTv -Iasi | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-11-17 | Yes | N/A |  |  |  | 0 | TE | 66 | Tower | N/A | PROTELCO | OK | KEN-KEN | 2000-11-02 | 2000-11-17 | YesV | 2000-11-29 | Doru | 2000-11-21 | 2000-12-07 |  |  |  |  | 2000-05-20 |  | 2000-08-16 | 2000-10-19 |  |  |  | 2000-10-23 | ICOM | IMSAT | 2000-10-23 | 2000-10-23 | 2000-10-23 | 2000-11-20 | 2000-11-30 |  | Yes | Theo Radoi | 2000-12-24 | 2000-12-21 | 2000-12-21 |  |  | K 739 494 | 10 | 0 | 48.5 | K 739 494 | 135 | 0 | 48.5 | K 739 494 | 300 | 0 | 48.5 |  |  |  |  | N/A | 77 | 77 | 1 1/4" | 74 | 74 | 1 1/4" | 80 | 80 | 1 1/4" |  |  |  | 462 | ML 23 E 1+0 | Baneasa | MW | 290 | 0.6 | 47.4/0.3 | 80 | 23/58 |  |  | 4U-1 |  |  |  | RBS | [9 empty] | 1 | BA022 | PIATRA NEAMT 1_RTC | 110 | 0.6 | 37.8/0.3 | 14 | 23/56 | [6 empty] | 1 | IMSAT | 2000-10-23 | 335 | 2000-10-23 | 2000-10-24 | 2000-11-24 | VLAD | OK | 2000-12-21 |  | 2001-01-22 | 2001-01-22 | 30N02 Piatra Neamt-Baneasa |  | 2000-12-22 | George IFRIM | George IFRIM | [32 empty] | 362 | Piatra Neamt | Neamt | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BA025 | ROMAN 1_RTC | Roman(2) | BA025 Roman 1_RTC | Moldova | 46 55 16.2 | 26 55 40.2 | 46 55 17.1 | 26 55 39.5 | Str. Cuza Voda, Romtelecom | Romtelecom/Dl. Asmarandei I. - 093/ 362 150 | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-10-11 | N/A | N/A |  |  |  | 25 | B | 32 | 9m new pylonet | Room | PROTELCO | OK | ORION | 2000-09-01 | 2000-09-25 | YesV | 2000-09-27 | Doru | 2000-09-27 | 2000-10-25 |  |  |  | N/A | 2000-06-15 |  | 2000-06-28 | 2000-08-15 |  |  |  | 2000-09-27 | YRO | TRY | 2000-09-27 | 2000-09-27 | 2000-09-28 | 2000-10-01 | 2000-10-03 |  | Yes | Theo Radoi | 2000-12-31 | 2000-12-22 | 2000-12-22 | 2001-03-02 | 2001-04-10 | K 739 494 | 110 | 0 | 34.5 | K 739 494 | 230 | 0 | 34.5 | K 739 494 | 350 | 0 | 34.5 |  |  |  |  | N/A | 35 | 35 | 7/8" | 35 | 35 | 7/8" | 35 | 35 | 7/8" |  |  |  | 210 | N/A | Baneasa | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | 4U-1 |  |  |  | Indoor Comteck | 20025 | 2001-06-25 | [7 empty] | 1 | BSC21 | BSC BANEASA | N/A | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | IVAN | OK | N/A |  | N/A | N/A | 30N01 Roman-Baneasa |  | 2000-12-22 | George IFRIM | George IFRIM | [32 empty] | 190 | Roman | Roman | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | BA026 | ROMAN 2 | Roman(2) | BA025 Roman 1_RTC | Moldova | 46 55 47.3 | 26 55 37.4 | 46 55 47.5 | 26 55 39.3 | Str. Rahovei Bl.15 | Asociatia 58 Rb/Zaharia Constantin - Str. Rahovei Bl.15 Ap.36, 033/720 164 | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-09-19 | N/A | N/A |  |  |  | 31.5 | B | 31.5 | C5m+C5m | Room | PROTELCO | OK | ORION | 2000-07-10 | 2000-07-31 | YesV | 2000-08-07 | Doru | 2000-09-06 | 2000-08-09 |  |  |  | N/A | 2000-06-05 |  | 2000-06-20 | 2000-07-17 |  |  |  | 2000-09-15 | YRO | TRY | 2000-08-22 | 22-08-00 | 2000-09-18 | 2000-09-21 | 2000-09-22 |  | Yes | Theo Radoi | 2000-12-31 | 2000-12-22 | 2000-12-22 | 2001-02-08 | 2001-02-16 | K 739 494 | 80 | 0 | 36.7 | K 739 494 | 200 | 0 | 36.7 | K 739 494 | 320 | 0 | 36.7 |  |  |  |  | N/A | 15 | 15 | 7/8" | 19 | 19 | 7/8" | 20 | 20 | 7/8" |  |  |  | 108 | ML 23 E 1+1 (PS) | Baneasa | MW | 180 | 0.6 | 36.4/0.3 | 17.5 | 23/58 |  |  | 2U-3 |  |  |  | N/A | [9 empty] | 1 | BA025 | ROMAN 1_RTC | 360 | 0.6 | 34/0.3 | 35 | 23/56 | [6 empty] | N/A | TRYLON | N/A | 245 | 2000-09-29 | 2000-09-29 | 2000-10-02 | IVAN | OK | 2000-12-22 |  | 2001-02-05 | 2001-03-02 | 30N01 Roman-Baneasa |  | 2000-12-22 | George IFRIM | George IFRIM | [32 empty] | 200 | Roman | Roman | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BA027 | STEFAN CEL MARE | Vaslui(4) | BA043 Vaslui_RTC_Tehnic | Moldova | 46 38 17.7 | 27 44 00.7 | 46 38 42.7 | 27 44 13.6 | Str. Stefan Cel Mare Bl.131 | Asociatia de locatari, nr. 10, - Dl. Caseriu Gheorghe/Dl. Caseriu-presedinte, str. Stefan Cel Mare , bl. 131, sc.A, et.4, ap. 37, tel. 094/ 931 334 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | Yes | N/A |  |  |  | 32.5 | B | 32.5 | T4.5m+T4.5m | N/A | IMSAT | OK | SETRACO | 2000-12-13 | 2001-02-05 | YesV | 2001-03-08 | Eugen | 2001-02-07 | 2001-03-14 |  |  |  |  | 2000-09-05 |  | 2000-12-06 | 2000-12-18 |  |  |  | 2001-02-14 | ICOM | Interactive | 2001-02-13 | 2001-02-13 | 2001-02-15 | 2001-02-20 | 2001-02-21 |  | Yes | Ion Soare | 2001-04-27 | 2001-04-27 | 2001-04-27 | 2001-06-06 | 2001-06-19 | K 739 494 | 10 | 0 | 38.9 | K 739 494 | 150 | 0 | 38.9 | K 739 494 | 270 | 0 | 38.9 |  |  |  |  | N/A | 20 | 20 | 7/8" | 24 | 24 | 7/8" | 24 | 24 | 7/8" |  |  |  | 130 | ML 38 E 1+0 | Baneasa | MW | 208 | 0.3 | 37.9 | 19.5 | 38/18 |  |  | 2U-3 |  |  |  | RBS | [9 empty] | 1 | BA043 | VASLUI_RTC_TEHNIC | 28 | 0.3 | 22/0.3 | 36.85 | 38/14 | [6 empty] | 43* | KEN-KEN | 2001-03-15 | 724 | 2001-03-19 | 2001-03-19 | 2001-04-12 | DINCA | OK | 2001-04-27 |  | 2001-05-21 | 2001-05-25 | 30N03 Vaslui-Baneasa |  | 2000-12-22 | Petrica BURGHIU | George IFRIM | [32 empty] | 97 | Vaslui | Vaslui | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BA028 | VASLUI-SILOZ | Vaslui(4) | BA043 Vaslui_RTC_Tehnic | Moldova | 46 37 56.1 | 27 43 24.7 | 46 37 49.4 | 27 43 21.8 | Terasa Silloz | SC CEREALCOM SA, str. Podul Inalt nr.1/Presedinte Strungaru Gheorghe -035/ 361 571/361 572 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | Yes | N/A |  |  |  | 50 | S | 50 | T4.5m+T4.5m | N/A | IMSAT | OK | SETRACO | 2001-01-18 | 2001-01-31 | YesV | 2001-03-08 | Eugen | 2001-02-05 | 2001-03-14 |  |  |  |  | 2000-10-24 |  | 2000-11-30 | 2001-01-19 |  |  |  | 2001-02-19 | ICOM | CAMUSAT | 2001-02-01 | 2001-02-01 | 2001-02-21 | 2001-02-23 | 2001-02-26 |  | Yes | Alexandru Toma | 2001-04-20 | 2001-04-20 | 2001-04-20 | 2001-04-26 | 2001-05-03 | K 739 494 | 30 | 0 | 53 | K 739 494 | 135 | 0 | 53 | K 739 494 | 265 | 0 | 52.5 |  |  |  |  | N/A | 21 | 21 | 7/8" | 14 | 14 | 7/8" | 14 | 14 | 7/8" |  |  |  | 98 | ML 38 E 1+0 | Baneasa | MW | 40 | 0.3 | 52.5 | 20.5 | 38/17 |  |  | 2U-3 |  |  |  | RBS | [9 empty] | 1 | BA043 | VASLUI_RTC_TEHNIC | 220 | 0.3 | 22/0.3 | 36.85 | 38/13 | [6 empty] | 43* | KEN-KEN | 2001-03-15 | 725 | 2001-03-19 | 2001-03-19 | 2001-04-12 | DINCA | OK | 2001-04-20 |  | 2001-05-03 | 2001-05-11 | 30N02 Vaslui-Baneasa |  | 2001-03-05 | Petrica BURGHIU | George IFRIM | [32 empty] | 96 | Vaslui | Vaslui | [7 empty] | 2 |  |  | 2
Phase_2 | CS | BA029 | VASLUI_DRTV | Road Albita-Crasna(6) | BA043 Vaslui_RTC_Tehnic | Moldova | 46 40 13.7 | 27 47 21.7 | 46 40 13.7 | 27 47 21.7 | Statia de Televiziune Vaslui, Dealul Mirenilor | DRTv/DRTv -Iasi | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-10-13 | N/A | N/A |  |  |  | 0 | TE | 101 | Tower | N/A | PROTELCO | OK | ORION | 2000-10-02 | 2000-10-12 | YesV | 2000-10-27 | Bogdan | 2000-10-12 | 2000-10-31 |  |  |  |  | 2000-08-05 |  | 2000-08-16 | 2000-09-13 |  |  |  | 2000-10-20 | ICOM | IMSAT | 2000-10-13 | 2000-10-13 | 2000-10-23 | 2000-10-25 | 2000-10-27 |  | Yes | Ion Soare | 2001-04-27 | 2001-04-27 | 2001-04-27 |  |  | K 739 494 | 190 | 0 | 47.9 | K 739 494 | 270 | 0 | 47.9 | K 739 494 | 340 | 0 | 48.5 |  |  |  |  | N/A | 81 | 81 | 1 1/4" | 75 | 75 | 1 1/4" | 75 | 75 | 1 1/4" |  |  |  | 462 | ML 23 E 1+0 | Baneasa | MW | 235 | 0.6 | 46.8/0.6 | 80 | 23/56 |  |  | 2U-3 |  |  |  | RBS | [9 empty] | 1 | BA027 | STEFAN CEL MARE | 55 | 0.6 | 37.9 | 19.5 | 23/58 | [6 empty] | 26* | INTERACTIVE | 2001-02-14 | 632 | 2001-02-15 | 2001-03-19 | 2001-04-12 | RADU | OK | 2001-04-27 |  | 2001-05-21 | 2001-05-25 | 30N01 Vaslui-Baneasa |  | 2000-12-22 | Petrica BURGHIU | George IFRIM | [32 empty] | 282 | Vaslui | Vaslui | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | TM | BA030 | PODUL ROS_RTC | Iasi(11+2) | BA030 Podul Ros_RTC | Moldova | 47 09 03 | 27 35 08 | 47 09 03 | 27 35 11 | Str. Nicolina nr.1 | Romtelecom/ | N/A | N/A | N/A | N/A | N/A | [7 empty] | N/A | N/A |  |  |  | N/A | B | 17 | C5m | Room | PROTELCO | OK | IMSAT | 2000-08-01 | 2000-09-02 | YesV | 2000-09-14 | Doru | 2000-10-05 | 2000-12-08 |  |  |  | N/A | 2000-06-10 |  | 2000-07-18 | 2000-08-16 |  |  |  | 2000-09-27 | YRO | TRY | N/A | N/A | 2000-09-28 | N/A | N/A |  | Yes | N/A | 2001-02-28 | 2000-12-22 | 2000-12-22 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A | Baneasa | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | 2U-3 |  |  |  | N/A | 20030 | 2001-06-25 | [5 empty] | 15/ |  | 1 | BSC21 | BSC BANEASA | N/A | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | IVAN | OK | N/A |  | N/A | N/A | N/A |  | 2000-12-20 | George IFRIM | George IFRIM | [32 empty] | 42 | Iasi | Iasi | [7 empty] | Site Near=Insertion Point
Phase_2 | TM | BA031 | INDEPENDENTEI_RTC | Iasi(11+2) | BA031 Independentei_RTC | Moldova | 47 10 07.2 | 27 34 39.4 | 47 10 07.2 | 27 34 39.4 | Str. Independentei | Romtelecom/ | N/A | N/A | N/A | N/A | N/A | [7 empty] | N/A | N/A |  |  |  | N/A | B | 18.8 | 15m existent pylonet | Room | PROTELCO | OK | IMSAT | 2000-09-11 | 2000-09-17 | YesV | 2000-09-27 | Doru | 2000-10-05 | 2000-09-29 |  |  |  | N/A | 2000-06-10 |  | 2000-07-18 | 2000-08-16 |  |  |  | 2000-09-27 | YRO | TRY | N/A | N/A | 2000-09-28 | N/A | N/A |  | Yes | N/A | 2001-02-28 | 2001-01-10 | 2001-01-10 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A | Baneasa | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | 4U-1 |  |  |  | N/A | 20031 | 2001-05-07 | YES |  | 2001-06-25 |  |  | 230/ |  | 1 | BSC21 | BSC BANEASA | N/A | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | IVAN | OK | N/A |  | N/A | N/A | N/A |  | 2000-12-20 | George IFRIM | George IFRIM | [32 empty] | 81 | Iasi | Iasi | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | BA032 | FOCSANI_RTC | Focsani(4) | BA032 Focsani_RTC | Moldova | 45 41 56.4 | 27 11 10 | 45 41 56.4 | 27 11 10 | Bd. Republicii nr.96 | Romtelecom/ | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-09-19 | N/A | N/A |  |  |  |  | B | 15.5 | 18.5m existing tower DRTv | Room | SVF | OK | SETRACO | 2000-08-05 | 2000-09-03 | YesV | 2000-09-22 | Bogdan | 2000-09-05 | 2000-10-06 |  |  |  | N/A | 2000-06-21 |  | 2000-07-13 | 2000-07-31 |  |  |  | 2000-09-07 | YRO | SVF | 2000-09-07 | 2000-09-07 | 2000-09-08 | 2000-09-10 | 2000-09-11 |  | Yes | Alexandru Toma | 2000-12-15 | 2000-12-12 | 2000-12-12 |  |  | K 739 494 | 0 | 0 | 32 | K 739 494 | 120 | 0 | 32 | K 739 494 | 240 | 0 | 32 |  |  |  |  | N/A | 50 | 50 | 1 1/4" | 50 | 50 | 1 1/4" | 50 | 50 | 1 1/4" |  |  |  | 300 | N/A | Galati | FO | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | TMR 9202 | 20032 | 2001-05-11 |  | XC21032 | [5 empty] | 1 | BSC22 | BSC GALATI |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | 30N02 Focsani-Galati | optimizare fluxuri(vezi harta de transmisiuni) | OK | Ionut GRIGORESCU | George IFRIM | [32 empty] | 54 | Focsani | Vrancea | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | BA033 | UNIRII | Focsani(4) | BA032 Focsani_RTC | Moldova | 45 41 26 | 27 11 07 | 45 41 26 | 27 11 07 | Bd.Unirii nr.14, Bl.G2, sc.1 | Asociatie de proprietari nr.96/Borcea Radu - Bd.Unirii nr.14, Bl.G2, sc.2, Et.4,Ap.55 037/ 61 34 88 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-11-17 | Yes | N/A |  |  |  | 33.5 | B | 36.5 | T4m+T4m | N/A | SVF | OK | SETRACO | 2000-10-20 | 2001-02-03 | YesV | 2001-03-05 | Bogdan | 2001-03-06 | 2001-03-13 |  |  |  | 2000-07-07 | 2000-06-21 |  | 2000-09-25 | 2000-10-18 |  |  |  | 2000-11-20 | ICOM | SVF | 2000-11-20 | 2000-11-20 | 2000-11-21 | 2000-11-21 | 2000-11-23 |  | Yes | Ion Soare | 2001-02-24 | 2001-02-24 | 2001-02-24 | 2001-03-02 | 2001-04-10 | K 739 494 | 100 | 0 | 36.7 | K 739 494 | 250 | 0 | 36.8 | K 739 494 | 350 | 0 | 36.1 |  |  |  |  | N/A | 33 | 33 | 7/8" | 33 | 33 | 7/8" | 15 | 15 | 7/8" |  |  |  | 162 | ML 23 E 1+0 | Galati | MW | 45 | 0.6 | 37.3/0.3 | 16 | 23/58 |  | 4x2/8 | 2U-3 |  |  |  | RBS | XC20032 | [8 empty] | 1 | BA035 | LUPENI | 225 | 0.6 | 20 | 19 | 23/56 | [6 empty] | 17 | SVF | 2000-11-20 | 385 | 2000-11-20 | 2000-11-20 | 2000-11-23 | VLAD | OK | 2001-02-24 |  | 2001-03-02 | 2001-04-06 | 30N01 Focsani-Galati | optimizare fluxuri(vezi harta de transmisiuni) | OK | Ionut GRIGORESCU | George IFRIM | [32 empty] | 52 | Focsani | Vrancea | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BA034 | SILOZ AGROSEM | Focsani(4) | BA032 Focsani_RTC | Moldova | 45 11 27 | 27 10 04 | 45 41 27 | 27 10 04 | Agrosem Str.Cotesti nr.79 | /Berdei - 037/ 62 16 75 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-09-19 | Yes | N/A |  |  |  | 48 | B | 48 | Pipe | N/A | SVF | OK | MMK | 2000-08-10 | 2000-08-25 | YesV | 2000-08-25 | Bogdan | 2000-08-31 | 2000-08-30 |  |  |  |  | 2000-06-21 |  | 2000-07-20 | 2000-08-14 |  |  |  | 2000-09-15 | YRO | TRY | 2000-08-31 | 2000-08-31 | 2000-09-18 | 2000-09-19 | 2000-09-20 |  | Yes | Alexandru Toma | 2000-12-15 | 2000-12-13 | 2000-12-13 | 2001-05-03 | 2001-05-15 | K 739 494 | 35 | 0 | 49 | K 739 494 | 215 | 0 | 49 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 10 | 10 | 7/8" | 10 | 10 | 7/8" | N/A | N/A | N/A |  |  |  | 38 | ML 23 E 1+0 | Galati | MW | 57 | 0.6 | 48 | 10 | 23/56 |  | 4x2/8 | 2U-3 |  |  |  | RBS |  |  |  | XC21032 | [5 empty] | 1 | BA032 | FOCSANI_RTC | 238 | 0.6 | 32 | 50 | 23/58 | [6 empty] | 5 | TRYLON | 2000-09-15 | 201 | 2000-09-15 | 2000-09-16 | 2000-09-20 | RADU | OK | 2000-12-13 |  | 2001-03-21 | 2001-01-08 | 30N02 Focsani-Baneasa | optimizare fluxuri(vezi harta de transmisiuni) | OK | Ionut GRIGORESCU | George IFRIM | [32 empty] | 59 | Focsani | Vrancea | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BA035 | LUPENI | Focsani(4) | BA032 Focsani_RTC | Moldova | 45 41 47 | 27 11 37 | 45 41 47 | 27 11 37 | Str.Lupeni nr.2, Bl.2, sc2 | Asociatie de proprietari/Nastasescu Cornelia - 037/ 61 57 75 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-09-09 | Yes | N/A |  |  |  | 14.25 | B | 14.25 | 9m new pylon | N/A | SVF | OK | MMK | 2000-08-15 | 2000-08-31 | YesV | 2000-08-31 | Bogdan | 2000-08-31 | 2000-09-04 |  |  |  |  | 2000-06-21 |  | 2000-08-02 | 2000-08-16 |  |  |  | 2000-09-07 | YRO | SVF | 2000-09-07 | 2000-09-07 | 2000-09-08 | 2000-09-12 | 2000-09-16 |  | Yes | Alexandru Toma | 2000-12-15 | 2000-12-13 | 2000-12-13 |  |  | K 739 494 | 355 | 0 | 22.9 | K 739 494 | 115 | 0 | 22.9 | K 739 494 | 220 | 0 | 22.9 |  |  |  |  | N/A | 22 | 22 | 7/8" | 22 | 22 | 7/8" | 22 | 22 | 7/8" |  |  |  | 132 | ML 23 E 1+0 | Galati | MW | 296 | 0.6 | 20/0.3 | 19 | 23/56 |  | 4x2/8 | 2U-3 |  |  |  | RBS | XC20032 | [8 empty] | 1 | BA032 | FOCSANI_RTC | 116 | 0.6 | 31 | 50 | 23/58 | [6 empty] | 8 | SVF | 2000-09-07 | 179 | 2000-09-07 | 2000-09-12 | 2000-09-16 | RADU | OK | 2000-12-13 |  | 2001-12-21 | 2001-01-08 | 30N01 Focsani-Galati | optimizare fluxuri(vezi harta de transmisiuni) | OK | Ionut GRIGORESCU | George IFRIM | [32 empty] | 51 | Focsani | Vrancea | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BA036 | MARASESTI_RTC | Road Urziceni-Tecuci(12) | BA036 Marasesti_RTC | Moldova | 45 52 28.4 | 27 10 48.9 | 45 52 28.4 | 27 10 48.9 | Str. Republicii nr.73 | Romtelecom/ | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-09-19 | N/A | N/A |  |  |  | 5.3 | TE | 30 |  | Room | SVF | OK | IMSAT | 2000-09-01 | 2000-09-29 | YesV | 2000-09-28 | Andrei | 2000-08-31 | 2000-10-06 |  |  |  | N/A | 2000-06-30 |  | 2000-07-13 | 2001-01-04 |  |  |  | 2000-09-15 | YRO | TRY | 2000-09-15 | 2000-09-15 | 2000-09-18 | 2000-09-19 | 2000-09-20 |  | Yes | Alexandru Toma | 2000-12-15 | 2000-12-15 | 2000-12-15 | 2001-03-02 | 2001-04-10 | K 739 494 | 130 | 0 | 28 | K 739 494 | 190 | 0 | 28 | K 739 494 | 350 | 0 | 28 |  |  |  |  | N/A | 48 | 48 | 1 1/4" | 48 | 48 | 1 1/4" | 49 | 49 | 1 1/4" |  |  |  | 290 | N/A | Galati | FO | N/A | N/A | N/A | N/A | N/A |  | 4x2/8 | 4U-1(TMR9202) |  |  |  | TMR 9202 | [7 empty] | 10/ |  |  | BSC11 | DRUMUL TABEREI | N/A | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | 30N01 Marasesti-Galati |  | OK | Ionut GRIGORESCU | Ionut GRIGORESCU | [32 empty] | 99 | Marasesti | Vrancea | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | BA037 | ADJUD_RTC | Road Urziceni-Tecuci(12) | BA037 Adjud_RTC | Moldova | 46 05 59.8 | 27 10 48.9 | 46 05 59.8 | 27 10 48.9 | Str. Republicii nr.36 | Romtelecom/ | 2202 | M | C+C+ | 2/2 | 2202 | [6 empty] | 2000-10-20 | N/A | N/A |  |  |  | 10 | B | 15 | 12m new pylon | Room | SVF | OK | IMSAT | 2000-10-16 | 2000-10-20 | YesV | 2000-11-15 | Andrei | 2000-11-10 | 2000-11-22 |  |  |  | N/A | 2000-06-30 |  | 2000-06-06 | 2000-07-21 |  |  |  | 2000-11-10 | ICOM | IMSAT | 2000-11-10 | 2000-10-11 | 2000-11-13 | 2000-11-13 | 2000-11-14 |  | Yes | Theo Radoi | 2000-12-30 | 2000-12-24 | 2000-12-24 |  |  | K 739 494 | 174 | 0 | 27 | K 739 494 | 332 | #N/A | 27 | N/A | N/A | N/A | N/A |  |  |  |  | N/A | 25 | 25 | 7/8" | 25 | 25 | 7/8" | N/A | N/A | N/A |  |  |  | 100 | N/A | Galati | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | [5 empty] | 20037 | [9 empty] | BSC22 | BSC GALATI |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | 30N01 |  | 2000-12-19 | Petrica BURGHIU | Petrica BURGHIU | [32 empty] | 92 | Adjud | Vrancea | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | BA038 | URECHESTI | Road Urziceni-Tecuci(12) | BA032 Focsani_RTC | Moldova | 45 36 07.5 | 27 06 20.6 | 45 35 51.4 | 27 05 59.4 | Com. Urechesti, tarla 54, parcela 3067 | Primaria com. Urechesti/Primar Golesteanu Maria | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-11-17 | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | SVF | OK | DIEKAT | 2000-10-16 | 2000-11-30 | YesV | 2000-12-08 | Andrei | 2000-12-04 | 2000-12-13 |  |  |  |  | 2000-06-30 |  | 2000-09-25 | 2000-10-17 |  |  |  | 2000-12-15 | ICOM | DIEKAT | 2000-12-14 | 2000-12-15 | 2000-12-19 | 2001-01-23 | 2001-01-25 |  | Yes | Ion Soare | 2001-03-15 | 2001-03-15 | 2001-03-15 |  |  | K 739 494 | 30 | 0 | 49 | K 739 494 | 180 | 0 | 49 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 70 | 70 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 140 | ML 15 E 1+0 | Galati | MW | 26 | 1.2 | 30/1.2 | 50 | 15/89 |  | 4x2/8 | 2U-3 |  |  |  | RBS | XC20032 | [8 empty] | 1 | BA034 | SILOZ AGROSEM | 206 | 1.2 | 49.8/1.2 | 10 | 15/84 | [6 empty] | 20* | CAMUSAT | 2001-01-24 | 473 | 2001-01-24 | 2001-01-30 | 2001-02-28 | ICOM | OK | 2001-03-14 |  | 2001-03-21 | 2001-04-06 | 30N01 Focsani-Galati | optimizare fluxuri(vezi harta de transmisiuni) | OK | Ionut GRIGORESCU | Cosmorom | [32 empty] | 126 | Urechesti | Vrancea | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BA039 | SLOBOZIA BRADULUI | Road Urziceni-Tecuci(12) | BX098 Rm. Sarat_RTC | Moldova | 45 28 27.5 | 27 03 31.7 | 45 29 13 | 27 03 22.2 | Loc. Slobozia Bradului, tarla 28, parcela 294 | Primaria Slobozia-Bradului/Zamfirescu Valerica - primar | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-11-17 | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | SVF | OK | DIEKAT | 2000-10-16 | 2000-11-30 | YesV | 2000-12-08 | Andrei | 2000-12-04 | 2000-12-13 |  |  |  |  | 2000-06-30 |  | 2000-09-25 | 2000-10-20 |  |  |  | 2000-12-15 | ICOM | DIEKAT | 2000-12-14 | 2000-12-15 | 2000-12-19 | 2001-01-23 | 2001-01-25 |  | Yes | Alexandru Toma | 2001-03-09 | 2001-03-09 | 2001-03-09 | 2001-03-27 | 2001-04-10 | K 739 494 | 25 | 0 | 48 | K 739 494 | 185 | 0 | 48 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 70 | 70 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 140 | ML 15 E 1+0 | Galati | MW | 187 | 0.6 | 30/1.2 | 60 | 15/89 |  | 4x2/8 | 4U-1 |  |  |  | RBS | [9 empty] | 1 | BX095 | RM. SARAT_DRTV | 6 | 0.6 | 40/1.2 | 60 | 15/84 | [6 empty] | 7* | DIEKAT | 2000-12-14 | 693 | 2001-06-03 | 2000-12-19 | 2001-02-15 | PAUN | OK | 2001-03-09 |  | 2001-03-21 | 2000-04-06 |  |  | OK | Ionut GRIGORESCU | Cosmorom | [32 empty] | 208 | Slobozia Bradului | Vrancea | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BA040 | GAROAFA | Road Urziceni-Tecuci(12) | BX105 Cosmesti_RTC | Moldova | 45 46 44.6 | 27 12 32.6 | 45 46 44.6 | 27 12 32.6 | Comuna Garoafa nr.3 | Cioineag Valentin/Cioineag Valentin - 037/ 23 17 88 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-10-20 | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | SVF | OK | IMSAT | 2000-09-12 | 2000-12-22 | YesV | 2001-02-08 | Andrei | 2001-01-29 | 2001-02-15 |  |  |  |  | 2000-06-30 |  | 2000-08-29 | 2000-09-11 |  |  |  | 2000-12-28 | ICOM | IMSAT | 2000-12-27 | 2001-01-10 | 2001-01-11 | 2001-01-23 | 2001-01-29 |  | Yes | Ion Soare | 2001-03-14 | 2001-03-14 | 2001-03-14 | 2001-05-31 | 2001-06-19 | K 739 494 | 0 | 0 | 49 | K 739 494 | 190 | 0 | 49 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 70 | 70 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 140 | ML 15 E 1+0 | Galati | MW | 38 | 0.6c | 30/1.2 | 50 | 15/89h |  | 4x2/8 | 4U-1 |  |  |  | RBS | XC30105 | [8 empty] | 1 | BX105 | COSMESTI_RTC | 218 | 0.6c | 36/1.2 | 48 | 15/84h | [6 empty] | 15* | IMSAT | 2001-01-08 | 507 | 2001-02-23 | 2001-02-23 | 2001-03-02 | OK | OK | 2001-03-14 |  | 2001-05-03 | 2001-05-11 | 30N01 Cosmesti-Galati |  | 2001-01-26 | Ionut GRIGORESCU | Cosmorom | [32 empty] | 64 | Com.Garoafa | Vrancea | [7 empty] | 2 |  |  | 2
Phase_2 | CS | BA041 | HOTEL VENUS | Slanic Moldova(1) | BA041 Hotel Venus | Moldova | 46 12 20.3 | 26 26 02.4 | 46 12 20.6 | 26 26 02.7 | Str. Mihai Eminescu nr.1, Hotel Venus - Slanic moldova | Str. Mihai Eminescu nr.1, Hotel Venus - Slanic moldova/Dir. Gen. Munteanu ioan - Hotel Venus, 034/ 348 027 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-10-13 | Yes | N/A |  |  |  | 37.5 | B | 40.2 | T6m | N/A | PROTELCO | OK | ORION | 2000-10-23 | 2000-11-09 | YesV | 2000-11-16 | Doru | 2000-11-08 | 2000-11-22 |  |  |  |  | 2000-09-05 |  | 2000-09-28 | 2000-10-12 |  |  |  | 2000-10-20 | ICOM | ORION | 2000-10-13 | 2000-10-13 | 2000-11-09 | 2000-11-10 | 2000-11-13 |  | Yes | Durugy Iosif | 2000-11-25 | 2000-11-22 | 2000-11-23 | 2000-12-18 | 2001-01-08 | K 739 494 | 45 | 0 | 44.9 | K 739 494 | 215 | 0 | 44.9 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 18 | 18 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 36 | N/A | Brasov | HDSL | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | RBS | [10 empty] | BSC12 | BSC BRASOV |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PITURCESCU | OK | N/A |  | N/A | N/A | HDSL+30N01 Slanic Moldova-Brasov |  | OK | Petrica BURGHIU | Cosmorom | [32 empty] | 585 | Slanic Moldova | Bacau | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | BA043 | VASLUI_RTC_TEHNIC | Vaslui(4) | BA043 Vaslui_RTC_Tehnic | Moldova | 46 38 14.3 | 27 43 52 | 46 38 14.3 | 27 43 52 | Str. Ing. Badea Romeo, nr.1 | Romtelecom/Dl. Frintescu - 092/ 821 779 | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [7 empty] | N/A |  |  |  |  | 10 | B | 15.35 | 18m new pylonet | Room/Rack19" | IMSAT | OK | SETRACO | 2000-12-04 | 2001-03-15 | YesV | 2001-05-04 | Bogdan | 2001-04-17 | 2001-05-09 |  |  |  | N/A | 2000-10-24 |  | 2000-12-13 | 2001-02-20 |  |  |  | 2001-03-15 | ICOM | KEN KEN | 2001-03-15 | 2001-03-15 | 2001-03-19 | 2001-03-19 | 2001-04-20 |  | Yes | Alexandru Toma | 2001-04-20 | 2001-04-20 | 2001-04-20 |  |  | K 739 494 | 30 | 0 | 32.1 | K 739 494 | 150 | 0 | 32.1 | K 739 494 | 270 | 0 | 32.1 |  |  |  |  | N/A | 46.8 | 46.8 | 7/8" | 46.8 | 46.8 | 7/8" | 46.8 | 46.8 | 7/8" |  |  |  | 280.8 | N/A | Baneasa | FO | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | TMR 9202 | 20043 | 2001-06-25 | [5 empty] | 35/Indoor |  | 1 | BSC21 | BSC BANEASA | N/A | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | DINCA | OK | N/A |  | N/A | N/A | 30N03 Vaslui-Baneasa |  | 2000-12-22 | Petrica BURGHIU | Cosmorom | [32 empty] | 97 | Vaslui | Vaslui | [7 empty] | Site Near=Insertion Point
Phase_2 | TM | BA044 | MOINESTI_RTC | Road Onesti-Moinesti(4+1) | BA044 Moinesti_RTC | Moldova | 46 28 24.6 | 26 29 20.6 | 46 28 24.6 | 26 29 24.7 | Str. Tudor Vladimirescu, Moinesti | Romtelecom/ | N/A | N/A | N/A | N/A | N/A | [12 empty] | N/A | B | 14.01 | C1m | Room | IMSAT | OK | CRIS-CORI | 2000-12-07 | 2000-12-22 | YesV | 2001-03-05 | Doru | 2001-01-19 | 2001-03-13 |  |  |  | N/A | 2000-10-24 |  | 2000-11-15 | 1900-01-11 | [6 empty] | N/A | N/A |  |  |  |  | Yes |  | CTR BA045 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A | Baneasa | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | [5 empty] | 20044 | [9 empty] | BSC21 | BSC BANEASA | N/A | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A |  |  |  | Petrica BURGHIU | Cosmorom | [32 empty] | 507 | Moinesti | Bacau | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | BA045 | MOINESTI | Road Onesti-Moinesti(4+1) | BA044 Moinesti_RTC | Moldova | 46 28 34.3 | 26 28 44.7 | 46 28 31 | 26 28 50.6 | Extravilan MOINESTI | Primaria orasului Moinesti | 2102 | M | C+C+C+ | 2/2/2 | N/A | [12 empty] | 0 | M | 30 |  | N/A | SETRACO | OK | CRIS-CORI | 2001-08-01 | 2001-08-30 | CROM |  | Doru | [5 empty] | 2001-03-14 |  |  | 2001-07-18 | [15 empty] | CTR |  |  |  |  | K 739 494 | 450 | 0 | 30 | K 739 494 | 110 | 0 | 30 | K 739 494 | 185 | 0 | 30 | N/A | N/A | N/A | N/A | N/A | 40 | 40 | 7/8" | 40 | 40 | 7/8" | 38 | 38 | 7/8" | N/A | N/A | N/A | 236 | ML 38 E 1+0 | Baneasa | MW | 102 |  | 32 | 37 | [7 empty] | RBS | [10 empty] | BA044 | MOINESTI_RTC | 286 |  | 14 | [24 empty] | Petrica BURGHIU | Cosmorom | [32 empty] | 559 | Moinesti | Bacau | [7 empty] | 2 |  |  | 2
Phase_2 | CS | BA046 | COMANESTI | Road Onesti-Moinesti(4+1) | BA044 Moinesti_RTC | Moldova | 46 25 38.2 | 26 26 13.9 | 46 25 38.2 | 26 26 13.9 | Dealul Viei, Intravilan Comanesti | Nastasa Gheorghe, Nastasa Dumitru-034 371 224/Nastasa Gheorghe, Nastasa Dumitru-034 371 224 | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | IMSAT | OK | CRIS-CORI | 2000-12-05 | 2001-04-05 | YesV |  | Doru | [6 empty] | 2000-10-24 |  | 2000-11-27 | 2001-01-04 | [6 empty] | 2001-04-09 | 2001-04-09 |  |  |  | GATA-2101 |  |  | RBS 2101 |  |  |  |  | K 739 494 | 130 | 0 | 48.3 | K 739 494 | 280 | 0 | 48.3 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 23 E 1+0 | Baneasa | MW | 31 |  | 41.5 | 50 | [7 empty] | RBS | [10 empty] | BA045 | MOINESTI | 211 |  | 32/0.6 | 37 | [14 empty] | OK | OK | 2000-12-11 |  |  | 2001-01-22 |  |  |  | Petrica BURGHIU | COSMOROM | [32 empty] | 485 | Comanesti | Bacau | [7 empty] | 2 |  |  | 2
Phase_2 | CS | BA047 | DARMANESTI | Road Onesti-Moinesti(4+1) | BA044 Moinesti_RTC | Moldova | 46 21 30.8 | 26 29 57.7 | 46 21 30.8 | 26 29 57.7 | Extravilan DARMANEST, Dealul Caraboia | Ariston Emil, str. Victoriei, nr. 8 , Darmanesti/Ariston Emil, str. Victoriei, nr. 8 , Darmanesti | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | IMSAT | OK | SVF | 2001-02-13 | 2001-03-18 | YesV | 2001-05-30 | Doru | 2001-04-06 | [5 empty] | 2000-10-24 |  | 2001-01-25 | 2001-02-20 | [6 empty] | 2001-03-19 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 145 | 0 | 48.25 | K 739 494 | 340 | 0 | 48.25 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Baneasa | MW | 328 | 0.6 | 23/0.6 | 40 | [7 empty] | RBS | [10 empty] | BA046 | COMANESTI | 148 |  | 41.5 | 50 | [23 empty] | Petrica BURGHIU | Cosmorom | [32 empty] | 400 | Darmanesti | Bacau | [7 empty] | 2 |  |  | 2
Phase_2 | CS | BA048 | MAGURA_DRTV | Road Onesti-Moinesti(4+1) | BA050 Onesti_RTC | Moldova | 46 16 13.4 | 26 35 12.4 | 46 16 13.4 | 26 35 12.4 | Teren manastire Magura Ocnei | Parintele Arhimandrit Bulancea Dumitru, str. Alexandru cel Mare, nr.5/Parintele Arhimandrit Bulancea Dumitru, str. Alexandru cel Mare, nr.5 | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  | 0 | TE | 36 |  | N/A | IMSAT | OK | EL-MONT | 2001-02-15 | 2001-03-10 | YesV | 2001-04-04 | Doru | 2001-03-14 | 2001-04-06 |  |  |  | N/A | 2000-10-24 |  | 2000-11-08 | 2001-01-30 | [6 empty] | 2001-03-13 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 90 | 0 | 21.8 | K 739 494 | 325 | 0 | 21.8 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 35 | 35 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 70 | ML 15 E 1+0 | Baneasa | MW | 99 |  | 20.5 | 35 | [7 empty] | RBS | [10 empty] | BA050 | ONESTI_RTC | 279 |  | 31.8 | 11.8 | [20 empty] | new |  |  | Petrica BURGHIU | Cosmorom | [32 empty] | 510 | Tg. Ocna | Bacau | [7 empty] | 2 |  |  | 2
Phase_2 | CS | BA049 | REBREANU | Onesti(3) | BA050 Onesti_RTC | Moldova | 46 14 37.7 | 26 45 25.4 | 46 14 37.7 | 26 45 25.4 | Str. Emil Rebreanu Bl.111 Sc.2 | Asociatie de locatari/Foltea petre - ap. 54, 054/ 323 914 | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [13 empty] | B | 35 | C4m+C4m |  | SETRACO | OK | COMARK | 2001-06-29 | 2001-07-12 | Yes |  | Doru | [5 empty] | 2000-11-07 | 2000-11-30 |  | 2000-12-04 | OK | [14 empty] | CTR |  |  |  |  | K 739 494 | 45 | 0 | 36.3 | K 739 494 | 165 | 0 | 36 | K 739 494 | 285 | 0 | 36.3 |  |  |  |  | N/A | 10 | 10 | 7/8" | 10 | 10 | 7/8" | 17 | 17 | 7/8" |  |  |  | 74 |  | Baneasa | MW | 46 |  | 35.5 | 9 | [18 empty] | BA060 | MARASESTI | 226 |  | 40 | [21 empty] | 30N01 Onesti-Baneasa |  | 2001-03-12 | Petrica BURGHIU | Cosmorom | [32 empty] | 216 | Onesti | Bacau | [7 empty] | 2 |  |  | 2
Phase_2 | CS | BA050 | ONESTI_RTC | Onesti(3) | BA050 Onesti_RTC | Moldova | 46 15 01.5 | 26 46 00.7 | 46 15 01.5 | 26 46 00.7 | Str. Postei nr.4 | Romtelecom/ | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [7 empty] | N/A | N/A |  |  |  | 20 | B | 25 | 9m new pylonet | Room | IMSAT | OK | COMARK | 2000-12-08 | 2001-02-05 | YesV | 2001-03-06 | Doru | 2001-02-02 | 2001-03-13 |  |  |  | N/A | 2000-10-24 |  | 2000-11-15 | 2000-12-07 |  |  |  | 2001-02-09 | ICOM | Interactive | 2001-02-07 | 2001-02-07 | 2001-02-12 | 2001-02-13 | 2001-02-14 |  | Yes | Alexandru Toma | 2001-03-23 | 2001-03-22 | 2001-03-22 | 2001-04-24 | 2001-05-03 | K 739 494 | 45 | 0 | 32.4 | K 739 494 | 165 | 0 | 32.3 | K 739 494 | 285 | 0 | 32.5 |  |  |  |  | N/A | 12.4 | 12.4 | 7/8" | 12.3 | 12.3 | 7/8" | 12.5 | 12.5 | 7/8" |  |  |  | 75 | N/A | Baneasa | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | [5 empty] | 20050 | 2001-06-25 | [5 empty] | 45/indoor 2p |  |  | BSC21 | BSC BANEASA | N/A | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | DINCA | OK | N/A |  | N/A | N/A | 30N01 Onesti-Baneasa |  | 2001-03-12 | Petrica BURGHIU | Cosmorom | [32 empty] | 199 | Onesti | Bacau | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | BA051 | PANCIU_RTC | Road Urziceni-Tecuci(12) | BA036 Marasesti_RTC | Moldova | 45 54 24.2 | 27 05 20 | 45 54 24.2 | 27 05 20 | Sos. Maresal Antonescu 131 | Romtelecom/ | 2202 | M | C+C+C+ | 2/2/2 | 2202 | FEEDER(+6m) | N/A | N/A | N/A | N/A | N/A | [6 empty] | 9.5 | B | 9.5 | 10.26 m new pylonet | Room | IMSAT | OK | IMSAT | 2000-11-29 | 2001-03-01 | YesV | 2001-04-04 | Doru | 2001-03-06 | 2001-04-10 |  |  |  | N/A | 2000-10-24 |  | 2000-11-24 | 2000-12-12 |  |  |  | 2001-03-15 | ICOM | SVF | 2001-02-20 | 2001-02-20 | 2001-03-20 | 2001-03-21 | 2001-03-23 |  | Yes | Ion Soare | 2001-03-27 | 2001-03-27 | 2001-03-27 |  |  | K 739 494 | 70 | 0 | 18.3 | K 739 494 | 155 | 0 | 18.3 | K 739 494 | 310 | 0 | 18 |  |  |  |  | N/A | 25 | 25 | 7/8" | 25 | 25 | 7/8" | 25 | 25 | 7/8" |  |  |  | 150 | ML 15 E 1+0 | Galati | MW | 109 | 0.6 | 17.7 | 27 | 15/89 |  | 4x2/8 | 2U-3 | [14 empty] | BA036 | MARASESTI_RTC | 297 | 0.6 | 30 | 50 | 15/84 | [6 empty] | 43* | SVF | 2000-03-15 | 683 | 2001-03-19 | 2001-03-20 | 2001-03-23 | YRO | OK | 2001-03-27 |  |  |  | 30N01 Marasesti-Galati |  | OK | Petrica BURGHIU | Cosmorom | [32 empty] | 240 | Panciu | Vrancea | [7 empty] | 2 |  |  | 2
Phase_2 | CS | BA052 | ODOBESTI_RTC | Road Urziceni-Tecuci(12) | BA032 Focsani_RTC | Moldova | 45 45 37 | 27 03 59.5 | 45 45 37 | 27 03 59.5 | Sos. Stefan cel Mare, Odobesti | Romtelecom/ | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [7 empty] | N/A | N/A |  |  |  | 8 | B | 12.5 | 10.26m existing pylonet | Room | IMSAT | OK | IMSAT | 2000-11-27 | 2001-04-12 | YesV | 2001-05-24 | Doru | 2001-04-20 |  |  |  |  | N/A | 2000-10-24 |  | 2000-11-17 | 2000-12-15 |  |  |  | 2001-04-03 | ICOM | VECTOR | 2001-04-03 | 2001-04-03 | 2001-04-05 | 2001-04-17 | 2001-04-20 |  | Yes | Ion Soare | 2001-05-13 | 2001-05-13 | 2001-05-13 | 2001-05-25 | 2001-06-19 | K 739 494 | 15 | 0 | 18.1 | K 739 494 | 130 | 0 | 18.2 | K 739 494 | 250 | 0 | 18.2 |  |  |  |  | N/A | 25 | 25 | 7/8" | 25 | 25 | 7/8" | 25 | 25 | 7/8" |  |  |  | 150 | ML 15 E 1+0 | Galati | MW | 126 | 0.6 | 17.8 | 27 | 15/84 |  | 4x2/8 | 2U-3 | [7 empty] | XC21032 | [5 empty] | 1 | BA032 | FOCSANI_RTC | 306 | 0.6 | 29 | 50 | 15/89 | [6 empty] | 53* | VECTOR | 2001-04-03 | 818 | 2001-04-04 | 2001-04-05 | 2001-04-25 | RADU | OK | 2001-05-13 |  | 2001-05-21 | 2001-05-25 | 30N02 Focsani-Baneasa | optimizare fluxuri(vezi harta de transmisiuni) | 2001-04-20 | Petrica BURGHIU | Cosmorom | [32 empty] | 154 | Odobesti | Vrancea | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BA053 | ALBITA | Road Albita-Crasna(6) | BA056 Husi_RTC | Moldova | 46 46 59.2 | 28 07 43.3 | 46 47 02.4 | 28 07 40.9 | Extravilan comuna Drancesti-parcela nr. 959/47 | Bucos Vasile, comuna Drancesti sat Rasesti/Bucos Vasile, comuna Drancesti sat Rasesti | 2102 | M | C+C+C+ | 2/2/2 | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | IMSAT | OK | SVF | 2000-11-30 | 2001-03-18 | YesV | 2001-04-20 | Bogdan | 2001-03-23 | 2001-04-25 |  |  | 2001-06-08 |  | 2000-10-24 |  | 2000-11-23 | 2001-02-26 | [6 empty] | 2001-07-13 | [5 empty] | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 50 | 0 | 48.25 | K 739 494 | 180 | 0 | 50 | K 739 494 | 345 | 0 | 50 | N/A | N/A | N/A | N/A | N/A | 60 | 60 | 1 1/4" | 60 | 60 | 1 1/4" | 60 | 60 | 1 1/4" | 60 | 60 | 1 1/4" | 360 | ML 15 E 1+0 | Baneasa | MW | 181 |  | 30 | 40 | [7 empty] | RBS | [10 empty] | BA054 | VALEA GRECULUI | 1 |  | 42 | 54 | [23 empty] | Petrica BURGHIU | #N/A | [32 empty] | 99 | Rusesti | Vaslui | [7 empty] | 2 |  |  | 2
Phase_2 | CS | BA054 | VALEA GRECULUI | Road Albita-Crasna(6) | BA056 Husi_RTC | Moldova | 46 43 04.4 | 28 07 35.3 | 46 43 4 | 28 07 35 | Extravilan com. Duda Epureni, sat Valea Grecului | Matei Ilie, com. Duda Epuri, sat Valea Grecului/Matei Ilie, com. Duda Epuri, sat Valea Grecului | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-12-11 | N/A | N/A |  |  |  | 0 | TN | 50 |  | N/A | IMSAT | OK | QUALITY | 2000-11-15 | 2001-03-05 | YesV | 2001-06-11 | Bogdan | 2001-03-14 | 2001-06-14 |  |  |  |  | 2001-07-10 |  | 2000-11-13 | 2000-11-23 |  | 2001-07-17 |  |  |  |  | 2001-03-07 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 0 | 0 | 48.25 | K 739 494 | 210 | 0 | 48.25 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+1 (PS) | Baneasa | MW | 243 |  | 42 | 54 | [7 empty] | RBS | [10 empty] | BA055 | HUSI | 63 |  | 41.5 | 52 | [23 empty] | Petrica BURGHIU | Cosmorom | [32 empty] | 118 | Valea Grecului | Vaslui | [7 empty] | 2 |  |  | 2
Phase_2 | CS | BA055 | HUSI | Road Albita-Crasna(6) | BA056 Husi_RTC | Moldova | 46 40 53.8 | 28 01 23.8 | 46 40 53.8 | 28 01 23.8 | Intravilan in orasul Husi-parcela 1568 | Elisei Maria, str. Fundatura Dobrina, nr. 13, Husi, jud. Vaslui/Elisei Maria, str. Fundatura Dobrina, nr. 13, Husi, jud. Vaslui | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | IMSAT | OK | SVF | 2000-11-28 | 2001-03-07 | YesV | 2001-03-27 | Bogdan | 2001-03-23 | 2001-03-29 |  |  |  |  | 2001-07-10 |  | 2000-11-17 | 2000-12-06 | [6 empty] | 2001-03-13 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 100 | 0 | 48.3 | K 739 494 | 230 | 0 | 48.3 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 38 E 1+1 | Baneasa | MW | 110 |  | 41.5 | 52 | [7 empty] | RBS | [10 empty] | BA056 | HUSI_RTC | 290 |  | 22.35 | 24 | [23 empty] | Petrica BURGHIU | Cosmorom | [32 empty] | 299 | Husi | Vaslui | [7 empty] | 2 |  |  | 2
Phase_2 | CS | BA056 | HUSI_RTC | Road Albita-Crasna(6) | BA056 Husi_RTC | Moldova | 46 40 22.1 | 28 03 29.8 | 46 40 22.1 | 28 03 29.8 | Str. Ion Alexandru Angheluta nr.2 | Romtelecom/ | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [7 empty] | N/A | N/A |  |  |  | 10 | B | 16.25 | 9m new pylonet | Room | IMSAT | OK | QUALITY | 2000-11-29 | 2001-01-20 | YesV | 2001-05-03 | Bogdan | 2001-02-21 | 2001-05-09 |  |  |  | N/A | 2001-07-05 |  | 2000-11-17 | 2000-12-06 |  |  |  | 2001-02-19 | ICOM | CAMUSAT | 2001-01-26 | 2001-01-26 | 2001-02-21 | 2001-02-27 | 2001-02-28 |  | Yes | Ion Soare | 2001-03-27 | 2001-03-27 | 2001-03-27 | 2001-04-24 | 2001-05-15 | K 739 494 | 20 | 0 | 23.07 | K 739 494 | 140 | 0 | 23.07 | K 739 494 | 260 | 0 | 23.07 |  |  |  |  | N/A | 24 | 24 | 7/8" | 24 | 24 | 7/8" | 24 | 24 | 7/8" |  |  |  | 144 | N/A | Baneasa | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | [5 empty] | 20056 | 2001-06-25 | [5 empty] | 50/Indoor |  |  | BSC21 | BSC BANEASA | N/A | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | DINCA | OK | N/A |  | N/A | N/A | 30N01 Husi-Baneasa |  | 2001-03-05 | Petrica BURGHIU | Cosmorom | [32 empty] | 98 | Husi | Vaslui | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | BA057 | CRETESTI | Road Albita-Crasna(6) | BA043 Vaslui_RTC_Tehnic | Moldova | 46 38 04.9 | 27 57 47.2 | 46 38 05.7 | 27 27 46.9 | Sat Cretestii de Jos, com. Cretesti | Primaria Cretesti, jud. Vaslui/Primar Cornea Corneliu | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | IMSAT | OK | QUALITY | 2000-12-13 | 2001-03-05 | YesV | 2001-05-03 | Bogdan | 2001-04-06 | 2001-05-09 |  |  |  |  | 2000-10-24 |  | 2000-12-06 | 2000-12-18 | [6 empty] | 2001-03-08 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 30 | 0 | 48.3 | K 739 494 | 225 | 0 | 48.3 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Baneasa | MW | 225 |  | 47 | 60 | [7 empty] | RBS | [10 empty] | BA058 | TARZII | 45 |  | 47 | 60 | [23 empty] | Petrica BURGHIU | Cosmorom | [32 empty] | 156 | Cretestii de Jos | Vaslui | [7 empty] | 2 |  |  | 2
Phase_2 | CS | BA058 | TARZII | Road Albita-Crasna(6) | BA043 Vaslui_RTC_Tehnic | Moldova | 46 34 17.1 | 27 52 11.9 | 46 34 17.1 | 27 52 11.9 | Intravilan com. Oltenesti, sat Tarzii, parcela nr.273 | Idriceanu Dumitru - com. Oltenesti, sat Tarzii/Idriceanu Dumitru - com. Oltenesti, sat Tarzii | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | IMSAT | OK | QUALITY | 2000-12-01 | 2001-03-23 | YesV | 2001-05-03 | Bogdan | 2001-04-06 | 2001-05-09 |  |  |  | OK | 2000-10-24 |  | 2000-11-24 | 2000-12-18 | [6 empty] | 2001-03-26 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 45 | 0 | 48.3 | K 739 494 | 205 | 0 | 48.3 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Baneasa | MW | 331 |  | 47 | 60 | [7 empty] | RBS | [10 empty] | BA029 | VASLUI_DRTV | 331 | 1.2 | 47/1.2 | [24 empty] | Petrica BURGHIU | Cosmorom | [32 empty] | 164 | Tirzii | Vaslui | [7 empty] | 2 |  |  | 2
Phase_2 | CS | BA060 | MARASESTI | Onesti(3) | BA050 Onesti_RTC | Moldova | 46 15 24 | 26 46 32.9 | 46 15 24.7 | 26 46 32.9 | Str. Marasesti bl.10, sc.D | Asociatie de locatari nr.34 - Ristea Nicolae, str. Armoniei nr.3,ap.41, sc.C 034/ 312 875/Ristea Nicolae, str. Armoniei nr.3,ap.41, sc.C, tel. 034/ 312 875 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [12 empty] | 36.5 | B | 36.5 | T4.5m+T4.5m | N/A | SETRACO | OK | COMARK | 2001-06-29 | 2001-07-12 | Yes |  | Doru | [5 empty] | 2000-11-10 | 2000-10-24 |  | 2000-12-06 | OK | [14 empty] | CTR |  |  |  |  | K 739 494 | 45 | 0 | 39.7 | K 739 494 | 165 | 0 | 39.5 | K 739 494 | 285 | 0 | 39.7 |  |  |  |  | N/A | 13 | 13 | 7/8" | 13 | 13 | 7/8" | 10 | 10 | 7/8" |  |  |  | 72 |  | Baneasa | MW | 225 |  | 39.3 | 9 | [7 empty] | RBS | [10 empty] | BA050 | ONESTI_RTC | 45 |  | 32 | 12 | [20 empty] | new |  |  | Petrica BURGHIU | Cosmorom | [32 empty] | 194 | Onesti | Bacau | [7 empty] | 2 |  |  | 2
Phase_2 | CS | BA061 | BULBOACA | Road Barlad-Vaslui(3) | BA043 Vaslui_RTC_Tehnic | Moldova | 46 32 30.9 | 27 47 17.8 | 46 33 30.9 | 27 47 17.8 | Sat Bulboaca, com. Deleni, parcela 520/24 | Tanase Vasile-sat Bolboaca, com. Deleni/Tanase Vasile-sat Bolboaca, com. Deleni | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | IMSAT | OK | IASSID | 2000-12-01 | 2001-02-15 | YesV | 2001-02-21 | Eugen | 2001-04-06 | 2001-02-26 |  |  |  |  | 2000-10-24 |  | 2000-11-23 | 2001-01-10 | [6 empty] | 2001-02-16 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 140 | 0 | 48.3 | K 739 494 | 345 | 0 | 48.3 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Baneasa | MW | 333 |  | 47 | 60 | [7 empty] | RBS | [10 empty] | BA028 | VASLUI-SILOZ | 153 |  | 52.5 | 13.5 | [23 empty] | Petrica BURGHIU | [33 empty] | 100 | Deleni | Vaslui | [7 empty] | 2 |  |  | 2
Phase_2 | CS | BA062 | GARA ROSIESTI | Road Barlad-Vaslui(3) | BA063 Gara Banca_RTC | Moldova | 46 25 46.5 | 27 50 07.1 | 46 26 46 | 27 50 07.8 | Teren intravilan in Sat Gara Rosiesti parcela 1019-tarla 55 | Chelaru Catalin, sat Gara Rosiesti, com. Rosiesti/Chelaru Catalin | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | IMSAT | OK | IASSID | 2000-11-29 | 2001-02-14 | YesV | 2001-02-21 | Eugen | 2001-02-26 | 2001-02-26 |  |  |  |  | 2000-10-24 |  | 2000-11-21 | 2000-12-08 | [6 empty] | 2001-02-16 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 210 | 0 | 48.25 | K 739 494 | 345 | 0 | 48.25 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Baneasa | MW | 197 |  | 47 | 60 | [7 empty] | RBS | [10 empty] | BA063 | GARA BANCA | 17 |  | 47 | 57 | [20 empty] | new |  |  | Petrica BURGHIU | Cosmorom | [32 empty] | 79 | Gara Rosiesti | Vaslui | [7 empty] | 2 |  |  | 2
Phase_2 | CS | BA063 | GARA BANCA | Road Barlad-Vaslui(3) | BA063 Gara Banca_RTC | Moldova | 46 20 09.7 | 27 47 34.1 | 46 20 09.7 | 27 47 34.1 | RTC Gara Banca, sat Gara Banca, Com. Banca | Romtelecom/ | 2202 | M | C+C+ | 2/2 | 2202 | [7 empty] | N/A | N/A |  |  |  |  | TN | 50 |  | Room | IMSAT | OK | IASSID | 2000-11-15 | 2001-02-05 | YesV | 2001-02-20 | Eugen | 2001-02-19 | 2001-02-26 |  |  |  | N/A | 2001-05-09 |  | 2000-11-13 | 2000-12-05 |  |  |  | 2001-02-19 | ICOM | CAMUSAT | 2001-02-05 | 2001-02-05 | 2001-02-21 | 2001-02-28 | 2001-03-02 | IVAN | Yes | Ion Soare | 2001-06-05 | 2001-06-07 | 2001-06-07 |  |  | K 739 494 | 0 | 0 | 48.3 | K 739 494 | 230 | 0 | 48.3 | N/A | N/A | N/A | N/A |  |  |  |  | N/A | 70 | 70 | 1 1/4" | 70 | 70 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | 280 | N/A | Baneasa | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | [5 empty] | 20063 | 2001-06-25 | [5 empty] | 25/2p indoor |  |  | BSC21 | BSC BANEASA | N/A | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | IVAN | OK | N/A |  | N/A | N/A | 30N01 Gara Banca-Baneasa |  | 2001-05-03 | Denis CIUCU | Cosmorom | [32 empty] | 79 | Gara Banca | Vaslui | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | BA064 | BARLAD K3 | Barlad(3+1) | BA067 Barlad_RTC | Moldova | 46 14 21.9 | 27 40 26.2 | 46 14 21.9 | 27 40 26.2 | B-dul. Republicii nr.304 bl.K3 sc.B | Asociatie de locatari nr.4, STR. Republicii, nr. 304/Badarau Emil - pres., Panaitescu Vasile-sef de scara | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | Yes | N/A |  |  |  | 27 | B | 30.2 | T6m | N/A | IMSAT | OK | GIRARDOT | 2000-12-19 | 2001-02-15 | YesV | 2001-04-19 | Eugen | 2001-05-07 | 2001-04-19 |  |  |  |  | 2000-10-24 |  | 2000-12-06 | 2001-01-19 |  |  |  | 2001-02-16 | ICOM | ORION | 2001-02-16 | 2001-02-16 | 2001-02-19 | 2001-02-28 | 2001-03-02 |  | Yes | Alexandru Toma | 2001-04-18 | 2001-04-19 | 2001-04-19 |  |  | K 739 494 | 30 | 0 | 31.65 | K 739 494 | 150 | 0 | 34.5 | K 739 494 | 270 | 0 | 34.5 |  |  |  |  | N/A | 16 | 16 | 7/8" | 18 | 18 | 7/8" | 18 | 18 | 7/8" | N/A | N/A | N/A | 104 | ML 23 E 1+0 | Baneasa | MW | 197 | 0.6 | 33.2 | 16.5 | 23/56 |  |  | 2U-3 |  |  |  | RBS | [9 empty] | 1 | BA065 | BARLAD-UMPS | 17 | 0.6 | 37.4/0.3 | 12.5 | 23/58 | [6 empty] | 28* | ORION | 2001-02-16 | 648 | 2001-02-19 | 2001-02-22 | 2001-03-02 | DINCA | OK | 2001-04-19 |  | 2001-04-23 | 2001-04-30 | 30N02 Barlad-Baneasa |  | 2001-03-15 | Petrica BURGHIU | Petrica BURGHIU | [32 empty] | 77 | Barlad | Vaslui | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BA065 | BARLAD-UMPS | Barlad(3+1) | BA067 Barlad_RTC | Moldova | 46 13 42 | 27 40 09.4 | 46 13 42.9 | 27 40 08.9 | Str. Republicii nr.217, bloc UMPS, sc.A | Asociatie de locatari/Ursu Octav; Dl. Carcota ap.7, tel. 035/ 417 310; Ionescu ap.1, tel.035/ 422 646 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | Yes | N/A |  |  |  | 34 | B | 37 | T6m+T6m | N/A | IMSAT | OK | ORION | 2001-01-18 | 2001-02-15 | YesV | 2001-03-14 | Eugen | 2001-03-26 | 2001-03-19 |  |  |  |  | 2000-10-24 |  | 2000-12-15 | 2001-01-23 |  |  |  | 2001-02-16 | ICOM | ORION | 2001-02-16 | 2001-02-16 | 2001-02-19 | 2001-02-27 | 2001-02-28 |  | Yes | Ion Soare | 2001-04-08 | 2001-04-08 | 2001-04-08 |  |  | K 739 494 | 20 | 0 | 38.2 | K 739 494 | 150 | 0 | 38.2 | K 739 494 | 270 | 0 | 38.2 |  |  |  |  | N/A | 14 | 14 | 7/8" | 14 | 14 | 7/8" | 22 | 22 | 7/8" | N/A | N/A | N/A | 100 | ML 38 E 1+1 | Baneasa | MW | 8 | 0.3 | 37/0.3 | 12 | 38/17 |  |  | 4U-1 |  |  |  | RBS | [9 empty] | 1 | BA067 | BARLAD_RTC | 188 | 0.3 | 17.5 | 42 | 38/13 | [6 empty] | 28* | ORION | 2001-02-16 | 649 | 2001-02-19 | 2001-02-22 | 2001-03-02 | DINCA | OK | 2001-04-08 | PENDING |  |  | 30N02 Barlad-Baneasa |  | 2001-03-15 | Petrica BURGHIU | Petrica BURGHIU | [32 empty] | 106 | Barlad | Vaslui | [7 empty] | 2 |  |  | 2
Phase_2 | CS | BA066 | BARLAD_P10 | Barlad(3+1) | BA067 Barlad_RTC | Moldova | 46 12 54.1 | 27 39 42.5 | 46 12 54.5 | 27 39 41.6 | Str. Republicii nr.1, bl.P10, sc.1 | Asociatie de locatari/Boboarca Daniel - ap.4, 035/ 420 530 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | Yes | N/A |  |  |  | 34 | B | 34 | T6m | N/A | IMSAT | OK | GIRARDOT | 2000-12-13 | 2001-02-05 | YesV | 2001-02-21 | Eugen | 2001-05-07 | 2001-02-26 |  |  |  |  | 2000-10-24 |  | 2000-12-06 | 2000-12-18 |  |  |  | 2001-02-19 | ICOM | CAMUSAT | 2001-02-05 | 2001-02-05 | 2001-02-21 | 2001-02-22 | 2001-02-23 |  | Yes | Alexandru Toma | 2001-04-18 | 2001-04-19 | 2001-04-19 |  |  | K 739 494 | 30 | 0 | 38.4 | K 739 494 | 130 | 0 | 37.9 | K 739 494 | 220 | 0 | 38.4 |  |  |  |  | N/A | 13 | 13 | 7/8" | 13 | 13 | 7/8" | 13 | 13 | 7/8" | N/A | N/A | N/A | 78 | ML 23 E 1+0 | Baneasa | MW | 21 | 0.6 | 37 | 13 | 23/56 |  |  | 2U-3 |  |  |  | RBS | [9 empty] | 1 | BA065 | BARLAD-UMPS | 201 | 0.6 | 37.5/0.3 | 21 | 23/58 | [6 empty] | 28* | CAMUSAT | 2001-02-16 | 672 | 2001-02-27 | 2001-02-27 | 2001-02-28 | DINCA | OK | 2001-04-19 |  | 2001-07-12 |  | 30N01 Barlad-Baneasa |  | 2001-03-15 | Petrica BURGHIU | Petrica BURGHIU | [32 empty] | 88 | Barlad | Vaslui | [7 empty] | 2 |  |  | 2
Phase_2 | TM | BA067 | BARLAD_RTC | Barlad(3+1) | BA067 Barlad_RTC | Moldova | 46 13 49.4 | 27 40 10.7 | 46 13 49.4 | 27 40 10.7 | Str. Republicii nr.277 | Romtelecom/D-nul. Sacoliuc - 094/ 924 681 | N/A | N/A | N/A | N/A | N/A | [12 empty] | N/A | B | 28 | C1.5m | Room | IMSAT | OK | GIRARDOT | 2000-12-04 | 2000-12-20 | YesV | 2001-04-19 | Eugen | 2001-01-11 | 2001-04-19 |  |  |  | N/A | 2000-10-24 |  | 2000-11-15 | 2000-12-04 |  |  |  | 2001-02-21 | ICOM | ORION | N/A | N/A | 2001-02-22 | N/A | N/A |  | Yes | N/A | 2001-04-08 | 2001-04-08 | 2001-04-08 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Baneasa | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | 2U-3 |  |  |  |  | 20068 | 2001-06-25 | [5 empty] | 10/Indoor |  |  | BSC21 | BSC BANEASA | N/A | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | DINCA | OK | N/A |  | N/A | N/A | N/A |  | 2001-03-15 | Petrica BURGHIU | Petrica BURGHIU | [32 empty] | 109 | Barlad | Vaslui | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | BA068 | TUTOVA | Road Barlad-Tecuci(3) | BA067 Barlad_RTC | Moldova | 46 07 44.2 | 27 34 16.2 | 46 07 38.1 | 27 34 03.7 | Intravilan sat Tutova, com. Tutova | Primaria Tutova/Sandu Stan-primar si Timoftei Mihaila contabil | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | IMSAT | OK | TEHNOROB | 2000-12-08 | 2001-02-26 | YesV | 2001-03-19 | Bogdan |  | 2001-03-21 |  |  |  |  | 2000-10-24 |  | 2000-12-04 | 2000-12-11 | [6 empty] | 2001-02-28 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 30 | 0 | 48.25 | K 739 494 | 225 | 0 | 48.25 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Baneasa | MW | 36 |  | 47 | 60 | [7 empty] | RBS | [10 empty] | BA066 | BARLAD_P10 | 216 | 1.2 | 37/1.2 | 13 | [20 empty] | 30N01 Barlad-Baneasa |  | 2001-03-15 | Petrica BURGHIU | Cosmorom | [32 empty] | 80 | Tutova | Vaslui | [7 empty] | 2 |  |  | 2
Phase_2 | CS | BA069 | NICHISENI | Road Barlad-Tecuci(3) | BA067 Barlad_RTC | Moldova | 46 02 39.7 | 27 27 28 | 46 02 37.2 | 27 27 36.5 | Extravilan com. Nichiseni | Primaria Nichiseni/Dl. Primar Chitiga Gheorghe-primaria Ghidigeni | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | IMSAT | OK | EL-MONT | 2000-12-21 | 2001-05-25 | YesV | 2001-06-07 | Bogdan |  | 2001-06-14 |  |  |  |  | 2000-10-24 |  | 2000-12-12 | 2001-01-09 | [6 empty] | 2001-05-28 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 30 | 0 | 48.25 | K 739 494 | 195 | 0 | 48.25 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Baneasa | MW | 42 | 1.2 | 47/1.2 | 60 | [7 empty] | RBS | [10 empty] | BA068 | TUTOVA | 222 |  | 47 | 60 | [20 empty] | 30N01 Barlad-Baneasa |  | 2001-03-15 | Petrica BURGHIU | Cosmorom | [32 empty] | 68 | Nichiseni | Vaslui | [7 empty] | 2 |  |  | 2
Phase_2 | CS | BA070 | MUNTENI | Road Barlad-Tecuci(3) | BA070 Munteni | Moldova | 45 57 27.2 | 27 25 48.4 | 45 55 06.6 | 27 26 53.1 | Sat Munteni, com. Munteni | Romtelecom/ | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  | 0 | TE | 30 |  | N/A | IMSAT | OK | TEHNOROB | 2001-02-13 | 2001-04-05 | YesV | 2001-05-03 | Bogdan |  | 2001-05-09 |  |  |  | 2000-11-01 | 2000-10-24 |  | 2000-12-04 | 2000-12-18 | [6 empty] | 2001-04-09 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 0 | 0 | 34 | K 739 494 | 185 | 0 | 34 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 44 | 44 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 88 | N/A | Baneasa | HDSL | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | RBS | N/A | [9 empty] | BSC21 | BSC BANEASA |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | HDSL+new |  |  | Petrica BURGHIU | Cosmorom | [32 empty] | 62 | Munteni | Galati | [7 empty] | Site Near=Insertion Point
Phase_3 | CS | BA071 | PUFESTI | Road Adjud-Focsani(1) | BX105 Cosmesti_RTC | Moldova | 46 00 0.3 | 27 11 24 | 46 00 03.3 | 27 11 24 | Com. Pufesti, punctul Hatas, tarla 9 | Nastasache Maria si Spataru Gavrila, com. Pufesti | 2101 | M | C+ | 2 | 2101 | [12 empty] | 0 | TN | 50/6mp |  | N/A | SETRACO | OK | EMONTAJ | 2001-06-20 | 2001-07-18 | in exec |  | Vali |  |  | 2001-04-25 |  |  | 2001-02-20 |  |  | 2001-04-09 | 2001-05-03 | [14 empty] | RBS 2101 |  |  |  |  | K 739 494 | 0 | 0 | 49 | K 739 494 | 170 | 0 | 49 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 63 | 63 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 126 | ML 15 E 1+0 | Galati | MW | 150 | 1.2 | 47/1.2 | 62 | [7 empty] | N/A | XC30105 | [9 empty] | BX105 | COSMESTI_RTC | 330 | 1.2 | 40 | [21 empty] | 30N01 Cosmesti-Galati |  | 2001-01-26 | Denis CIUCU | Calin ACHIM | [32 empty] | ? | Pufesti | Vrancea | [7 empty] | 3 |  |  | 3
Phase_3 | CS | BA072 | SASCUT | Road Adjud-Bacau(4) | BA037 Adjud_RTC | Moldova | 46 12 23.9 | 27 06 46.8 | 46 12 23.9 | 27 06 46.8 | Siloz Sascut | Comcereal Bacau-Director, tel. 092/514978/Dir Blulata Corneliu, tel. 092/514978 si contabil sef-Moise Constantin, tel. 095/514973 | MAXITE | M | 1 | 2 | 2PBC | [7 empty] | YES |  |  |  |  | 60 | S | 60 | S-drapel+S-colt ?m | N/A/TMR9000 | ORION | OK | ORION | 2001-07-05 | 2001-07-19 | in exec |  | Vali |  |  | 2001-02-28 |  |  | 2001-03-21 |  |  | 2001-05-07 | 2001-06-25 | [14 empty] | MAXITE |  |  |  |  | AAU | 160 | 0 | 59 | AAU | 335 | 0 | 59 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 20 | 20 | 1/2" | 26 | 26 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A | 94 |  | Galati | MW | 157 | 0.6 | 61 | 10 | [18 empty] | BA037 | ADJUD_RTC | [24 empty] | 30N01 |  |  | Denis CIUCU | Calin ACHIM | [32 empty] | 148 | Sascut | Bacau | [7 empty] | 3 |  |  | missing
Phase_3 | CS | BA073 | RACACIUNI | Road Adjud-Bacau(4) | BA037 Adjud_RTC | Moldova | 46 19 21.1 | . | 46 19 19.7 | 27 00 37.3 | Comuna Racaciuni | Consiliul Local Racaciuni/Primar I. Ichim 034/251212 | 2101 | M | C+ | 2 | 2101 | [12 empty] | 0 | TN | 50 |  | N/A | ORION | OK | ORION | 2001-07-05 | 2001-07-31 | in exec |  | Vali |  |  | 2001-02-28 |  |  | 2001-03-21 |  |  | 2001-06-12 | [15 empty] | RBS 2101 |  |  |  |  | K 739 494 | 145 | 0 | 30 | K 739 494 | 350 | 0 | 30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | 45 | 45 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 90 |  | Galati | MW | 149 | 1.2 | 28 | 45 | [7 empty] | N/A | [10 empty] | BA072 | SASCUT | 329 | 1.2 | 62 | 13 | [20 empty] | 30N01 |  |  | Denis CIUCU | Calin ACHIM | [32 empty] | 149 | Comuna Racaciuni | Bacau | [7 empty] | 3 |  |  | 3
Phase_3 | CS | BA074 | CLEJA | Road Adjud-Bacau(4) | BA013 Cornisei_RTC | Moldova | 46 24 11 | 26 56 27 | 46 24 39.5 | 26 55 46.7 | Cleja | Serban P. Mihai, loc. Cleja, nr. 438 | MAXITE | M | 1 | 2 | 2PBC | [12 empty] | 0 | TN | 30/6mp |  | N/A/TMR9000 | ORION | OK | ORION | 2001-07-05 | 2001-07-31 | in exec |  | Vali |  |  | 2001-02-28 | [5 empty] | 2001-06-25 | [15 empty] | RBS 2101 |  |  |  |  | AAU | 140 | 0 | 30 | AAU | 355 | 0 | 30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | 45 | 45 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 90 |  | Baneasa | MW | 335 | 0.6 | 28 | 45 | [18 empty] | BA075 | BACAU UZINA | 175 | [23 empty] | new |  |  | Denis CIUCU | Calin ACHIM | [32 empty] | 161 | Cleja | Bacau | [7 empty] | 3 |  |  | 3
Phase_3 | CS | BA075 | BACAU UZINA | Road Adjud-Bacau(4) | BA013 Cornisei_RTC | Moldova | 46 31 04.1 | 26 55 42.7 |  |  |  |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | YES | [9 empty] | SVF |  | @ | 2001-08-01 | 2001-09-10 |  |  | Bogdan |  |  | 2001-02-28 | 2001-06-07 | [20 empty] | CTR | [35 empty] | Baneasa | MW | 37 | [21 empty] | BA013 | CORNISEI | 163 | [23 empty] | new |  |  | Denis CIUCU | Calin ACHIM | [42 empty] | 3 |  |  | missing
Phase_3 | CS | BA076 | ITESTI | Road Bacau-Roman(2) | BA014 Stefan Cel Mare_RTC | Moldova | 46 39 46 | 26 51 32 | 46 39 46.7 | 26 51 32.9 | Itesti | Ciubotaru, Itesti | 2102 | M | C+C+C+ | 2/2/2 | N/A | [12 empty] | 0 | TN | 50 |  | N/A | ORION | OK | ORION | 2001-08-01 | 2001-09-10 |  |  | Vali |  |  | 2001-02-28 |  |  | 2001-03-30 |  |  | 2001-07-18 | 2001-07-18 | [14 empty] | CTR |  |  |  |  | K 739 494 | 50 | 0 | 49.3 | K 739 494 | 120 | 0 | 49.3 | K 739 494 | 270 | 0 | 49.3 | N/A | N/A | N/A | N/A | N/A | 70 | 70 | 1 1/4" | 70 | 70 | 1 1/4" | 70 | 70 | 1 1/4" | N/A | N/A | N/A | 420 | ML 15 E 1+0 | Baneasa | MW | 155 | 0.6 | 48 | 65 | [18 empty] | BA014 | STEFAN CEL MARE | 334 | [23 empty] | new |  |  | Denis CIUCU | Calin ACHIM | [32 empty] | 185 | Itesti | Bacau | [7 empty] | 3 |  |  | missing
Phase_3 | CS | BA077 | FILIPESTI | Road Bacau-Roman(2) | BA014 Stefan Cel Mare_RTC | Moldova | 46 44 51 | 26 52 37 | 46 44 51.9 | 26 52 30.8 | Cirligi | Canachi Dumitru - Cirligi, 034/ 215 681 | MAXITE | M | 1 | 2 | 2PBC | [12 empty] | 0 | TN | 50 |  | N/A/TMR9000 | ORION | OK | ORION | 2001-07-05 | 2001-07-31 | in exec |  | Vali |  |  | 2001-02-28 |  |  | 2001-03-30 |  |  | 2001-05-20 | 2001-06-13 | [14 empty] | RBS 2101 |  |  |  |  | AAU | 10 | 0 | 50 | AAU | 165 | 0 | 50 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | 70 | 70 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 140 |  | Baneasa | MW | 189 | 1.2 | 49 | 65 | [18 empty] | BA076 | ITESTI | 9 |  | 48.5/0.6 | 65 | [20 empty] | new |  |  | Denis CIUCU | Calin ACHIM | [32 empty] | 98.5 | Cirligi | Bacau | [7 empty] | 3 |  |  | 3
Phase_3 | CS | BA078 | SABAOANI | Road Iasi-Roman(4+1) | BA025 Roman 1_RTC | Moldova | 47 01 42 | 26 52 58 | 47 01 44 | 26 52 59 | Comuna Sabaoani | Cobzaru Tereza | 2102 | M | C+C+C+ | 2/2/2 | N/A | [12 empty] | 0 | TN | 50 |  | N/A | PROTELCO | OK | EMONTAJ | 2001-08-01 | 2001-08-30 |  |  | Vali |  |  | 2001-02-28 |  |  | 2001-03-21 |  |  | 2001-06-12 |  | Old Obs: | [13 empty] | CTR |  |  |  |  | K 739 494 | 15 | 0 | 48 | K 739 494 | 160 | 0 | 48 | K 739 494 | 290 | 0 | 48 | N/A | N/A | N/A | N/A | N/A | 57 | 57 | 1 1/4" | 57 | 57 | 1 1/4" | 57 | 57 | 1 1/4" | N/A | N/A | N/A | 342 |  | Baneasa | MW | 163 | 0.6 | 47.5 | 56.5 | [18 empty] | BA026 | ROMAN_2 | 343 | [23 empty] | new |  |  | Denis CIUCU | Calin ACHIM | [32 empty] | 253 | Comuna Sabaoani | Neamt | [6 empty] | 1 | 3 |  |  | missing
Phase_3 | CS | BA079 | SOCI | Road Iasi-Roman(4+1) | BA025 Roman 1_RTC | Moldova | 47 09 36 | 26 56 45 |  |  |  |  | 2101 | M | C+ | 2 | 2101 | [17 empty] | PROTELCO |  | @ | 2001-08-01 | 2001-09-10 |  |  | Vali |  |  | 2001-02-28 |  |  | 2001-06-25 | [18 empty] | RBS 2101 | [35 empty] | Baneasa | MW | 198 | [21 empty] | BA078 | SABAOANI | 18 | 1.2 | 47 | 56 | [20 empty] | new |  |  | Denis CIUCU | [43 empty] | 3 |  |  | missing
Phase_3 | CS | BA080 | TARGU FRUMOS | Road Iasi-Roman(4+1) | BA031 Independentei_RTC | Moldova | 47 12 40 | 27 00 47 | 47 12 38.9 | 27 00 51.2 | Str. Petru Rares bl.19 sc.B | Asociatie de locatari/Moisache Aurelia - str. Petru Rares bl.19 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | YES |  |  |  |  | 15 | B | 17.2 |  | N/A | PROTELCO | OK | EMONTAJ | 2001-08-01 | 2001-08-20 |  |  | Vali |  |  | 2001-02-28 | 2001-06-22 |  | 2001-03-30 |  |  | 2001-07-02 |  | Old Obs: | [13 empty] | CW NOT STARTED |  |  |  |  | K 739 494 | 80 | 0 | 19 | K 739 494 | 220 | 0 | 19.7 | K 739 494 | 320 | 0 | 19 | N/A | N/A | N/A | N/A | N/A | 18 | 18 | 7/8" | 16 | 16 | 7/8" | 18 | 18 | 7/8" | N/A | N/A | N/A | 104 | ML 15 E 1+0* | Baneasa | MW | 85 | 0.6 | 20.5 | 19 | [18 empty] | BA172 | MADIRJESTI | 265 | [23 empty] | new |  |  | Denis CIUCU | Calin ACHIM | [33 empty] | Tg. Frumos | Iasi | [7 empty] | missing |  |  | missing
Phase_3 | CS | BA081 | PODU ILOAIEI | Road Iasi-Roman(4+1) | BA031 Independentei_RTC | Moldova | 47 13 07.6 | 27 16 01.6 | 47 13 11 | 27 16 02.6 | Comuna Podu Iloaiei | Dascalu Vasile, Falcescu Maria, Roman, str. Uzinei, nr.4, sc.B, et.2, ap.5, tel. 032/740306 | MAXITE | M | 1 | 2 | 2PBC | [12 empty] | 0 | TN | 50 |  | TMR9000 | PROTELCO | OK | EMONTAJ | 2001-06-20 | 2001-07-18 | in exec |  | Vali |  |  | 2001-02-28 | 2001-06-22 |  | 2001-03-20 |  |  | 2001-04-18 | 2001-05-10 | [14 empty] | MAXITE |  |  |  |  | AAU | 105 | 0 | 48.5 | AAU | 275 | 0 | 48.5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | 58 | 58 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 116 | ML 15 E 1+0* | Baneasa | MW | [22 empty] | BA173 | LETCANI | [24 empty] | new |  |  | Denis CIUCU | Calin ACHIM | [32 empty] | 94.3 | Podu Iloaiei | Iasi | [7 empty] | missing |  |  | missing
Phase_3 | CS | BA083 | BUHUSI | Road Bacau-Piatra Neamt(2) | BA014 Stefan Cel Mare_RTC | Moldova | 46 43 15.0 | 26 42 01 | 46 43 15.6 | 26 42 01 | Buhusi, str. 1 Mai, bl.2, Sc.B | Asociatie de locatari/Pascaru Ioan - Str. 1Mai, bl.2, sc.B, ap.5; 034/263928 | 2101 | M | C+ | 2 | 2101 | [7 empty] | YES |  |  |  |  | 25.5 | B | 25.5 | T6m+T6m | N/A | PROTELCO | OK | DUAL | 2001-07-05 | 2001-07-19 | in exec |  | Vali |  |  | 2001-02-28 |  |  | 2001-04-02 |  |  | 2001-06-08 | 2001-06-25 | [14 empty] | RBS 2101 |  |  |  |  | K 739 494 | 140 | 0 | 30 | K 739 494 | 310 | 0 | 30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 17.5 | 17.5 | 7/8" | 23 | 23 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A | 71 | ML 15 E 1+0 | Baneasa | MW | 118 | 0.6 | 29 | 16.5 | [18 empty] | BA076 | ITESTI | 298 |  | 47/1.2 | 65 | [20 empty] | new |  |  | Denis CIUCU | Calin ACHIM | [33 empty] | Buhusi | Bacau | [7 empty] | 3 |  |  | missing
Phase_3 | CS | BA084 | ZANESTI | Road Bacau-Piatra Neamt(2) | BA014 Stefan Cel Mare_RTC | Moldova | 46 49 01.6 | 26 32 45 | 46 48 17.7 | 26 34 20.3 | Comuna Zanesti, DN15 Km21 | Andrei Gheorghe, comuna Zanesti, jud. Neamt | 2101 | M | C+ | 2 | 2101 | [12 empty] | 0 | TN | 50 |  | N/A | PROTELCO | OK | DUAL | 2001-07-04 | 2001-07-31 | in exec |  | Vali |  |  | 2001-02-28 |  |  | 2001-03-20 |  |  | 2001-05-10 | 2001-06-13 | [14 empty] | RBS 2101 |  |  |  |  | K 739 494 | 130 | 0 | 48.5 | K 739 494 | 310 | 0 | 48.5 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 59 | 59 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 118 | ML 15 E 1+0 | Baneasa | MW | 134 | 1.2 | 48.5 | 59 | [7 empty] | N/A | [10 empty] | BA083 | BUHUSI | 314 | 0.6 | 29 | 22 | [20 empty] | new |  |  | Denis CIUCU | Calin ACHIM | [32 empty] | 252 | Comuna Zanesti | Neamt | [7 empty] | 3 |  |  | 3
Phase_3 | CS | BA085 | PETRICICA | Road Bacau-Onesti(3) | BA013 Cornisei_RTC | Moldova | 46 30 33 | 26 48 08.7 | 46 30 33 | 26 48 08.7 | Com. Liizi Calugara | Horvat Petre | MAXITE | M | 1 | 2 | 2PBC | [12 empty] | 0 | TN | 50 |  | N/A/TMR9000 | SETRACO | OK | VECTOR | 2001-08-01 | 2001-08-30 |  |  | Vali |  |  | 2001-02-28 |  |  | N/A |  |  | 2001-07-02 |  | Old Obs: | [13 empty] | RBS 2101 |  |  |  |  | AAU | 30 | 0 | 48.45 | AAU | 210 | 0 | 48.45 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | 59.5 | 59.5 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 119 | ML 15 E 1+0 | Baneasa | MW | 64 | 0.6 | 47.5 | 58 | [18 empty] | BA013 | CORNISEI | 244 | [23 empty] | new |  |  | Denis CIUCU | Calin ACHIM | [32 empty] | 551 | Petricica | Bacau | [7 empty] | 3 |  |  | missing
Phase_3 | CS | BA089 | COTOFANESTI | Road Adjud-Onesti(2) | BA037 Adjud_RTC | Moldova | 46 08 42.6 | 26 59 51.2 |  |  |  |  | MAXITE | M | 1 | 2 | 2PBC | [12 empty] | 0 | TN | 50 | [12 empty] | 2001-02-28 | 2001-06-07 | [20 empty] | RBS 2101 | [35 empty] | Galati | MW | 110 | [21 empty] | BA037 | ADJUD_RTC | [24 empty] | 30N01 |  |  | Denis CIUCU | Calin ACHIM | [42 empty] | 3 |  |  | missing
Phase_3 | CS | BA090 | TG. NEAMT | Road Suceava-Piatra Neamt(6) | BA017 Suceava_RTC | Moldova | 47 12 41.9 | 26 21 57.5 | 47 12 43.6 | 26 22 02 | Intravilan loc Targu Neamt | Diaconescu Aglaia si Diaconescu Viorel, str.Izvor, nr.2 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [12 empty] | 0 | TN | 50 |  | N/A | SVF | OK | SVF | 2001-06-20 | 2001-07-13 | YesV |  | Vali |  |  | 2001-03-26 |  |  | N/A | 2001-07-10 |  |  | 2001-06-11 | [14 empty] | CW NOT STARTED |  |  |  |  | K 739 494 | 30 | 0 | 49.5 | K 739 494 | 130 | 0 | 49.5 | K 739 494 | 210 | 0 | 49.5 |  |  |  |  | N/A | 65 | 65 | 1 1/4" | 65 | 65 | 1 1/4" | 65 | 65 | 1 1/4" |  |  |  | 390 | ML 15 E 1+0 | Baneasa | MW | 12 | 1.2 | 47 | 65 | [18 empty] | BA094 | ROSIORI | 192 | 1.2 | 36 | 50 | [20 empty] | new |  |  | Marius Lungu | Catalin ANGHEL | [32 empty] | 432.5 | Targu Neamt | Neamt | [7 empty] | 3 |  |  | 3
Phase_3 | CS | BA091 | CRACAOANI | Road Suceava-Piatra Neamt(6) | BA017 Suceava_RTC | Moldova | 47 06 07.5 | 26 19 19.3 | 47 06 00.2 | 26 19 25 | Intravilan Com Cracaoani | Savin Teodora | 2102 | M | C+C+C+ | 2/2/2 | N/A | [12 empty] | 0 | TN | 50 |  | N/A | SVF | OK | SVF | 2001-07-05 | 2001-07-31 | in exec |  | Vali |  |  | 2001-03-26 |  |  | N/A | 2001-07-10 |  | 2001-06-08 | 2001-06-25 | [14 empty] | CW NOT STARTED |  |  |  |  | K 739 494 | 90 | 0 | 49.5 | K 739 494 | 170 | 0 | 49.5 | K 739 494 | 310 | 0 | 49.5 | N/A | N/A | N/A | N/A | N/A | 65 | 65 | 1 1/4" | 65 | 65 | 1 1/4" | 65 | 65 | 1 1/4" | N/A | N/A | N/A | 390 | ML 15 E 1+0 | Baneasa | MW | 16 | 0.6 | 41.5 | 55 | [7 empty] | N/A | [10 empty] | BA090 | TG. NEAMT | 195 | 0.6 | 46 | 65 | [20 empty] | new |  |  | Vasile PETCU | Florin RIZESCU | [32 empty] | 564 | Cracaoani | Neamt | [7 empty] | 3 |  |  | 3
Phase_3 | CS | BA092 | MIROSLOVESTI | Road Roman-Tg.Neamt(2) | BA025 Roman 1_RTC | Moldova | 47 09 53.1 | 26 38 29.7 | 47 09 54.4 | 26 538 33 | Intravilan Miroslovesti | Ghebeaza Mihai, loc Miroslovesti | 2101 | M | C+ | 2 | 2101 | [12 empty] | 0 | TN | 50 |  | N/A | SVF | OK | SVF | 2001-06-20 | 2001-06-26 | YesV |  | Vali |  |  | 2001-03-26 |  |  | 2001-05-07 |  |  |  | 2001-06-01 | Old Obs: | [5 empty] | 2001-07-13 |  |  |  |  | GATA-2101 |  |  | RBS 2101 |  |  |  |  | K 739 494 | 0 | 0 | 49 | K 739 494 | 180 | 0 | 49 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 65 | 65 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 130 | ML 15 E 1+0 | Baneasa | MW | 144 | 1.2 | 47 | 63 | [7 empty] | N/A | [10 empty] | BA108 | NISIPORESTI | 324 | 0.6 | 47.8 | 60 | [20 empty] | new |  |  | Marius Lungu | Catalin ANGHEL | [33 empty] | Miroslovesti | Iasi | [7 empty] | 3 |  |  | 3
Phase_3 | CS | BA093 | DRAGUSANI | Road Suceava-Piatra Neamt(6) | BA017 Suceava_RTC | Moldova | 47 16 48.4 | 26 30 28.4 | 47 17 03.4 | 26 30 15.5 | Draguseni | Atanasoaiei Grigore, com Draguseni | 2101 | M | C+ | 2 | 2101 | [12 empty] | 0 | TN | 40 |  | N/A | SVF | OK | SVF | 2001-06-20 | 2001-06-21 | YesV |  | Vali |  |  | 2001-03-26 |  |  | OK | 2001-07-10 |  | 2001-05-07 | 2001-05-14 | [6 empty] | 2001-07-13 |  |  |  |  | GATA-2101 |  |  | RBS 2101 |  |  |  |  | K 739 494 | 120 | 0 | 39 | K 739 494 | 310 | 0 | 39 | N/A | N/A | N/A | N/A |  |  |  |  | YES | 54 | 54 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 108 | ML 15 E 1+0 | Baneasa | MW | 319 | 0.6 | 37 | 58 | [7 empty] | N/A | [10 empty] | BA094 | ROSIORI | 139 | 0.6 | 49.5 | 65 | [20 empty] | new |  |  | Marius Lungu | Catalin ANGHEL | [32 empty] | 314 | Draguseni | Suceava | [7 empty] | 3 |  |  | 3
Phase_3 | CS | BA094 | ROSIORI | Road Suceava-Piatra Neamt(6) | BA017 Suceava_RTC | Moldova | 47 21 23.1 | 26 24 38.3 | 47 21 24.9 | 26 24 42.1 | Localitatea Rosiori | Stefan Mihai, loc. Rosiori | 2102 | M | C+C+C+ | 2/2/2 | N/A | [12 empty] | 0 | TN | 50 |  | N/A | SVF | OK | SVF | 2001-06-20 | 2001-06-26 | YesV |  | Vali |  | 2001-07-06 |  |  |  | OK | 2001-07-10 |  | OK | 2001-05-16 | [6 empty] | 2001-07-13 | [7 empty] | CW NOT STARTED |  |  |  |  | K 739 494 | 130 | 0 | 49.5 | K 739 494 | 225 | 0 | 49 | K 739 494 | 300 | 0 | 49.5 |  |  |  |  | N/A | 65 | 65 | 1 1/4" | 65 | 65 | 1 1/4" | 65 | 65 | 1 1/4" |  |  |  | 390 | ML 15 E 1+0 | Baneasa | MW | 323 | 1.2 | 36 | 50 | [18 empty] | BA095 | FALTICENI | 143 | 1.2 | 49 | 64 | [20 empty] | new |  |  | Marius Lungu | Catain ANGHEL | [32 empty] | 387.5 | Rosiori | Suceava | [7 empty] | 3 |  |  | 3
Phase_3 | CS | BA095 | FALTICENI | Road Suceava-Piatra Neamt(6) | BA017 Suceava_RTC | Moldova | 47 28 14.4 | 26 17 04.1 | 47 28 11.1 | 26 17 07.9 | Str. Victor Baiesu, nr. 19 | Chirila Ion, str. Victor Baiesu, nr.19, Falticeni | 2102 | M | C+C+C+ | 2/2/2 | N/A | [12 empty] | 0 | TN | 50 |  | N/A | SVF | OK | SVF | 2001-05-16 | 2001-06-15 | YesV | 2001-06-07 | Vali |  | 2001-06-14 | 2001-03-26 |  |  | OK | 2001-07-10 |  | OK | 2001-05-10 | [6 empty] | 2001-06-04 |  |  |  |  | NO-CIPRIAN |  |  | CW BA096 |  |  |  |  | K 739 494 | 0 | 0 | 49.5 | K 739 494 | 130 | 0 | 49.3 | K 739 494 | 260 | 0 | 49.5 |  |  |  |  | N/A | 60 | 60 | 1 1/4" | 60 | 60 | 1 1/4" | 60 | 60 | 1 1/4" |  |  |  | 390 | ML 15 E 1+1 (PS) | Baneasa | MW | 5 | 0.6 | 41.8 | 57 | [7 empty] | N/A | [10 empty] | BA096 | BOSANCI | 185 | 0.6 | 45 | [21 empty] | new |  |  | Marius Lungu | Catalin ANGHEL | [32 empty] | 394.6 | Falticeni | Suceava | [6 empty] | 1 | 3 |  | 1 | 3
Phase_3 | CS | BA096 | BOSANCI | Road Suceava-Piatra Neamt(6) | BA017 Suceava_RTC | Moldova | 47 35 05.3 | 26 18 00.1 | 47 35 55.8 | 26 17 37.7 | Extravilan Bosanci | Carlan Gheorghe, Bujoreanu Nicolae, loc Bosanci, tel. 030/527108 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [12 empty] | 0 | TN | 50 |  | N/A | SVF | OK | SVF | 2001-06-20 | 2001-06-29 | YesV |  | Vali |  |  | 2001-03-26 |  |  | 2001-05-07 | 2001-07-10 |  |  | 2001-06-01 | [6 empty] | 2001-07-13 | [7 empty] | CW NOT STARTED |  |  |  |  | K 739 494 | 90 | 0 | 49 | K 739 494 | 170 | 0 | 49 | K 739 494 | 300 | 0 | 49 |  |  |  |  | N/A | 65 | 65 | 1 1/4" | 65 | 65 | 1 1/4" | 65 | 65 | 1 1/4" |  |  |  | 390 | ML 15 E 1+1 (PS) | Baneasa | MW | 351 | 0.6 | 47 | 63 | [18 empty] | BA019 | BURDUJENI | [24 empty] | new |  |  | Marius Lungu | Catalin ANGHEL | [32 empty] | 425 | Bosanci | Suceava | [6 empty] | 1 | 3 |  |  | missing
Phase_3 | CS | BA097 | DUMBRAVENI | Road Botosani-Suceava(2) | BA020 Botosani_RTC | Moldova | 47 39 22.2 | 26 23 52.5 | 47 39 25.6 | 26 24 13.4 | Comuna Dumbraveni | Gafitescu Gheorghita, com Cumbraveni | 2102 | M | C+C+C+ | 2/2/2 | N/A | [12 empty] | 0 | TN | 50 |  | N/A | SVF | OK | SVF | 2001-05-09 | 2001-05-31 | YesV |  | Vali |  | 2001-07-06 | 2001-03-26 |  |  | OK | 2001-04-05 |  | OK | 2001-05-10 | [6 empty] | 2001-06-04 |  |  |  |  | NO-CIPRIAN |  |  | CW BA098 |  |  |  |  | K 739 494 | 35 | 0 | 49 | K 739 494 | 115 | 0 | 49 | K 739 494 | 280 | 0 | 49 |  |  |  |  | N/A | 65 | 65 | 1 1/4" | 65 | 65 | 1 1/4" | 65 | 65 | 1 1/4" |  |  |  | 390 | ML 15 E 1+0* | Baneasa | MW | 68 | 0.6 | 45 | 60 | [18 empty] | BA098 | VLADENI | 248 | 0.6 | 45 | 60 | [20 empty] | new |  |  | Vasile PETCU | Catalin ANGHEL | [32 empty] | 356 | Dumbraveni | Suceava | [7 empty] | 3 |  |  | 3
Phase_3 | CS | BA098 | VLADENI | Road Botosani-Suceava(2) | BA020 Botosani_RTC | Moldova | 47 41 44.6 | 26 32 38.5 | 47 43 08.8 | 26 33 21.6 | Vladeni, jud. Botosani | Rusu Ilie - Vladeni | 2102 | M | C+C+C+ | 2/2/2 | N/A | [12 empty] | 0 | TN | 50 |  | N/A | SVF | OK | SVF | 2001-05-21 | 2001-06-14 | YesV |  | Vali |  | 2001-07-06 | 2001-03-26 |  |  | 2001-04-17 | 2001-04-05 |  | OK | 2001-05-14 | [6 empty] | 2001-07-13 | [7 empty] | CW NOT READY |  |  |  |  | K 739 494 | 70 | 0 | 49.5 | K 739 494 | 190 | 0 | 49.5 | K 739 494 | 270 | 0 | 49.5 |  |  |  |  | N/A | 65 | 65 | 1 1/4" | 65 | 65 | 1 1/4" | 65 | 65 | 1 1/4" |  |  |  | 390 | ML 15 E 1+0* | Baneasa | MW | 60 | 0.6 | 45 | 60 | [7 empty] | N/A | [10 empty] | BA020 | BOTOSANI_RTC | [24 empty] | new |  |  | Vasile PETCU | Catalin ANGHEL | [33 empty] | Vladeni | Botosani | [7 empty] | 3 |  |  | missing
Phase_3 | CS | BA099 | BUZENI | Road Botosani-Tg. Frumos(5) | BA020 Botosani_RTC | Moldova | 47 40 00.6 | 26 44 49.1 | 47 39 55.2 | 26 45 03.1 | sat Buzeni | Lupascu Florin | 2101 | M | C+ | 2 | 2101 | [12 empty] | 0 | TN | 50 |  | N/A | IASSID | OK | VECTOR | 2001-05-16 | 2001-06-19 | YesV |  | Vali |  | 2001-07-06 | 2001-03-26 |  |  | OK | 2001-04-05 |  | 2001-05-03 | 2001-06-14 | [6 empty] | 2001-07-13 |  |  |  |  | GATA-2101 |  |  | RBS 2101 |  |  |  |  | K 739 494 | 140 | 0 | 48.5 | K 739 494 | 300 | 0 | 48.5 | N/A | N/A | N/A | N/A |  |  |  |  | YES | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+1 (PS)* | Baneasa | MW | 326 | 0.6 | 45 | 56 | [7 empty] | N/A | [10 empty] | BA020 | BOTOSANI_RTC | [24 empty] | new |  |  | Marius Lungu | [33 empty] | 202 | Baluseni | Botosani | [6 empty] | 1 | 3 |  |  | missing
Phase_3 | CS | BA100 | BALCESCU | Road Botosani-Tg. Frumos(5) | BA020 Botosani_RTC | Moldova | 47 34 49.1 | 26 51 54.3 | 47 34 44.2 | 26 52 00.1 | Sat Nicoalae Balcescu | Bursuc Petru | 2101 | M | C+ | 2 | 2101 | [12 empty] | 0 | TN | 50 |  | N/A | IASSID | OK | VECTOR | 2001-06-20 | 2001-07-18 | in exec |  | Vali |  |  | 2001-03-26 |  |  | OK | 2001-04-05 |  | 2001-06-08 | 2001-06-14 | [14 empty] | RBS 2101 |  |  |  |  | K 739 494 | 130 | 0 | 47.5 | K 739 494 | 340 | 0 | 47.5 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 58 | 58 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 116 | ML 15 E 1+0* | Baneasa | MW | 317 | 1.2 | 49.4 | 60 | [7 empty] | N/A | [10 empty] | BA099 | BUZENI | 137 | 1.2 | 47 | 56 | [20 empty] | new |  |  | Marius Lungu | Catalin ANGHEL | [32 empty] | 208 | Comuna Flamanzi | Botosani | [7 empty] | 3 |  |  | 3
Phase_3 | CS | BA101 | FEREDENI | Road Botosani-Tg. Frumos(5) | BA020 Botosani_RTC | Moldova | 47 28 07 | 26 53 14.2 | 47 28 13.31 | 26 52 41.6 | Sat Deleni | Nita Elena | 2101 | M | C+ | 2 | 2101 | [12 empty] | 0 | TN | 50 |  | N/A | IASSID | OK | VECTOR | 2001-08-01 | 2001-09-10 |  |  | Vali |  |  | 2001-03-26 |  |  | OK | 2001-04-05 |  | 2001-07-04 | [15 empty] | RBS 2101 |  |  |  |  | K 739 494 | 120 | 0 | 47 | K 739 494 | 330 | 0 | 47 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0* | Baneasa | MW | 352 | 1.2 | 49 | 62 | [18 empty] | BA100 | BALCESCU | 172 | 1.2 | 49.4 | 60 | [20 empty] | new | [36 empty] | 322 | Com. Deleni | Iasi | [7 empty] | 3 |  |  | 3
Phase_3 | CS | BA102 | HARLAU | Road Botosani-Tg. Frumos(5) | BA020 Botosani_RTC | Moldova | 47 25 37.3 | 26 54 09.3 | 47 25 35.1 | 26 54 13.1 | Str Stefan Cel Mare si Sfant, bl. 24, sc. B | Asociatia de locatari a blB nr24 str. Stefan Cel Mare si Sfant | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | YES |  |  |  |  | 27 | B | 31.7 | S3m+S3m | N/A | IASSID | OK | VECTOR | 2001-06-20 | 2001-06-28 | YesV |  | Vali |  |  | 2001-03-26 |  |  | OK | 2001-04-05 |  | 2001-05-25 | 2001-06-01 | [6 empty] | 2001-07-13 | [7 empty] | CW NOT STARTED |  |  |  |  | K 739 494 | 120 | 0 | 35.5 | K 739 494 | 240 | 0 | 35.5 | K 739 494 | 350 | 0 | 35.5 |  |  |  |  | N/A | 24 | 24 | 7/8" | 18 | 18 | 7/8" | 18 | 18 | 7/8" |  |  |  | 120 | ML 23 E 1+0* | Baneasa | MW | 346 | 0.6 | 34 | 23 | [7 empty] | N/A | [10 empty] | BA101 | FEREDENI | 165.9 | 0.6 | 35 | 50 | [20 empty] | new |  |  | Marius Lungu | Catalin ANGHEL | [33 empty] | Hirlau | Iasi | [7 empty] | 3 |  |  | 3
Phase_3 | CS | BA104 | PASCANI | Road Tg. Frumos-Tg.Neamt(2) | BA025 Roman 1_RTC | Moldova | 47 14 56 | 26 43 12.6 | 47 14 56 | 26 43 12.6 | Str. Mihail Kogalniceanu bl.C5, sc.B | Asociatie proprietariLabus Leonard - bl. C5 sc.B, 032/764464 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | YES |  |  |  |  | 33.62 | B | 33.62 | T4.5m+T4.5m | N/A | SVF | OK | FIBEC | 2001-07-01 | 2001-07-20 | in exec |  | Vali |  |  | 2001-03-26 |  |  | 2001-04-17 |  |  |  | 2001-06-01 | Old Obs: | [13 empty] | CW NOT STARTED |  |  |  |  | K 739 494 | 0 | 0 | 37 | K 739 494 | 90 | 0 | 37 | K 739 494 | 260 | 0 | 36.8 |  |  |  |  | N/A | 25 | 25 | 7/8" | 12 | 12 | 7/8" | 25 | 25 | 7/8" |  |  |  | 124 | ML 15 E 1+0 | Baneasa | MW | 95 | 0.6 | 35.4 | 12 | [7 empty] | N/A | [10 empty] | BA109 | RUGINOASA | 275 | [23 empty] | new |  |  | Vasile PETCU | Catalin ANGHEL | [33 empty] | Pascani | Iasi | [7 empty] | 3 |  |  | 3
Phase_3 | CS | BA105 | HARJA | Road Brasov-Onesti(9) | BA050 Onesti_RTC | Moldova | 46 11 24.6 | 26 29 27.1 | 46 11 24.6 | 26 29 27.1 | Sat Harja | Tutuianu Mircea , Onesti, str. Belvedere, nr. 1, ap.14 | MAXITE | M | 1 | 2 | 2PBC | [12 empty] | 0 | TN | 50/6mp |  | N/A/TMR9000 | NUTEX | OK | DUAL | 2001-07-12 | 2001-08-10 | in exec |  | Andrei | [5 empty] | 2001-04-18 |  |  |  | 2001-06-12 | [14 empty] | MAXITE |  |  |  |  | AAU | 50 | 0 | 48.27 | AAU | 220 | 0 | 48.27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | 66 | 66 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 132 | ML 15 E 1+0 | Baneasa | MW | 72 | 0.6 | 47 | 61 | [18 empty] | BA106 | FERESTRAU OITUZ | 252 | 1.2 | 47.15 | 64 | [20 empty] | new |  |  | Dragos BICIU | CATALINA CIOCAN | [32 empty] | 569 | Comuna Oituz | Bacau | [7 empty] | 3 |  |  | 3
Phase_3 | CS | BA106 | FERESTRAU OITUZ | Road Brasov-Onesti(9) | BA050 Onesti_RTC | Moldova | 46 12 36.1 | 26 34 38.2 | 46 12 36.1 | 26 34 38.2 | Sat Ferastrau | Rosca Gheorghe, sat Ferastrau, , tel. 034/337137 | MAXITE | M | 1 | 2 | 2PBC | [12 empty] | 0 | TN | 50 |  | N/A/TMR9000 | NUTEX | OK | COMARK | 2001-07-12 | 2001-08-05 | in exec |  | Andrei | [5 empty] | 2001-04-18 |  |  | 2001-06-12 | 2001-07-04 | [14 empty] | CTR |  |  |  |  | AAU | 90 | 0 | 48.27 | AAU | 260 | 0 | 48.27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | 62 | 62 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 124 | ML 15 E 1+0 | Baneasa | MW | 73 | 1.2 | 47.15 | 64 | [18 empty] | BA050 | ONESTI_RTC | [24 empty] | new |  |  | Dragos BICIU | CATALINA CIOCAN | [32 empty] | 653.8 | Comuna Oituz | Bacau | [7 empty] | 3 |  |  | missing
Phase_3 | CS | BA107 | BOGDANESTI | Road Brasov-Onesti(9) | BA050 Onesti_RTC | Moldova | 46 13 02.3 | 26 40 49.1 | 46 13 01.3 | 26 40 32.2 | Sat Bogdanesti | Elena Lungu, sat Bogdanesti | MAXITE | M | 1 | 2 | 2PBC | [12 empty] | 0 | TN | 50 |  | N/A/TMR9000 | NUTEX | OK | COMARK | 2001-07-04 | 2001-07-31 | in exec |  | Andrei | [5 empty] | 2001-04-18 |  |  | 2001-06-14 | 2001-07-04 | [14 empty] | MAXITE |  |  |  |  | AAU | 70 | 0 | 48.15 | AAU | 260 | 0 | 48.15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | 62 | 62 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 124 | ML 15 E 1+0 | Baneasa | MW | 264 | 1.2 | 41 | 64 | [18 empty] | BA106 | FERESTRAU OITUZ | 84 | [23 empty] | new |  |  | Dragos BICIU | CATALINA CIOCAN | [32 empty] | 284.5 | Comuna Oituz | Bacau | [7 empty] | 3 |  |  | 3
Phase_3 | CS | BA108 | NISIPORESTI | Road Roman-Tg.Neamt(2) | BA025 Roman 1_RTC | Moldova | 47 04 21.7 | 26 44 19.6 | 47 04 17.6 | 26 44 20 | Intravilan loc. Nisiporesti | Lupu Ion,com Botesti | 2101 | M | C+ | 2 | 2101 | [12 empty] | 0 | TN | 50 |  | N/A | SVF | OK | SVF | 2001-06-05 | 2001-06-14 | YesV |  | Vali |  | 2001-07-06 | 2001-03-26 |  |  | OK |  |  | 2001-05-07 | 2001-06-13 | Old Obs: | [5 empty] | 2001-07-13 |  |  |  |  | GATA-2101 |  |  | RBS 2101 |  |  |  |  | K 739 494 | 120 | 0 | 49.5 | K 739 494 | 300 | 0 | 49.5 | N/A | N/A | N/A | N/A |  |  |  |  | YES | 65 | 65 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 130 | ML 15 E 1+0 | Baneasa | MW | 114 | 0.6 | 41 | 55 | [7 empty] | N/A | [10 empty] | BA078 | SABAOANI | 294 | 1.2 | 47 | 56 | [20 empty] | new |  |  | Cosmorom | Cosmorom | [33 empty] | Nisiporesti | Neamt | [7 empty] | 3 |  |  | 3
Phase_3 | CS | BA109 | RUGINOASA | Road Tg. Frumos-Tg.Neamt(2) | BA025 Roman 1_RTC | Moldova | 47 14 23.6 | 26 52 27.4 |  |  |  |  | 2101 | M | C+ | 2 | 2101 | [12 empty] | 0 | TN | 50 | [15 empty] | 2001-06-25 | [18 empty] | RBS 2101 | [34 empty] | ML 15 E 1+0 | Baneasa | MW | 149 | [21 empty] | BA079 | SOCI | [24 empty] | new | [46 empty] | 3 |  |  | missing
Phase_3 | CS | BA110 | LEPSA | Road Focsani-Tg. Secuiesc(3) | BA032 Focsani_RTC | Moldova | 45 57 08.7 | 26 34 21.9 | 45 57 09.3 | 26 34 27.3 | Intravilan Lepsa | Neagu Gheorghe Vasile - loc. Leapsa | 2102 | M | C+C+C+ | 2/2/2 | N/A | [12 empty] | 0 | TN | 40 |  | N/A | SVF | OK | FIBEC | 2001-07-04 | 2001-07-31 | in exec |  | Vali |  |  | 2001-04-06 |  |  | 2001-04-18 |  |  | 2001-05-07 | 2001-06-01 | [14 empty] | CW NOT STARTED |  |  |  |  | K 739 494 | 0 | 0 | 39.5 | K 739 494 | 120 | 0 | 39.5 | K 739 494 | 240 | 0 | 39.5 |  |  |  |  | N/A | 55 | 55 | 1 1/4" | 55 | 55 | 1.25 | 55 | 55 | 1 1/4' |  |  |  | 330 | N/A | Galati | HDSL | N/A | N/A | N/A | N/A | N/A |  | N/A | [15 empty] | BA150 | TULNICI |  | N/A |  |  | N/A | [8 empty] | N/A |  | N/A |  | N/A |  |  | N/A |  |  |  | HDSL+30N01 Lepsa-Tulnici |  | 2001-08-01 | Marius Lungu | Catalin ANGHEL | [32 empty] | 583 | Lepsa | Vrancea | [7 empty] | Site Near=Insertion Point
Phase_3 | CS | BA111 | MAG OLD_DRTV | Road Focsani-Tg. Secuiesc(3) | BA032 Focsani_RTC | Moldova | 45 51 22.5 | 26 56 59.8 |  |  |  | 032 202 456 | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [13 empty] | TE |  |  |  | SVF |  | FIBEC | 2001-08-01 | 2001-09-10 |  |  | Vali |  |  | 2001-04-06 | [21 empty] | CTR | [34 empty] | N/A | Galati | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | [15 empty] | BA032 | FOCSANI_RTC |  | N/A |  |  | N/A | [10 empty] | N/A |  | N/A |  |  | N/A |  |  |  | 30N01 Magura Odobesti-Focsani |  | 2001-08-01 | Marius Lungu | Catalin ANGHEL | [42 empty] | Site Near=Insertion Point
Phase_3 | CS | BA114 | GRIGORENI | Road Bacau-Comanesti(5+1) | BA013 Cornisei_RTC | Moldova | 46 35 27.9 | 26 41 02.3 |  |  |  |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [12 empty] | 0 | TN | 40 |  |  | DIEKAT |  | DIEKAT | 2001-08-01 | 2001-09-10 |  |  | Vali | [24 empty] | CTR | [35 empty] | Baneasa | MW | 135 | [21 empty] | BA085 | PETRICICA | 315 | 1.2 | 48.5 | [21 empty] | new |  |  | Denis CIUCU | George JUMARA | [42 empty] | 3 |  |  | missing
Phase_3 | CS | BA115 | FLORESTI | Road Bacau-Comanesti(5+1) | BA013 Cornisei_RTC | Moldova | 46 31 59.4 | 26 39 25.7 | 46 31 47 | 26 39 20 | Parcela Coman | Ondu Cornel, sat Floresti, comuna Scorteni, tel. 034/353430 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [12 empty] | 0 | TN | 50/6mp |  | N/A | DIEKAT | OK | DIEKAT | 2001-07-12 | 2001-08-10 | in exec |  | Vali | [5 empty] | 2001-05-09 |  |  | 2001-06-27 | 2001-07-04 | [14 empty] | CW NOT STARTED |  |  |  |  | K 739 494 | 150 | 0 | 49 | K 739 494 | 260 | 0 | 49 | K 739 494 | 330 | 0 | 49 | N/A | N/A | N/A | N/A | N/A | 60 | 60 | 1 1/4" | 60 | 60 | 1 1/4" | 60 | 60 | 1 1/4" | N/A | N/A | N/A | 360 |  | Baneasa | MW | 18 | 0.6 | 47 | 57 | [18 empty] | BA114 | GRIGORENI | 198 | [23 empty] | new |  |  | Denis CIUCU | George JUMARA | [32 empty] | 361 | comuna Ardeoani | Bacau | [7 empty] | 3 |  |  | 3
Phase_3 | CS | BA116 | LUNCANI | Road Bacau-Comanesti(5+1) | BA120 Luncani_RTC | Moldova | 46 36 34.6 | 26 45 22.7 | [58 empty] | CTR | [35 empty] | Baneasa | MW | 263 | [21 empty] | BA120 | LUNCANI_RTC | 83 | [23 empty] | new |  |  | Denis CIUCU | George JUMARA | [42 empty] | 3 |  |  | 3
Phase_3 | CS | BA117 | VERSESTI | Road Bacau-Onesti(3) | BA013 Cornisei_RTC | Moldova | 46 26 20.5 | 26 42 51.8 | 46 26 20.5 | 26 42 51.8 | sat Versesti | Ion Dumitru | 2102 | M | C+C+C+ | 2/2/2 | N/A | [12 empty] | 0 | TN | 40/6mp |  | N/A | DIEKAT | OK | DIEKAT | 2001-07-01 | 2001-07-31 | in exec |  | Vali | [5 empty] | 2001-05-09 |  |  | 2001-06-11 | 2001-06-14 | [14 empty] | CW NOT STARTED |  |  |  |  | K 739 494 | 70 | 0 | 39 | K 739 494 | 170 | 0 | 39 | K 739 494 | 340 | 0 | 39 |  |  |  |  | N/A | 50 | 50 | 1 1/4" | 50 | 50 | 1 1/4" | 50 | 50 | 1 1/4" |  |  |  | 300 |  | Baneasa | MW | 41 | 1.2 | 35 | 45 | [18 empty] | BA085 | PETRICICA | 221 | 1.2 | 49 | [21 empty] | new |  |  | Denis CIUCU | George JUMARA | [32 empty] | 382 | comuna Sanduleni | Bacau | [7 empty] | 3 |  |  | 3
Phase_3 | CS | BA118 | TREBES_DRTV | Road Bacau-Comanesti(5+1) | BA013 Cornisei_RTC | Moldova | 46 35 45.7 | 26 50 19.7 |  |  |  |  | 2101 | M | C+ | 2 | 2101 | [17 empty] | DIEKAT | OK | DIEKAT | 2001-08-01 | 2001-09-10 |  |  | Vali | [24 empty] | RBS 2101 | [34 empty] | ML 15 E 1+0 | Baneasa | MW | 197 | [21 empty] | BA013 | CORNISEI | [24 empty] | new |  |  | Denis CIUCU | George JUMARA | [42 empty] | 3 |  |  | missing
Phase_3 | TM | BA120 | LUNCANI_RTC | Road Bacau-Comanesti(5+1) | BA120 Luncani_RTC | Moldova | 46 36 31.6 | 26 44 46.7 | [93 empty] | N/A | Baneasa | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | [15 empty] | BSC21 | BSC BANEASA | N/A | N/A |  |  | N/A | [10 empty] | N/A | N/A | N/A |  |  | N/A |  |  |  | new |  |  | Denis CIUCU | George JUMARA | [42 empty] | Site Near=Insertion Point
Phase_3 | CS | BA122 | POIANA LUI ALEXA | Road Bacau-Vaslui(4) | BA043 Vaslui_RTC_Tehnic | Moldova | 46 37 05.8 | 27 36 28.7 | 46 37 03 | 27 36 16.4 | Comuna Poiana lui Alexa | Aprodu Constantin | 2102 | M | C+C+C+ | 2/2/2 | N/A | [12 empty] | 0 | TN | 50 |  | N/A | A&A | OK | DIEKAT | 2001-08-01 | 2001-08-30 |  |  | Bogdan |  |  | 2001-05-18 | 2001-06-22 |  |  | 2001-05-18 |  | 2001-07-02 | [15 empty] | CTR |  |  |  |  | K 739 494 | 80 | 0 | 48.5 | K 739 494 | 280 | 0 | 48.5 | K 739 494 | 340 | 0 | 48.5 | N/A | N/A | N/A | N/A | N/A | 60 | 60 | 1 1/4" | 60 | 60 | 1 1/4" | 60 | 60 | 1 1/4" | N/A | N/A | N/A | 360 |  | Baneasa | MW | 81 | 0.6 | 41 | 52 | [18 empty] | BA028 | VASLUI-SILOZ | 261 | [26 empty] | Denis CIUCU | George JUMARA | [32 empty] | 292.5 | Poiana lui Alexa | Vaslui | [7 empty] | 3 |  |  | missing
Phase_3 | CS | BA123 | DRAGOMIRESTI | Road Bacau-Vaslui(4) | BA012 Bacau_RTC | Moldova | 46 38 35.5 | 27 22 34.9 | 46 38 35.5 | 27 22 34.9 | Extravilan in localitatea Dragomiresti | Plesovu Ioan | 2102 | M | C+C+C+ | 2/2/2 | N/A | [12 empty] | 0 | TN | 50 |  | N/A | A&A | OK | DIEKAT | 2001-08-01 | 2001-08-30 |  |  | Bogdan |  |  | 2001-05-18 | 2001-06-22 |  | N/A | 2001-05-18 |  | 2001-06-27 | [15 empty] | CTR |  |  |  |  | K 739 494 | 85 | 0 | 48.5 | K 739 494 | 180 | 0 | 48.5 | K 739 494 | 275 | 0 | 48.5 | N/A | N/A | N/A | N/A | N/A | 60 | 60 | 1 1/4" | 60 | 60 | 1 1/4" | 60 | 60 | 1 1/4" | N/A | N/A | N/A | 300 | ML 15 E 1+0 | Baneasa | MW | 291 | 1.2 | 25 | 35 | [18 empty] | BA124 | FUNDU TUTOVEI | 110 | 1.2 | 25 | 36 | [20 empty] | new02 |  |  | Denis CIUCU | George JUMARA | [32 empty] | 429 | Dragomiresti | Vaslui | [7 empty] | missing |  |  | missing
Phase_3 | CS | BA124 | FUNDU TUTOVEI | Road Bacau-Vaslui(4) | BA012 Bacau_RTC | Moldova | 46 41 52.3 | 27 10 09.1 | 46 41 52.9 | 27 10 09.2 | Comuna Plopana | Andries Niculai | MAXITE | M | 1 | 2 | 2PBC | [12 empty] | 0 | TN | 50 |  | N/A/TMR9000 | A&A | OK | DIEKAT | 2001-08-01 | 2001-09-10 |  |  | Bogdan |  |  | 2001-05-18 |  |  | N/A | 2001-05-18 |  | 2001-07-04 | [15 empty] | RBS 2101 |  |  |  |  | AAU | 115 | 0 | 48.5 | AAU | 220 | 0 | 48.5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | 60 | 60 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Baneasa | MW | 232 | 0.6 | 48.5 | 60 | [18 empty] | BA125 | ZAPODIA | 52 | [23 empty] | 30N01 Bacau-Baneasa |  | 2001-01-29 | Denis CIUCU | George JUMARA | [32 empty] | 440 | Plopana | Buzau | [7 empty] | missing |  |  | missing
Phase_3 | CS | BA125 | ZAPODIA | Road Bacau-Vaslui(4) | BA012 Bacau_RTC | Moldova | 46 38 29.6 | 27 04 07.7 | 46 38 39.2 | 27 04 07.6 | Extravilan in comuna Zapodia | Burca Gheorghe | MAXITE | M | 1 | 2 | 2PBC | [12 empty] | 0 | TN | 30 |  | N/A/TMR9000 | A&A | OK | DIEKAT | 2001-08-01 | 2001-08-30 |  |  | Bogdan |  |  | 2001-05-18 | 2001-06-22 |  | N/A | 2001-05-18 |  | 2001-06-27 | [15 empty] | RBS 2101 |  |  |  |  | AAU | 90 | 0 | 28.5 | AAU | 220 | 0 | 28.5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | 40 | 40 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 80 | ML 15 E 1+0 | Baneasa | MW | 234 | 1.2 | 25 | 35 | [18 empty] | BA012 | BACAU_RTC | [24 empty] | 30N01 Bacau-Baneasa |  | 2001-01-29 | Denis CIUCU | George JUMARA | [32 empty] | 251 | Comuna Zapodia | Bacau | [7 empty] | missing |  |  | missing
Phase_3 | CS | BA126 | TUTU | Road Adjud-Barlad(2) | BA037 Adjud_RTC | Moldova | 46 10 49.3 | 27 16 13.3 | 46 10 54.2 | 27 16 12.8 | Sat Tutu | Diaconasu Stana | 2102 | M | C+C+C+ | 2/2/2 | N/A | [12 empty] | 0 | TN | 50 |  |  | PERFECT | OK | QUALITY | 2001-07-18 | 2001-08-15 | in exec |  | Bogdan |  |  | 2001-05-18 |  |  |  | 2001-05-18 |  | 2001-06-27 | [15 empty] | RBS 2101 |  |  |  |  | K 739 494 | 75 | 0 | 48.5 | K 739 494 | 140 | 0 | 48.5 | K 739 494 | 230 | 0 | 48.5 | N/A | N/A | N/A | N/A | N/A | 65 | 65 | 1 1/4" | 65 | 65 | 1 1/4" | 65 | 65 | 1 1/4" | N/A | N/A | N/A | 390 |  | Galati | MW | 283 | 0.6 | 48 | 65 | [18 empty] | BA072 | SASCUT | 103 | 0.6 | 62 | 10 | [23 empty] | Denis CIUCU | George JUMARA | [32 empty] | 303 | Corbita | Vrancea | [7 empty] | missing |  |  | missing
Phase_3 | CS | BA127 | PODU TURCULUI | Road Adjud-Barlad(2) | BA037 Adjud_RTC | Moldova | 46 12 40.2 | 27 25 16.2 |  |  |  |  | 2101 | M | C+ | 2 | 2101 | [12 empty] | 0 | TN | 50 |  |  | PERFECT |  | @ | 2001-08-01 | 2001-09-10 |  |  | Bogdan |  |  | 2001-05-18 |  |  |  | 2001-05-18 | [17 empty] | RBS 2101 | [35 empty] | Galati | MW | 73.5 | [21 empty] | BA126 | TUTU | 254 | 1.2 | 30 | 45 | [23 empty] | Denis CIUCU | George JUMARA | [42 empty] | missing |  |  | missing
Phase_3 | CS | BA128 | BARLAD_DRTV | Road Barlad_Husi(5) | BA056 Husi_RTC | Moldova | 46 14 27.9 | 27 51 05.3 |  |  |  |  | 2202 | M | C+C+ | 2/2 | 2202 | [12 empty] | 0 | TN | 50 |  |  | NUTEX |  | COMARK | 2001-08-01 | 2001-09-10 |  |  | Bogdan |  |  | 2001-05-18 | 2001-07-17 |  |  | 2001-07-10 |  |  |  |  | 2001-07-05 | [12 empty] | CTR |  |  |  |  | K 739 494 | 90 | 0 | 50 | K 739 494 | 280 | 0 | 50 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 65 | 65 | 1 1/4" | 65 | 65 | 1 1/4" | N/A | N/A | N/A |  |  |  | 260 | ML 15 E 1+0 | Baneasa | MW | [22 empty] | BA129 | MURGENI | [24 empty] | new |  |  | Denis CIUCU | Dan VARTOPEAN | [42 empty] | missing |  |  | missing
Phase_3 | CS | BA129 | MURGENI | Road Barlad_Husi(5) | BA056 Husi_RTC | Moldova | 46 11 56.4 | 28 03 40.2 | 46 11 56.4 | 28 03 40.23 | Loc. Harja | Blasciuc Carol | 2102 | M | C+C+C+ | 2/2/2 | N/A | [12 empty] | 0 | TN | 50 |  | N/A | NUTEX | OK | COMARK | 2001-08-01 | 2001-09-10 |  |  | Bogdan |  |  | 2001-05-18 | 2001-07-17 |  | OK | 2001-07-10 |  | 2001-07-02 | 2001-07-04 | S-a Schimbat FAR END-ul | [13 empty] | RBS 2101 |  |  |  |  | K 739 494 | 35 | 0 | 48 | K 739 494 | 210 | 0 | 48 | K 739 494 | 300 | 0 | 48 | N/A | N/A | N/A | N/A | N/A | 65 | 65 | 1 1/4" | 65 | 65 | 1 1/4" | 65 | 65 | 1 1/4" | N/A | N/A | N/A | 390 | ML 15 E 1+0 | Baneasa | MW | 286 | 1.2 | 31.4 | 42 | [18 empty] | BA130 | FALCIU | 106 | 1.2 | 42 | [21 empty] | new |  |  | Denis CIUCU | Dan VARTOPEAN | [33 empty] | Harja | Bacau | [7 empty] | missing |  |  | missing
Phase_3 | CS | BA130 | FALCIU | Road Barlad_Husi(5) | BA056 Husi_RTC | Moldova | 46 16 54.8 | 28 07 48.3 | 46 16 54.75 | 28 07 48.25 | SC PYRETUS , Falciu | Hristian Maria | MAXITE | M | 1 | 2 | 2PBC | [12 empty] | 0 | TN | 40 |  | N/A/TMR9000 | NUTEX | OK | COMARK | 2001-08-01 | 2001-08-30 |  |  | Bogdan |  |  | 2001-05-18 | 2001-07-17 |  |  | 2001-07-10 |  | 2001-06-14 |  | S-a Schimbat FAR END-ul | [13 empty] | RBS 2101 |  |  |  |  | AAU | 5 | 0 | 39 | AAU | 195 | 0 | 39 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | 45 | 45 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 90 | ML 15 E 1+0 | Baneasa | MW | 210 | 1.2 | 30 | 42 | [18 empty] | BA131 | VETRISOARA | 30 | 1.2 | 31.4 | 42 | [20 empty] | new |  |  | Denis CIUCU | Dan VARTOPEAN | [32 empty] | 199 | Falciu | Vaslui | [7 empty] | 3 |  |  | missing
Phase_3 | CS | BA131 | VETRISOAIA | Road Barlad_Husi(5) | BA056 Husi_RTC | Moldova | 46 25 09.3 | 28 11 52.9 | 46 25 09.33 | 28 11 52.89 | Comuna Vetrisoaia | Agache Gabriela si Miclea Valentin | MAXITE | M | 1 | 2 | 2PBC | [12 empty] | 0 | TN | 50 |  | N/A/TMR9000 | NUTEX | OK | COMARK | 2001-08-01 | 2001-08-30 |  |  | Bogdan |  |  | 2001-05-18 | 2001-07-17 |  |  | 2001-07-10 |  | 2001-07-02 |  | S-a Schimbat FAR END-ul | 2001-07-05 | [12 empty] | RBS 2101 |  |  |  |  | AAU | 210 | 0 | 48 | AAU | 355 | 0 | 48 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | 62 | 62 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 124 | ML 15 E 1+0 | Baneasa | MW | 199 | 1.2 | 32 | 54 | [18 empty] | BA132 | FOCSA | 19 | 1.2 | 30 | 42 | [20 empty] | new |  |  | Denis CIUCU | Dan VARTOPEAN | [33 empty] | Vetrisoaia | Vaslui | [7 empty] | missing |  |  | 3
Phase_3 | CS | BA132 | FOCSA | Road Barlad_Husi(5) | BA056 Husi_RTC | Moldova | 46 34 04 | 28 11 30.1 | 46 34 03.9 | 28 11 30.7 | Sat Focsa | Zaharia Costachi | MAXITE | M | 1 | 2 | 2PBC | [12 empty] | 0 | TN | 50/6mp |  | N/A/TMR9000 | NUTEX | OK | COMARK | 2001-07-18 | 2001-08-15 | in exec |  | Bogdan |  |  | 2001-05-18 | 2001-07-17 |  | N/A | 2001-07-10 |  | 2001-06-14 | [15 empty] | MAXITE |  |  |  |  | AAU | 185 | 0 | 48 | AAU | 345 | 0 | 48 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | 62 | 62 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 124 | ML 15 E 1+1 (PS) | Baneasa | MW | 343 | 1.2 | 32 | 42 | [18 empty] | BA054 | VALEA GRECULUI | 163 | [26 empty] | Denis CIUCU | Dan VARTOPEAN | [33 empty] | Comuna Lunca Dealului | Vaslui | [7 empty] | 3 |  |  | 2
Phase_3 | CS | BA133 | PIETRARIA_DRTV | Road Iasi_Vaslui | BA030 Podul Ros_RTC | Moldova | 47 05 22.4 | 27 38 39 |  |  |  |  | MAXITE | M | 1 | 2 | 2PBC | [17 empty] | SVF |  | @ | 2001-08-01 | 2001-09-10 |  |  | Bogdan |  |  | 2001-05-18 |  |  |  | 2001-05-18 | [17 empty] | MAXITE | [35 empty] | Baneasa | MW | [22 empty] | BA007 | NICOLINA | [27 empty] | Marius Lungu | Catalin ANGHEL | [41 empty] | 1 | 3 |  |  | missing
Phase_3 | CS | BA134 | BLAGA | Road Iasi_Vaslui | BA030 Podul Ros_RTC | Moldova | 47 01 49.1 | 27 44 40.9 |  |  |  |  | MAXITE | M | 1 | 2 | 2PBC | [17 empty] | SVF |  | @ | 2001-08-01 | 2001-09-10 |  |  | Bogdan |  |  | 2001-05-18 |  |  |  | 2001-05-18 | [17 empty] | MAXITE | [35 empty] | Baneasa | MW | [22 empty] | BA133 | PIETRARIA_DRTV | [27 empty] | Marius Lungu | Catalin ANGHEL | [42 empty] | 3 |  |  | 3
Phase_3 | CS | BA135 | CORAPCENI | Road Iasi_Vaslui | BA030 Podul Ros_RTC | Moldova | 46 57 42.2 | 27 47 27.7 |  |  |  |  | MAXITE | M | 1 | 2 | 2PBC | [17 empty] | SVF |  | @ | 2001-08-01 | 2001-09-10 |  |  | Bogdan |  |  | 2001-05-18 |  |  |  | 2001-05-18 | [17 empty] | MAXITE | [35 empty] | Baneasa | MW | [22 empty] | BA136 | SERBESTI | 345 | 0.6 | 45 | 58 | [23 empty] | Marius Lungu | Catalin ANGHEL | [42 empty] | 3 |  |  | 3
Phase_3 | CS | BA136 | SERBESTI | Road Iasi_Vaslui | BA030 Podul Ros_RTC | Moldova | 46 51 29 | 27 49 47.4 | 46 51 29.7 | 27 49 49.8 | Intravilan loc Ciortesti | Tiron Ion | MAXITE | M | 1 | 2 | 2PBC | [12 empty] | 0 | TN | 50 |  | N/A/TMR9000 | SVF | OK | SVF | 2001-07-12 | 2001-08-10 | in exec |  | Bogdan |  |  | 2001-05-18 |  |  | N/A | 2001-05-18 |  | 2001-07-04 | [15 empty] | MAXITE |  |  |  |  | AAU | 190 | 0 | 49 | AAU | 340 | 0 | 49 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | 62 | 62 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 124 |  | Baneasa | MW | 341 | 1.2 | 41 | 53 | [18 empty] | BA134 | BLAGA | 161 | [26 empty] | Marius Lungu | Catalin ANGHEL | [32 empty] | 287 | Ciortesti | Iasi | [7 empty] | 3 |  |  | 3
Phase_3 | CS | BA137 | STEFAN CEL MARE_2 | Road Roman-Vaslui | BA043 Vaslui_RTC_Tehnic | Moldova | 46 43 15.53 | 27 38 17.84 | 46 42 37.8 | 27 38 06.1 | Intravilan loc. Stefan cel Mare | Tunaru Ioan, com Stefan cel Mare | MAXITE | M | 1 | 2 | 2PBC | [12 empty] | 0 | TN | 40 |  | N/A/TMR9000 | SVF | OK | EL-MONT | 2001-08-01 | 2001-08-30 |  |  | Bogdan |  |  | 2001-05-18 |  |  | N/A | 2001-05-18 |  | 2001-07-04 | [15 empty] | MAXITE |  |  |  |  | AAU | 170 | 0 | 39 | AAU | 315 | 0 | 39 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | 55 | 55 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 110 |  | Baneasa | MW | 147 | 0.6 | 38 | 55 | [18 empty] | BA028 | VASLUI-SILOZ | 327 | [26 empty] | Marius Lungu | Catalin ANGHEL | [32 empty] | 103.5 | Stefan cel Mare | Vaslui | [7 empty] | 3 |  |  | missing
Phase_3 | CS | BA138 | NEGRESTI | Road Roman-Vaslui | BA043 Vaslui_RTC_Tehnic | Moldova | 46 50 57.95 | 27 28 27.33 |  |  |  |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [13 empty] | TE |  |  |  | SVF |  | @ | 2001-08-01 | 2001-09-10 |  |  | Bogdan |  |  | 2001-05-18 |  |  |  | 2001-05-18 | [17 empty] | CTR | [35 empty] | Baneasa | MW | [22 empty] | BA137 | STEFAN CEL MARE_2 | [27 empty] | Marius Lungu | Catalin ANGHEL | [42 empty] | 3 |  |  | 3
Phase_3 | CS | BA139 | DUMESTI | Road Roman-Vaslui | BA043 Vaslui_RTC_Tehnic | Moldova | 46 50 37 | 27 14 59.89 | 46 50 23.6 | 27 15 43 | Loc. Dumesti | Ionita Gheorghe | MAXITE | M | 1 | 2 | 2PBC | [12 empty] | 0 | TN | 50 |  | N/A/TMR9000 | SVF | OK | EL-MONT | 2001-07-12 | 2001-08-10 | in exec |  | Bogdan |  |  | 2001-06-07 |  |  | OK | 2001-05-18 |  | OK | 2001-07-04 | Old Obs: | [18 empty] | AAU | 90 | 0 | 49.5 | AUU | 280 | 0 | 65 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | 65 | 65 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 130 |  | Baneasa | MW | 88 | 1.2 | 42 | 55 | [18 empty] | BA138 | NEGRESTI | 268 | [26 empty] | Marius Lungu | Catalin ANGHEL | [33 empty] | Dumesti | Neamt | [7 empty] | missing |  |  | missing
Phase_3 | CS | BA140 | VALENI | Road Iasi_Vaslui | BA030 Podul Ros_RTC | Moldova | 46 44 53.83 | 27 45 37.08 | 46 44 42.6 | 27 45 49.7 | Intravilan Valeni | Diaconu Gheorghe | 2101 | M | C+ | 2 | 2101 | [12 empty] | 0 | TN | 40 |  | N/A | SVF | OK | SVF | 2001-08-01 | 2001-08-30 |  |  | Bogdan |  |  | 2001-05-18 |  |  | N/A | 2001-05-18 |  | 2001-07-04 | [15 empty] | RBS 2101 |  |  |  |  | K 739 494 | 40 | 0 | 39 | K 739 494 | 180 | 0 | 39 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | 53 | 53 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 106 |  | Baneasa | MW | 24 | 0.6 | 34.5 | 48 | [18 empty] | BA136 | SERBESTI | 203 | 0.6 | 41 | 53 | [23 empty] | Marius Lungu | Catalin ANGHEL | [32 empty] | 163.5 | Valeni | Vaslui | [7 empty] | 3 |  |  | 3
Phase_3 | CS | BA150 | TULNICI | Road Focsani-Tg. Secuiesc(3) | BA032 Focsani_RTC | Moldova | 45 55 26 | 26 40 53 | [36 empty] | 2001-04-06 |  |  |  | 2001-05-18 | [17 empty] | CTR | [34 empty] | N/A | Galati | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | [15 empty] | BA111 | MAG OLD_DRTV |  | N/A |  |  | N/A | [10 empty] | N/A | N/A | N/A |  |  | N/A |  |  |  | 30N01 Tulnici-Magura Odobesti |  | 2001-08-01 | Marius Lungu | Catalin ANGHEL | [42 empty] | Site Near=Insertion Point
Phase_3 | CS | BA151 | DARMANESTI | Road Siret-Suceava(3) | BA017 Suceava_RTC | Moldova | 47 43 41.7 | 26 08 00.09 |  |  |  |  | 2101 | M | C+ | 2 | 2101 | [17 empty] | PROTELCO |  | @ | 2001-08-01 | 2001-09-10 |  |  | Marin |  |  | 2001-05-18 | 2001-07-06 |  |  | 2001-07-09 |  |  |  |  | 2001-07-06 | [12 empty] | RBS 2101 | [34 empty] | ML 15 E 1+1* | Baneasa | MW | [22 empty] | BA177 | TEIUSOARA_DRTV | [27 empty] | Marius Lungu | Dan VARTOPEAN | [42 empty] | missing |  |  | missing
Phase_3 | CS | BA152 | GRANICESTI | Road Siret-Suceava(3) | BA017 Suceava_RTC | Moldova | 47 48 31.6 | 26 02 58.9 |  |  |  |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [17 empty] | PROTELCO |  | @ | 2001-08-01 | 2001-09-10 |  |  | Marin |  |  | 2001-05-18 | 2001-07-06 |  |  | 2001-07-09 |  |  |  |  | 2001-07-06 | [12 empty] | CTR | [34 empty] | ML 15 E 1+0* | Baneasa | MW | [22 empty] | BA177 | TEIUSOARA_DRTV | [27 empty] | Marius Lungu | Dan VARTOPEAN | [42 empty] | missing |  |  | missing
Phase_3 | CS | BA153 | SIRET | Road Siret-Suceava(3) | BA017 Suceava_RTC | Moldova | 47 56 26 | 26 03 51.5 | 47 56 25.1 | 26 03 46.6 | Extravilan oras Siret | Merla Vasile | 2102 | M | C+C+C+ | 2/2/2 | N/A | [12 empty] | 0 | TN | 50 |  | N/A | PROTELCO | OK | DUAL | 2001-08-01 | 2001-08-30 |  |  | Marin |  |  | 2001-05-18 |  |  | N/A | 2001-07-10 |  | 2001-07-04 |  |  | 2001-07-06 | [12 empty] | CTR |  |  |  |  | K 739 494 | 100 | 0 | 48 | K 739 494 | 160 | 0 | 48 | K 739 494 | 300 | 0 | 48 | N/A | N/A | N/A | N/A | N/A | 59 | 59 | 1 1/4" | 59 | 59 | 1 1/4" | 59 | 59 | 1 1/4" | N/A | N/A | N/A | 354 | ML 15 E 1+0 | Baneasa | MW | 185 | 1.2 | 45 | 59 | [18 empty] | BA152 | GRANICESTI | 4 | [26 empty] | Marius Lungu | Dan VARTOPEAN | [32 empty] | 391 | Siret | Suceava | [7 empty] | missing |  |  | missing
Phase_3 | CS | BA154 | RADAUTI_1 | Radauti(4) | BA017 Suceava_RTC | Moldova | 47 50 47 | 25 54 46 |  |  |  |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [17 empty] | PROTELCO* | [6 empty] | Marin* |  |  | 2001-05-18 |  |  |  | 2001-07-10 |  |  |  |  | 2001-07-06 | [12 empty] | CTR | [34 empty] | ML 15 E 1+0 | Baneasa | MW | [22 empty] | BA151 | DARMANESTI | [27 empty] | Marius Lungu | Dan VARTOPEAN | [42 empty] | missing |  |  | missing
Phase_3 | CS | BA155 | RADAUTI_2 | Radauti(4) | BA017 Suceava_RTC | Moldova | 47 50 08.2 | 25 55 23.9 |  |  |  |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [17 empty] | PROTELCO* | [6 empty] | Marin* |  |  | 2001-05-18 | 2001-07-06 |  |  | 2001-05-18 |  |  |  |  | 2001-07-06 | [12 empty] | CTR | [34 empty] | ML 38 E 1+0* | Baneasa | MW | [22 empty] | BA154 | RADAUTI_1 | [27 empty] | Marius Lungu | Dan VARTOPEAN | [42 empty] | missing |  |  | missing
Phase_3 | CS | BA156 | FRATAUTII NOI | Radauti(4) | BA017 Suceava_RTC | Moldova | 47 55 42.8 | 25 50 31.8 |  |  |  |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [17 empty] | PROTELCO* | [6 empty] | Marin* |  |  | 2001-05-18 | 2001-07-06 |  |  | 2001-05-18 |  |  |  |  | 2001-07-06 | [12 empty] | RBS 2101 | [34 empty] | ML 15 E 1+0* | Baneasa | MW | [22 empty] | BA154 | RADAUTI_1 | [27 empty] | Marius Lungu | Dan VARTOPEAN | [42 empty] | missing |  |  | missing
Phase_3 | CS | BA157 | VICOVU DE SUS | Radauti(4) | BA017 Suceava_RTC | Moldova | 47 53 30 | 25 42 25.1 |  |  |  |  | 2101 | M | C+ | 2 | 2101 | [17 empty] | PROTELCO* | [6 empty] | Marin* |  |  | 2001-05-18 | 2001-07-06 |  |  | 2001-05-18 | [17 empty] | RBS 2101 | [34 empty] | ML 15 E 1+0* | Baneasa | MW | [22 empty] | BA156 | FRATAUTII NOI | [27 empty] | Marius Lungu | Dan VARTOPEAN | [42 empty] | missing |  |  | missing
Phase_3 | CS | BA158 | ADANCATA | Road Dorohoi-Suceava(3) | BA020 Botosani_RTC | Moldova | 47 43 32.5 | 26 18 27 |  |  |  |  | 2101 | M | C+ | 2 | 2101 | [17 empty] | PROTELCO |  | @ | 2001-08-01 | 2001-09-10 |  |  | Marin |  |  | 2001-05-18 |  |  |  | 2001-07-09 |  |  |  |  | 2001-07-05 | [12 empty] | RBS 2101 | [35 empty] | Baneasa | MW | [22 empty] | BA097 | VLADENI | [27 empty] | Marius Lungu | Dan VARTOPEAN | [42 empty] | missing |  |  | missing
Phase_3 | CS | BA159 | STINCA | Road Dorohoi-Suceava(3) | BA020 Botosani_RTC | Moldova | 47 48 33.1 | 26 16 10.7 |  |  |  |  | 2101 | M | C+ | 2 | 2101 | [17 empty] | PROTELCO | OK | SVF | 2001-08-01 | 2001-09-10 |  |  | Marin |  |  | 2001-05-18 | 2001-06-07 |  |  | 2001-07-09 |  |  |  |  | 2001-07-05 | [12 empty] | RBS 2101 | [34 empty] | ML 15 E 1+0* | Baneasa | MW | [22 empty] | BA158 | ADANCATA | [27 empty] | Marius Lungu | Dan VARTOPEAN | [42 empty] | missing |  |  | missing
Phase_3 | CS | BA160 | DEALU MARE | Road Dorohoi-Suceava(3) | BA020 Botosani_RTC | Moldova | 47 55 39.5 | 26 24 01.7 |  |  |  |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [17 empty] | PROTELCO | OK | SVF | 2001-08-01 | 2001-09-10 |  |  | Marin |  |  | 2001-05-18 |  |  |  | 2001-07-09 |  |  |  |  | 2001-07-05 | [12 empty] | CTR | [35 empty] | Baneasa | MW | [22 empty] | BA164 | LEORDA SILOZ | [27 empty] | Marius Lungu | Dan VARTOPEAN | [42 empty] | missing |  |  | missing
Phase_3 | CS | BA161 | DOROHOI | Dorohoi(1) | BA020 Botosani_RTC | Moldova | 47 57 10.9 | 26 24 07.4 |  |  |  |  | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [17 empty] | ORION |  | @ | 2001-08-01 | 2001-09-10 |  |  | Marin |  |  | 2001-05-18 |  |  |  | 2001-07-09 |  |  |  |  | 2001-07-05 | [12 empty] | CTR | [35 empty] | Baneasa | MW | [22 empty] | BA164 | LEORDA SILOZ | [27 empty] | Marius Lungu | Dan VARTOPEAN | [42 empty] | missing |  |  | missing
Phase_3 | CS | BA162 | LISNA | Road Darabani-Dorohoi(2) | BA020 Botosani_RTC | Moldova | 48 05 59.2 | 26 28 28.1 |  |  |  |  | 2101 | M | C+ | 2 | 2101 | [17 empty] | ORION | OK | ORION | 2001-08-01 | 2001-09-10 |  |  | Marin |  |  | 2001-05-18 |  |  |  | 2001-07-09 |  |  |  |  | 2001-07-05 | [12 empty] | RBS 2101 | [35 empty] | Baneasa | MW | [22 empty] | BA160 | DEALU MARE | [27 empty] | Marius Lungu | Dan VARTOPEAN | [42 empty] | missing |  |  | missing
Phase_3 | CS | BA163 | DARABANI_DRTV | Road Darabani-Dorohoi(2) | BA020 Botosani_RTC | Moldova | 48 11 53.1 | 26 34 19.1 | 48 11 47.6 | 26 34 23.5 | Sediul DRTv -Darabani | DRTv Darbani | 2102 | M | C+C+C+ | 2/2/2 | N/A | [12 empty] | 0 | TE | 40 |  | N/A | ORION |  | @ | 2001-08-01 | 2001-09-10 |  |  | Marin |  |  | 2001-05-18 |  |  | OK | 2001-07-09 |  | 2001-07-04 | [15 empty] | CTR |  |  |  |  | K 739 494 | 60 | 0 | 24 | K 739 494 | 130 | 0 | 24 | K 739 494 | 220 | 0 | 25 | N/A | N/A | N/A | N/A | N/A | 35 | 35 | 7/8" | 35 | 35 | 7/8" | 35 | 35 | 7/8" | N/A | N/A | N/A | 210 |  | Baneasa | MW | 214 | 0.6 | 0 | 35 | [18 empty] | BA162 | LISNA | 35 | [26 empty] | Marius Lungu | Dan VARTOPEAN | [32 empty] | 170 | Darabani | Botosani | [7 empty] | missing |  |  | missing
Phase_3 | CS | BA164 | LEORDA SILOZ | Road Botosani-Dorohoi(1) | BA020 Botosani_RTC | Moldova | 47 49 37.1 | 26 30 06.4 | 47 55 39.5 | 26 24 01.7 | Siliz apartinand SuidProd in loc. Leorda | SC Nutricomb SA Leorda | 2101 | M | C+ | 2 | 2101 | [12 empty] | 42 | S | 42 |  | N/A | ORION | OK | KEN-KEN | 2001-08-01 | 2001-09-10 |  |  | Marin |  |  | 2001-05-18 |  |  | OK | 2001-07-09 |  | 2001-07-04 | [15 empty] | RBS 2101 |  |  |  |  | K 739 494 | 140 | 0 | 43 | K 739 494 | 330 | 0 | 45 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 25 | 25 | 7/8" | 25 | 25 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A | 100 |  | Baneasa | MW | 325 | 1.2 | 43 | 20 | [18 empty] | BA160 | DEALU MARE | 146 | [26 empty] | Marius Lungu | Dan VARTOPEAN | [33 empty] | Leorda | Botosani | [7 empty] | missing |  |  | missing
Phase_3 | CS | BA165 | STEFAN CEL MARE | Road Piatra Neamt-Roman | BA022 Piatra Neamt 1_RTC | Moldova | 46 58 49.2 | 26 31 55.3 |  |  |  |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [17 empty] | SVF |  | @ | 2001-08-01 | 2001-09-10 |  |  | Bogdan |  |  | 2001-05-18 | 2001-06-22 |  |  | 2001-05-18 | [17 empty] | RBS 2101 | [35 empty] | Baneasa | MW | [22 empty] | BA024 | PIATRA-NEAMT PIETRICICA | [24 empty] | new |  |  | Marius Lungu | George JUMARA | [42 empty] | 3 |  |  | missing
Phase_3 | CS | BA166 | BOZIENII DE SUS | Road Piatra Neamt-Roman | BA022 Piatra Neamt 1_RTC | Moldova | 46 57 47.5 | 26 42 06.4 |  |  |  |  | 2101 | M | C+ | 2 | 2101 | [17 empty] | SVF |  | @ | 2001-08-01 | 2001-09-10 |  |  | Bogdan |  |  | 2001-05-18 |  |  |  | 2001-05-18 | [17 empty] | RBS 2101 | [35 empty] | Baneasa | MW | [22 empty] | BA165 | STEFAN CEL MARE | [24 empty] | new |  |  | Marius Lungu | George JUMARA | [42 empty] | 3 |  |  | 3
Phase_3 | CS | BA167 | BD. REPUBLICII | Roman | BA025 Roman 1_RTC | Moldova | 46 55 38.2 | 26 56 30.8 | 46 55 38 | 26 56 30 | B-ul Republicii, bl. 62 | Asociatia de locatari GRP14 | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [7 empty] | YES |  |  |  |  | 32 | B | 35 | S4m+S4m | Room/Rack19" | SVF | OK | VECTOR | 2001-08-01 | 2001-08-20 |  |  | Bogdan |  |  | 2001-05-18 | 2001-06-22 |  | OK | 2001-05-18 |  | 2001-07-04 |  | Old Obs: | [13 empty] | CTR |  |  |  |  | K 739 494 | 60 | 0 | 37.5 | K 739 494 | 220 | 0 | 37.5 | K 739 494 | 310 | 0 | 37.5 | N/A | N/A | N/A | N/A | Yes | 16 | 16 | 7/8" | 12 | 12 | 7/8" | 6 | 6 | 7/8" | N/A | N/A | N/A | 68 | ML 38 E 1+0 | Baneasa | MW | 285 | 0.6 | 36 | 5 | [18 empty] | BA026 | ROMAN 2 | 105 | [23 empty] | new |  |  | Marius Lungu | Dan VARTOPEAN | [33 empty] | Roman | Neamt | [7 empty] | 3 |  |  | missing
Phase_3 | CS | BA168 | GEORGE ENESCU | Suceava | BA017 Suceava_RTC | Moldova | 47 38 33.6 | 26 14 18.6 | 47 38 32.9 | 26 14 13.7 | B-ul Gheorghe Enescu, bl. 94, sc. C | Asociatia de locatari "Turn" nr.46 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [12 empty] | 31.6 | B | 31.6 |  |  | PROTELCO | OK | VEGA | 2001-08-01 | 2001-08-20 |  |  | Marin |  |  | 2001-05-18 | 2001-07-06 |  | OK | 2001-07-10 |  | 2001-07-04 | [15 empty] | CTR |  |  |  |  | K 739 494 | 0 | 0 | 37 | K 739 494 | 120 | 0 | 37 | K 739 494 | 240 | 0 | 37 | N/A | N/A | N/A | N/A | N/A | 22 | 22 | 7/8" | 22 | 22 | 7/8" | 22 | 22 | 7/8" | N/A | N/A | N/A | 132 | ML 38 E 1+0* | Baneasa | MW | 49 | 0.3 | 36.5 | 21.5 | [18 empty] | BA169 | BD. MARASESTI | 229 | [26 empty] | Marius Lungu | George JUMARA | [33 empty] | Suceava | Suceava | [7 empty] | missing |  |  | missing
Phase_3 | CS | BA169 | BD. MARASESTI | Suceava | BA017 Suceava_RTC | Moldova | 47 38 36.4 | 26 14 57.4 |  |  |  |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [17 empty] | PROTELCO | OK | VEGA | 2001-08-01 | 2001-09-10 |  |  | Marin |  |  | 2001-05-18 |  |  |  | 2001-07-10 | [17 empty] | CTR | [34 empty] | ML 38 E 1+0 | Baneasa | MW | [22 empty] | BA017 | SUCEAVA_RTC | [27 empty] | Marius Lungu | Dan VARTOPEAN | [42 empty] | missing |  |  | missing
Phase_3 | CS | BA170 | BD. TRAIAN | Road Piatra Neamt-Roman | BA022 Piatra Neamt 1_RTC | Moldova | 46 55 30.5 | 26 22 41.9 | 46 55 28.7 | 26 22 34.5 | B-ul Traian, bl.76, sc.B | Asociatia de locatari nr. 76H1B | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [7 empty] | YES |  |  |  |  | 32 | B | 35 |  | Room/Rack19" | SVF | OK | VECTOR | 2001-07-12 | 2001-07-25 | in exec |  | Bogdan |  |  | 2001-05-18 | 2001-06-22 |  | OK | 2001-05-18 |  | OK | 2001-07-04 | [14 empty] | CTR |  |  |  |  | K 739 494 | 80 | 0 | 37.6 | K 739 494 | 170 | 0 | 35.5 | K 739 494 | 260 | 0 | 35.5 | N/A | N/A | N/A | N/A | N/A | 16 | 16 | 7/8" | 35 | 35 | 7/8" | 35 | 35 | 7/8" | N/A | N/A | N/A | 176 |  | Baneasa | MW | 311 | 0.3 | 35.5 | 35 | [18 empty] | BA022 | PIATRA NEAMT 1_RTC | 131 | [23 empty] | new |  |  | Marius Lungu | George JUMARA | [33 empty] | Piatra Neamt | Neamt | [7 empty] | 3 |  |  | missing
Phase_3 | CSH | BA171 | TURN APA_2 | Suceava | BA017 Suceava_RTC | Moldova | 47 41 06.8 | 26 13 55.3 |  |  |  |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | YES | [9 empty] | PROTELCO* | [6 empty] | Marin* |  |  | 2001-05-18 |  |  |  | 2001-05-18 | [17 empty] | CTR | [35 empty] | Baneasa | MW | [22 empty] | BA019 | BURDUJENI | [27 empty] | Marius Lungu | Dan VARTOPEAN | [42 empty] | missing |  |  | missing
Phase_3 | CS | BA172 | MADIRJESTI | Road Iasi-Roman | BA031 Independentei_RTC | Moldova | 47 13 03.8 | 27 08 10.5 |  |  |  |  | MAXITE | M | 1 | 2 | 2PBC | [17 empty] | DIEKAT |  | @ | 2001-09-01 | 2001-09-30 |  |  | Bogdan |  |  | 2001-07-10 | [8 empty] | 2001-07-10 | [47 empty] | ML 15 E 1+0* | Baneasa | MW | [22 empty] | BA081 | PODU ILOAIEI | [27 empty] | Denis CIUCU | Calin ACHIM
Phase_3 | CS | BA173 | LETCANI | Road Iasi-Roman | BA031 Independentei_RTC | Moldova | 47 11 58.4 | 27 24 40 |  |  |  |  | MAXITE | M | 1 | 2 | 2PBC | [17 empty] | DIEKAT |  | @ | 2001-09-01 | 2001-09-30 |  |  | Bogdan |  |  | 2001-07-10 | [8 empty] | 2001-07-10 | [47 empty] | ML 15 E 1+0* | Baneasa | MW | [22 empty] | BA005 | COPOU | [27 empty] | Denis CIUCU | Calin ACHIM
Phase_3 | CS | BA174 | CIORTEA | Bacau-Onesti | BA050 Onesti_RTC | Moldova | 46 18 24.8 | 26 44 28 | [26 empty] | SVF |  | @ | 2001-08-01 | 2001-09-10 |  |  | Bogdan |  |  | 2001-06-07 | [21 empty] | CTR | [34 empty] | ML 15 E 1+0 | Baneasa | MW | [22 empty] | BA060 | MARASESTI | [27 empty] | Dragos BICIU | Calin ACHIM | [42 empty] | missing |  |  | missing
Phase_3 | CS | BA177 | TEIUSOARA_DRTV | Road Campulung Moldovenesc-Suceava | BA017 Suceava_RTC | Moldova | 47 39 43.6 | 26 09 01.7 |  |  |  |  | MAXITE | M | 1 | 2 | 2PBC | [17 empty] | DIEKAT |  | @ | 2001-08-01 | 2001-09-10 |  |  | Marin |  |  | 2001-07-06 |  |  |  | 2001-07-10 |  |  |  |  | 2001-07-06 | [47 empty] | ML 15 E 1+1 (PS) | Baneasa | MW | [22 empty] | BA017 | SUCEAVA_RTC | [27 empty] | Marius Lungu | Catalin ANGHEL
Phase_1 | MSC/BSC | BSC11 | BSC TRC BUC. | Bucuresti |  | Muntenia | [5 empty] | RTC/ | [25 empty] | OK | OK |  | OK | [19 empty] | Yes | Yes | Yes |  |  |  | Yes | Yes | Yes | Yes | Yes | [30 empty] | N/A | Dr. Taberei | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | [15 empty] | MSC01 | MSC DRUMUL TABEREI |  | N/A |  |  | N/A | [6 empty] | OK | OK | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [45 empty] | Yes |  |  |  |  | Site Near=Insertion Point
Phase_2 | MSC/BSC | BSC11 | DRUMUL TABEREI | Bucuresti | BSC11 D.TABEREI | Muntenia |  |  |  |  | DRUMUL TABEREI | [36 empty] | 2000-11-01 |  |  | N/A | N/A | [8 empty] | Yes | Yes | Yes |  |  |  | Yes | Yes | Yes | Yes | Yes | [30 empty] | N/A | Dr. Taberei | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | [15 empty] | MSC02 | MSC BANEASA |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | [44 empty] | Yes |  |  | Site Near=Insertion Point
Phase_1 | MSC/BSC | BSC12 | REMOTE BSC BRASOV | Brasov |  | Transilvania | [5 empty] | RTC/ | [25 empty] | OK | OK |  | OK | [19 empty] | Yes | Yes | Yes |  |  |  | Yes | Yes | Yes | Yes | Yes | [30 empty] | N/A | Brasov | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | [15 empty] | MSC02 | MSC BANEASA |  | N/A |  |  | N/A | [6 empty] | OK | OK | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [46 empty] | Yes |  |  |  | Site Near=Insertion Point
Phase_2 | MSC/BSC | BSC12 | BRASOV | Brasov | BSC12 BRASOV | Transilvania | [41 empty] | 2000-11-01 |  |  | N/A | N/A | [8 empty] | Yes | Yes | Yes |  |  |  | Yes | Yes | Yes | Yes | Yes | [30 empty] | N/A | Brasov | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | [15 empty] | MSC02 | MSC BANEASA |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | [44 empty] | Yes |  |  | Site Near=Insertion Point
Phase_1 | MSC/BSC | BSC13 | REMOTE BSC CONSTANTA | Constanta | BSC13 | Dobrogea | [5 empty] | RTC/ | [25 empty] | OK | OK |  | OK | [19 empty] | Yes | Yes | Yes |  |  |  | Yes | Yes | Yes | Yes | Yes | [30 empty] | N/A | Constanta | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | [15 empty] | MSC02 | MSC BANEASA |  | N/A |  |  | N/A | [6 empty] | OK | OK | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [46 empty] | Yes |  |  |  | Site Near=Insertion Point
Phase_2 | MSC/BSC | BSC13 | EXTENSION BSC CONSTANTA | Constanta | BSC13 CONSTANTA | Dobrogea | [41 empty] | 2000-11-01 |  |  | N/A | N/A | [8 empty] | Yes | Yes | Yes |  |  |  | Yes | Yes | Yes | Yes | Yes | [30 empty] | N/A | Constanta | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | [15 empty] | MSC02 | MSC BANEASA |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | [44 empty] | Yes |  |  | Site Near=Insertion Point
Phase_2 | MSC/BSC | BSC14 | REMOTE BSC TG. MURES | Targu Mures | BSC14 TG. MURES | Transilvania | [41 empty] | 2000-11-01 |  |  | N/A | N/A | [8 empty] | Yes | Yes | Yes |  |  |  | Yes | Yes | Yes | Yes | Yes | [30 empty] | N/A | Tg. Mures | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | [15 empty] | MSC01 | MSC DRUMUL TABEREI |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | [43 empty] | Yes |  |  |  | Site Near=Insertion Point
Phase_2 | MSC/BSC | BSC21 | BSC TRC BANEASA | Bucuresti | BSC21 BANEASA | Muntenia |  |  |  |  | Bucharest, 61th, Nicolae Caramfil Str. | [36 empty] | 2000-11-01 |  |  | N/A | N/A | [8 empty] | Yes | Yes | Yes |  |  |  | Yes | Yes | Yes | Yes | Yes | [30 empty] | N/A | Baneasa | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | [15 empty] | MSC02 | MSC BANEASA |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | [42 empty] | Yes |  |  |  |  | Site Near=Insertion Point
Phase_2 | MSC/BSC | BSC22 | REMOTE BSC GALATI | Galati | BSC22 GALATI | Moldova | [41 empty] | 2000-11-01 |  |  | N/A | N/A | [8 empty] | Yes | Yes | Yes |  |  |  | Yes | Yes | Yes | Yes | Yes | [30 empty] | N/A | Galati | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | [15 empty] | MSC02 | MSC BANEASA |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | [43 empty] | Yes |  |  |  | Site Near=Insertion Point
Phase_2 | MSC/BSC | BSC22 | EXTENSION BSC GALATI | Galati | BSC22 | Moldova | [41 empty] | 2000-11-01 |  |  | N/A | N/A | [8 empty] | Yes | Yes | Yes |  |  |  | Yes | Yes | Yes | Yes | Yes | [30 empty] | N/A | Galati | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | [15 empty] | MSC02 | MSC BANEASA |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | [44 empty] | Yes |  |  | Site Near=Insertion Point
Phase_2 | MSC/BSC | BSC23 | REMOTE BSC CRAIOVA | Craiova | BSC23 CRAIOVA | Oltenia | [41 empty] | 2000-11-01 |  |  | N/A | N/A | [8 empty] | Yes | Yes | Yes |  |  |  | Yes | Yes | Yes | Yes | Yes | [30 empty] | N/A | Craiova | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | [15 empty] | MSC02 | MSC BANEASA |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | [43 empty] | Yes |  |  |  | Site Near=Insertion Point
Phase_2 | MSC/BSC | BSC31 | BSC TRC TIMISOARA | Timisoara | BSC31 TIMISOARA | Banat | [41 empty] | 2000-11-01 |  |  | N/A | N/A | [8 empty] | Yes | Yes | Yes |  |  |  | Yes | Yes | Yes | Yes | Yes | [30 empty] | N/A | Timisoara | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | [15 empty] | MSC03 | MSC TIMISOARA | N/A | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | [42 empty] | Yes |  |  |  |  | Site Near=Insertion Point
Phase_2 | MSC/BSC | BSC32 | REMOTE BSC ORADEA | Oradea | BSC32 ORADEA | Banat | [41 empty] | 2000-11-01 |  |  | N/A | N/A | [8 empty] | Yes | Yes | Yes |  |  |  | Yes | Yes | Yes | Yes | Yes | [30 empty] | N/A | Oradea | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | [15 empty] | MSC03 | MSC TIMISOARA | N/A | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | [43 empty] | Yes |  |  |  | Site Near=Insertion Point
Phase_2 | MSC/BSC | BSC41 | BSC TRC CLUJ | Cluj | BSC41 CLUJ | Transilvania | [41 empty] | 2000-11-01 |  |  | N/A | N/A | [8 empty] | Yes | Yes | Yes |  |  |  | Yes | Yes | Yes | Yes | Yes | [30 empty] | N/A | Cluj | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | [15 empty] | MSC04 | MSC CLUJ |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | [42 empty] | Yes |  |  |  |  | Site Near=Insertion Point
Phase_1 | CS | BU001 | PALATUL TELEFOANELOR | Bucharest | BU001 Palatul Telefoanelor | Muntenia | 44 26 12.0 | 26 05 49.0 | 44 26 12.0 | 26 05 49.0 | Calea Victoriei 37(Palatul Telefoanelor) | RTC/ | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | 2000-06-27 |  |  |  |  | B |  | 2x4m+drapel | OUTDOOR | ISAF | OK | ISAF | OK | 1999-10-18 | YesV | OK | AUREL | 1999-10-18 | 1999-10-22 |  |  |  | OK | 1999-10-04 |  | 1999-10-04 | 1999-10-01 |  |  |  | 99:0002 | ETR | N/A | OK | OK | 2000-01-25 | 2000-01-25 | 2000-01-28 |  | Yes | Alexandru Bucur | 2000-02-09 | 2000-05-02 | 2000-05-02 | 2000-05-03 | OK | K 739 494 | 0 | 0 | 45 | K 739 494 | 120 | 2 | 45 | K 739 494 | 240 | 4 | 45 |  |  |  |  | N/A | 30 | 30 | 7/8" | 11 | 11 | 7/8" | 30 | 30 | 7/8" |  |  |  | 60 | N/A | Dr. Taberei | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | RBS | 10001 | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | BSC11 | DRUMUL TABEREI | N/A | N/A | N/A | N/A | N/A | [6 empty] | OK | OK | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 30N01 Palatul Telefoanelor-Dr.Taberei |  |  | COSMIN | COSMIN | [32 empty] | 79 | Bucuresti | Sector 1 | [7 empty] | Site Near=Insertion Point
Phase_1 | CS | BU004 | PAJURA | Bucharest | BU004 Pajura | Muntenia | 44 28 49.0 | 26 02 38.0 | 44 28 50.2 | 26 02 42.1 | Strada Pajura nr.2 | RTC/ | 2202 | M/E | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | B |  | 2x6.5m | ROOM | DIEKAT | OK | DIEKAT | OK | 1999-10-21 | YesV | OK | AUREL | 1999-10-21 | 1999-10-22 |  |  |  | OK | OK |  | OK | 1999-10-01 |  |  |  | 99:0002 | ETR | N/A | 1999-11-11 | OK | 1999-11-12 | OK | 1999-11-22 |  | Yes | Theo Radoi | 1999-12-14 | 2000-04-18 | 2000-04-18 | 2000-04-19 | OK | K 739 494 | 0 | 2 | 0 | K 739 494 | 120 | 2 | 0 | K 739 494 | 240 | 2 | 0 |  |  |  |  | N/A | 35 | 35 | 7/8" | 35 | 35 | 7/8" | 35 | 35 | 7/8" |  |  |  | 210 | N/A | Dr. Taberei | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | 10004 | Phase_1 | [6 empty] | N/A | N/A | BSC11 | DRUMUL TABEREI | N/A | N/A | N/A | N/A | N/A | [6 empty] | OK | OK | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 30N01 Pajura-Dr.Taberei |  | OK | COSMIN | COSMIN | [32 empty] | 84 | Bucuresti | Sector 1 | [7 empty] | Site Near=Insertion Point
Phase_1 | TM | BU005 | PLEVNEI_RTC | Bucharest | BU005 Plevnei_RTC | Muntenia | 44 26 22.3 | 26 04 42.4 | 44 26 22.3 | 26 04 42.4 | Strada Virgiliu | Romtelecom/Gheorghe RASNOVEANU, 01/6371251 | N/A | N/A | N/A | N/A | N/A | [8 empty] | N/A |  |  |  | N/A | B | 20 | C4m (+2m atic) | ROOM | ISAF | OK | ISAF | OK | 2000-02-09 | YesV | OK | AUREL | OK | 2000-02-04 |  |  |  | OK | OK |  | OK | OK |  |  |  | OK | ETR | N/A | N/A | N/A | N/A | N/A | N/A |  | Yes | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 0 | N/A | Dr. Taberei | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | 10005 | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | BSC11 | DRUMUL TABEREI | N/A | N/A | N/A | N/A | N/A | [6 empty] | OK | OK | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [6 empty] | Dan MUSAT | Dan MUSAT | [32 empty] | 80 | Bucuresti | Sector 1 | [7 empty] | Site Near=Insertion Point
Phase_1 | CS | BU007 | PIATA VICTORIEI | Bucharest | BU007 Piata Victoriei | Muntenia | 44 26 51.0 | 26 05 25.0 | 44 26 51.0 | 26 05 25.0 | Strada Nicolae nr. 5 | RTC/ | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | 2000-06-27 |  |  |  | 18 | B |  |  | OUTDOOR | IMSAT | OK | IMSAT | OK | 1999-11-03 | YesV | OK | AUREL | 1999-11-03 | 1999-10-22 |  |  |  | OK | 1999-10-04 |  | 1999-10-04 | 1999-09-15 |  |  |  | 99:0002 | ETR | N/A | OK | OK | 1999-11-16 | OK | 1999-11-19 |  | Yes | Bogdan Bogodai | 2000-01-04 | 2000-01-17 | 2000-01-17 | 2000-03-14 | OK | K 739 494 | 0 | 4 | 0 | K 739 494 | 120 | 0 | 0 | K 739 494 | 240 | 0 | 0 |  |  |  |  | N/A | 10 | 10 | 7/8" | 10 | 10 | 7/8" | 10 | 9 | 7/8" |  |  |  | 59 | N/A | Dr. Taberei | FO | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | RBS | N/A | [9 empty] | BSC11 | DRUMUL TABEREI |  | N/A |  |  | N/A | [6 empty] | OK | OK | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 30N01 Piata Victoriei-Dr.Taberei |  | OK | COSMIN | COSMIN | [32 empty] | 81 | Bucuresti | Sector 1 | [7 empty] | Site Near=Insertion Point
Phase_1 | CS | BU008 | DOROBANTI | Bucharest | BU008 Dorobanti | Muntenia | 44 27 28.0 | 26 05 46.0 | 44 27 28.0 | 26 05 46.0 | Calea Dorobantilor nr.165 | RTC/ | 2102 | M/E | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | 2000-06-27 |  |  |  | 18 | B | 22 | PILONET 15 m | OUTDOOR | IMSAT | OK | IMSAT | OK | 1999-11-15 | YesV | OK | AUREL | 1999-11-15 | OK |  |  |  | OK | OK |  | OK | 1999-11-08 |  |  |  | 99:0002 | ETR | N/A | OK | OK | 1999-11-19 | OK | 1999-11-19 |  | Yes | DANIEL C. | 1999-12-21 | 2000-03-06 | 2000-03-10 | 2000-03-14 | OK | K 739 494 | 0 | 0 | 36 | K 739 494 | 120 | 0 | 36 | K 739 494 | 240 | 0 | 25 |  |  |  |  | N/A | 25 | 25 | 7/8" | 25 | 25 | 7/8" | 25 | 25 | 7/8" |  |  |  | 150 | N/A | Dr. Taberei | FO | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | RBS | N/A | [9 empty] | BSC11 | DRUMUL TABEREI |  | N/A |  |  | N/A | [6 empty] | OK | OK | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 30N01 Dorobanti-Dr. Taberei |  | OK | COSMIN | COSMIN | [32 empty] | 80 | Bucuresti | Sector 1 | [7 empty] | Site Near=Insertion Point
Phase_1 | CS | BU009 | ROMTELECOM BANEASA | Bucharest | BU009 Baneasa_RTC | Muntenia | 44 29 00.0 | 26 05 27.0 | 44 29 00.0 | 26 05 27.0 | Strada Nicolae Caranfil 85C, Baneasa | RTC/ | 2102 | M/E | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | 2000-06-27 |  |  |  | 15 | B |  | 3x8m | OUTDOOR | RADCOM | OK | RADCOM | OK | 1999-11-08 | YesV | OK | MUGUREL | 1999-11-08 | 1999-11-08 |  |  |  | OK | OK |  | OK | 1999-10-01 |  |  |  | 99:0003 | ETR | N/A | 1999-11-09 | OK | 1999-11-12 | OK | 1999-11-12 |  | Yes | DANIEL C. | 1999-12-10 | 2000-03-06 | 2000-03-10 | 2000-03-14 | OK | K 739 494 | 0 | 3 | 0 | K 739 494 | 120 | 3 | 0 | K 739 494 | 240 | 4 | 0 |  |  |  |  | N/A | 34 | 34 | 7/8" | 21 | 24 | 7/8" | 17 | 17 | 7/8" |  |  |  | 147 | N/A | Baneasa | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | RBS | 10009 | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | BSC21 | BANEASA | N/A | N/A | N/A | N/A | N/A | [6 empty] | OK | OK | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2000-05-31 | 30N01 Baneasa-Dr.Taberei |  | OK | COSMIN | COSMIN | [32 empty] | 82 | Bucuresti | Sector 1 | [7 empty] | Site Near=Insertion Point
Phase_1 | CS | BU010 | DACIA | Bucharest | BU010 Dacia | Muntenia | 44 26 46.0 | 26 06 29.0 | 44 26 46.0 | 26 06 29.0 | Bd. Dacia no 99 | RTC/ | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | 2000-06-27 |  |  |  | 18 | B |  | 1x12m | OUTDOOR | IMSAT | OK | IMSAT | OK | 1999-11-03 | YesV | OK | AUREL | 1999-11-03 | 1999-10-22 |  |  |  | OK | OK |  | OK | 1999-10-01 |  |  |  | 99:0002 | ETR | N/A | OK | OK | 1999-11-11 | OK | 1999-11-19 |  | Yes | Daniel Constantinescu | 1999-12-21 | 1999-12-21 | 2000-03-10 | 2000-03-14 | OK | K 739 494 | 0 | 0 | 0 | K 739 494 | 120 | 0 | 0 | K 739 494 | 240 | 0 | 0 |  |  |  |  | N/A | 14 | 14 | 7/8" | 8 | 8 | 7/8" | 8 | 8 | 7/8" |  |  |  | 60 | N/A | Dr. Taberei | FO | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | RBS | 10010 | Phase_1 | [8 empty] | BSC11 | DRUMUL TABEREI |  | N/A |  |  | N/A | [6 empty] | OK | OK | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 30N01 Dacia-Dr.Taberei |  | OK | COSMIN | COSMIN | [32 empty] | 80 | Bucuresti | Sector 1 | [7 empty] | Site Near=Insertion Point
Phase_1 | TM | BU018 | TITAN-2 | Bucharest | BU018 Titan_CTA | Muntenia | 44 25 27.0 | 26 09 44.6 | 44 25 27.0 | 26 09 44.6 | Centrala Telefonica Titan2 | RTC/ | N/A | N/A | N/A | N/A | N/A | [8 empty] | N/A |  |  |  | N/A | B |  |  | ROOM |  | OK |  | OK | OK | YesV | OK |  | OK | 2000-02-02 |  |  |  | OK | OK |  | OK | OK |  |  |  | N/A | YRO | YRO | N/A | N/A | N/A | N/A | N/A |  | Yes | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 0 | N/A | Dr. Taberei | FO | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | Indoor Comteck | [10 empty] | BSC11 | DRUMUL TABEREI |  | N/A |  |  | N/A | [6 empty] | OK | OK | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | [36 empty] | 71 | Bucuresti | Sector 3 | [7 empty] | Site Near=Insertion Point
Phase_1 | CS | BU021 | MIRAJ | Bucharest | BU021 Miraj | Muntenia | 45 35 39.9 | 25 32 56.0 | 44 24 47.0 | 26 08 18.2 | Centrala Miraj, Str. Racari nr. 57 | RTC/ | 2202 | M/E | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | B |  |  | ROOM | SVF | OK | SVF | OK | 1999-10-18 | YesV | OK | DRAGOS | 1999-10-18 | 1999-10-22 |  |  |  | OK | 1999-10-08 |  | 1999-10-08 | 1999-10-08 |  |  |  | 99:0002 | ETR | N/A | OK | OK | 1999-11-10 | OK | 1999-11-19 |  | Yes | Alexandru Bucur | 1999-12-21 | 2000-01-11 | 2000-01-11 | 2000-03-14 | OK | K 739 494 | 0 | 0 | 0 | K 739 494 | 120 | 0 | 0 | K 739 494 | 240 | 0 | 0 |  |  |  |  | N/A | 22 | 22 | 7/8" | 21 | 21 | 7/8" | 21 | 21 | 7/8" |  |  |  | 128 | N/A | Dr. Taberei | FO | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | Indoor Comteck | N/A | [9 empty] | BSC11 | DRUMUL TABEREI |  | N/A |  |  | N/A | [6 empty] | OK | OK | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 30N01 Miraj-Dr.Taberei |  | OK | COSMIN | COSMIN | [32 empty] | 70 | Bucuresti | Sector 3 | [7 empty] | Site Near=Insertion Point
Phase_1 | CS | BU022 | PIATA | Bucharest | BU022 11 Iunie | Muntenia | 45 35 45.8 | 25 33 11.0 | 44 25 16.0 | 26 05 49.0 | Centrala Telefonica Sud, Cpt. Preotescu nr. 8-10 | RTC/ | 2202 | M/E | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | B |  |  | ROOM | ISAF | OK | ISAF | OK | 1999-10-18 | YesV | OK | AUREL | 1999-10-18 | 1999-10-22 |  |  |  | OK | OK |  | OK | 1999-10-06 |  |  |  | 99:0005 | ETR | N/A | OK | OK | 1999-11-11 | OK | 1999-11-19 |  | Yes | Alexandru Bucur | 1999-12-22 | 2000-01-11 | 2000-01-11 | 2000-03-14 | OK | K 739 494 | 0 | 0 | 0 | K 739 494 | 120 | 0 | 0 | K 739 494 | 240 | 0 | 0 |  |  |  |  | N/A | 22 | 23 | 7/8" | 21 | 21 | 7/8" | 19 | 19 | 7/8" |  |  |  | 125 | N/A | Dr. Taberei | FO | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | Indoor Comteck | 10022 | [9 empty] | BSC11 | DRUMUL TABEREI | N/A | N/A |  |  | N/A | [6 empty] | OK | OK | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 30N01 11 Iunie Sud-Dr.Taberei |  | OK | COSMIN | COSMIN | [32 empty] | 71 | Bucuresti | Sector 2 | [7 empty] | Site Near=Insertion Point
Phase_1 | CS | BU026 | PIATA SUDULUI | Bucharest | BU026 Piata Sudului | Muntenia | 45 35 45.8 | 25 33 11.0 | 44 23 31.0 | 26 06 53.0 | Centrala Piata Sudului, Str. Secuilor nr. 9 | RTC/ | 2102 | M/E | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | 2000-06-27 |  |  |  | N/A | B |  |  | OUTDOOR | SVF | OK | SVF | OK | 1999-10-18 | YesV | OK | DRAGOS | 1999-10-18 | 1999-10-22 |  |  |  | OK | 1999-10-08 |  | 1999-10-08 | 1999-10-08 |  |  |  | 99:0002 | ETR | N/A | 1999-11-08 | OK | 1999-11-10 | OK | 1999-11-19 |  | Yes | Theo Radoi | 2000-01-06 | 2000-05-02 | 2000-05-02 | 2000-05-03 | OK | K 739 494 | 4 | 0 | 0 | K 739 494 | 120 | 0 | 0 | K 739 494 | 240 | 0 | 0 |  |  |  |  | N/A | 16 | 16 | 7/8" | 16 | 16 | 7/8" | 16 | 16 | 7/8" |  |  |  | 96 | N/A | Dr. Taberei | FO | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | RBS | 10026 | Phase_1 | [7 empty] | 1 | BSC11 | DRUMUL TABEREI |  | N/A |  |  | N/A | [6 empty] | OK | OK | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2000-05-31 | 30N01 Piata Sudului-Dr.Taberei |  | OK | COSMIN | COSMIN | [32 empty] | 80 | Bucuresti | Sector 4 | [7 empty] | Site Near=Insertion Point
Phase_1 | CS | BU027 | PUISOR | Bucharest | BU027 Puisor | Muntenia | 44 56 08.6 | 25 59 32.9 | 44 25 29.0 | 26 04 43.0 | Calea 13 Septembrie | RTC/ | 2202 | M/E | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | B |  |  | ROOM | DIEKAT | OK | DIEKAT | OK | 1999-11-01 | YesV | OK | AUREL | 1999-11-01 | 1999-11-01 |  |  |  | OK | OK |  | OK | 1999-10-08 |  |  |  | 99:0003 | ETR | N/A | 1999-11-08 | OK | 1999-11-12 | OK | 1999-11-19 |  | Yes | Cristian Croitor | 1999-12-15 | 2000-04-05 | 2000-04-05 | 2000-04-06 | OK | K 739 494 | 0 | 0 | 31.3 | K 739 494 | 120 | 0 | 0 | K 739 494 | 240 | 0 | 0 |  |  |  |  | N/A | 25 | 25 | 7/8" | 25 | 25 | 7/8" | 25 | 25 | 7/8" |  |  |  | 150 | N/A | Dr. Taberei | FO | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | Indoor Comteck | N/A | [9 empty] | BSC11 | DRUMUL TABEREI |  | N/A |  |  | N/A | [6 empty] | OK | OK | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 30N01 Puisor-Dr.Taberei |  | OK | THEO | THEO | [32 empty] | 81 | Bucuresti | Sector 5 | [7 empty] | Site Near=Insertion Point
Phase_1 | CS | BU032 | CNT2_MSC | Bucharest | BU032 CNT_2 | Muntenia | 44 25 18.6 | 26 01 54.2 | 44 25 18.6 | 26 01 54.2 | Drumul Taberei nr. 41 | RTC/ | 2202 | M/E | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | B |  |  | ROOM | SVF | OK | SVF | OK | 1999-10-27 | YesV | OK | DRAGOS | 1999-10-27 | 1999-11-01 |  |  |  | OK | OK |  | OK | 1999-09-15 |  |  |  | 99:0002 | ETR | N/A | OK | OK | 1999-11-05 | 1999-11-08 | 1999-11-12 |  | Yes | Theo Radoi | 1999-12-05 | 2000-04-05 | 2000-04-05 | 2000-04-06 | OK | K 739 494 | 0 | 0 | 26 | K 739 494 | 150 | 0 | 26 | K 739 494 | 240 | 0 | 26 |  |  |  |  | N/A | 30 | 30 | 7/8" | 30 | 30 | 7/8" | 30 | 30 | 7/8" |  |  |  | 180 | N/A | Dr. Taberei | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | TMR 9202 |  | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | BSC11 | DRUMUL TABEREI | N/A | N/A | N/A | N/A | N/A | [6 empty] | OK | OK | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2000-10-04 | 30N01 conectare locala |  | OK | THEO | THEO | [32 empty] | 74 | Bucuresti | Sector 6 | [7 empty] | Site Near=Insertion Point
Phase_1 | CS | BU040 | DINICU GOLESCU | Bucharest | BU005 Plevnei_RTC | Muntenia | 45 14 30.8 | 25 38 02.5 | 44 26 42.2 | 26 04 30.9 | Bd. Dinicu Golescu no 23-25 | Private/NENCIU ALEXANDRU, TEL. 6385578 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | 2000-06-27 |  |  |  |  | B |  | 3x4m | OUTDOOR | ISAF | OK | ISAF | OK | OK | YesV | OK | AUREL | 1999-12-17 | 1999-12-15 |  |  |  | OK | OK |  | OK | 1999-10-01 |  |  |  | 00:0008 | ETR | N/A | OK | OK | OK | OK | 2000-01-21 |  | Yes | Theo Radoi | 2000-02-15 | 2000-04-18 | 2000-04-18 | 2000-04-19 | OK | K 739 494 | 0 | 4 | 0 | K 739 494 | 120 | 0 | 0 | K 739 494 | 240 | 4 | 0 |  |  |  |  | N/A | 22 | 22 | 7/8" | 34 | 34 | 7/8" | 25 | 25 | 7/8" |  |  |  | 162 | ML 38 E 1+0 | Dr. Taberei | MW | 232.8 | 0.3 |  |  | 38/14 | [6 empty] | RBS | [9 empty] | 1 | BU005 | PLEVNEI_RTC | 52.8 | 0.3 |  |  | 38/18 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-08-10 | PENDING |  |  |  |  | OK | THEO | THEO | [32 empty] | 80 | Bucuresti | Sector 1 | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BU041 | TELEGRAF | Bucharest | BU009 Baneasa_RTC | Muntenia | 45 26 40.6 | 25 33 20.1 | 44 27 11.0 | 26 06 00.0 | Sos. Stefan cel Mare | RTC/ | 2202 | M/E | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | B |  |  | ROOM | IMSAT | OK | IMSAT | OK | 1999-11-08 | YesV | OK | AUREL | 1999-11-08 | 1999-11-08 |  |  |  | OK | 1999-10-13 |  | 1999-10-13 | 1999-09-15 |  |  |  | N/A | YRO | ISAF | 1999-11-25 | OK | 1999-12-01 | 2000-01-14 | 2000-02-07 |  | Yes | Alexandru Bucur | 2000-02-08 | 2000-03-13 | 2000-03-13 | 2000-03-14 | OK | K 739 494 | 0 | 4 | 39 | K 739 494 | 120 | 0 | 39 | K 739 494 | 240 | 4 | 39 |  |  |  |  | N/A | 55 | 55 | 1 1/4" | 55 | 55 | 1 1/4" | 55 | 55 | 1 1/4" |  |  |  | 330 | ML 38 E 1+0 | Baneasa | MW | 359.2 | 0.3 |  |  | 38/18 |  | 4x2/8 | 4U-1 |  |  |  | Indoor Comteck | [10 empty] | BU044 | IPA | 179.2 | 0.3 |  |  | 38/14 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-05-10 |  |  | 2000-05-10 | 30N05 Baneasa-Dr.Taberei |  | OK | THEO | THEO | [32 empty] | 80 | Bucuresti | Saector 2 | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BU042 | CHITILA(OPTIMIZARE) | Bucharest | BU042 Chitila | Muntenia | 44 33 53.8 | 27 21 30.0 | 44 30 16.2 | 25 59 22.7 | Romtelecom, Strada Pacii, Chitila | RTC/ | 2202 | M | C+C+C+ | 2/2/2 | N/A | FEEDER | N/A | N/A | N/A | N/A | N/A | OK | N/A | N/A |  |  |  | N/A | TN |  |  | EXISTSHELT | DIEKAT | OK | DIEKAT | OK | 1999-11-08 | YesV | OK | AUREL | 1999-11-08 | 1999-10-22 |  |  |  | OK | OK |  | OK | 1999-09-20 |  |  | N/A | N/A | YRO | N/A | 2000-11-17 | 2000-11-17 | 2000-11-18 | 2000-11-19 | 2000-11-20 |  | Yes | Cristian Croitor | 2000-11-20 | 2000-11-20 | 2000-11-20 | 2001-01-15 | 2001-06-16 | K 739 494 | 325 | 0 | 45 | K 739 494 | 120 | 0 | 30 | K 739 494 | 240 | 0 | 30 | N/A | N/A | N/A | N/A | N/A | 60 | 60 | 1 1/4" | 47 | 47 | 7/8" | 47 | 47 | 7/8" | N/A | N/A | N/A | 308 | N/A | Dr. Taberei | FO | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | 10041 | 2001-06-04 | [8 empty] | BSC11 | DRUMUL TABEREI | N/A | N/A |  |  | N/A | [6 empty] | OK | OK | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 30N01 Chitila-Dr.Taberei |  | OK | COSMIN | COSMIN | [21 empty] | 1999-11-17 |  | 99:0003 | ETR | N/A | 1999-11-19 | C.Croitor | 8-Mai-00 | 8-Mai-00 | 36655 | OK | 91 | Chitila | Ilfov | [7 empty] | Site Near=Insertion Point
Phase_1 | CS | BU043 | ION MIHALACHE | Bucharest | BU004 Pajura | Muntenia | 44 20 31.4 | 28 02 16.0 | 44 27 47.6 | 26 04 14.6 | Bd. Ion Mihalache | As. De locatari/ | 2202 | M/E | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | B |  |  | ROOM | DUAL | OK | DUAL | OK | 1999-11-23 | YesV | OK | MUGUREL | 1999-11-23 | 1999-11-08 |  |  |  | OK | OK |  | OK | 1999-09-20 |  |  |  | 99:0004 | ETR | N/A | OK | OK | 1999-11-19 | OK | 1999-11-22 |  | Yes | Alexandru Bucur | 1999-12-20 | 2000-05-02 | 2000-05-02 | 2000-05-03 | OK | K 739 494 | 0 | 0 | 0 | K 739 494 | 120 | 0 | 0 | K 739 494 | 240 | 0 | 0 |  |  |  |  | N/A | 30 | 30 | 7/8" | 8 | 8 | 7/8" | 24 | 24 | 7/8" |  |  |  | 124 | ML 38 E 1+0 | Dr. Taberei | MW | 303.3 | 0.3 | 31 |  | 38/13 | [6 empty] | Indoor Comteck | [9 empty] | 1 | BU089 | BD.BRATIANU | 123.73 | 0.3 | 31 |  | 38/17 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-08-10 | PENDING |  |  | 30N03 Pajura-Dr.Taberei |  | OK | THEO | THEO | [32 empty] | 81 | Bucuresti | Sector 1 | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BU044 | IPA | Bucharest | BU009 Baneasa_RTC | Muntenia | 44 28 01.0 | 26 05 59.0 | 44 28 01.0 | 26 05 59.0 | Mircea Eliade 18 | Automatica/ | 2202 | M/E | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | B |  |  | ROOM | DUAL | OK | DUAL | OK | OK | YesV | OK | MUGUREL | OK | 1999-11-26 |  |  |  | OK | OK |  | OK | 1999-09-20 |  |  |  | N/A | YRO | YRO | 1999-11-29 | OK | 1999-12-01 | 1999-12-03 | 1999-12-06 |  | Yes | Alexandru Bucur | 2000-02-12 | 2000-03-07 | 2000-03-07 | 2000-03-14 | OK | K 739 494 | 0 | 0 | 0 | K 739 494 | 120 | 0 | 0 | K 739 494 | 240 | 0 | 0 |  |  |  |  | N/A | 25 | 25 | 7/8" | 25 | 25 | 7/8" | 25 | 25 | 7/8" |  |  |  | 150 | ML 23 E 1+0 | Baneasa | MW | 338.8 | 0.6 | 28.5 | 20 | 23/56 |  | 4x2/8 | 2U-3 |  |  |  | Indoor Comteck | [9 empty] | 1 | BU009 | ROMTELECOM BANEASA | 158.8 | 0.6 | 27.5 | 25 | 23/58 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-05-24 |  |  | 2000-05-31 | 30N03 Baneasa-Dr.Taberei |  | OK | THEO | THEO | [32 empty] | 77 | Bucuresti | Sector 1 | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BU045 | ROMTELECOM LIBERTATII | Bucharest | BU001 Palatul Telefoanelor | Muntenia | 44 25 36.2 | 26 05 37.1 | 44 25 36.2 | 26 05 37.1 | Sediul Romtelecom, Piata Constitutiei | RTC/ | 2202 | M/E | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | B |  |  | ROOM | ISAF | OK | ISAF | OK | 1999-10-18 | YesV | OK | AUREL | 1999-10-18 | 1999-10-22 |  |  |  | OK | OK |  | OK | 1999-09-15 |  |  |  | N/A | YRO | YRO | 1999-11-25 | OK | 1999-11-29 | 1999-11-30 | 1999-12-02 |  | Yes | Alexandru Bucur | 1999-12-02 | 2000-01-12 | 2000-01-12 | 2000-03-14 | OK | K 739 494 | 0 | 4 | 0 | K 739 494 | 120 | 0 | 0 | K 739 494 | 240 | 0 | 0 |  |  |  |  | N/A | 23 | 23 | 7/8" | 29 | 29 | 7/8" | 15 | 15 | 7/8" |  |  |  | 134 | ML 38 E 1+0 | Dr. Taberei | MW | 67.8 | 0.3 | 45 | 30 | 38/18 |  | 4x2/8 | 2U-3 |  |  |  | N/A | [9 empty] | 1 | BU053 | MAGAZIN_UNIREA | 247.6 | 0.3 | 45 | 35 | 38/14 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-08-03 |  |  | 2000-10-24 | 30N04 Palatul Telefoanelor-Dr.Taberei |  | OK | COSMIN | COSMIN | [32 empty] | 75 | Bucuresti | Sector 5 | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BU046 | CASA PRESEI | Bucuresti | BU046 Casa Presei | Muntenia | 44 28 50.0 | 26 04 13.0 | 44 28 48.8 | 26 04 14.0 | Casa Presei, Piata Presei Libere |  | 2202 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | B |  |  | ROOM | RADCOM | OK | RADCOM | OK | 2000-01-07 | YesV | OK | MUGUREL | 2000-01-07 | 1999-12-29 |  |  |  | OK | 2001-07-11 |  | OK | 2000-01-04 |  |  |  | N/A | YRO | YRO | 2000-01-24 | OK | 2000-01-25 | 2000-01-25 | 2000-01-28 |  | Yes | Alexandru Bucur | 2000-02-03 | 2000-02-03 | 2000-02-03 | 2000-03-14 | OK | K 739 494 | 0 | 6 | 0 | K 739 494 | 120 | 6 | 0 | K 739 494 | 240 | 6 | 0 |  |  |  |  | N/A | 27 | 28 | 7/8" | 7 | 10 | 7/8" | 20 | 20 | 7/8" |  |  |  | 112 | N/A | Dr. Taberei | FO | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | Indoor Comteck | 10046 | [9 empty] | BSC11 | DRUMUL TABEREI |  | N/A |  |  | N/A | [6 empty] | OK | OK | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 30N01 Casa Presei-Dr.Taberei |  | OK | THEO | THEO | [32 empty] | 80 | Bucuresti | Sector 1 | [7 empty] | Site Near=Insertion Point
Phase_1 | CS | BU047 | MICROELECTRONICA | Bucharest | BU047 Microelectronica | Muntenia | 44 30 55.0 | 26 06 41.0 | 44 30 52.5 | 26 06 41.9 | STR. EROU IANCU NICOLAE NR. 32B |  | 2202 | M/E | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | B | 33.5 | tripoda+montant | ROOM | RADCOM | OK | RADCOM | OK | OK | YesV | OK | MUGUREL | OK | 1999-11-19 |  |  |  | OK | 1999-10-13 |  | 1999-10-13 | OK |  |  |  | N/A | YRO | YRO | 1999-11-25 | OK | 1999-12-01 | 1999-12-01 | 1999-12-03 |  | Yes | Alexandru Bucur | 1999-12-10 | 2000-03-07 | 2000-03-07 | 2000-03-14 | OK | K 739 494 | 0 | 7 | 0 | K 739 494 | 120 | 7 | 0 | K 739 494 | 240 | 7 | 0 |  |  |  |  | N/A | 25 | 25 | 7/8" | 25 | 25 | 7/8" | 25 | 25 | 7/8" |  |  |  | 150 | N/A | Dr. Taberei | FO | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | Indoor Comteck | N/A | [9 empty] | BSC11 | DRUMUL TABEREI |  | N/A |  |  | N/A | [6 empty] | OK | OK | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 30N01 Microelectronica-Dr.Taberei |  | OK | PETRICA | PETRICA | [32 empty] | 90 | Bucuresti | Sector 2 | [7 empty] | Site Near=Insertion Point
Phase_1 | CS | BU048 | VITAN 2 | Bucharest | BU001 Palatul Telefoanelor | Muntenia | 44 25 30.0 | 26 07 29.0 | 44 25 31.2 | 26 07 29.0 | Centrala Telefonica Vitan 2 | RTC/ | 2202 | M/E | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | B |  |  | ROOM | DUAL | OK | DUAL | OK | OK | YesV | OK | MUGUREL | OK | 1999-11-26 |  |  |  | OK | OK |  | OK | 1999-09-20 |  |  |  | N/A | YRO | YRO | 1999-11-29 | OK | 1999-11-30 | 1999-12-02 | 1999-12-04 |  | Yes | Alexandru Bucur | 1999-12-17 | 2000-03-16 | 2000-03-16 | 2000-03-17 | OK | K 739 494 | 0 | 0 | 0 | K 739 494 | 120 | 0 | 0 | K 739 494 | 240 | 0 | 0 |  |  |  |  | N/A | 25 | 25 | 7/8" | 25 | 25 | 7/8" | 25 | 25 | 7/8" |  |  |  | 150 | ML 38 E 1+0 | Dr. Taberei | MW | 286.7 | 0.3 | 35 |  | 38/18 |  | 4x2/8 |  |  |  |  | Indoor Comteck | [9 empty] | 1 | BU052 | BD_UNIRII | 106.7 | 0.3 | 35 |  | 38/14 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-10-03 |  | 2000-09-25 | 2000-10-03 | 30N02 Palatul Telefoanelor-Dr.Taberei |  | OK | THEO | THEO | [32 empty] | 79 | Bucuresti | Sector 2 | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BU050 | POLITEHNICA | Bucharest | BU004 Pajura | Muntenia | 44 26 02.8 | 26 04 39.6 | 44 26 07.7 | 26 02 29.8 | Str.Politehnicii nr 5, bl. 8, Sector 6, Bucuresti | As. De locatari/ | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | 2000-06-27 |  |  |  | 36 | B | 33 | tripods | OUTDOOR | DIEKAT | OK | DIEKAT | OK | OK | YesV | OK |  | OK | OK |  |  |  | 2000-02-17 | OK |  | OK | 2000-04-26 |  |  |  | 00:0009 | YRO | YRO | 2000-04-26 | OK | OK | OK | OK |  | Yes | Alexandru Bucur | 2000-05-09 | 2000-05-10 | 11-Mai-00 | 2000-05-18 | OK | K 739 494 | 0 | 0 | 39 | K 739 494 | 120 | 0 | 36 | K 739 494 | 240 | 4 | 36 |  |  |  |  | N/A | 10 | 10 | 7/8" | 14 | 14 | 7/8" | 14 | 14 | 7/8" |  |  |  | 76 | ML 38 E 1+0 | Dr. Taberei | MW | 44.5 | 0.3 |  |  | 38/18 |  | 4x2/8 | 2u-3 |  |  |  | RBS | [10 empty] | BU086 | PRIORIPOST | 224.89 | 0.3 |  |  | 38/14 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-05-12 |  |  | 2000-07-05 | 30N06 Pajura-Dr.Taberei |  | OK | SORIN UNTARU | SORIN UNTARU | [32 empty] | 88 | Bucuresti | Sector 6 | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BU051 | STIRBEI VODA | Bucharest | BU005 Plevnei_RTC | Muntenia | 44 26 21.2 | 26 05 16.6 | 44 26 20.5 | 26 05 05.8 | Stirbei Voda no. 65 | As de locatari/Administrator Ciurea, pager. 0186100960/ 46245 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | 2000-06-27 |  |  |  | N/A | B | 30 | C6m+C6m+C6m | OUTDOOR | IMSAT | OK | IMSAT | OK | OK | YesV | OK | AUREL | 2000-03-09 | OK |  |  |  | 1999-11-10 | 1999-11-30 |  | 1999-11-30 | 2000-01-07 |  |  |  | 00:0009 | ETR | Electotrade | OK | OK | 2000-03-13 | 2000-03-14 | 2000-03-15 |  | Yes | Theo Radoi | 2000-03-20 | 2000-04-19 | 2000-04-19 | 2000-04-21 | OK | K 739 494 | 0 | 4 | 28 | K 739 494 | 120 | 0 | 28 | K 739 494 | 240 | 4 | 28 |  |  |  |  | N/A | 15 | 15 | 7/8" | 28 | 28 | 7/8" | 28 | 28 | 7/8" |  |  |  | 142 | ML 38 E 1+0 | Dr. Taberei | MW | 111.6 | 0.3 |  |  | 38/18 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [9 empty] | 1 | BU040 | DINICU GOLESCU | 291.6 | 0.3 |  |  | 38/14 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-08-09 |  |  | 2000-10-25 |  |  | OK | THEO | THEO | [32 empty] | 80 | Bucuresti | Sector 1 | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BU052 | BD_UNIRII | Bucharest | BU001 Palatul Telefoanelor | Muntenia | 44 25 38.5 | 26 06 49.5 | 44 25 38.5 | 26 06 49.5 | Bd. Unirii nr. 45, bl. E3-4, sc. 5 | As. De locatari/Adm. Stana Martac et. 6, ap. 134, sc. 5; te;. 3200710 | 2202 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | B | 30 |  | ROOM | DUAL | OK | DUAL | OK | 2000-01-04 | YesV | OK | MUGUREL | 2000-01-04 | 1999-12-16 |  |  |  | 1999-09-24 | 1999-11-05 |  | 1999-11-05 | 1999-11-26 |  |  |  | 00:0008 | ETR | N/A | OK | OK | OK | OK | 2000-01-21 |  | Yes | Cristian Croitor | 2000-02-10 | 2000-04-05 | 2000-04-05 | 2000-04-06 | OK | K 739 494 | 0 | 0 | 0 | K 739 494 | 120 | 0 | 0 | K 739 494 | 240 | 0 | 0 |  |  |  |  | N/A | 30 | 30 | 7/8" | 30 | 30 | 7/8" | 30 | 30 | 7/8" |  |  |  | 180 | ML 38 E 1+0 | Dr. Taberei | MW | 294.1 | 0.3 | 35 | 40 | 38/14 |  | 4x2/8 | 4U-1 |  |  |  | Indoor Comteck | [9 empty] | 1 | BU053 | MAGAZIN_UNIREA | 114.1 | 0.3 | 35 | 40 | 38/18 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-10-11 |  |  | 2000-12-18 | 30N02 Palatul Telefoanelor-Dr.Taberei |  | OK | DAN | DAN | [32 empty] | 80 | Bucuresti | Sector 3 | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BU053 | MAGAZIN_UNIREA | Bucharest | BU001 Palatul Telefoanelor | Muntenia | 44 25 48.4 | 26 06 18.6 | 44 25 42.7 | 26 06 15.9 | Magazin Unirea, Piata Unirii no. 1 | Private/Palade Carmen, Director Tehnic | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | 2000-06-27 |  |  |  | 40 | B | 33 | T4m+T4m+T4m | OUTDOOR | DUAL | OK | DUAL | OK | 2000-01-11 | YesV | OK | MUGUREL | 2000-01-11 | 2000-01-11 |  |  |  | 1999-12-15 | 1999-12-23 |  | 1999-12-23 | 2000-01-04 |  |  |  | 00:0008 | ETR | N/A | OK | OK | OK | OK | 2000-01-21 |  | Yes | Cristian Croitor | 2000-02-10 | 2000-04-05 | 2000-04-05 | 2000-04-06 | OK | K 739 494 | 0 | 2 | 35 | K 739 494 | 120 | 4 | 35 | K 739 494 | 240 | 0 | 35 |  |  |  |  | N/A | 32 | 32 | 7/8" | 38 | 38 | 7/8" | 48 | 48 | 7/8" |  |  |  | 236 | ML 38 E 1+0 | Dr. Taberei | MW | 318 | 0.3 |  |  | 38/18 |  | 4x2/8 | 4U-1 |  |  |  | RBS | [9 empty] | 1 | BU001 | PALATUL TELEFOANELOR | 138 | 0.3 |  |  | 38/14 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-10-11 |  |  | 2000-12-18 | 30N04 Palatul Telefoanelor-Dr.Taberei |  | OK | DAN | DAN | [32 empty] | 80 | Bucuresti | Sector 3 | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BU054 | MOSILOR | Bucharest | BU010 Dacia | Muntenia | 44 26 22.6 | 26 07 03.0 | 44 26 21.7 | 26 07 02.3 | Calea Mosilor nr. 260, bl. 6 | As. De locatari/Gradinaru Ctin., tel. 6105833 | 2202 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | B | 28 | Tripods | ROOM | SETRACO | OK | SETRACO | OK | OK | YesV | OK | AUREL | 1999-12-21 | 1999-12-16 |  |  |  | 1999-10-14 | OK |  | OK | OK |  |  |  | N/A | YRO | YRO | 2000-01-07 | OK | 2000-01-11 | 2000-01-11 | 2000-01-14 |  | Yes | Cristian Croitor | 2000-02-10 | 2000-03-07 | 2000-03-13 | 2000-03-14 | OK | K 739 494 | 0 | 0 | 30 | K 739 494 | 120 | 0 | 30 | K 739 494 | 240 | 0 | 30 |  |  |  |  | N/A | 18 | 18 | 7/8" | 12 | 12 | 7/8" | 30 | 30 | 7/8" |  |  |  | 120 | ML 38 E 1+0 | Dr. Taberei | MW | 315.5 | 0.3 |  |  | 38/14 |  | 4x2/8 | 4U-1 |  |  |  | Indoor Comteck | [10 empty] | BU010 | DACIA | 135.5 | 0.3 |  |  | 38/18 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-05-10 |  |  | 2000-05-10 | 30N02 Dacia-Dr.Taberei |  | OK | MIHAI C. | MIHAI C. | [32 empty] | 80 | Bucuresti | Sector 3 | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BU055 | HYPERION | Bucharest | BU010 Dacia | Muntenia | 44 26 02.3 | 26 07 41.1 | 44 25 55.7 | 26 07 55.7 | Calea Calarasi 177, bl. 45 | Private/ | 2202 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | B | 34 | Tripods | ROOM | SETRACO | OK | SETRACO | OK | 2000-01-18 | YesV | OK | AUREL | 2000-01-18 | 1999-12-23 |  |  |  | 1999-11-18 | OK |  | OK | 1999-12-16 |  |  |  | N/A | YRO | YRO | 2000-01-24 | OK | 2000-01-25 | 2000-01-25 | 2000-01-28 |  | Yes | Alexandru Bucur | 2000-02-17 | 2000-03-31 | 2000-03-31 | 2000-04-04 | OK | K 739 494 | 0 | 0 | 34 | K 739 494 | 120 | 0 | 34 | K 739 494 | 240 | 0 | 34 |  |  |  |  | N/A | 30 | 30 | 7/8" | 24 | 24 | 7/8" | 20 | 20 | 7/8" |  |  |  | 148 | ML 38 E 1+0 | Dr. Taberei | MW | 307.2 | 0.3 |  |  | 38/18 |  | 4x2/8 |  |  |  |  | Indoor Comteck | [10 empty] | BU054 | MOSILOR | 127.2 | 0.3 |  |  | 38/14 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-05-10 |  |  | 2000-05-10 | 30N01 Dacia-Dr.Taberei |  | OK | COSMIN | COSMIN | [32 empty] | 79 | Bucuresti | Sector 2 | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BU056 | OBOR | Bucharest | BU010 Dacia | Muntenia | 44 26 42.3 | 26 07 49.1 | 44 26 40.3 | 26 07 49.2 | Sos. Mihai Bravu nr. 47-49, bl. P16-P16A, sc. A | As. De locatari/Patrascioiu, ap. 8 | 2202 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | B |  |  | ROOM | SETRACO | OK | SETRACO | OK | OK | YesV | OK | AUREL | 1999-12-21 | 1999-12-16 |  |  |  | OK | OK |  | OK | 1999-11-22 |  |  |  | N/A | YRO | YRO | 2000-01-07 | OK | 2000-01-11 | 2000-01-11 | 2000-01-14 |  | Yes | Alexandru Bucur | 2000-02-26 | 2000-03-30 | 2000-03-30 | 2000-04-07 | OK | K 739 494 | 0 | 0 | 0 | K 739 494 | 120 | 0 | 0 | K 739 494 | 240 | 0 | 0 |  |  |  |  | N/A | 10 | 10 | 7/8" | 35 | 35 | 7/8" | 35 | 35 | 7/8" |  |  |  | 160 | ML 38 E 1+0 | Dr. Taberei | MW | 241 | 0.3 |  |  | 38/18 |  | 4x2/8 |  |  |  |  | Indoor Comteck | [10 empty] | BU054 | MOSILOR | 61 | 0.3 |  |  | 38/14 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-05-12 |  |  | 2000-05-10 | 30N02 Dacia-Dr.Taberei |  | OK | THEO | THEO | [32 empty] | 80 | Bucuresti | Sector 2 | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BU057 | MEGAIMAGE LIZEANU | Bucharest | BU001 Palatul Telefoanelor | Muntenia | 44 27 05.1 | 26 07 08.0 | 44 27 07.7 | 26 07 12 | Sos. Stefan cel Mare nr. 33, bl. 50, sc. 1 | As. De locatari/Dan Ioan, 610.6156 | 2202 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | B | 30 | T4m+T4m+T4m | ROOM | SVF | OK | SVF | OK | 2000-02-08 | YesV | OK | DRAGOS | 2000-02-08 | 1999-12-27 |  |  |  | 1999-11-25 | OK |  | OK | 1999-12-15 |  |  |  | 00:0009 | ETR | Electotrade | 2000-02-18 | OK | 2000-02-18 | 2000-02-18 | 2000-02-20 |  | Yes | Alexandru Bucur | 2000-02-26 | 2000-05-02 | 2000-05-02 | 2000-05-03 | OK | K 739 494 | 0 | 4 | 27 | K 739 494 | 120 | 4 | 26 | K 739 494 | 240 | 0 | 26 |  |  |  |  | N/A | 27 | 27 | 7/8" | 22 | 22 | 7/8" | 10 | 10 | 7/8" |  |  |  | 118 | ML 38 E 1+0 | Dr. Taberei | MW | 226.8 | 0.3 | 32.5 | 40 | 38/18 |  | 4X2/8 | 2U-3 |  |  |  | Indoor Comteck | [9 empty] | 1 | BU001 | PALATUL TELEFOANELOR | 46.8 | 0.3 | 45 | 40 | 38/14 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-10-11 |  |  | 2000-12-18 | 30N01 Palatul Telefoanelor-Dr.Taberei |  | OK | DAN | DAN | [32 empty] | 80 | Bucuresti | Sector 2 | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BU058 | LACUL TEI | Bucharest | BU009 Baneasa_RTC | Muntenia | 44 27 39.7 | 26 06 45.1 | 44 27 33.6 | 26 06 44.2 | Str. Lacul Tei nr. 63, bl. 81, sc. 1 | As. De locatari/Titorian Stefan 01/6105538 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | 2000-06-27 |  |  |  | 30 | B | 30 | T6m+T4m+T4m | OUTDOOR | SVF | OK | SVF | OK | 2000-01-25 | YesV | OK | DRAGOS | 2000-01-25 | 1999-12-22 |  |  |  | OK | 1999-11-11 |  | 1999-11-11 | 1999-12-14 |  |  |  | N/A | YRO | YRO | 2000-01-18 | OK | 2000-01-21 | 2000-01-27 | 2000-01-30 |  | Yes | Cristian Croitor | 2000-02-20 | 2000-02-20 | 2000-03-07 | 2000-03-14 | OK | K 739 494 | 90 | 0 | 34 | K 739 494 | 120 | 3 | 33 | K 739 494 | 240 | 4 | 33 |  |  |  |  | N/A | 40 | 40 | 7/8" | 45 | 45 | 7/8" | 25 | 25 | 7/8" |  |  |  | 220 | ML 38 E 1+0 | Baneasa | MW | 310 | 0.3 | 28.5 | 23 | 38/18 |  | 4x2/8 | N/A |  |  |  | RBS | [10 empty] | BU044 | IPA | 130.2 | 0.3 | 32.5 | 40 | 38/14 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-05-10 |  |  | 2000-05-10 | 30N03 Baneasa-Dr.Taberei |  | OK | DAN | DAN | [32 empty] | 80 | Bucuresti | Sector 2 | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BU059 | COLENTINA_1 | Bucharest | BU009 Baneasa_RTC | Muntenia | 44 27 32.3 | 26 07 48.6 | 44 27 22.1 | 26 07 49.6 | Sos. Colentina no. 10, Bloc S6 Scara C | As. De locatari/Ungureanu, Sos. Colentina no. 10, bloc S6, Sc. C, tel. 01/687 22 73 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | 2000-06-27 |  |  |  | 30 | B | 30 | T6m+T6m | OUTDOOR | SVF | OK | SVF | OK | 2000-02-15 | YesV | OK | DRAGOS | 2000-02-15 | 2000-02-10 |  |  |  | 1999-11-24 | 2000-01-31 |  | 2000-01-31 | 2000-02-07 |  |  |  | 00:0009 | ETR | Electotrade | 2000-02-22 | OK | 2000-02-23 | 2000-02-23 | 2000-02-25 |  | Yes | Theo Radoi | 2000-03-03 | 2000-04-19 | 2000-04-19 | 2000-04-21 | OK | K 739 494 | 0 | 0 | 34.5 | K 739 494 | 120 | 0 | 34.6 | K 739 494 | 200 | 0 | 34 |  |  |  |  | N/A | 15 | 15 | 7/8" | 20 | 20 | 7/8" | 15 | 15 | 7/8" |  |  |  | 100 | ML 38 E 1ÉÉ | Baneasa | MW | 45.6 | 0.3 |  |  | 38/18 |  | 4X2/8 | 2U-3 |  |  |  | RBS | [10 empty] | BU094 | COLENTINA-2 | 225.6 | 0.3 |  |  | 38/14 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-05-24 |  |  | 2000-05-31 | 30N04 Baneasa-Dr.Taberei |  | OK | DAN | DAN | [32 empty] | 80 | Bucuresti | Sector 2 | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BU060 | DNA. GHICA | Bucharest | BU010 Dacia | Muntenia | 44 27 11.8 | 26 08 48.6 | 44 27 21.6 | 26 08 36.6 | Str. Doamna Ghica nr. 32, bl 12 Sud | /D-na Ghica 32,BL.12 SUD | 2202 | M/E | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | B |  |  | ROOM | EL-MONT | OK | EL-MONT | OK | 1999-12-14 | YesV | OK | DRAGOS | 1999-12-14 | OK |  |  |  | 1999-10-04 | 1999-11-10 |  | 1999-11-10 | 1999-11-15 |  |  |  | N/A | YRO | YRO | 1999-12-15 | OK | 1999-12-15 | 1999-12-14 | 1999-12-17 |  | Yes | Alexandru Bucur | 2000-03-14 | 2000-03-14 | 2000-03-14 | 2000-03-15 | OK | K 739 494 | 0 | 0 | 0 | K 739 494 | 120 | 4 | 0 | K 739 494 | 240 | 0 | 0 |  |  |  |  | N/A | 10 | 10 | 7/8" | 35 | 35 | 7/8" | 10 | 10 | 7/8" |  |  |  | 110 | ML 38 E 1+0 | Dr. Taberei | MW | 174.1 | 0.3 | 30.5 |  | 38/13 |  | 4x2/8 | 2U-3 |  |  |  | Indoor Comteck | [10 empty] | BU061 | IANCULUI-2 | 354.1 | 0.3 | 43 |  | 38/17 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-05-10 |  |  | 2000-05-10 | 30N03 Dacia-Dr.Taberei |  | OK | MIHAI C. | MIHAI C. | [32 empty] | 74 | Bucuresti | Sector 2 | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BU061 | IANCULUI_2 | Bucharest | BU010 Dacia | Muntenia | 44-26-35.1 | 26 08 42.4 | 44 26 35.5 | 26 08 36.8 | Sos. Iancului nr. 37, bl. 103B | As. Locatari/Stoenescu Romeo (Adm.), Sos. Iancului nr. 37, bl. 103B, et. 6 | 2202 | M/E | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | B | 42 |  | ROOM | EL-MONT | OK | EL-MONT | OK | 1999-12-14 | YesV | OK | DRAGOS | 1999-12-14 | 1999-12-03 |  |  |  | 1999-09-29 | OK |  | OK | OK |  |  |  | N/A | YRO | YRO | 1999-12-15 | OK | 1999-12-15 | 1999-12-14 | 1999-12-17 |  | Yes | Alexandru Bucur | 2000-02-16 | 2000-03-14 | 2000-03-14 | 2000-03-15 | OK | K 739 494 | 0 | 0 | 0 | K 739 494 | 120 | 0 | 0 | K 739 494 | 240 | 0 | 0 |  |  |  |  | N/A | 40 | 40 | 7/8" | 12 | 12 | 7/8" | 28 | 28 | 7/8" |  |  |  | 160 | ML 38 E 1+0 | Dr. Taberei | MW | 278.1 | 0.3 |  |  | 38/14 |  | 4x2/8 |  |  |  |  | Indoor Comteck | [10 empty] | BU056 | OBOR | 98.1 | 0.3 |  |  | 38/18 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-05-10 |  |  | 2000-05-10 | 30N03 Dacia-Dr.Taberei |  | OK | THEO | THEO | [32 empty] | 76 | Bucuresti | Sector 2 | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BU062 | BASARABIA | Bucharest | BU018 Titan_CTA | Muntenia | 44 25 52.1 | 26 08 45.0 | 44 25 52.1 | 26 08 45.0 | Bd. Basarabia 42, bl. 32, sc. A | As. De locatari/Presedinte Ispas Stan - parter; 6487752 | 2202 | M/E | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | B | 30 |  | ROOM | DUAL | OK | DUAL | OK | OK | YesV | OK | MUGUREL | 2000-01-04 | 1999-12-08 |  |  |  | 1999-09-24 | OK |  | OK | 1999-11-25 |  |  |  | 99:0005 | ETR | N/A | 1999-11-29 | OK | OK | OK | 1999-12-18 |  | Yes | Cristian Croitor | 2000-02-20 | 2000-04-06 | 2000-04-06 | 2000-04-07 | OK | K 739 494 | 0 | 2 | 30 | K 739 494 | 120 | 0 | 30 | K 739 494 | 240 | 0 | 30 |  |  |  |  | N/A | 20 | 20 | 7/8" | 55 | 55 | 7/8" | 55 | 55 | 7/8" |  |  |  | 260 | ML 38 E 1+0 | Dr. Taberei | MW | 62.6 | 0.3 |  |  | 38/18 |  | 4x2/8 |  |  |  |  | Indoor Comteck | [10 empty] | BU067 | DIHAM | 242.6 | 0.3 |  |  | 38/14 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-05-10 |  |  | 2000-05-10 | 30N03 Titan-Dr.taberei |  | OK | DAN | DAN | [32 empty] | 75 | Bucuresti | Sector 2 | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BU063 | DRISTOR | Bucharest | BU018 Titan_CTA | Muntenia | 44 25 21.4 | 26 08 16.6 | 44 25 22.1 | 26 08 17.1 | Str. Dristor 96, bl. 17 | As. De locatari/Adm. Lupu, et. 6; tel. 6476548 | 2202 | M/E | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | B | 32 |  | ROOM | DUAL | OK | DUAL | OK | OK | YesV | OK | MUGUREL | 2000-01-04 | 1999-12-08 |  |  |  | 1999-09-24 | OK |  | OK | 1999-11-25 |  |  |  | 99:0005 | ETR | N/A | 1999-11-29 | OK | OK | OK | 1999-12-18 |  | Yes | Cristian Croitor | 2000-02-20 | 2000-04-07 | 2000-04-07 | 2000-04-10 | OK | K 739 494 | 0 | 0 | 0 | K 739 494 | 120 | 0 | 0 | K 739 494 | 240 | 0 | 0 |  |  |  |  | N/A | 28 | 28 | 7/8" | 12 | 12 | 7/8" | 50 | 50 | 7/8" |  |  |  | 180 | ML 38 E 1+0 | Dr. Taberei | MW | 33.6 | 0.3 |  |  | 38/14 |  | 4x2/8 | 2U-3 |  |  |  | Indoor Comteck | [10 empty] | BU062 | BASARABIA | 213.6 | 0.3 |  |  | 38/18 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-05-10 |  |  | 2000-05-10 | 30N03 Titan-Dr.taberei |  | OK | DAN | DAN | [32 empty] | 74 | Bucuresti | Sector 3 | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BU064 | CAMIL RESSU | Bucharest | BU018 Titan_CTA | Muntenia | 44 25 03.8 | 26 09 03.7 | 44 25 00.2 | 26 09 02.0 | Bdul. Camil Ressu, NR. 33, bl. N4, scara 3 | ASOCIATIA DE LOCATARI, BL. N4, SECT. 3/PRES. ALEXIE FLORIN; VICEPRES. PAUN ADRIAN | 2202 | M/E | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | N/A |  |  |  | 34 | B | 34 | TRIPODS | ROOM | TEHNOROB | OK | TEHNOROB | OK | 1999-12-15 | YesV | OK | MARIUS | 1999-12-15 | OK |  |  |  | 1999-09-24 | 1999-11-15 |  | 1999-11-15 | OK |  |  |  | 99:0007 | ETR | N/A | OK | OK | 1999-12-17 | 1999-12-20 | 1999-12-28 |  | Yes | Cristian Croitor | 2000-03-03 | 2000-04-07 | 2000-04-07 | 2000-04-10 | OK | K 739 494 | 0 | 4 | 37 | K 739 494 | 120 | 0 | 37 | K 739 494 | 240 | 0 | 37 |  |  |  |  | N/A | 45 | 45 | 7/8" | 45 | 45 | 7/8" | 45 | 45 | 7/8" |  |  |  | 270 |  | Dr. Taberei | MW | 52.9 | 0.3 |  |  | 38/14 |  | 4x2/8 | 2U-3 |  |  |  | Indoor Comteck | [10 empty] | BU066 | REBREANU | 232.9 | 0.3 |  |  | 38/18 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-02-15 |  |  | 2000-07-05 | 30N01 Titan-Dr.taberei |  | OK | COSMIN | COSMIN | [32 empty] | 70 | Bucuresti | Sector 3 | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BU065 | MACARALEI | Bucharest | BU018 Titan_CTA | Muntenia | 44 24 40.2 | 26 10 09.2 | 44 24 47.0 | 26 09 57.0 | Bd. Theodor Pallady nr.11-13, Bl. R5, sect. 3 |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | 2000-06-27 |  |  |  | 30 | B |  |  | OUTDOOR | TEHNOROB | OK | TEHNOROB | OK | OK | YesV | OK | MARIUS | OK | OK |  |  |  | OK | OK |  | OK | 2000-02-28 |  |  |  | 00:0009 | YRO | YRO | OK | OK | OK | OK | 2000-03-13 |  | Yes | Cristian Croitor | 2000-03-14 | 2000-05-08 | 2000-05-08 | 2000-05-09 | OK | K 739 494 | 0 | 4 | 0 | K 739 494 | 120 | 0 | 0 | K 739 494 | 240 | 0 | 0 |  |  |  |  | N/A | 25 | 25 | 7/8" | 25 | 25 | 7/8" | 25 | 25 | 7/8" |  |  |  | 150 | ML 38 E 1+0 | Dr. Taberei | MW | 338.9 | 0.3 |  |  | 38/14 |  | 4X2/8 | 2U-3 |  |  |  | RBS | [9 empty] | 1 | BU066 | REBREANU | 158.9 | 0.3 |  |  | 38/18 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-06-28 |  |  | 2000-11-21 | 30N01 Titan-Dr.taberei |  | OK | PETRICA | PETRICA | [32 empty] | 64 | Bucuresti | Sector 3 | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BU066 | REBREANU | Bucharest | BU018 Titan_CTA | Muntenia | 44 25 29.9 | 26 09 56.7 | 44 25 25.9 | 26 09 44.6 | Str. Padurea Craiului, nr. 1, bl. B2, sect. 3 | Dl. Staniloiu, Tel. 01/3400169/ | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | 2000-06-27 |  |  |  |  | B |  |  | OUTDOOR | TEHNOROB | OK | TEHNOROB | OK | 2000-01-28 | YesV | OK | MARIUS | 2000-01-28 | 1999-12-06 |  |  |  | 1999-09-30 | 1999-11-15 |  | 1999-11-15 | OK |  |  |  | N/A | YRO | YRO | 2000-01-11 | OK | 2000-01-14 | 2000-01-28 | 2000-01-30 |  | Yes | Cristian Croitor | 2000-02-05 | 2000-02-28 | 2000-03-07 | 2000-03-14 | OK | K 739 494 | 0 | 0 | 0 | K 739 494 | 120 | 0 | 0 | K 739 494 | 240 | 0 | 0 |  |  |  |  | N/A | 15 | 15 | 7/8" | 15 | 15 | 7/8" | 15 | 15 | 7/8" |  |  |  | 90 | N/A | Dr. Taberei | CABLU | CABLU | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | RBS | 10066 | Phase_1 | [7 empty] | 1 | BU018 | TITAN_2 | CABLU | N/A |  |  | N/A | [6 empty] | OK | OK | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 30N02 Titan-Dr.taberei |  | OK | COSMIN | COSMIN | [32 empty] | 71 | Bucuresti | Sector 3 | [7 empty] | missing |  |  | missing
Phase_1 | CS | BU067 | DIHAM | Bucharest | BU018 Titan_CTA | Muntenia | 44 26 06.4 | 26 09 43.4 | 44 26 11.0 | 26 09 36.0 | Bd. Basarabia nr. 57, bl. M27, sc. B | As. De locatari/Niculae Nicolae, ap. 10, bl. M27A; tel. 3400013 | 2202 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | B | 35 | TRIPODS | ROOM | TEHNOROB | OK | TEHNOROB | OK | 2000-01-28 | YesV | OK | MARIUS | 2000-01-28 | 1999-12-27 |  |  |  | 1999-11-04 | 1999-12-10 |  | 1999-12-10 | OK |  |  |  | N/A | YRO | ISAF | 2000-01-31 | OK | OK | 2000-02-10 | 2000-02-11 |  | Yes | Alexandru Bucur | 2000-02-23 | 2000-03-10 | 2000-03-10 | 2000-03-14 | OK | K 739 494 | 0 | 0 | 37 | K 739 494 | 120 | 0 | 34 | K 739 494 | 240 | 0 | 34 |  |  |  |  | N/A | 25 | 25 | 7/8" | 38 | 38 | 7/8" | 38 | 38 | 7/8" |  |  |  | 202 |  | Dr. Taberei | MW | 172.2 | 0.3 |  |  | 38/14 |  | 4x2/8 | 4U-1 |  |  |  | Indoor Comteck | [10 empty] | BU066 | REBREANU | 172.2 | 0.3 |  |  | 38/18 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-05-29 |  |  | 2000-05-31 | Se muta pe new06 de pe 30N02 Titan-Dr.taberei | Optimizare fluxuri cand se va integra BU149 | 2001-08-06 | THEO | THEO | [32 empty] | 75 | Bucuresti | Sector 3 | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BU068 | BRANDUSELOR | Bucharest | BU026 Piata Sudului | Muntenia | 44 24 51.8 | 26 07 28.2 | 44 24 55.0 | 26 07 30.0 | Str. Branduselor nr. 11, bl. H1, sc.3, sect. 3 | As. De locatari/Gheorghe Dulgheru, 323.59.13, ap. 33 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | 2000-06-27 |  |  |  | N/A | B | 25 | T4m+T4m | OUTDOOR | TEHNOROB | OK | TEHNOROB | OK | 2000-01-28 | YesV | OK | MARIUS | 2000-01-28 | 1999-12-27 |  |  |  | OK | OK |  | OK | OK |  |  |  | N/A | YRO | ISAF | 2000-01-31 | OK | OK | 2000-02-10 | 2000-02-11 |  | Yes | Alexandru Bucur | 2000-02-16 | 2000-03-21 | 2000-03-21 | 2000-03-22 | OK | K 739 494 | 0 | 0 | 27.5 | K 739 494 | 120 | 0 | 27.5 | K 739 494 | 240 | 0 | 27.5 |  |  |  |  | N/A | 15 | 15 | 7/8" | 15 | 15 | 7/8" | 15 | 15 | 7/8" |  |  |  | 90 | ML 38 E 1+0 | Dr. Taberei | MW | 190.5 | 0.3 | 27 | 20 | 38/14 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [10 empty] | BU070 | VACARESTI | 10.5 | 0.3 | 35 |  | 38/18 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-05-08 |  |  | 2000-08-09 | 30N05 Piata Sudului-Dr.Taberei |  | OK | THEO | THEO | [32 empty] | 70 | Bucuresti | Sector 3 | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BU069 | TINERETULUI | Bucharest | BU026 Piata Sudului | Muntenia | 44 24 45.6 | 26 06 33.4 | 44 24 35.4 | 26 06 51.5 | Tneretului 37, bl. 50, sc. B | Asoc. De locatari, bl. 50, tel.6756114/cheile la PETCU ap. 89 | 2202 | M/E | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | B | 34 | TRIPODS | ROOM | DIEKAT | OK | DIEKAT | OK | 1999-12-15 | YesV | OK | AUREL | 1999-12-15 | 1999-12-02 |  |  |  | 1999-09-29 | OK |  | OK | 1999-11-22 |  |  |  | N/A | YRO | YRO | OK | OK | 1999-12-17 | 1999-12-20 | 1999-12-24 |  | Yes | Alexandru Bucur | 2000-02-12 | 2000-03-22 | 2-Mai-00 | 2000-05-17 | OK | K 739 494 | 0 | 4 | 34 | K 739 494 | 120 | 0 | 34 | K 739 494 | 240 | 0 | 34 |  |  |  |  | N/A | 20 | 20 | 7/8" | 15 | 15 | 7/8" | 28 | 28 | 7/8" |  |  |  | 126 | ML 38 E 1+0 | Dr. Taberei | MW | 234.5 | 0.3 | 32.5 | 20 | 38/18 |  | 4x2/8 | 2U-3 |  |  |  | Indoor Comteck | [9 empty] | 1 | BU071 | SERBAN VODA | 54.5 | 0.3 | 27.5 | 30 | 38/14 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-05-08 |  |  | 2000-08-22 | 30N04 Piata Sudului-Dr.Taberei |  | OK | COSMIN | COSMIN | [32 empty] | 67 | Bucuresti | Sector 4 | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BU070 | VACARESTI | Bucharest | BU026 Piata Sudului | Muntenia | 44 24 09.4 | 26-07-18.0 | 44 24 10.7 | 26 07 18.6 | Calea Vacaresti, 330, bl. 10A, sc. A, sect. 4 | AS. LOCAT. BL. 10A; Vlad Vasile, 3304949/ADMINISTR. GRIGORE CEZAR, 3307833 | 2202 | M/E | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | B | 35 | TRIPODS | ROOM | DIEKAT | OK | DIEKAT | OK | 1999-12-15 | YesV | OK | AUREL | 1999-12-15 | 1999-12-02 |  |  |  | 1999-09-29 | 1999-10-25 |  | 1999-10-25 | 1999-11-22 |  |  |  | N/A | YRO | YRO | OK | OK | 1999-12-17 | 1999-12-20 | 1999-12-24 |  | Yes | Alexandru Bucur | 2000-02-15 | 2000-03-30 | 2000-03-30 | 2000-03-31 | OK | K 739 494 | 0 | 0 | 35.5 | K 739 494 | 120 | 0 | 35.5 | K 739 494 | 240 | 0 | 35.5 |  |  |  |  | N/A | 21 | 21 | 7/8" | 20 | 20 | 7/8" | 28 | 28 | 7/8" |  |  |  | 138 | ML 23 E 1+0 | Dr. Taberei | MW | 267.4 | 0.6 |  |  | 23/58 |  | 4X2/8 | 2U-3 |  |  |  | Indoor Comteck | [9 empty] | 1 | BU071 | SERBAN VODA | 87.4 | 0.6 |  |  | 23/56 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-05-08 |  |  | 2000-08-09 | 30N05 Piata Sudului-Dr.Taberei |  | OK | COSMIN | COSMIN | [32 empty] | 67 | Bucuresti | Sector 4 | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BU071 | SERBAN VODA | Bucharest | BU026 Piata Sudului | Muntenia | 44 24 08.1 | 26 05 58.1 | 44 24 08.1 | 26 05 58.1 | CALEA SERBAN VODA 288, BL. 2, SC. A, SECT.4 | Asoc. Locatarilor, bl. 2, Serban voda 288/Alexandru Moise, bl. 2, ap. 101, tel. 3353178 | 2202 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | B | 25 | PILONET | ROOM | DIEKAT | OK | DIEKAT | OK | 1999-12-15 | YesV | OK | AUREL | 1999-12-15 | 1999-12-02 |  |  |  | 1999-09-29 | 2001-07-11 |  | 1999-10-25 | 1999-11-17 |  |  |  | N/A | YRO | YRO | 2000-01-11 | OK | 2000-01-13 | 2000-01-13 | 2000-01-15 |  | Yes | Alexandru Bucur | 2000-02-12 | 2000-03-30 | 2000-03-30 | 2000-03-31 | OK | K 739 494 | 0 | 0 | 29 | K 739 494 | 120 | 0 | 29 | K 739 494 | 240 | 0 | 29 |  |  |  |  | N/A | 22 | 22 | 7/8" | 22 | 22 | 7/8" | 22 | 22 | 7/8" |  |  |  | 132 | ML 38 E 1+0 | Dr. Taberei | MW | 201.2 | 0.3 |  |  | 38/14 |  | 4x2/8 | 4U-1 |  |  |  | Indoor Comteck | [9 empty] | 1 | BU072 | PROGRESUL | 21.2 | 0.3 |  |  | 38/18 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-05-08 |  |  | 2000-10-03 | 30N04 Piata Sudului-Dr.Taberei |  | OK | COSMIN | COSMIN | [32 empty] | 82 | Bucuresti | Sector 4 | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BU072 | PROGRESUL | Bucharest | BU026 Piata Sudului | Muntenia | 44 23 32.5 | 26 05 38.8 | 44 23 32.5 | 26 05 38.8 | Sos. Giurgiului 113-115, bloc O | AS DE LOCATARI/Sos. Giurgiului 113-115, bl. O, ap. 39; 6290638; Ionescu Stefan | 2202 | M/E | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | B | 33 | TRIPODS 4/4/5 | ROOM | PROFIL | OK | PROFIL | OK | 1999-12-08 | YesV | OK | DORU | 1999-12-08 | OK |  |  |  | OK | 1999-11-10 |  | 1999-11-10 | 1999-11-24 |  |  |  | 99:0006 | ETR | N/A | OK | OK | 1999-12-10 | OK | 1999-12-10 |  | Yes | Theo Radoi | 2000-02-10 | 2000-04-04 | 2000-04-04 | 2000-04-04 | OK | K 739 494 | 0 | 0 | 35 | K 739 494 | 120 | 0 | 35 | K 739 494 | 240 | 0 | 36 |  |  |  |  | N/A | 29 | 29 | 7/8" | 31 | 31 | 7/8" | 41 | 41 | 7/8" |  |  |  | 202 | ML 38 E 1+1 | Dr. Taberei | MW | 91.6 | 0.3 |  |  | 38/18 |  | 4x2/8 | 4U-1 |  |  |  | Indoor Comteck | [9 empty] | 1 | BU026 | PIATA SUDULUI | 271.6 | 0.3 |  |  | 38/14 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-05-08 |  |  | 2000-10-24 | 30N01 Piata Sudului-Dr.Taberei |  | OK | THEO | THEO | [32 empty] | 83 | Bucuresti | Sector 5 | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BU073 | NASAUD | Bucharest | BU032 CNT_2 | Muntenia | 44 24 44.4 | 26 04 44.2 | 44 24 47.6 | 26 04 51.8 | Str. Nasaud nr. 64, bl. 32, sc. C | AS DE LOCATARI/Adm. Durca Vasile, 092209140 | 2202 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | B | 27 | tripods | ROOM | DIEKAT | OK | DIEKAT | OK | 2000-02-01 | YesV | OK | MARIUS | 2000-02-01 | OK |  |  |  | 1999-11-02 | OK |  | OK | 2000-01-04 |  |  |  | 00:0009 | ETR | Electotrade | 2000-01-31 | OK | OK | OK | 2000-02-05 |  | Yes | Theo Radoi | 2000-02-15 | 2000-05-02 | 2000-05-02 | 2000-03-29 | OK | K 739 494 | 0 | 4 | 30 | K 739 494 | 120 | 0 | 30 | K 739 494 | 240 | 0 | 30 |  |  |  |  | N/A | 20 | 20 | 7/8" | 20 | 20 | 7/8" | 20 | 20 | 7/8" |  |  |  | 120 | ML 38 E 1+0 | Dr. Taberei | MW | 299.2 | 0.3 |  |  | 38/18 |  | 4x2/8 | 2U-3 |  |  |  | Indoor Comteck | [9 empty] | 1 | BU078 | 13 SEPTEMBRIE | 119.2 | 0.3 |  |  | 38/14 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-10-04 |  |  | 2000-10-04 | 30N03 conectare locala |  | OK | THEO | THEO | [32 empty] | 84 | Bucuresti | Sector 5 | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BU074 | TUNSU PETRE | Bucharest | BU026 Piata Sudului | Muntenia | 44 23 24.0 | 26 04 49.9 | 44 23 20.2 | 26 04 46.2 | Str. Tunsu Petre nr. 4, bl. 14 | AS DE LOCATARI/Dir. Padureanu, 092549654 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | 2000-06-27 |  |  |  | N/A | B | 15 m | T4m+T4m+T4m+T4m | OUTDOOR | DIEKAT | OK | DIEKAT | OK | 2000-02-01 | YesV | OK | MARIUS | 2000-02-01 | OK |  |  |  | OK | OK |  | OK | 2000-01-04 |  |  |  | N/A | YRO | ISAF | 2000-02-02 | OK | OK | 2000-02-10 | 2000-02-11 |  | Yes | Alexandru Bucur | 2000-02-23 | 2000-03-27 | 2000-03-27 | 2000-03-29 | OK | K 739 494 | 0 | 0 | 20 | K 739 494 | 120 | 0 | 20 | K 739 494 | 240 | 0 | 20 |  |  |  |  | N/A | 40 | 40 | 7/8" | 25 | 25 | 7/8" | 25 | 25 | 7/8" |  |  |  | 180 | ML 38 E 1+0 | Dr. Taberei | MW | 47.1 | 0.3 | 47.1 | 25 | 38/18 |  | 4X2/8 | 2U-3 |  |  |  | RBS | [9 empty] | 1 | BU071 | SERBAN VODA | 227.1 | 0.3 | 0 | 30 | 38/14 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-05-08 |  |  | 2000-10-18 | 30N03 Piata Sudului-Dr.Taberei |  | OK | THEO | THEO | [32 empty] | 82 | Bucuresti | Sector 5 | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BU075 | CICEU | Bucharest | BU076 Popesti-Leordeni | Muntenia | 44 22 48.4 | 26 07 23.9 | 44 22 44.7 | 26 07 31.4 | Str. Turnu magurele nr. 15, bl. 17 | As. De locatari bl. 17/ | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | 2000-06-27 |  |  |  | 33 | B | 33 |  | OUTDOOR | PROFIL | OK | PROFIL | OK | OK | YesV | OK | DORU | 2000-02-02 | 1999-12-17 |  |  |  | 1999-11-24 | 1999-12-13 |  | 1999-12-13 | 1999-12-21 |  |  |  | N/A | YRO | IMSAT | OK | OK | OK | OK | 2000-02-11 |  | Yes | Alexandru Bucur | 2000-02-16 | 2000-03-21 | 2000-03-21 | 2000-03-22 | OK | K 739 494 | 0 | 0 | 38 | K 739 494 | 120 | 0 | 38 | K 739 494 | 240 | 0 | 38 |  |  |  |  | N/A | 28 | 28 | 7/8" | 40 | 40 | 7/8" | 32 | 32 | 7/8" |  |  |  | 200 |  | Dr. Taberei | MW | 88.3 | 0.6 |  |  | 23/58 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [10 empty] | BU076 | POPESTI LEORDENI | 268.3 | 0.6 | 35 |  | 23/56 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-05-24 |  |  | 2000-09-29 | 30N01 Popesti Leordeni-Dr.Taberei |  | OK | MIHAI T. | MIHAI T. | [32 empty] | 82 | Bucuresti | Sector 4 | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BU076 | POPESTI LEORDENI | Bucharest | BU076 Popesti-Leordeni | Muntenia | 44 22 52.1 | 26 10 25.8 | 44 22 46.8 | 26 10 11.0 | ROMTELECOM POPESTI-LEORDENI-DECT TOWER | RTC/ | 2202 | M/E | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | TE | 36 | PIPES | EXISTSHELT | DIEKAT | OK | DIEKAT | OK | 1999-11-19 | YesV | OK | AUREL | 1999-11-19 | OK |  |  |  | 1999-09-29 | OK |  | OK | 1999-11-09 |  |  |  | N/A | YRO | YRO | OK | OK | 1999-11-30 | 1999-11-30 | 1999-12-02 |  | Yes | Alexandru Bucur | 1999-12-14 | 2000-03-17 | 2000-03-17 | 2000-03-21 | OK | K 739 494 | 0 | 4 | 30 | K 739 494 | 120 | 0 | 30 | K 739 494 | 240 | 0 | 30 |  |  |  |  | N/A | 45 | 45 | 7/8" | 45 | 45 | 7/8" | 45 | 45 | 7/8" |  |  |  | 270 | N/A | Dr. Taberei | FO | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | 10076 | 2000-04-19 | [8 empty] | BSC11 | DRUMUL TABEREI | N/A | N/A |  |  | N/A | [6 empty] | OK | OK | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 30N01 Popesti Leordeni-Dr.Taberei |  | 2001-03-09 | COSMIN | COSMIN | [32 empty] | 72 | Popesti-Leordeni | Ilfov | [7 empty] | Site Near=Insertion Point
Phase_1 | CS | BU077 | RAHOVEI | Bucharest | BU032 CNT_2 | Muntenia | 44 24 23.6 | 26 03 53.9 | 44 24 23.6 | 26 03 53.9 | Calea Rahovei 327, bl. 11A, sc. 2 | As. De locatari bloc 11, sc. 2/Dl MUNTEANU ( tel . 016290461 ), Dl Enache ,Ap 56 (Cheie usa acces ) | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | 2000-06-27 |  |  |  | 31 | B | 33 | TRIPODS | OUTDOOR | ESROM | OK | ESROM | OK | 1999-12-16 | YesV | OK | DORU | 1999-12-16 | 1999-12-03 |  |  |  | 1999-11-04 | 1999-11-30 |  | 1999-11-30 | 1999-12-02 |  |  |  | 00:0008 | ETR | N/A | 2000-01-12 | OK | OK | OK | 2000-01-20 |  | Yes | Theo Radoi | 2000-02-03 | 2000-04-04 | 2000-04-04 | 2000-04-04 | OK | K 739 494 | 0 | 3 | 30 | K 739 494 | 120 | 0 | 30 | K 739 494 | 240 | 0 | 30 |  |  |  |  | N/A | 24 | 24 | 7/8" | 15 | 15 | 7/8" | 16 | 16 | 7/8" |  |  |  | 110 | ML 23 E 1+1* | Dr. Taberei | MW | 300.6 | 0.6 |  |  | 23/58 |  | 4x2/8 | 4U-1 |  |  |  | RBS | [9 empty] | 1 | BU080 | Ghencea | 120.3 | 0.6 |  |  | 23/56 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-10-03 |  |  | 2000-10-03 | 30N02 conectare locala |  | 2001-03-09 | THEO | THEO | [32 empty] | 87 | Bucuresti | Sector 5 | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BU078 | 13 SEPTEMBRIE | Bucharest | BU032 CNT_2 | Muntenia | 44 25 09.7 | 26-03-49.8 | 44 25 13.9 | 26 03 45.3 | Calea 13 Septembrie, 216, bl. V46 | As. Locatari bl. V54 (new building)/Dl. Cocos, ap. 8; 4111532 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | 2000-06-27 |  |  |  | 30 | B | 33 | TRIPODS | OUTDOOR | ESROM | OK | ESROM | OK | 1999-12-16 | YesV | OK | DORU | 1999-12-16 | 1999-12-16 |  |  |  | 1999-11-12 | 2001-07-11 |  | OK | 1999-12-09 |  |  |  | 00:0008 | ETR | N/A | 2000-01-12 | OK | OK | OK | 2000-01-20 |  | Yes | Theo Radoi | 2000-02-03 | 2000-04-04 | 2000-04-04 | 2000-04-04 | OK | K 739 494 | 0 | 4 | 35 | K 739 494 | 120 | 0 | 33 | K 739 494 | 240 | 0 | 33 |  |  |  |  | N/A | 12 | 12 | 7/8" | 14 | 14 | 7/8" | 25 | 25 | 7/8" |  |  |  | 102 | ML 23 E 1+1 | Dr. Taberei | MW | 273.3 | 0.6 |  |  | 23/56 |  | 4x2/8 |  |  |  |  | RBS | [9 empty] | 1 | BU032 | CNT2_MSC | 93.4 | 0.6 |  |  | 23/58 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-10-04 |  |  | 2000-10-04 | 30N03 conectare locala |  | 2001-03-09 | COSMIN | COSMIN | [32 empty] | 86 | Bucuresti | Sector 5 | [7 empty] | missing |  |  | 1
Phase_1 | CS | BU079 | ALEXANDRIEI | Bucharest | BU032 CNT_2 | Muntenia | 44 23 45.0 | 26 03 13.8 | 44 24 07.7 | 26 03 09.9 | Sos. Alexandriei, 112, bl. M1 | /administrator, 7762178 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | 2000-06-27 |  |  |  | 30 | B | 30 |  | OUTDOOR | ESROM | OK | ESROM | OK | 1999-12-16 | YesV | OK | DORU | 1999-12-16 | 1999-12-16 |  |  |  | 1999-11-16 | 1999-12-01 |  | 1999-12-01 | 1999-12-13 |  |  |  | 00:0008 | ETR | N/A | OK | OK | OK | OK | 2000-01-20 |  | Yes | Theo Radoi | 2000-02-03 | 2000-05-02 | 2000-05-02 | 2000-05-03 | OK | K 739 494 | 0 | 0 | 31 | K 739 494 | 120 | 0 | 31 | K 739 494 | 240 | 0 | 31 |  |  |  |  | N/A | 25 | 25 | 7/8" | 18 | 18 | 7/8" | 20 | 20 | 7/8" |  |  |  | 126 | ML 38 E 1+0 | Dr. Taberei | MW | 63.2 | 0.3 |  |  | 38/14 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [9 empty] | 1 | BU077 | RAHOVEI | 243.2 | 0.3 |  |  | 38/18 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-10-09 | RAU 38/14 RETURNAT???? |  | 2000-10-09 | 30N02 conectare locala |  | 2001-03-09 | COSMIN | COSMIN | [32 empty] | 84 | Bucuresti | Sector 5 | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BU080 | Ghencea | Bucharest | BU032 CNT_2 | Muntenia | 44 24 57.0 | 26 02 44.8 | 44 24 55.0 | 26 02 40.0 | BD. GHENCEA NR. 34, BL. C 65, SC. B | As. De locatari/???? Ask VECTOR - 092.514.891 | 2102 | M/E | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | 2000-06-27 |  |  |  | N/A | B |  |  | OUTDOOR | VECTOR | OK | VECTOR | OK | OK | YesV | OK | DORU | 1999-12-17 | 1999-11-29 |  |  |  | 1999-10-13 | 1999-11-11 |  | 1999-11-11 | OK |  |  |  | 99:0005 | ETR | N/A | 1999-11-30 | OK | 1999-11-30 | OK | 1999-12-18 |  | Yes | Theo Radoi | 2000-02-03 | 2000-04-05 | 2000-04-05 | 2000-04-06 | OK | K 739 494 | 0 | 80 | 0 | K 739 494 | 120 | 0 | 0 | K 739 494 | 240 | 0 | 0 |  |  |  |  | N/A | 14 | 14 | 7/8" | 16 | 16 | 7/8" | 24 | 24 | 7/8" |  |  |  | 108 | ML 38 E 1+1 | Dr. Taberei | MW | 305.7 | 0.3 |  |  | 38/14 |  | 4x2/8 | 4U-1 |  |  |  | RBS | [9 empty] | 1 | BU032 | CNT2_MSC | 12.7 | 0.3 |  |  | 38/18 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-10-04 |  |  | 2000-10-04 | 30N01 conectare locala |  | 2001-03-09 | THEO | THEO | [32 empty] | 88 | Bucuresti | Sector 6 | [7 empty] | missing |  |  | 1
Phase_1 | CS | BU081 | COTROCENI | Bucharest | BU032 CNT_2 | Muntenia | 44 25 42.2 | 26 03 41.8 | 44 26 20.59 | 26 04 07.72 | Sos Cotroceni nr. 5-7, Sector 6, BUCURESTI. | As. Locatari/administrotor TONI | 2202 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | 2000-06-27 |  |  |  | 35.4 | B | 15 | TRIPODS | OUTDOOR | SERACOM | OK | SERACOM | OK | OK | YesV | OK | DRAGOS | OK | OK |  |  |  | OK | OK |  | OK | 2000-04-26 |  |  |  | 00:0009 | YRO | YRO | 2000-04-26 | OK | OK | OK | OK |  | Yes | Theo Radoi | 2000-05-17 | 2000-05-23 | 2000-05-23 | 2000-05-25 | OK | K 739 494 | 0 | 0 | 38 | K 739 494 | 120 | 0 | 38 | K 739 494 | 240 | 0 | 37 |  |  |  |  | N/A | 7 | 7 | 7/8" | 7 | 7 | 7/8" | 24 | 24 | 7/8" |  |  |  | 76 | ML 38 E 1+0 | Dr. Taberei | MW | 174.9 | 0.3 |  |  | 38/14 |  | 4X2/8 | N/A |  |  |  | TMR 9202 | [9 empty] | 1 | BU078 | 13 SEPTEMBRIE | 354.9 | 0.3 |  |  | 38/18 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-07-17 |  |  | 2000-08-22 | 30N04 conectare locala |  | 2001-03-09 | COSMIN | COSMIN | CSFT1802-DONOR | BU805 | K 739 134 | 0 | 0 | 38 | 15 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COUPLER | [11 empty] | 83 | Bucuresti | Sector 6 | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BU082 | Bdul. Timisoara | Bucharest | BU032 CNT_2 | Muntenia | 44 25 37.6 | 26 02 37.5 | 44 25 40 | 26 02 37 | Bd. Timisoarei, nr. 29, bl. F |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | 2000-06-27 |  |  |  |  | B |  |  | OUTDOOR | VECTOR | OK | VECTOR | OK | OK | YesV | OK | DORU | 1999-12-17 | 1999-12-02 |  |  |  | OK | 1999-11-11 |  | 1999-11-11 | OK |  |  |  | 00:0008 | ETR | N/A | 2000-01-12 | OK | OK | OK | 2000-01-20 |  | Yes | Theo Radoi | 2000-02-04 | 2000-04-06 | 2000-04-06 | 2000-04-07 | OK | K 739 494 | 0 | 0 | 0 | K 739 494 | 120 | 0 | 0 | K 739 494 | 240 | 0 | 0 |  |  |  |  | N/A | 25 | 25 | 7/8" | 25 | 25 | 7/8" | 25 | 25 | 7/8" |  |  |  | 150 | ML 38 E 1+0 | Dr. Taberei | MW | 238.5 | 0.3 |  |  | 38/14 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [9 empty] | 1 | BU032 | CNT2_MSC | 58.5 | 0.3 |  |  | 38/18 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-10-04 |  |  | 2000-10-04 | 30N05 conectare locala |  | 2001-03-09 | THEO | THEO | [32 empty] | 88 | Bucuresti | Sector 6 | [7 empty] | missing |  |  | 1
Phase_1 | CS | BU083 | DR. TABEREI | Bucharest | BU032 CNT_2 | Muntenia | 44 25 12.6 | 26 01 24.1 | 44 25 15.0 | 26 01 16.0 | Bd. Drumul Taberei, nr. 75, bl. TS39 | As. De locatari/Dl. Adamescu, tel. 7265231 | 2102 | M/E | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | 2000-06-27 |  |  |  | N/A | B |  |  | OUTDOOR | VECTOR | OK | VECTOR | OK | OK | YesV | OK | DORU | 1999-12-17 | 1999-11-29 |  |  |  | 1999-11-04 | 1999-11-11 |  | 1999-11-11 | OK |  |  |  | 99:0005 | ETR | N/A | 1999-11-30 | OK | 1999-11-30 | OK | 1999-12-17 |  | Yes | Theo Radoi | 2000-02-04 | 2000-04-06 | 2000-04-06 | 2000-04-07 | OK | K 739 494 | 0 | 0 | 0 | K 739 494 | 120 | 0 | 0 | K 739 494 | 240 | 0 | 0 |  |  |  |  | N/A | 15 | 15 | 7/8" | 32 | 32 | 7/8" | 15 | 15 | 7/8" |  |  |  | 124 | ML 38 E 1+0 | Dr. Taberei | MW | 82.5 | 0.3 |  |  | 38/14 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [9 empty] | 1 | BU032 | CNT2_MSC | 262.5 | 0.3 |  |  | 38/18 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-10-09 |  |  | 2000-10-09 | 30N05 conectare locala |  | 2001-03-09 | THEO | THEO | [32 empty] | 90 | Bucuresti | Sector 6 | [7 empty] | missing |  |  | 1
Phase_1 | CS | BU084 | IULIU MANIU | Bucharest | BU004 Pajura | Muntenia | 44 26 06.3 | 26 01 50.0 | 44 26 05 | 26 01 50 | Bdul. Iuliu Maniu, nr. 74-76, bl. B5 |  | 2202 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | B |  |  | ROOM | VECTOR | OK | VECTOR | OK | OK | YesV | OK | DORU | 1999-12-17 | 1999-12-02 |  |  |  | OK | 1999-11-11 |  | 1999-11-11 | OK |  |  |  | N/A | YRO | YRO | 2000-01-18 | OK | 2000-01-21 | 2000-01-25 | 2000-01-28 |  | Yes | Alexandru Bucur | 2000-02-29 | 2000-03-28 | 2000-03-28 | 2000-03-29 | OK | K 739 494 | 0 | 0 | 0 | K 739 494 | 120 | 0 | 0 | K 739 494 | 240 | 0 | 0 |  |  |  |  | N/A | 18 | 18 | 7/8" | 60 | 60 | 7/8" | 40 | 40 | 7/8" |  |  |  | 236 | ML 23 E 1+0 | Dr. Taberei | MW | 34.1 | 0.6 |  |  | 23/56 |  | 4X2/8 | 2u-3 |  |  |  | Indoor Comteck | [9 empty] | 1 | BU087 | GIULESTI-1 | 214.1 | 0.6 |  |  | 23/58 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-10-11 |  |  | 2000-12-18 | 30N07 Pajura-Dr.Taberei |  | OK | DAN | DAN | [32 empty] | 91 | Bucuresti | Sector 6 | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BU085 | BANUL_MANTA | Bucharest | BU009 Baneasa_RTC | Muntenia | 44 27 16.9 | 26 04 43.6 | 44 27 25.0 | 26 04 7.7 | B-dul Banul Manta nr 39, Bloc 30, sector 1, Bucuresti. |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | 2000-06-27 |  |  |  | 30 | B | 33 | T4m+T4m+T4m | ROOM | IMSAT | OK | IMSAT | OK | OK | YesV | OK | AUREL | OK | OK |  |  |  | 2000-03-29 | OK |  | OK | 2000-04-26 |  |  |  | N/A | YRO | YRO | ROBERT | OK | OK | OK | 2000-05-18 |  | Yes | Theo Radoi | 2000-05-19 | 2000-05-24 | 2000-05-24 | 2000-05-25 | OK | K 739 494 | 0 | 0 | 35.10 | K 739 494 | 120 | 0 | 34.9 | K 739 494 | 240 | 0 | 34.9 |  |  |  |  | N/A | 12 | 12 | 7/8" | 12 | 12 | 7/8" | 16 | 16 | 7/8" |  |  |  | 80 | ML 38 E 1+0 | Baneasa | MW | 45 | 0.3 |  |  | 38/18 |  | 4x2/8 | 2U-3 |  |  |  | Indoor Comteck | [9 empty] | 1 | BU044 | IPA | 245.7 | 0.3 |  |  | 38/14 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-07-17 |  |  | 2000-08-22 | 30N05 Baneasa-Dr.Taberei |  | 2001-03-09 | [34 empty] | 81 | Bucuresti | Sector 1 | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BU086 | PRIORIPOST | Bucharest | BU004 Pajura | Muntenia | 44 26 58.1 | 26 03 48.1 | 44 27 01.8 | 26 03 45.0 | PrioriPost, Calea Giulesti 6-8, Sector 6 Bucuresti | Directia de Posta prioripost/Stanciu Nicolae, 4001388/int. 197; 197 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | 2000-06-27 |  |  |  | 15 | B | 15 | C4m+T4m+C4m | OUTDOOR | IMSAT | OK | IMSAT | OK | OK | YesV | OK | AUREL | 2000-02-18 | OK |  |  |  | 1999-12-21 | 2000-02-07 |  | 2000-02-07 | OK |  |  |  | N/A | YRO | IMSAT | 2000-02-11 | OK | 2000-02-14 | 2000-02-14 | 2000-02-16 |  | Yes | Alexandru Bucur | 2000-02-29 | 2000-03-27 | 2000-03-27 | 2000-03-29 | OK | K 739 494 | 0 | 0 | 25 | K 739 494 | 120 | 0 | 25 | K 739 494 | 240 | 0 | 25 |  |  |  |  | N/A | 30 | 30 | 7/8" | 20 | 20 | 7/8" | 25 | 25 | 7/8" |  |  |  | 150 | ML 38 E 1+0 | Dr. Taberei | MW | 314.9 | 0.3 | 32.5 | 25 | 38/13 |  | 4x2/8 | N/A |  |  |  | RBS | [9 empty] | 1 | BU087 | GIULESTI-1 | 134.9 | 0.3 | 25 | 30 | 38/17 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-10-11 |  |  | 2000-12-18 | 30N06 Pajura-Dr.Taberei |  | OK | MIHAI C. | MIHAI C. | [32 empty] | 80 | Bucuresti | Sector 6 | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BU087 | GIULESTI-1 | Bucharest | BU004 Pajura | Muntenia | 44 27 29.0 | 26 03 08.3 | 44 27 29.1 | 26 03 48.0 | Calea Giulesti nr. 28, bl. Z1 | /Voicu, et. 6, ap. 41, 2215593 | 2202 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | B |  |  | ROOM | RADCOM | OK | RADCOM | OK | 2000-02-05 | YesV | OK | MUGUREL | 2000-02-18 | 2000-02-05 |  |  | 2001-06-28 | 1999-11-29 | 1999-12-21 |  | 1999-12-21 | 2000-01-24 |  |  |  | N/A | YRO | SVF | 2000-02-11 | OK | 2000-02-14 | 2000-02-14 | 2000-02-19 |  | Yes | Alexandru Bucur | 2000-02-29 | 2000-03-24 | 2000-03-24 | 2000-03-24 | OK | K 739 494 | 0 | 0 | 0 | K 739 494 | 120 | 0 | 0 | K 739 494 | 240 | 0 | 0 |  |  |  |  | N/A | 24 | 24 | 7/8" | 22 | 22 | 7/8" | 18 | 18 | 7/8" |  |  |  | 128 | ML 23 E 1+1* | Dr. Taberei | MW | 344.8 | 0.6 |  |  | 23/58 | [6 empty] | Indoor Comteck | [9 empty] | 1 | BU004 | PAJURA | 164.8 | 0.6 |  |  | 23/56 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-06-06 | PENDING |  |  | 30N07 Pajura-Dr.Taberei |  | OK | COSMIN | COSMIN | [32 empty] | 80 | Bucuresti | Sector 6 | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BU088 | DHL | Bucharest | BU004 Pajura | Muntenia | 44 27 50.0 | 26 05 04.8 | 44 27 57.5 | 26 05 01.1 | Str. Emanuel Porumbaru 85-87 | Private; Ion Tiriac/Dir. Catalin Tiseac, 222.17.71; fax. 222.14.69 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | 2000-06-27 |  |  |  | N/A | B | 28 | T6m+T6m | OUTDOOR | IMSAT | OK | IMSAT | OK | 2000-02-14 | YesV | OK | AUREL | 2000-02-14 | 2000-01-21 |  |  |  | 1999-12-22 | 1999-01-05 |  | 1999-01-05 | OK |  |  |  | N/A | YRO | IMSAT | OK | OK | 2000-02-08 | OK | 2000-02-12 |  | Yes | Alexandru Bucur | 2000-02-25 | 2000-03-22 | 2000-03-22 | 2000-03-23 | OK | K 739 494 | 0 | 0 | 24 | K 739 494 | 120 | 0 | 24 | K 739 494 | 240 | 0 | 24 |  |  |  |  | N/A | 28 | 28 | 7/8" | 12 | 12 | 7/8" | 12 | 12 | 7/8" |  |  |  | 104 | ML 38 E 1+0 | Dr. Taberei | MW | 74.5 | 0.3 | 20 |  | 38/17 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [9 empty] | 1 | BU043 | ION MIHALACHE | 254.5 | 0.3 | 20 |  | 38/13 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-10-03 |  |  | 2000-10-03 | 30N03 Pajura-Dr.Taberei |  | OK | DAN | DAN | [32 empty] | 80 | Bucuresti | Sector 1 | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BU089 | BD. BRATIANU | Bucharest | BU004 Pajura | Muntenia | 44 28 13.3 | 26 03 23.2 | 44 28 11.9 | 26 03 23.0 | Ion Mihalache Nr 325 Bl 19 | Private/Bd. Bratianu no 325 bl. 19 | 2202 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | B | 31 | T4m+T4m | ROOM | ISAF | OK | ISAF | OK | 2000-01-21 | YesV | OK | AUREL | 2000-02-17 | 2000-01-21 |  |  | 2001-06-28 | OK | OK |  | OK | 1999-11-12 |  |  |  | N/A | YRO | ISAF | 2000-02-04 | OK | 2000-02-07 | OK | 2000-02-09 |  | Yes | Alexandru Bucur | 2000-02-25 | 2000-03-23 | 2000-03-23 | 2000-03-24 | OK | K 739 494 | 0 | 0 | 32 | K 739 494 | 120 | 0 | 32 | K 739 494 | 240 | 0 | 32 |  |  |  |  | N/A | 35 | 35 | 7/8" | 22 | 22 | 7/8" | 22 | 22 | 7/8" |  |  |  | 158 | ML 38 E 1+1* | Dr. Taberei | MW | 322.6 | 0.3 | 22 |  | 38/17 | [6 empty] | Indoor Comteck | [9 empty] | 1 | BU004 | PAJURA | 142.6 | 0.3 |  |  | 38/13 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-06-06 |  | 2001-03-02 |  | Mutat de pe 30N04 pe 30N01Pajura-Dr.Taberei |  | OK | DAN | DAN | [32 empty] | 80 | Bucuresti | Sector 1 | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BU092 | NEAMULUI | Bucharest | BU004 Pajura | Muntenia | 44 29 07.6 | 26 01 30.0 | 44 29 00.3 | 26 01 26.3 | Strada Neamului no 50 (Chitila) | Private/Strada Neamului no 50 (Chitila) | 2202 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | TN | 30 | Tower 30m | SHELTER | ISAF | OK | ISAF | OK | 1999-12-23 | YesV | OK | AUREL | 2000-02-18 | 1999-12-28 |  |  |  | OK | 1999-11-15 |  | 1999-11-15 | OK |  |  |  | N/A | YRO | IMSAT | 2000-02-04 | OK | 2000-02-08 | OK | 2000-02-11 |  | Yes | Alexandru Bucur | 2000-02-25 | 2000-03-21 | 2000-03-21 | 2000-03-22 | OK | K 739 494 | 0 | 2 | 30 | K 739 494 | 120 | 2 | 30 | K 739 494 | 240 | 2 | 30 |  |  |  |  | N/A | 45 | 45 | 7/8" | 45 | 45 | 7/8" | 45 | 45 | 7/8" |  |  |  | 270 | ML 23 E 1+0 | Dr. Taberei | MW | 32 | 0.6 | 28 | 40 | 23/56 |  | 4x2/8 | 2u-3 |  |  |  | Indoor Comteck | [9 empty] | 1 | BU093 | EPISCOP VULCAN | 211.9 | 0.6 | 0 | 15 | 23/58 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-10-11 |  |  | 2000-12-18 | 30N05 Pajura-Dr.Taberei |  | OK | DAN | DAN | [32 empty] | 85 | Chitila | Ilfov | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BU093 | EPISCOP VULCAN | Bucharest | BU004 Pajura | Muntenia | 44 29 39.2 | 26 02 25.8 | 44 29 55.4 | 26 02 14.3 | Strada Episcop Vulcan no.26, Sc2, apt 1-65 | Private/Ratoi Marinel, Strada Episcop Vulcan no 26 blE apt7, 01/6689215 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | 2000-06-27 |  |  |  | 30 | B | 30 | T3m+T3m+T3m | OUTDOOR | ISAF | OK | ISAF | OK | 1999-12-23 | YesV | OK | AUREL | 2000-02-17 | 1999-12-23 |  |  |  | 1999-11-12 | OK |  | OK | OK |  |  |  | N/A | YRO | ISAF | 2000-02-04 | OK | 2000-02-07 | OK | 2000-02-09 |  | Yes | Alexandru Bucur | 2000-02-23 | 2000-03-24 | 2000-03-24 | 2000-03-29 | OK | K 739 494 | 0 | 2 | 33 | K 739 494 | 120 | 2 | 33 | K 739 494 | 240 | 2 | 33 |  |  |  |  | N/A | 25 | 25 | 7/8" | 35 | 35 | 7/8" | 10 | 10 | 7/8" |  |  |  | 140 | ML 38 E 1+0 | Dr. Taberei | MW | 166.1 | 0.3 |  |  | 38/17 | [6 empty] | RBS | [9 empty] | 1 | BU004 | PAJURA | 346.1 | 0.3 | 20 |  | 38/13 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-06-06 | PENDING |  |  | 30N02 Pajura-Dr.Taberei |  | OK | DAN | DAN | [32 empty] | 91 | Bucuresti | Sector 1 | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BU094 | COLENTINA_2 | Bucharest | BU009 Baneasa_RTC | Muntenia | 44 28 05.2 | 26 08 39.4 | 44 28 08.6 | 26 08 40.6 | Sos. Colentina nr. 76, bl. 111 | As. De locatari/Sos. Colentina 76, bl. 111, sc. C; Ion Ion, 6555517 | 2202 | M/E | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | B | 40 |  | ROOM | EL-MONT | OK | EL-MONT | OK | 1999-12-14 | YesV | OK | DRAGOS | 1999-12-14 | 1999-12-03 |  |  |  | OK | 1999-11-10 |  | 1999-11-10 | 1999-11-15 |  |  |  | N/A | YRO | YRO | 1999-12-15 | OK | 1999-12-16 | 1999-12-20 | 1999-12-24 |  | Yes | Alexandru Bucur | 2000-02-23 | 2000-03-10 | 2000-03-10 | 2000-03-14 | OK | K 739 494 | 0 | 0 | 42 | K 739 494 | 120 | 4 | 42 | K 739 494 | 240 | 0 | 42 |  |  |  |  | N/A | 20 | 20 | 7/8" | 38 | 38 | 7/8" | 28 | 28 | 7/8" |  |  |  | 172 | ML 38 E 1+0 | Baneasa | MW | 302.9 | 0.3 |  |  | 38/14 |  | 4x2/8 | N/A |  |  |  | Indoor Comteck | [10 empty] | BU099 | INTRAROM | 122.9 | 0.3 |  |  | 38/18 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-05-08 |  |  | 2000-07-05 | 30N04 Baneasa-Dr.Taberei |  | OK | MIHAI C. | MIHAI C. | [32 empty] | 75 | Bucuresti | Sector 2 | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BU095 | COLENTINA_3 | Bucharest | BU009 Baneasa_RTC | Muntenia | 44 28 31.6 | 26 09 38.0 | 44 28 36.0 | 26 09 33.0 | str. Colentina 276, UNISEM | UNISEM/2404125 | 2202 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | TN | 30 | Tower 30m | SHELTER | EL-MONT | OK | EL-MONT | OK | 1999-12-16 | YesV | OK | DRAGOS | 1999-12-16 | 1999-12-13 |  |  |  | OK | 1999-11-19 |  | 1999-11-19 | 1999-12-09 |  |  |  | N/A | YRO | YRO | 2000-01-11 | OK | 2000-01-13 | 2000-01-15 | 2000-01-22 |  | Yes | Alexandru Bucur | 2000-02-18 | 2000-03-07 | 2000-03-07 | 2000-03-14 | OK | K 739 494 | 0 | 0 | 28 | K 739 494 | 120 | 4 | 28 | K 739 494 | 240 | 0 | 28 |  |  |  |  | N/A | 35 | 35 | 7/8" | 35 | 35 | 7/8" | 35 | 35 | 7/8" |  |  |  | 210 | ML 38 E 1+1 | Baneasa | MW | 276.2 | 0.3 |  |  | 38/14 |  | 4x2/8 | 4u-1 |  |  |  | Indoor Comteck | [10 empty] | BU099 | INTRAROM | 96.2 | 0.3 |  |  | 38/18 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-05-08 |  |  | 2000-07-05 | 30N24 Baneasa-Dr.Taberei |  | 2001-05-31 | COSMIN | COSMIN | [32 empty] | 85 | Bucuresti | Sector 2 | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BU096 | LAMOTESTI | Bucharest | BU026 Piata Sudului | Muntenia | 44 22 58.4 | 26 06 39.2 | 44 22 53.1 | 26 06 35.2 | Str. Lamotesti nr. 1, bl. 13 | As. De locatari/Bumbescu Aurelian, 683.00.33 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | 2000-06-27 |  |  |  | 33 | B | 30 | tripode4/4/5 | OUTDOOR | PROFIL | OK | PROFIL | OK | 2000-01-07 | YesV | OK | DORU | 2000-01-07 | 1999-12-16 |  |  |  | 1999-11-18 | 1999-12-03 |  | 1999-12-03 | 1999-12-15 |  |  |  | N/A | YRO | ISAF | 2000-01-12 | OK | 2000-02-08 | 2000-02-10 | 2000-02-13 |  | Yes | Alexandru Bucur | 2000-02-16 | 2000-03-28 | 2000-03-28 | 2000-03-29 | OK | K 739 494 | 0 | 4 | 35 | K 739 494 | 120 | 0 | 39 | K 739 494 | 240 | 0 | 39 |  |  |  |  | N/A | 10 | 10 | 7/8" | 40 | 40 | 7/8" | 40 | 40 | 7/8" |  |  |  | 180 | ML 38 E 1+0 | Dr. Taberei | MW | 18.6 | 0.3 |  |  | 38/18 |  | 4x2/8 | 4U-1 |  |  |  | RBS | [10 empty] | BU026 | PIATA SUDULUI | 198.6 | 0.3 |  |  | 38/14 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-05-24 |  |  | 2000-05-31 | 30N02 Piata Sudului-Dr.Taberei |  | OK | THEO | THEO | [32 empty] | 79 | Bucuresti | Sector 4 | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BU097 | FERENTARI | Bucharest | BU026 Piata Sudului | Muntenia | 44 24 00.2 | 26 04 46.8 | 44 24 18 | 26 04 40 | Str. Valdamar Lascarescu bloc Z1, sc. 2 |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | 2000-06-27 |  |  |  | N/A | B | 15 | TOWER | OUTDOOR | SERACOM | OK | SERACOM | OK | 1999-12-21 | YesV | OK |  | 1999-12-21 | 1999-12-16 |  |  |  | OK | OK |  | OK | 1999-11-30 |  |  |  | N/A | YRO | YRO | OK | OK | 2000-01-10 | 2000-01-10 | 2000-01-13 |  | Yes | Alexandru Bucur | 2000-02-16 | 2000-03-23 | 2000-03-23 | 2000-03-24 | OK | K 739 494 | 0 | 0 | 20 | K 739 494 | 120 | 0 | 20 | K 739 494 | 240 | 0 | 20 |  |  |  |  | N/A | 25 | 25 | 7/8" | 25 | 25 | 7/8" | 25 | 25 | 7/8" |  |  |  | 150 | ML 38 E 1+0 | Dr. Taberei | MW | 126.6 | 0.3 |  |  | 38/14 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [9 empty] | 1 | BU072 | PROGRESUL | 306.6 | 0.3 |  |  | 38/18 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-05-08 |  |  | 2000-10-25 | 30N03 Piata Sudului-Dr.Taberei |  | OK | THEO | THEO | [32 empty] | 85 | Bucuresti | Sector 5 | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BU098 | LUICA | Bucharest | BU026 Piata Sudului | Muntenia | 44 22 50.9 | 26 05 43.9 | 44 22 46.0 | 26 05 39.0 | Str. Luica nr. 9, bl. 1, sc. 1 | AS DE LOCATARI, Str. Luica nr 9, bl. 1/ZGARANCEA MARIN, ap. 5; tel. 6859310 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | 2000-06-27 |  |  |  | N/A | B | 33 | TRIPODE 4/4/5 | OUTDOOR | PROFIL | OK | PROFIL | OK | 2000-01-07 | YesV | OK | DORU | 2000-01-07 | 1999-12-16 |  |  |  | 1999-11-04 | 1999-11-08 |  | 1999-11-08 | OK |  |  |  | N/A | YRO | IMSAT | 2000-01-24 | OK | 2000-02-08 | OK | 2000-02-11 |  | Yes | Alexandru Bucur | 2000-02-20 | 2000-03-28 | 2000-03-28 | 2000-03-29 | OK | K 739 494 | 0 | 0 | 37 | K 739 494 | 120 | 0 | 37 | K 739 494 | 240 | 0 | 37 |  |  |  |  | N/A | 28 | 28 | 7/8" | 40 | 40 | 7/8" | 32 | 32 | 7/8" |  |  |  | 200 | ML 38 E 1+0 | Dr. Taberei | MW | 80 | 0.3 |  |  | 38/14 |  | 4x2/8 |  |  |  |  | RBS | [10 empty] | BU096 | LAMOTESTI | 260 | 0.3 |  |  | 38/18 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-05-24 |  |  | 2000-05-31 | 30N02 Piata Sudului-Dr.Taberei |  | OK | THEO | THEO | [32 empty] | 80 | Bucuresti | Sector 4 | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BU099 | INTRAROM | Bucharest | BU009 Baneasa_RTC | Muntenia | 44 28 46.5 | 26 07 18.9 | 44 28 46.5 | 26 07 18.9 | Str. Fabrica de Glucoza, nr. | INTRAROM/ | 2202 | M/E | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | TN | 50 | New 50m tower | SHELTER | SVF | OK | SVF | OK | OK | YesV | OK | DRAGOS | OK | 1999-12-13 |  |  |  | OK | OK |  | OK | OK |  |  |  | N/A | YRO | YRO | OK | OK | 1999-12-20 | 2000-01-27 | 2000-01-31 |  | Yes | Alexandru Bucur | 2000-02-03 | 2000-03-13 | 2000-03-13 | 2000-03-14 | OK | K 739 494 | 0 | 0 | 0 | K 739 494 | 120 | 2 | 0 | K 739 494 | 240 | 2 | 0 |  |  |  |  | N/A | 60 | 60 | 1 1/4" | 60 | 60 | 1 1/4" | 60 | 60 | 1 1/4" |  |  |  | 360 | ML 23 E 1+1 | Baneasa | MW | 279.6 | 0.6 | 47.5 | 140 | 23/56 |  | 34+2 | 4U-1 | 2U-3 |  |  | Indoor Comteck | [9 empty] | 1 | BU009 | ROMTELECOM BANEASA | 279.6 | 0.6 | 27.5 | 74 | 23/58 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-05-24 |  |  | 2000-05-31 | 30N01 Baneasa-Dr.Taberei |  | OK | COSMIN | COSMIN | [32 empty] | 98 | Bucuresti | Sector 2 | [7 empty] | 1 |  |  | 1
Phase_2 | CS | BU100 | MAGURELE | Bucuresti(19) | BU032 CNT_2 | Muntenia | 44 21 02.00 | 26 01 52.01 | 44 21 00.2 | 26 01 51.2 | IFA Magurele, Strada Atomistilor nr. 111, Magurele, Ilfov | Institutul Fizica Atomica/Reta HARTOPANU, 01/7807040, int 3201 | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-06-13 | N/A | N/A |  |  |  | N/A | B | 45 | Pilon de 9m | Room | PROTELCO | OK | FIBEC | 2000-05-12 | 2000-05-31 | YesV | 2000-05-31 | Doru | 2000-06-02 | 2000-06-02 |  |  |  | 2000-03-23 | 2000-03-22 |  | 2000-04-26 | 2000-05-17 |  |  |  | NA | YRO | NA | 2000-06-02 | 2000-06-02 | 2000-06-13 | 2000-06-13 | 2000-06-16 |  | Yes | Alexandru Toma | 2000-07-15 | 2000-07-05 | 2000-07-05 | 2000-08-02 | 2000-08-09 | K 739 494 | 85 | 0 | 53 | K 739 494 | 215 | 0 | 53 | K 739 494 | 305 | 0 | 53 |  |  |  |  | N/A | 19 | 19 | 7/8" | 19 | 19 | 7/8" | 19 | 19 | 7/8" |  |  |  | 114 | ML 23 E 1+0 | Dr. Taberei | MW | 9 | 0.6 | 52 | 18.5 | 23/56 | [6 empty] | TMR 9202 | [10 empty] | BU080 | Ghencea |  | 0.6 |  |  | 23/58 | [6 empty] | N/A | YRO | N/A | 8 | 2000-06-16 | 2000-06-16 | 2000-06-22 | PITURCESCU | OK | 2000-07-05 |  | 2000-09-21 | 2000-09-25 | 30N09 conectare locala |  | OK | Liviu CHIRCA | Cosmorom | [32 empty] | 79 | Magurele | Ilfov | [5 empty] | 1 |  | 2 |  |  | 1
Phase_2 | CS | BU101 | JILAVA | Road Buc-Giurgiu(5) | BU026 Piata Sudului | Muntenia | 44 20 20 | 26 05 04 | 44 20 46.2 | 26 04 59.6 | Sos Giurgiului nr.33 Bl. A3, orasul Beius | Asociatie de proprietari/Opritescu Petre - Com. Jilava, Sos giurgiului nr. 33 Bl. A3, tel: 092/ 684 294 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-06-19 | 2000-06-15 | N/A |  |  |  | 16.8 | B | 14.8 | T6m+T6m | ROOM | PROTELCO | OK | FIBEC | 2000-05-12 | 2000-06-09 | YesV | 2000-06-09 | Doru | 2000-06-19 | 2000-12-08 |  |  |  | 2000-03-23 | 2000-03-22 |  | 2000-05-16 | 2000-05-17 |  |  |  | 2000-06-19 | YRO | MIC | 2000-06-02 | 2000-06-02 | 2000-06-20 | 2000-06-20 | 2000-06-23 |  | Yes | Alexandru Bucur | 2000-07-15 | 2000-07-18 | 2000-07-18 | 2000-08-02 | 2000-08-09 | K 739 494 | 0 | 0 | 19 | K 739 494 | 120 | 0 | 19 | K 739 494 | 240 | 0 | 19 |  |  |  |  | N/A | 14.5 | 14.5 | 7/8" | 15.5 | 15.5 | 7/8" | 15.5 | 15.5 | 7/8" |  |  |  | 91 | ML 23 E 1+0 | Dr. Taberei | MW | 13 | 0.6 | 18.5 | 14 | 23/58 | [6 empty] | RBS | [10 empty] | BU098 | LUICA |  | 0.6 |  |  | 23/56 | [6 empty] | N/A | YRO | N/A | N/A | 2000-06-20 | 2000-06-20 | 2000-06-23 | PITURCESCU | OK | 2000-07-18 |  | 2000-09-15 | 2000-09-25 | 30N06 Piata Sudului-Dr.Taberei |  | OK | Liviu CHIRCA | Cosmorom | [32 empty] | 73 | Jilava | Ilfov | [5 empty] | 1 |  | 2 |  |  | 1
Phase_2 | CS | BU102 | 1_DECEMBRIE | Road Buc-Giurgiu(5) | BU026 Piata Sudului | Muntenia | 44 17 23.01 | 26 03 46.43 | 44 17 30.9 | 26 03 43.4 | Strada Oituz nr. 2, Comuna 1 Decembrie, Ilfov | Privat/Iulian MITRAN, 092/296 292 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-06-13 | N/A | N/A |  |  |  | N/A | TN | 40 | New 40m tower | N/A | PROTELCO | OK | FIBEC | 2000-05-12 | 2000-06-05 | YesV | 2000-06-05 | Doru | 2000-06-19 | 2000-06-07 |  |  |  | 2000-03-23 | 2000-03-22 |  | 2000-04-26 | 2000-05-09 |  |  |  | NA | YRO | NA | 2000-06-07 | 2000-06-07 | 2000-06-08 | 2000-06-08 | 2000-06-12 |  | Yes | Alexandru Bucur | 2000-07-15 | 2000-07-18 | 2000-07-18 | 2000-08-02 | 2000-08-09 | K 739 494 | 16 | 0 | 38 | K 739 494 | 197 | #N/A | 38 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 55 | 55 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 110 | ML 23 E 1+0 | Dr. Taberei | MW | 16 | 0.6 | 37 | 55 | 23/56 |  |  | 2U-3 |  |  |  | RBS | [7 empty] | 3/2 pairs - outdoor |  |  | BU101 | JILAVA | 196 | 0.6 | 18.5 | 15 | 23/58 | [6 empty] | N/A | YRO | N/A | 2001-02-13 | 6/8/00-6/13/00 | 2000-06-13 | 2000-06-13 | PITURCESCU | OK | 2000-07-18 |  | 2000-09-15 | 2000-09-25 | 30N06 Piata Sudului-Dr.Taberei |  | OK | Liviu CHIRCA | #N/A | [32 empty] | 62 | 1 Decembrie | Ilfov | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BU103 | DEALUL MACINULUI | Bucuresti(19) | BU032 CNT_2 | Muntenia | 44 25 28.5 | 26 00 53.3 | 44 25 28.7 | 26 00 52.9 | Dealul Macinului nr.12 Bl.M43 Sc.A | Asociatie de locatari - Pres. Crasovski Niculina - 01/ 778 82 72/Cracovski Niculina - 01/ 778 82 | 2102 | M/E | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-09-06 | Yes | N/A |  |  |  | 32.5 | B | 36 | C2m+C2m | N/A | IMSAT | OK | DUAL | 2000-08-15 | 2000-09-04 | YesV | 2000-09-05 | Doru | 2000-09-07 | 2000-09-06 |  |  |  | 2000-07-03 | 2001-07-11 |  | 2000-07-25 | 2000-08-14 |  |  |  | 2000-09-07 | YRO | Electotrade | 2000-09-07 | 2000-09-07 | 2000-09-08 | 2000-09-09 | 2000-09-11 |  | Yes | Alexandru Bucur | 2000-09-26 | 2000-09-26 | 2000-09-26 | 2000-12-08 | 2001-01-08 | k 739 494 | 0 | 0 | 34 | k 739 494 | 120 | 0 | 33.9 | k 739 494 | 240 | 0 | 34 |  |  |  |  | N/A | 37 | 37 | 7/8" | 27 | 27 | 7/8" | 27 | 27 | 7/8" |  |  |  | 182 | ML 23/38 E 1+1 | Dr. Taberei | MW | 102 | 0.6 | 35.75 | 29 | 23/56 |  |  | 2U-3 |  |  |  | RBS | [9 empty] | 1 | BU032 | CNT2_MSC | 283 | 0.6 | 30 |  | 23/58 | [6 empty] | 3 | RADCOM | 2000-09-18 | 209 | 2000-09-08 | 2000-09-09 | 2000-09-11 | PITURCESCU | OK | 2000-09-26 |  | 2000-10-04 | 2001-01-10 | 30N07 conectare locala |  | OK | Vasile MANEA | Cosmorom | [32 empty] | 88 | Bucuresti | Bucuresti | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BU104 | IULIU MANIU_2 | Bucuresti(19) | BU032 CNT_2 | Muntenia | 44 26 03 | 26 00 31 | 44 26 03.5 | 26 00 31.4 | B-dul Iuliu Maniu nr.192 Bl.B | Asociatie de locatari - PRES. Elina Popescu, 01/ 769 12 20/Elina Popescu | 2102 | M/E | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-09-06 | Yes | N/A |  |  |  | 35.5 | B | 35.5 | T4m+T4m | N/A | IMSAT | OK | DUAL | 2000-08-15 | 2000-08-29 | YesV | 2000-09-05 | Doru | 2000-09-07 | 2000-09-06 |  |  |  | 2000-07-03 | 2000-06-10 |  | 2000-07-24 | 2000-08-14 |  |  |  | 2000-09-07 | YRO | Electotrade | 2000-09-07 | 2000-09-07 | 2000-09-08 | 2000-09-09 | 2000-09-11 |  | Yes | Alexandru Bucur | 2000-09-28 | 2000-09-27 | 2000-09-27 | 2000-10-04 | 2000-10-13 | K 739 494 | 0 | 0 | 37.5 | K 739 494 | 120 | 0 | 37.5 | K 739 494 | 240 | 0 | 37.5 |  |  |  |  | N/A | 16 | 16 | 7/8" | 15 | 15 | 7/8" | 15 | 15 | 7/8" |  |  |  | 72 | ML 23 E 1+0 | Dr. Taberei | MW | 155 | 0.6 | 39 | 17 | 23/58 |  |  | 4U-1 |  |  |  | RBS | [9 empty] | 1 | BU103 | DEALUL MACINULUI | 335 | 0.6 | 35.7 | 38 | 23/56 | [6 empty] | 1 | RADCOM | 2000-09-07 | 178 | 2000-09-08 | 2000-09-09 | 2000-09-11 | PITURCESCU | OK | 2000-09-27 |  | 2000-10-04 | 2000-12-06 | 30N08 conectare locala |  | OK | Vasile MANEA | Cosmorom | [32 empty] | 90 | Bucuresti | Bucuresti | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BU105 | CERNISOARA | Bucuresti(19) | BU032 CNT_2 | Muntenia | 44 47 22.7 | 24 09 54.7 | 44 26 21.7 | 26 01 22.6 | Str. Cernisoara nr.45 Bl.O13 Sc.A | Presedinte asociatie de locatari - Onciu Alina ,str. Cernisoara nr.45 Bl. O13 Sc.A Ap.28 Et.10, 01/ 760 60 10 | 2102 | M/E | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-09-06 | Yes | N/A |  |  |  | 32.5 | B | 32.5 | T4m+T4m | N/A | IMSAT | OK | PROFIL | 2000-08-15 | 2000-08-25 | YesV | 2000-09-05 | Doru | 2000-12-08 | 2000-09-06 |  |  |  | 2000-07-03 | 2000-07-10 |  | 2000-07-20 | 2000-08-14 |  |  |  | 2000-09-07 | YRO | Electotrade | 2000-09-07 | 2000-09-07 | 2000-09-08 | 2000-09-09 | 2000-09-11 |  | Yes | Bogdan Motoc | 2000-12-15 | 2000-12-28 | 2000-12-28 | 2001-02-08 | 2001-04-10 | K 739 494 | 0 | 0 | 35 | K 739 494 | 120 | 0 | 35 | K 739 494 | 240 | 0 | 36 |  |  |  |  | N/A | 35.5 | 35.5 | 7/8" | 16 | 16 | 7/8" | 18 | 18 | 7/8" |  |  |  | 139 | ML 23 E 1+0 | Dr. Taberei | MW | 243 | 0.6 | 38 | 20 | 23/56 |  |  | 2U-3 |  |  |  | RBS | [9 empty] | 1 | BU104 | IULIU MANIU_2 | 63 | 0.6 | 39 | 16 | 23/58 | [6 empty] | 1 | RADCOM | 2000-09-07 | 177 | 2000-09-08 | 2000-09-09 | 2000-09-11 | PITURCESCU | OK | 2000-12-28 |  | 2001-01-22 | 2001-01-22 | 30N08 conectare locala |  | OK | Vasile MANEA | CATALINA CIOCAN | [32 empty] | 90 | Bucuresti | Bucuresti | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BU114 | MOGOSOAIA_RTC | Road Bucuresti-Buftea-Ploiesti(6) | BU114 Mogosoia_RTC | Muntenia | 44 31 27.8 | 26 00 21.1 | 44 31 27.8 | 26 00 21.1 | Romtelecom, Str. Poeni,com. Mogosoaia | Romtelecom/ | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-11-17 | N/A | N/A |  |  |  | 0 | TE | 35 |  | N/A | PROTELCO | OK | SETRACO | 2000-10-27 | 2000-11-20 | YesV | 2000-11-23 | Mugur | 2001-03-06 | 2000-11-27 |  |  |  | N/A | 2000-09-26 |  | 2000-10-09 | 2000-10-19 |  |  |  | 2000-11-20 | ICOM | TRY | 2000-11-20 | 2000-11-20 | 2000-11-21 | 2000-11-21 | 2000-11-22 |  | Yes | Bogdan Bogodai | 2001-03-02 | 2001-03-02 | 2001-03-02 | 2001-04-24 | 2001-05-15 | K 739 494 | 0 | 0 | 33.5 | K 739 494 | 120 | 0 | 32 | K 739 494 | 240 | 0 | 32 |  |  |  |  | N/A | 65 | 65 | 1 1/4" | 65 | 65 | 1 1/4" | 65 | 65 | 1 1/4" |  |  |  | 390 | N/A | Dr. Taberei | FO | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | [6 empty] | 20/ |  |  | BSC11 | DRUMUL TABEREI |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PITURCESCU | OK | N/A |  | N/A | N/A | 30N01 Mogosoaia-Dr.Taberei |  | 2001-01-30 | Cristian CROITOR | Cosmorom | CSFT1802-DONOR | BU806 | K 739 134 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COUPLER | [11 empty] | 90 | Mogosoaia | SAI | [7 empty] | Site Near=Insertion Point
Phase_2 | CSH | BU115 | BUFTEA_RTC | Road Bucuresti-Buftea-Ploiesti(6) | BU115 Buftea_RTC | Muntenia | 44 33 46.8 | 25 56 55.3 | 44 33 46.8 | 25 56 55.3 | Sediul Romtelecom, Buftea, jud. Ilfov | Romtelecom/ | 2102 | M | C+C+C+ | 2/2/2 | N/A | [13 empty] | M | 25 |  | N/A | PROTELCO* |  | SETRACO* |  |  |  |  | Doru | [6 empty] | N/A |  | 2001-03-14 | [15 empty] | HOLD |  |  |  |  | K 739 494 | 0 | 0 | 23.5 | K 739 494 | 120 | 0 | 23.5 | K 739 494 | 240 | 0 | 23.5 |  |  |  |  | N/A | 30 | 30 | 7/8" | 30 | 30 | 7/8" | 30 | 30 | 7/8" |  |  |  | 180 | N/A | Dr. Taberei | FO | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | RBS | [7 empty] | 51/outdoor |  |  | BSC11 | DRUMUL TABEREI |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | HOLD |  |  | Cosmorom | [33 empty] | 90 | Mogosoaia | SAI | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | BU116 | LACUL TEI_2 | Bucuresti(19) | BU009 Baneasa_RTC | Muntenia | 44 27 51.7 | 26 07 40.9 | 44 27 49 | 26 07 36 | Aleea Teiul Doamnei nr.4, bl.21, sector 2 | Asociatie de proprietari/Dl. Alexe Iulian - 01/ 2423942 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | Yes | N/A |  |  |  | 29.67 | B | 32.88 | S3.9m+S3.9m | N/A | SVF | OK | SVF | 2001-01-19 | 2001-01-26 | YesV | 2001-02-16 | Doru | 2001-03-26 | 2001-02-26 |  |  |  |  | 2000-12-18 |  | 2000-12-18 | 2001-02-05 |  |  |  | 2001-02-01 | ICOM | SVF | 2001-02-01 | 2001-02-01 | 2001-02-06 | 2001-02-08 | 2001-02-13 |  | Yes | Bogdan Bogodai | 2001-03-26 | 2001-03-26 | 2001-03-26 | 2001-05-03 | 2001-05-28 | K 739 494 | 0 | 0 | 34.8 | K 739 494 | 120 | 0 | 34.8 | K 739 494 | 240 | 0 | 34.9 |  |  |  |  | N/A | 20 | 20 | 7/8" | 25 | 25 | 7/8' | 20 | 20 | 7/8" |  |  |  | 130 | ML 38 E 1+0 | Baneasa | MW | 348 | 0.3 | 33.8 | 20 | 38/14 |  |  | 2U-3 |  |  |  | RBS | [9 empty] | 1 | BU099 | INTRAROM |  | 0.3 |  | 70 | 38/18 | [6 empty] | 22* | SVF | 2001-02-01 | 584 | 2001-02-02 | 2001-02-05 | 2001-02-15 | DINCA | OK | 2001-03-26 |  | 2001-04-11 | 2001-04-20 | 30N23 Baneasa-Dr.Taberei |  | 2001-02-15 | Denis CIUCU | Cosmorom | [32 empty] | 79 | Bucuresti | Bucuresti | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BU117 | VALEA ARGESULUI | Bucuresti(19) | BU032 CNT_2 | Muntenia | 44 24 56 | 26 01 04 | 44 24 56.4 | 26 01 04.2 | Str. Valea Argesului nr.5 bl.C1 sc. A sector 6 | Asociatie de locatari/D-na. Adriana Dragomirescu - 01/ 777 78 79 | 2102 | M/E | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-11-17 | Yes | N/A |  |  |  | 31.55 | B | 34.85 | C2m+C2m+C2m | N/A | SVF | OK | SVF | 2000-10-20 | 2000-11-02 | YesV | 2000-11-15 | Doru | 2000-11-02 | 2000-11-22 |  |  |  | 2000-09-25 | 2000-09-21 |  | 2000-09-25 | 2000-10-17 |  |  |  | 2000-11-03 | ICOM | SVF | 2000-11-03 | 2000-11-03 | 2000-11-03 | 2000-11-03 | 2000-11-06 |  | Yes | Bogdan Bogodai | 2001-01-22 | 2001-01-22 | 2001-01-22 | 2001-02-21 | 2001-04-10 | K 739 494 | 0 | 0 | 37.35 | K 739 494 | 120 | 0 | 37.35 | K 739 494 | 240 | 0 | 37.35 |  |  |  |  | N/A | 21 | 21 | 7/8" | 17 | 17 | 7/8" | 17 | 17 | 7/8" |  |  |  | 110 | ML 38 E 1+0 | Dr. Taberei | MW | 58 | 0.6 | 36.45/0.3 | 17 | 38/13 |  |  | 4U-1 |  |  |  | RBS | [9 empty] | 1 | BU032 | CNT2_MSC | 226 | 0.6 |  |  | 38/17 | [6 empty] | 13 | SVF | 2000-11-03 | 358 | 2000-11-03 | 2000-11-03 | 2000-11-06 | RADU | OK | 2001-01-22 |  | 2001-02-05 | 2001-02-06 | 30N06 conectare locala |  | OK | Ionut GRIGORESCU | Cosmorom | [32 empty] | 87 | Bucuresti | Sector 6 | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_3 | CS | BU118 | OBCINA MARE | Bucuresti(x) | BU032 CNT_2 | Muntenia | 44 24 57 | 26 03 51 | [36 empty] | 2001-01-29 |  |  |  | 2001-07-11 | [17 empty] | CTR | [34 empty] | ML 38 E 1+0 | Dr. Taberei | MW | [22 empty] | BU032 | CNT2_MSC | [26 empty] | OK | Denis CIUCU | [33 empty] | 88 | [9 empty] | missing |  |  | missing
Phase_2 | CS | BU119 | BRAUUNION | Bucuresti(19) | BU032 CNT_2 | Muntenia | 44 26 16 | 25 59 14.7 | 44 26 11.8 | 25 59 17 | Str. Osiei nr.18-34 | SC BRAUUNION SA - Str. Osiei nr18-34/Angelea Niculea - Str. Osiei nr.18-34, 220 10 94 | 2102 | M | C+C+C+ | 2002-02-02 | N/A | [6 empty] | 2000-11-17 | Yes | N/A |  |  |  | 12.2 | B | 16.8 | C3.5m+C3.5m | N/A | PROTELCO | OK | MULTISERV | 2000-12-07 | 2001-01-18 | YesV | 2001-01-26 | Doru | 2001-03-08 | 2001-02-13 |  |  |  |  | 2000-09-11 |  | 2000-10-04 | 2001-01-19 |  |  |  | 2001-02-01 | ICOM | DIEKAT | 2001-01-26 | 2001-01-26 | 2001-02-05 | 2001-02-16 | 2001-02-23 |  | Yes | Ion Soare | 2001-03-13 | 2001-03-13 | 2001-03-13 | 2001-05-28 | 2001-06-19 | K 739 494 | 90 | 0 | 15 | K 739 494 | 210 | 0 | 15.7 | K 739 494 | 330 | 0 | 15.6 |  |  |  |  | N/A | 24 | 24 | 7/8" | 27 | 27 | 7/8" | 27 | 27 | 7/8" |  |  |  | 156 | ML 23 E 1+0 | Dr. Taberei | MW | 99 | 0.6 | 14.5/0.3 | 24 | 23/56 |  |  | 2U-3 |  |  |  | RBS | [9 empty] | 1 | BU104 | IULIU MANIU_2 | 279 | 0.6 | 39/0.3 | 16 | 23/58 | [6 empty] | 22* | DIEKAT | 2001-02-01 | 553 | 2001-02-02 | 2001-02-06 | 2001-02-23 | IVAN | OK | 2001-03-13 |  | 2001-03-21 | 2001-04-06 | 30N07 conectare locala |  | OK | Denis CIUCU | Petrica BURGHIU | [32 empty] | 89 | Bucuresti | Bucuresti | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BU120 | PANTELIMON_2 | Bucuresti(19) | BU009 Baneasa_RTC | Muntenia | 44 26 27.7 | 26 1058.6 | 44 26 27.7 | 26 10 58.6 | Soseaua Pantelimon 365, bl.A2, sc.A | Asociatie de locatari/Dl. Anghelescu - 01/ 627 99 92 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | Yes | N/A |  |  |  | 33 | B | 36.8 | C3m+C3m | N/A | ISAF | OK | SETRACO | 2000-11-14 | 2000-12-06 | YesV | 2000-12-22 | Doru | 2001-01-11 | 2001-01-10 |  |  |  |  | 2000-11-02 |  | 2000-11-07 | 2000-11-20 |  |  |  | 2000-12-11 | ICOM | DIEKAT | 2000-12-08 | 2000-12-13 | 2000-12-14 | 2000-12-14 | 2000-12-16 |  | Yes | Alexandru Toma | 2001-03-20 | 2001-03-20 | 2001-03-20 | 2001-07-10 |  | K 739 494 | 0 | 0 | 40.23 | K 739 494 | 120 | 0 | 40.5 | K 739 494 | 240 | 0 | 40.5 |  |  |  |  | N/A | 22 | 22 | 7/8" | 21 | 21 | 7/8" | 17 | 17 | 7/8" |  |  |  | 120 | ML 23 E 1+0 | Baneasa | MW | 76 | 0.6 | 42 | 22 | 23/58 |  |  | 2U-3 |  |  |  | RBS | [9 empty] | 1 | BU701 | PANTELIMON | 256 | 0.6 | 48.5 | 70 | 23/56 | [6 empty] | 9* | DIEKAT | 2000-12-18 | 446 | 2000-12-18 | 2001-01-30 | 2001-02-05 | PAUN | OK | 2001-03-20 |  | 2001-04-11 | 2001-04-20 | 30N23 Baneasa-Dr.Taberei |  | 2001-02-15 | Ionut GRIGORESCU | Cosmorom | [32 empty] | 71 | Bucuresti | Bucuresti | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BU121 | 1 DECEMBRIE 1918 | Bucuresti(19) | BU018 Titan_CTA | Muntenia | 44 26 09.2 | 23 10 21.9 | 44 26 09.2 | 26 10 21.9 | B-dul. 1 Decembrie 1918 nr.2, bl.My 9, sc.2 | Asociatie de locatari/Dl. Serbu - Et.6, ap.57 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-12-11 | Yes | N/A |  |  |  | 27 | B | 30.2 | C2m+C2m | N/A | ISAF | OK | SETRACO | 2000-11-14 | 2000-12-07 | YesV | 2000-12-22 | Doru | 2001-01-11 | 2001-01-10 |  |  |  |  | 2000-10-21 |  | 2000-11-07 | 2000-11-20 |  |  |  | 2000-12-11 | ICOM | DIEKAT | 2000-12-08 | 2000-12-13 | 2000-12-14 | 2001-02-16 | 2001-02-21 |  | Yes | Ion Soare | 2001-03-02 | 2001-03-01 | 2001-03-01 | 2001-03-06 | 2001-04-10 | K 739 494 | 0 | 0 | 30.8 | K 739 494 | 120 | 0 | 30.5 | K 739 494 | 240 | 0 | 30.6 |  |  |  |  | N/A | 13 | 13 | 7/8" | 28 | 28 | 7/8" | 28 | 28 | 7/8" |  |  |  | 138 | ML 38 E 1+0 | Dr. Taberei | MW | 189 | 0.3 | 32 | 30 | 38/14 |  |  | 4U-1 |  |  |  | RBS | [9 empty] | 1 | BU122 | VASILE GOLDIS | 9 | 0.3 | 36 | 12 | 38/18 | [6 empty] | 19* | DIEKAT | 2001-01-24 | 536 | 2001-01-30 | 2001-01-30 | 2001-02-21 | RADU | OK | 2001-03-01 | PENDING |  |  | 30N04 Titan-Dr.Taberei |  | 2001-02-15 | Ionut GRIGORESCU | #N/A | [32 empty] | 76 | Bucuresti | Bucuresti | [7 empty] | 2 |  |  | 2
Phase_2 | CS | BU122 | VASILE GOLDIS | Bucuresti(19) | BU018 Titan_CTA | Muntenia | 44 25 43.5 | 26 10 16.1 | 44 25 43.5 | 26 10 16.1 | Aleea Vasile Goldisi nr.6 bl.M41 | Asociatie de locatari/Dl. Turcu Liviu - et.9, ap.40, 01/ 644 20 97 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-12-11 | Yes | N/A |  |  |  | 30 | B | 30 | 6m new pylonet | N/A | ISAF | OK | PROFIL | 2000-11-14 | 2000-12-19 | YesV | 2000-12-21 | Doru | 2001-01-09 | 2001-01-19 |  |  |  |  | 2000-10-21 |  | 2000-11-07 | 2000-11-20 |  |  |  | 2000-12-19 | ICOM | DIEKAT | 2000-12-19 | 2001-01-10 | 2001-01-11 | 2001-01-23 | 2001-01-25 |  | Yes | Ion Soare | 2001-03-01 | 2001-03-01 | 2001-03-01 | 2001-03-15 | 2001-04-10 | K 739 494 | 0 | 0 | 36 | K 739 494 | 120 | 0 | 36 | K 739 494 | 240 | 0 | 36 |  |  |  |  | N/A | 12 | 12 | 7/8" | 12 | 12 | 7/8" | 12 | 12 | 7/8" |  |  |  | 72 | ML 38 E 1+0 | Dr. Taberei | MW | 184 | 0.3 | 36 | 12 | 38/18 |  |  | 4U-1 |  |  |  | RBS | [9 empty] | 1 | BU065 | MACARALEI |  | 0.3 |  | 30 | 38/14 | [6 empty] | 19* | DIEKAT | 2001-01-24 | 537 | 2001-01-30 | 2001-01-30 | 2001-02-21 | PAUN | OK | 2001-03-01 |  | 2001-07-12 |  | 30N04 Titan-Dr.Taberei |  | 2001-02-15 | Theo RADOI | Cosmorom | [32 empty] | 72 | Bucuresti | Bucuresti | [7 empty] | 2 |  |  | 1
Phase_2 | CS | BU123 | CIUCEA | Bucuresti(19) | BU076 Popesti-Leordeni | Muntenia | 44 24 54.8 | 26 10 47.6 | 44 24 53.7 | 26 10 47.6 | Str. Ciucea nr.5 bl. L19 sc.5, Bucuresti | Asociatie de locatari/Dl. Ivan Ion - Et.9, ap.121 - 01/ 630 14 55 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | Yes | N/A |  |  |  | 33 | B | 33.8 | 9m new pylonet | N/A | ISAF | OK | EL-MONT | 2001-01-29 | 2001-02-10 | YesV | 2001-02-19 | Doru | 2001-03-23 | 2001-02-26 |  |  |  |  | 2000-10-21 |  | 2001-01-17 | 2001-03-01 |  |  |  | 2001-02-16 | ICOM | SVF | 2001-02-16 | 2001-02-16 | 2001-02-19 | 2001-02-22 | 2001-02-23 |  | Yes | Bogdan Bogodai | 2001-03-09 | 2001-03-27 | 2001-03-27 | 2001-04-19 | 2001-04-23 | K 739 494 | 0 | 0 | 42 | K 739 494 | 120 | 0 | 42 | K 739 494 | 240 | 0 | 42 |  |  |  |  | N/A | 18 | 18 | 7/8" | 18 | 18 | 7/8" | 18 | 18 | 7/8" |  |  |  | 108 |  | Dr. Taberei | MW | 187 | 0.6 | 43.5/0.3 | 22 | 23/58 |  |  | 2U-3 |  |  |  | RBS | [9 empty] | 1 | BU076 | POPESTI LEORDENI | 7 | 0.6 | 48 | 60 | 23/56 | [6 empty] | 28* | SVF | 2001-02-16 | 647 | 2001-02-19 | 2001-02-20 | 2001-02-23 | PAUN | OK | 2001-03-27 | PENDING |  |  | 30N02 Popesti Leordeni-Dr.Taberei |  | 2001-03-09 | Theo RADOI | CATALINA CIOCAN | [32 empty] | 72 | Bucuresti | Bucuresti | [7 empty] | 2 |  |  | 2
Phase_2 | CS | BU125 | CEAHLAU | Bucuresti(19) | BU004 Pajura | Muntenia | 44 25 18.1 | 26 02 39.6 | 44 27 25.6 | 26 02 51 | B-dul. Ceahlau nr.20 bl.103 sc.2 | Asociatie de locatari/Dl. Zecheru - 092/ 392 228 | 2102 | M/E | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-11-17 | Yes | N/A |  |  |  | 26.8 | B | 26.8 | C3.9m+C3.9m+C3.9m | N/A | SVF | OK | SVF | 2000-10-25 | 2000-11-06 | YesV | 2000-11-15 | Doru | 2001-01-09 | 2000-11-22 |  |  |  | 2000-09-25 | 2000-09-21 |  | 2000-09-25 | 2000-10-20 |  |  |  | 2000-11-06 | ICOM | SVF | 2000-11-03 | 2000-11-03 | 2000-11-06 | 2000-11-06 | 2000-11-09 |  | Yes | Bogdan Bogodai | 2001-01-22 | 2001-01-23 | 2001-01-23 | 2001-03-20 | 2001-04-10 | K 739 494 | 0 | 0 | 32.2 | K 739 494 | 120 | 0 | 32.2 | K 739 494 | 240 | 0 | 32.2 |  |  |  |  | N/A | 20 | 20 | 7/8" | 22 | 22 | 7/8" | 10 | 10 | 7/8" |  |  |  | 104 | ML 38 E 1+0 | Dr. Taberei | MW | 75 | 0.6 | 31.3/0.3 | 21 | 38/14 |  |  | 4U-1 |  |  |  | RBS | [9 empty] | 1 | BU087 | GIULESTI-1 | 255 | 0.6 |  | 30 | 38/18 | [6 empty] | 15 | TRYLON | 2000-11-21 | 360 | 2000-11-21 | 2000-11-22 | 2000-11-24 | RADU | OK | 2001-01-23 |  | 2001-02-05 | 2001-02-06 | 30N04 Pajura-Dr.Taberei |  | OK | Ionut GRIGORESCU | CATALINA CIOCAN | [32 empty] | 84 | Bucuresti | Sector 6 | [5 empty] | 1 |  | 2 | 1 |  | 1
Phase_3 | CS | BU126 | DIHAM_1 | Bucuresti(x) | BU018 Titan_CTA | Muntenia | 44 26 18 | 26 09 21 | 44 26 18 | 26 09 20 | Str. Herta nr.16 bl.X4 sector 2 | Asociatie de locatari bl. X4/Popa Emil adm. Str. Herta nr.16 bl.X4 ap.43, 01/624 2000 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | YES |  |  |  |  | 31.5 | B | 35 | T5m+C | N/A | DIEKAT | OK | ROMPSAR | 2001-07-04 | 2001-07-17 | in exec |  | Doru |  |  | 2001-04-02 |  |  | 2001-04-18 |  |  | 2001-05-14 | 2001-06-13 | [14 empty] | CW NOT STARTED |  |  |  |  | K 739 494 | 0 | 0 | 35 | K 739 494 | 120 | 0 | 35 | K 739 494 | 240 | 0 | 36.5 |  |  |  |  | N/A | 20 | 20 | 7/8" | 20 | 20 | 7/8" | 18 | 18 | 7/8" |  |  |  | 76 | ML 38 E 1+0 | Dr. Taberei | MW | 182 | 0.3 | 34 | 20 | [18 empty] | BU130 | IOR | 2 | [23 empty] | new05 Titan-Dr.Taberei |  | 2001-08-06 | Dragos BICIU | Catalin ANGHEL | [33 empty] | Bucuresti | Bucuresti | [7 empty] | 3 |  |  | 3
Phase_2 | CS | BU127 | SUBSITE_1 | Otopeni(3) | BU502 Balotesti_RTC | Muntenia | 44 34 07 | 26 04 42.9 | 44 34 07 | 26 04 42.9 | Aeroport Otopeni | Aeroport Otopeni/Dispecerat tehnic Aeroprt Otopeni - 092/ 278 026; 01/ 204 22 07/2207 | 2101 | M | C+ | 2 | N/A | [6 empty] | 2000-12-11 | N/A | N/A |  |  |  |  | B |  | C4m | N/A | IMSAT | OK | IMSAT | 2000-11-28 | 2001-02-12 | YesV | 2001-03-16 | Doru | 2001-03-23 | 2001-03-21 |  |  |  | 2000-12-21 | 2000-12-20 |  | 2001-01-12 | 2001-01-29 |  |  |  | 2001-02-15 | ICOM | Interactive | 2001-02-13 | 2001-02-15 | 2001-02-16 | 2001-02-20 | 2001-02-21 |  | Yes | Mihai Constantin | 2001-03-16 | 2001-03-16 | 2001-03-16 | 2001-03-20 | 2001-04-10 | K 739 494 | 210 | 0 | 12 | K 739 494 | 350 | 0 | 12 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 15 | 15 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 30 |  | Dr. Taberei | MW | 10 | 0.3 | 11.5 | 15 | 38/14 |  | 4x2/8 | 4U-1 |  |  |  | RBS | [9 empty] | 1 | BU128 | SUBSITE_2 | 190 | 0.3 | 30 | 40 | 38/18 | [6 empty] | 27* | INTERACTIVE | 2001-02-15 | 641 | 2001-02-16 | 2001-02-16 | 2001-02-21 | VLAD | OK | 2001-03-16 |  | 2001-03-21 | 2001-04-06 | 30N02 Balotesti-Dr.Taberei |  | OK | Petrica BURGHIU | Cosmorom | [32 empty] | 97 | Otopeni | Ilfov | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BU128 | SUBSITE_2 | Otopeni(3) | BU502 Balotesti_RTC | Muntenia | 44 34 20.9 | 26 04 46.5 | 44 34 20.8 | 26 04 46.5 | Aeroport Otopeni, Stalpul 11 | Aeroport Otopeni/Dispecerat tehnic Aeroprt Otopeni - 092/ 278 026; 01/ 204 22 07/2207 | 2101 | M | C+ | 2 | N/A | [6 empty] | 2000-12-11 | N/A | N/A |  |  |  | 0 | TE | 30 | C4m | N/A | IMSAT | OK | IMSAT | 2000-11-28 | 2001-02-12 | YesV | 2001-04-06 | Doru |  | 2001-04-10 |  |  |  | 2000-12-21 | 2000-12-20 |  | 2001-01-12 | 2001-01-29 |  |  |  | 2001-02-15 | ICOM | Interactive | 2001-02-13 | 2001-02-15 | 2001-02-16 | 2001-02-20 | 2001-02-21 |  | Yes | Ion Soare | 2001-03-02 | 2001-03-02 | 2001-03-02 | 2001-03-27 | 2001-04-10 | K 739 494 | 90 | 0 | 30 | K 739 494 | 210 | 0 | 30 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 40 | 40 | 7/8" | 40 | 40 | 7/8" | N/A | N/A | N/A |  |  |  | 160 | ML 38 E 1+0 | Dr. Taberei | MW | 233 | 0.3 | 30 | 40 | 38/18 |  | 4x2/8 | 4U-1 |  |  |  | RBS | [9 empty] | 1 | BU129 | SUBSITE_3 | 53 | 0.3 | 28 | 41 | 38/14 | [6 empty] | 27* | INTERACTIVE | 2001-02-15 | 642 | 2001-02-16 | 2001-02-16 | 2001-02-21 | PAUN | OK | 2001-03-02 |  | 2001-03-21 | 2001-04-06 | 30N02 Balotesti-Dr.Taberei |  | OK | Petrica BURGHIU | Cosmorom | [32 empty] | 97 | Otopeni | Ilfov | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BU129 | SUBSITE_3 | Otopeni(3) | BU502 Balotesti_RTC | Muntenia | 44 34 13.5 | 26 04 45.8 | 44 34 11.7 | 26 04 29.5 | Aeroport Otopeni - Centrala termica | Aeroport Otopeni/Dispecerat tehnic Aeroprt Otopeni - 092/ 278 026; 01/ 204 22 07/2207 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-12-11 | N/A | N/A |  |  |  | 27 | B | 27 | C5m | N/A | IMSAT | OK | IMSAT | 2000-11-28 | 2000-12-12 | YesV | 2000-12-21 | Doru | 2000-12-18 | 2001-02-07 |  |  |  | 2000-10-19 | 2000-09-15 |  | 2000-11-07 | 2000-11-20 |  |  |  | 2000-12-12 | ICOM | IMSAT | 2000-12-12 | 2000-12-13 | 2000-12-14 | 2000-12-15 | 2000-12-20 | RADU | Yes | Ionut Grigorescu | 2000-12-24 | 2000-12-21 | 2000-12-22 | 2001-07-05 | 2001-07-11 | K 739 494 | 60 | 0 | 30.5 | K 739 494 | 120 | 0 | 30.3 | K 739 494 | 270 | 0 | 30.4 |  |  |  |  | N/A | 41 | 41 | 7/8" | 41 | 41 | 7/8" | 41 | 41 | 7/8" |  |  |  | 246 | ML 23 E 1+0 | Dr. Taberei | MW | 358 | 1.2 | 29.4 | 41 | 23/56 |  | 4x2/8 | 4U-1 |  |  |  | RBS | [9 empty] | 1 | BU502 | BALOTESTI_RTC | 178 | 0.6 | 30 | 60 | 23/58 | [6 empty] | 6* | IMSAT | 2000-12-12 | 456 | 2000-12-13 | 2000-12-14 | 2000-12-20 | RADU | OK | 2000-12-22 | PENDING |  |  | 30N02 Balotesti-Dr.Taberei |  | OK | Cosmorom | Cosmorom | [32 empty] | 97 | Otopeni | Ilfov | [7 empty] | 2 |  |  | 2
Phase_3 | CS | BU130 | IOR | Bucuresti(x) | BU018 Titan_CTA | Muntenia | 44 25 51 | 26 09 20 | 44 25 50 | 26 09 20 | Str. Copaceni nr.47 bl.W3 sc.B sector 3 | Asociatie de locatari bl. W3 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | YES |  |  |  |  | 32 | B | 32 | C-5m+C-4.5m | N/A | DIEKAT | OK | PROFIL | 2001-07-12 | 2001-07-25 | in exec |  | Doru |  |  | 2001-04-02 |  |  | 2001-04-18 |  |  | 2001-07-04 | 2001-07-04 | [14 empty] | CW NOT STARTED |  |  |  |  | K 739 494 | 0 | 0 | 38 | K 739 494 | 120 | 0 | 38 | K 739 494 | 240 | 0 | 37 | N/A | N/A | N/A | N/A | N/A | 16 | 16 | 7/8" | 16 | 16 | 7/8" | 20 | 20 | 7/8" | N/A | N/A | N/A | 104 | ML 38 E 1+0 | Dr. Taberei | MW | 144 | 0.3 | 37 | 16 | [18 empty] | BU066 | REBREANU | [24 empty] | new05 Titan-Dr.Taberei |  | 2001-08-06 | Dragos BICIU | Catalin ANGHEL | [33 empty] | Bucuresti | Bucuresti | [7 empty] | 3 |  |  | missing
Phase_3 | CS | BU131 | GARA OBOR | Bucuresti(x) | BU010 Dacia | Muntenia | 44 26 48.21 | 26 08 12.24 | 44 26 51 | 26 08 31 | Bd. Garii Obor, nr.10-14, bl.B3, sector 2 | Asociatie de locatari bl. B3/Manea Ilie - adm. Bd. Garii Obor nr.10-14, bl.B2, 01/252 3261, Radu Gheorghe pres. 01/6423462 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | YES |  |  |  |  | 25.5 | B | 25.5 | T4.5m-T4.5m | N/A | DIEKAT | OK | ROMPSAR | 2001-07-12 | 2001-07-25 | in exec |  | Doru |  |  | 2001-04-02 |  |  | 2001-04-18 |  |  | 2001-06-12 | 2001-07-04 | [14 empty] | CW NOT STARTED |  |  |  |  | K 739 494 | 0 | 0 | 29 | K 739 494 | 120 | 0 | 29 | K 739 494 | 240 | 0 | 29 | N/A | N/A | N/A | N/A | N/A | 12 | 12 | 7/8" | 12 | 12 | 7/8" | 12 | 12 | 7/8" | N/A | N/A | N/A | 72 | ML 23 E 1+0 | Dr. Taberei | MW | 157 | 0.3 | 29.5 | 12 | [7 empty] | N/A | [10 empty] | BU061 | IANCULUI-2 | 337 | [26 empty] | Dragos BICIU | Catalin ANGHEL | [32 empty] | 56 | Bucuresti | Bucuresti | [7 empty] | 3 |  |  | missing
Phase_3 | CS | BU132 | HOBITA | Bucuresti(x) | BU010 Dacia | Muntenia | 44 26 37.6 | 26 09 08 | 44 26 37.6 | 26 09 08 | Sos. Pantelimon, nr.239, bl. 62, sec.2 | Asociatia civila a proprietarilor bl. 62 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | YES |  |  |  |  | 45 | B | 48 | T3m+T3.5m | N/A | DUAL | OK | DUAL | 2001-07-12 | 2001-07-25 | in exec |  | Doru | [5 empty] | OK |  |  | 2001-05-14 | 2001-06-25 | [14 empty] | CW NOT STARTED |  |  |  |  | K 739 494 | 0 | 0 | 47.4 | K 739 494 | 120 | 0 | 47.5 | K 739 494 | 240 | 0 | 47.5 | N/A | N/A | N/A | N/A | N/A | 55 | 55 | 1 1/4" | 27 | 27 | 7/8" | 10 | 10 | 7/8" | N/A | N/A | N/A | 182 | ML 38 E 1+0 | Dr. Taberei | MW | 265 | 0.3 | 48.2 | 10 | [18 empty] | BU061 | IANCULUI-2 | [27 empty] | Dragos BICIU | Catalin ANGHEL | [32 empty] | 75 | Bucuresti | Bucuresti | [7 empty] | 3 |  |  | missing
Phase_3 | CS | BU134 | MARIA ROSETTI | Bucuresti(x) | BU001 Palatul Telefoanelor | Muntenia | 44 26 58 | 26 06 29.1 | 44 26 31.5 | 26 06 22.6 | B-ul Maria Rosetti, nr. 7-9 | Davidescu Serban, tel. 094540307 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | YES |  |  |  |  | 31.1 | B | 35.3 | T6m+S zid 4.5m | N/A | SVF | OK | EL-MONT | 2001-07-12 | 2001-07-25 | in exec |  | Doru |  |  | 2001-01-29 |  |  | 2001-02-20 |  |  | 2001-05-09 | 2001-05-14 | [14 empty] | CW NOT STARTED |  |  |  |  | K 739 494 | 0 | 0 | 37.5 | K 739 494 | 120 | 0 | 36.6 | K 739 494 | 240 | 0 | 36.6 |  |  |  |  | N/A | 29 | 29 | 7/8" | 14 | 14 | 7/8" | 14 | 14 | 7/8" |  |  |  | 112 | ML 38 E 1+0 | Dr. Taberei | MW | 245 | 0.3 | 33.5 | 14 | [18 empty] | BU001 | PALATUL TELEFOANELOR | [26 empty] | OK | SORIN UNTARU | [33 empty] | 81 | Bucuresti | Bucuresti | [7 empty] | 3 |  |  | missing
Phase_3 | CS | BU135 | U2 | Bucuresti(x) | BU004 Pajura | Muntenia | 44 26 38.05 | 26 03 31.81 |  |  | Splaiu Independentei, Bucuresti, sec.6 |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | YES | [9 empty] | SVF |  | @ | 2001-08-01 | 2001-09-10 |  |  | Doru |  |  | 2001-01-29 | [21 empty] | CTR |  |  |  |  | K 739 494 | 0 | 0 |  | K 739 494 | 120 | 0 |  | K 739 494 | 240 | 0 | [5 empty] | N/A | [13 empty] | ML 38 E 1+0 | Dr. Taberei | MW | 21 | [21 empty] | BU086 | PRIORIPOST | [24 empty] | 30N04 Pajura-Dr.Taberei |  | OK | [44 empty] | 3 |  |  | missing
Phase_3 | CS | BU137 | HOTEL MARNA | Bucuresti(x) | BU001 Palatul Telefoanelor | Muntenia | 44 26 48.13 | 26 04 52.97 | 44 26 49 | 26 04 55 | Calea Grivitei 107-109, bl.A, sc. C | Asociatie de locatari, Calea Grivitei, nr.107-109, sec.1/D-nul ing. Gruescu, tel. 6506462 | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [7 empty] | YES |  |  |  |  | 20.4 | B | 21.4 | S4.5m+S4.5m+S4.5m | Room/Rack19" | SVF | OK | EMONTAJ | 2001-07-12 | 2001-07-25 | in exec |  | Doru |  |  | 2001-01-29 |  |  | 2001-02-20 |  |  | 2001-03-14 | 2001-05-14 | [14 empty] | CW NOT STARTED |  |  |  |  | K 739 494 | 0 | 0 | 25.4 | K 739 494 | 120 | 0 | 25.5 | K 739 494 | 240 | 0 | 24 |  |  |  |  | N/A | 30 | 30 | 7/8" | 34 | 34 | 7/8" | 22 | 22 | 7/8" |  |  |  | 172 | ML 38 E 1+0 | Dr. Taberei | MW | 134 | 0.3 | 24.5/0.3 | 31 | [18 empty] | BU001 | PALATUL TELEFOANELOR | [26 empty] | OK | Marius Lungu | [33 empty] | 80 | Bucuresti | Bucuresti | [7 empty] | 3 |  |  | missing
Phase_3 | CS | BU138 | AEROGARII | Bucuresti | BU046 Casa Presei | Muntenia | 44 29 40.3 | 26 04 48.3 |  |  |  |  | 2102 | M/E | C+C+C+ | 2/2/2 | N/A | [17 empty] | DUAL | OK | DUAL | 2001-07-12 | 2001-07-25 | in exec |  | Doru |  |  | 2001-07-06 |  |  |  | 2001-07-11 |  |  |  |  | 2001-07-06 | [47 empty] | ML 38 E 1+0 | Dr. Taberei | MW | [22 empty] | BU046 | CASA PRESEI | [22 empty] | Theo RADOI | Theo RADOI | 30N01 Casa Presei-Dr.Taberei |  | OK | [34 empty] | 90
Phase_3 | CS | BU139 | TEATRUL DE OPERETA | Bucuresti(x) | BU001 Palatul Telefoanelor | Muntenia | 44 26 13.16 | 26 06 09.47 | 44 26 13.16 | 26 06 09.47 | Teatru de Opereta Ion Dacian, Bd. Nicolae Balcescu, nr.2 |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | YES |  |  |  |  | 21 | B | 22.5 | C+T | N/A | DUAL | OK | FAB | 2001-08-01 | 2001-08-20 |  |  | Doru | [8 empty] | 2001-05-14 | [15 empty] | CW NOT STARTED |  |  |  |  | K 739 494 | 0 | 0 | 21.5 | K 739 494 | 120 | 0 | 21.5 | K 739 494 | 260 | 0 | 15.5 |  |  |  |  | N/A | 55 | 55 | 1 1/4" | 40 | 40 | 7/8" | 25 | 25 | 7/8" |  |  |  | 240 | ML 38 E 1+0 | Dr. Taberei | MW | 265 | 0.3 | 26.5 | 35 | [18 empty] | BU001 | PALATUL TELEFOANELOR | [26 empty] | OK | Dragos BICIU | Leonard BANU | [32 empty] | 80 | Bucuresti | Bucuresti | [7 empty] | 3 |  |  | missing
Phase_3 | CS | BU141 | SOLDAT ILIE MIHAI | Bucuresti(x) | BU032 CNT_2 | Muntenia | 44 24 46.11 | 26 03 49.71 | 44 24 47 | 26 03 49 | Str. Soldat Ilie Mihai, nr.13, bl. M132A, sc.A, Bucuresti | Asociatie de locatari bl. M132A/Teodosescu Alexandru - presedinte, bl. M132a, ap. 11, et.2; 01/4200359, Iscu Elena adm. Ap.45, 01/4209055 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | YES |  |  |  |  | 30 | B | 30 | T6m+T4m | N/A | DIEKAT | OK | FAB | 2001-07-12 | 2001-07-25 | in exec |  | Doru | [5 empty] | 2001-04-18 | 2001-07-11 |  | 2001-05-09 | 2001-06-01 | [14 empty] | CW NOT STARTED |  |  |  |  | K 739 494 | 0 | 0 | 35 | K 739 494 | 120 | 0 | 33.5 | K 739 494 | 240 | 0 | 36 |  |  |  |  | N/A | 31 | 31 | 7/8" | 22 | 22 | 7/8" | 26 | 26 | 7/8" |  |  |  | 158 | ML 38 E 1+0 | Dr. Taberei | MW | 172 | 0.6 | 32 | 22 | [18 empty] | BU077 | RAHOVEI | [26 empty] | OK | Dragos BICIU | Leonard BANU | [32 empty] | 87 | Bucuresti | Bucuresti | [7 empty] | 3 |  |  | missing
Phase_3 | CS | BU142 | VULCAN | Bucuresti(x) | BU032 CNT_2 | Muntenia | 44 24 59.48 | 26 04 13.16 |  |  |  |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | YES | [5 empty] | B |  |  |  | DIEKAT* | [6 empty] | Doru* | [6 empty] | 2001-07-11 | [17 empty] | CTR | [34 empty] | ML 23 E 1+0 | Dr. Taberei | MW | [22 empty] | BU078 | 13 SEPTEMBRIE | [26 empty] | OK | Dragos BICIU | Leonard BANU | [32 empty] | 85 | [9 empty] | missing |  |  | missing
Phase_3 | CS | BU144 | CARREFOUR | Bucuresti(x) | BU032 CNT_2 | Muntenia | 44 26 19 | 26 56 22 | [40 empty] | 2001-07-11 | [17 empty] | CTR | [34 empty] | ML 23 E 1+0 | Dr. Taberei | MW | 93 | [21 empty] | BU119 | BRAUUNION | [26 empty] | OK | [34 empty] | 93 | [9 empty] | 3 |  |  | missing
Phase_3 | CS | BU145 | MAGHERU | Bucuresti(x) | BU001 Palatul Telefoanelor | Muntenia | 44 26 38.7 | 26 05 51.3 |  |  |  |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | YES | [9 empty] | DUAL* | [6 empty] | Doru* |  |  |  | 2001-06-28 | [7 empty] | 2001-06-28 | [12 empty] | CTR | [34 empty] | ML 38 E 1+0 | Dr. Taberei | MW | 185 | [21 empty] | BU001 | PALATUL TELEFOANELOR | [26 empty] | OK | Dragos BICIU | Leonard BANU | [42 empty] | 3 |  |  | missing
Phase_3 | CS | BU146 | METRO VOLUNTARI | Bucuresti(x) | BU009 Baneasa_RTC | Muntenia | 44 29 44.7 | 26 11 52.7 | [26 empty] | SVF |  | @ | 2001-08-01 | 2001-09-10 |  |  | Doru |  |  | 2001-05-03 |  |  |  | 2001-05-15 | [17 empty] | CTR | [34 empty] | ML 23 E 1+0 | Baneasa | MW | 249 | [21 empty] | BU095 | COLENTINA_3 | [24 empty] | 30N24 Baneasa-Dr.Taberei |  | 2001-05-31 | Petrica BURGHIU | Tiberiu LICA | [32 empty] | 80 | [9 empty] | 3 |  |  | missing
Phase_3 | CS | BU147 | PROGRESU | Bucuresti(x) | BU032 CNT_2 | Muntenia | 44 25 42.6 | 26 04 30.1 | [26 empty] | SVF |  | @ | 2001-08-01 | 2001-09-10 |  |  | Doru |  |  | 2001-05-03 |  |  |  | 2001-05-15 | [17 empty] | CTR | [34 empty] | ML 38 E 1+0 | Dr. Taberei | MW | [22 empty] | BU081 | COTROCENI | [27 empty] | Petrica BURGHIU | Tiberiu LICA | [32 empty] | 78 | [9 empty] | 3 |  |  | missing
Phase_3 | CS | BU148 | APIMONDIA | Bucuresti(x) | BU009 Baneasa_RTC | Muntenia | 44 29 35.4 | 26 05 09.2 | [16 empty] | YES | [9 empty] | SVF |  | @ | 2001-08-01 | 2001-09-10 |  |  | Doru |  |  | 2001-05-03 |  |  |  | 2001-05-15 | [17 empty] | CTR | [34 empty] | ML 38 E 1+0 | Baneasa | MW | [22 empty] | BU009 | ROMTELECOM BANEASA | [24 empty] | new25 |  |  | Petrica BURGHIU | Tiberiu LICA | [42 empty] | 3 |  |  | missing
Phase_3 | CS | BU149 | GRIGORESCU | Bucuresti(x) | BU018 Titan_CTA | Muntenia | 44 24 46.1 | 26 09 46.9 | 44 24 46.2 | 26 09 47.2 | B-ul Camil Ressu, nr.76, bl. S1B-S1C, sc.2 | Asociatia de locatari din B-ul Canil Ressu nr.74-76, bl.S1B-S1C, sc.2 | 2202 | M/E | C+C+C+ | 2/2/2 | 2202 | [7 empty] | YES |  |  |  |  | 32 | B | 36 | S5m+S5m+S5m | Room/Rack19" | SVF | OK | DIRDATES | 2001-07-05 | 2001-07-19 | in exec |  | Doru |  |  | 2001-05-04 |  |  | OK | 2001-05-15 |  | 2001-05-30 | 2001-06-13 | [14 empty] | CW NOT STARTED |  |  |  |  | K 739 494 | 0 | 0 | 39.45 | K 739 494 | 120 | 0 | 39.45 | K 739 494 | 240 | 0 | 39.45 |  |  |  |  | N/A | 24 | 24 | 7/8" | 22 | 22 | 7/8" | 15 | 15 | 7/8" |  |  |  | 122 | ML 38 E 1+0 | Dr. Taberei | MW | 358 | 0.3 | 38.35 | 22 | [7 empty] | N/A | [10 empty] | BU066 | REBREANU | [24 empty] | 30N02 Titan-Dr.Taberei |  | OK | Petrica BURGHIU | Petrica BURGHIU | [32 empty] | 70 | Bucuresti | Bucuresti | [7 empty] | 3 |  |  | missing
Phase_3 | CS | BU150 | 1 DECEMBRIE | Bucuresti(x) | BU076 Popesti-Leordeni | Muntenia | 44 25 23.2 | 26 10 37.1 | 44 25 23.7 | 26 10 38.0 | Str. 1 Decembrie 1918, nr.25, bl.U6, sc.A, sec.3 | Asociatia de locatari din str. 1 Decembrie 1918 nr.25, bl.U6 | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [7 empty] | YES |  |  |  |  | 27.80 | B | 31.30 | S4m+S4m | Room/Rack19" | SVF | OK | DIRDATES | 2001-07-05 | 2001-07-19 | in exec |  | Doru |  |  | 2001-05-04 |  |  | OK | 2001-05-15 |  | 2001-05-30 | 2001-06-13 | [14 empty] | CW NOT STARTED |  |  |  |  | K 739 494 | 0 | 0 | 33.9 | K 739 494 | 120 | 0 | 34 | K 739 494 | 240 | 0 | 33.7 |  |  |  |  | N/A | 25 | 25 | 7/8" | 12 | 12 | 7/8" | 25 | 25 | 7/8" |  |  |  | 124 | ML 38 E 1+0* | Dr. Taberei | MW | 165 | 0.3 | 33 | 10 | [7 empty] | N/A | [10 empty] | BU123 | CIUCEA | [24 empty] | 30N02 Popesti Leordeni-Dr.Taberei |  | 2001-03-09 | Petrica BURGHIU | Petrica BURGHIU | [32 empty] | 70 | Bucuresti | Bucuresti | [7 empty] | 3 |  |  | missing
Phase_3 | CS | BU151 | BRANCUSI | Bucuresti(x) | BU018 Titan_CTA | Muntenia | 44 25 49 | 26 09 55.9 | 44 25 49 | 26 09 55.9 | Str. C-tin Brancusi, nr. 23, bl. T4-T5, sec. 3 | Asociatia de locatari bl. T4-T5 din strada Constantin Brancusi | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [12 empty] | 31 | B | 34 | T-6m | Room/Rack19" | DUAL | OK | COMARK | 2001-08-01 | 2001-09-10 |  |  | Doru |  |  | 2001-05-28 |  |  | OK | 2001-05-30 |  | 2001-07-04 | [15 empty] | CTR |  |  |  |  | K 739 494 | 0 | 0 | 40 | K 739 494 | 120 | 0 | 40 | K 739 494 | 240 | 0 | 40 | N/A | N/A | N/A | N/A | N/A | 20 | 20 | 7/8" | 13 | 13 | 7/8" | 13 | 13 | 7/8" | N/A | N/A | N/A | 92 | ML 38 E 1+0 | Dr. Taberei | MW | 327 | 0.3 | 38.3 | 20 | [18 empty] | BU067 | DIHAM | 147 | [23 empty] | new06 Titan-Dr.Taberei |  | 2001-08-06 | Petrica BURGHIU | Petrica BURGHIU | [33 empty] | Bucuresti | Bucuresti | [7 empty] | missing |  |  | missing
Phase_3 | CS | BU152 | BABA NOVAC | Bucuresti(x) | BU010 Dacia | Muntenia | 44 25 31 | 26 08 52.1 |  |  |  |  | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [17 empty] | DUAL |  | @ | 2001-08-01 | 2001-09-10 |  |  | Doru |  |  | 2001-05-28 |  |  |  | 2001-05-30 | [17 empty] | CTR | [34 empty] | ML 23 E 1+0 | Dr. Taberei | MW | [22 empty] | BU153 | MATEI VOIEVOD | [27 empty] | Petrica BURGHIU | Petrica BURGHIU | [42 empty] | missing |  |  | missing
Phase_3 | CS | BU153 | MATEI VOIEVOD | Bucuresti(x) | BU010 Dacia | Muntenia | 44 26 15.9 | 26 08 07.3 |  |  |  |  | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [17 empty] | DUAL | OK | COMARK | 2001-08-01 | 2001-09-10 |  |  | Doru |  |  | 2001-05-28 |  |  |  | 2001-05-30 | [17 empty] | CTR | [34 empty] | ML 38 E 1+0 | Dr. Taberei | MW | [22 empty] | BU055 | HYPERION | [27 empty] | Petrica BURGHIU | Petrica BURGHIU | [42 empty] | missing |  |  | missing
Phase_3 | CS | BU154 | OLTENITEI | Bucuresti(x) | BU076 Popesti-Leordeni | Muntenia | 44 23 09.1 | 26 08 19.4 | [40 empty] | 2001-05-30 | [17 empty] | CTR | [34 empty] | ML 23 E 1+0 | Dr. Taberei | MW | [22 empty] | BU076 | POPESTI LEORDENI | [71 empty] | missing |  |  | missing
Phase_3 | CS | BU155 | BRANCOVEANU | Bucuresti(x) | BU026 Piata Sudului | Muntenia | 44 23 53.1 | 26 06 30.5 | 44 23 53.1 | 26 06 30.5 | Strada Alunisului, nr. 2, bl. 11B, sec.4 | Asociatia de locatari bl.11B din str. Alunisului nr.2 | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [12 empty] | 34 | B | 36 | T-4.5m+C | Room/Rack19" | DUAL | OK | COMARK | 2001-08-01 | 2001-09-10 |  |  | Doru |  |  | 2001-05-28 |  |  | OK | 2001-05-30 |  | 2001-07-04 | [15 empty] | CTR |  |  |  |  | K 739 494 | 0 | 0 | 39 | K 739 494 | 120 | 0 | 39 | K 739 494 | 290 | 0 | 39 | N/A | N/A | N/A | N/A | N/A | 18 | 18 | 7/8" | 18 | 18 | 7/8" | 18 | 18 | 7/8" | N/A | N/A | N/A | 108 | ML 38 E 1+0 | Dr. Taberei | MW | 144 | 0.3 | 38 | 18 | [18 empty] | BU026 | PIATA SUDULUI | 324 | [26 empty] | Petrica BURGHIU | Petrica BURGHIU | [32 empty] | 82 | Bucuresti | Bucuresti | [7 empty] | missing |  |  | missing
Phase_3 | CS | BU156 | IZVORU RECE | Bucuresti(x) | BU026 Piata Sudului | Muntenia | 44 23 18.6 | 26 06 14.8 | 44 23 18.6 | 26 06 14.8 | Str. Izvorul Rece, nr.7, bl. A8, sc.3, sec.4 | Asociatia de locatari, bl. A8 | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [12 empty] | 34.2 | B | 37 | T-6m+C | Room/TMR9000 | DUAL | OK | COMARK | 2001-08-01 | 2001-09-10 |  |  | Doru |  |  | 2001-05-28 |  |  | OK | 2001-05-30 |  | 2001-07-04 | [15 empty] | CTR |  |  |  |  | K 739 494 | 0 | 0 | 38 | K 739 494 | 120 | 0 | 41 | K 739 494 | 240 | 0 | 41 | N/A | N/A | N/A | N/A | N/A | 23 | 23 | 7/8" | 18 | 18 | 7/8" | 18 | 18 | 7/8" | N/A | N/A | N/A | 118 | ML 38 E 1+0 | Dr. Taberei | MW | 18 | 0.3 | 37.5 | 23 | [18 empty] | BU155 | BRANCOVEANU | 198 | 0.3 | 38 | 18 | [23 empty] | Petrica BURGHIU | Petrica BURGHIU | [32 empty] | 81 | Bucuresti | Bucuresti | [7 empty] | missing |  |  | missing
Phase_3 | CS | BU157 | SINCAI | Bucuresti(x) | BU022 11 Iunie | Muntenia | 44 24 54 | 26 06 24.8 |  |  | Str, C-tin Radulescu Motru, nr. 6, Bl. 35 , Sc. B |  | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [17 empty] | DUAL | OK | COMARK | 2001-08-01 | 2001-09-10 |  |  | Doru |  |  | 2001-05-28 |  |  |  | 2001-05-30 | [17 empty] | CTR | [35 empty] | Dr. Taberei | MW | [22 empty] | BU158 | BUDAPESTA | [24 empty] | new02 11 Iunie Sud-Dr.Taberei |  |  | Petrica BURGHIU | Petrica BURGHIU | [42 empty] | missing |  |  | missing
Phase_3 | CS | BU158 | BUDAPESTA | Bucuresti(x) | BU022 11 Iunie | Muntenia | 44 25 14.5 | 26 06 15.8 |  |  |  | cheia este la ap 84, et 9, interfon 984C | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [17 empty] | DUAL | OK | @ | 2001-08-01 | 2001-09-10 |  |  | Doru |  |  | 2001-05-28 |  |  |  | 2001-05-30 | [17 empty] | CTR | [35 empty] | Dr. Taberei | MW | [22 empty] | BU022 | PIATA | [24 empty] | 30N01 11 Iunie Sud-Dr.Taberei |  | OK | Petrica BURGHIU | Petrica BURGHIU | [42 empty] | missing |  |  | missing
Phase_3 | CS | BU159 | NERVA TRAIAN | Bucuresti(x) | BU022 11 Iunie | Muntenia | 44 25 06 | 26 06 47.7 |  |  | Str Nerva Traian, Nr 23-25, Bl M71, Sc 1, Sec 3, Bucuresti | Asociatia de locatari, M 71 | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [17 empty] | DUAL | OK | @ | 2001-08-01 | 2001-09-10 |  |  | Doru |  |  | 2001-05-28 |  |  |  | 2001-05-30 | [17 empty] | CTR | [35 empty] | Dr. Taberei | Mw | [22 empty] | BU157 | SINCAI | [24 empty] | new02 11 Iunie Sud-Dr.Taberei |  |  | Petrica BURGHIU | Petrica BURGHIU | [42 empty] | missing |  |  | missing
Phase_3 | CS | BU160 | CHIAJNA | Bucuresti(x) | BU160 Chiajna | Muntenia | 44 27 44.9 | 25 58 42.9 | 44 27 43.8 | 25 58 31.4 | Sediul Romtelecom Chiajna | Romtelecom | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [12 empty] | 0 | TE | 36.4 |  | Shelter existent | SVF | OK | SVF | 2001-06-15 | 2001-06-07 | YesV | 2001-06-15 | Doru |  | 2001-06-26 | 2001-05-22 |  |  | OK | 2001-05-22 |  | 2001-05-30 | 2001-06-13 |  |  | 1902-11-02 | 2001-06-06 | ICOM | SVF | 2001-06-06 |  | 2001-06-07 | 2001-06-07 | 2001-06-08 | VLAD |  | Alexandru Toma | 2001-06-12 | 2001-06-12 | 2001-06-12 | 2001-06-19 | 2001-07-11 | K 739 494 | 0 | 0 | 30 | K 739 494 | 120 | 0 | 30 | K 739 494 | 240 | 0 | 30 |  |  |  |  | N/A | 41 | 41 | 7/8" | 42 | 42 | 7/8" | 42 | 42 | 7/8" | N/A | N/A | N/A | 250 | N/A | Dr. Taberei | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | [5 empty] | N/A | [6 empty] | 6m/outdoor |  |  | BSC11 | DRUMUL TABEREI |  | N/A |  |  | N/A | [10 empty] | N/A | N/A | N/A | RADU |  | N/A |  |  |  | 30N01 Chiajna-Dr.Taberei |  | 2001-06-10 | Petrica BURGHIU | Tiberiu LICA | [32 empty] | 95 | Comuna Chiajna | Ilfov | [7 empty] | Site Near=Insertion Point
Phase_3 | CS | BU161 | BRAGADIRU | Bucuresti(x) | BU161 Bragadiru | Muntenia | 44 22 09.1 | 25 58 30.9 | 44 22 09.1 | 25 58 30.9 | Sediul Romtelecom Bragadiru | Romtelecom | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [12 empty] | 6.8 | TE | 54 |  | room | SVF | OK | SVF | 2001-06-15 | 2001-06-07 | YesV | 2001-06-15 | Doru |  | 2001-06-26 | 2001-05-22 |  |  | OK | 2001-05-22 |  | 2001-05-30 | 2001-06-13 |  |  | 1902-11-01 | 2001-06-06 | ICOM | SVF | 2001-06-06 |  | 2001-06-07 | 2001-06-07 | 2001-06-08 | VLAD |  | Alexandru Toma | 2001-06-14 | 2001-06-14 | 2001-06-14 |  |  | K 739 494 | 0 | 0 | 48.5 | K 739 494 | 120 | 0 | 48.5 | K 739 494 | 240 | 0 | 48.5 |  |  |  |  | N/A | 72 | 72 | 7/8" | 72 | 72 | 7/8" | 72 | 72 | 7/8" | N/A | N/A | N/A | 432 | N/A | Dr. Taberei | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | [5 empty] | N/A | [6 empty] | 6m/indoor |  |  | BSC11 | DRUMUL TABEREI |  | N/A |  |  | N/A | [10 empty] | N/A | N/A | N/A | VLAD |  | N/A |  |  |  | 30N01 Bragadiru-Dr.Taberei |  | 2001-06-10 | Petrica BURGHIU | Tiberiu LICA | [32 empty] | 81 | Comuna Bragadiru | Ilfov | [7 empty] | Site Near=Insertion Point
Phase_3 | CS | BU162 | GEORGE CALBORNE | Bucuresti | BU032 CNT_2 | Muntenia | 44 25 56.4 | 26 01 22.71 | [94 empty] | Dr. Taberei | MW | [22 empty] | BU103 | DEALUL MACINULUI
Phase_3 | CS | BU163 | BANU MANTA | Bucuresti(x) | BU004 Pajura | Muntenia | 44 27 10.8 | 26 04 22.7 |  |  |  |  | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [17 empty] | DIEKAT |  | @ | 2001-09-01 | 2001-09-30 |  |  | Doru |  |  | 2001-06-28 | [8 empty] | 2001-06-28 | [48 empty] | Dr. Taberei | MW | [22 empty] | BU087 | GIULESTI-1 | [24 empty] | new08 Pajura-Dr.Taberei |  |  | Theo RADOI | Theo RADOI
Phase_3 | CS | BU164 | BARBU LAUTARU | Bucuresti(x) | BU004 Pajura | Muntenia | 44 27 23.1 | 26 03 56.1 |  |  |  |  | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [17 empty] | DIEKAT |  | @ | 2001-09-01 | 2001-09-30 |  |  | Doru |  |  | 2001-06-28 | [8 empty] | 2001-06-28 | [48 empty] | Dr. Taberei | MW | [22 empty] | BU087 | GIULESTI-1 | [24 empty] | new08 Pajura-Dr.Taberei |  |  | Theo RADOI | Theo RADOI
Phase_3 | CS | BU165 | COPSA MICA | Bucuresti | BU046 Casa Presei | Muntenia | 44 27 56.9 | 26 01 48.8 | [94 empty] | Dr. Taberei | MW | [22 empty] | BU168 | CRANGASI
Phase_3 | CS | BU166 | VALEA ROSIE | Bucuresti | BU032 CNT_2 | Muntenia | 44 24 54.5 | 26 01 55.8 | [94 empty] | Dr. Taberei | MW | [22 empty] | BU032 | CNT2_MSC
Phase_3 | CS | BU167 | VIRTUTII | Bucuresti | BU032 CNT_2 | Muntenia | 44 26 20.6 | 26 02 09.6 | [94 empty] | Dr. Taberei | MW | [22 empty] | BU104 | IULIU MANIU_2
Phase_3 | CS | BU168 | CRANGASI |  | BU046 Casa Presei | Muntenia | 44 27 12.1 | 26 02 47.3 | [94 empty] | Dr. Taberei | MW | [22 empty] | BU046 | CASA PRESEI
Phase_3 | CS | BU170 | BUCURESTII NOI | Bucuresti | BU046 Casa Presei | Muntenia | 44 29 10.8 | 26 02 15.1 |  |  | Str. Pietei, Nr. 36-42, Bl. A8, Sc. B, Ap.45-88. |  |  | M |  | 2/2/2 | [86 empty] | Dr. Taberei | MW | [22 empty] | BU046 | CASA PRESEI
Phase_3 | CS | BU171 | DOMENII | Bucuresti(x) | BU004 Pajura | Muntenia | 44 28 01 | 26 03 21.4 |  |  |  |  | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [17 empty] | DIEKAT |  | @ | 2001-09-01 | 2001-09-30 |  |  | Doru |  |  | 2001-06-28 |  |  |  | 2001-06-29 |  |  |  |  | 2001-06-28 | [48 empty] | Dr. Taberei | MW | [22 empty] | BU043 | ION MIHALACHE | [24 empty] | new09 Pajura-Dr.Taberei
Phase_3 | CS | BU173 | JIULUI | Bucuresti | BU046 Casa Presei | Muntenia | 44 29 00.3 | 26 03 29.9 | [94 empty] | Dr. Taberei | MW | [22 empty] | BU046 | CASA PRESEI
Phase_3 | CS | BU174 | ELIAS | Bucuresti(x) | BU004 Pajura | Muntenia | 44 27 57.9 | 26 04 17.4 |  |  |  |  | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [17 empty] | DIEKAT |  | @ | 2001-09-01 | 2001-09-30 |  |  | Doru |  |  | 2001-06-28 |  |  |  | 2001-06-29 |  |  |  |  | 2001-06-28 | [48 empty] | Dr. Taberei | MW | [22 empty] | BU043 | ION MIHALACHE | [24 empty] | new09 Pajura-Dr.Taberei
Phase_3 | CS | BU175 | REGINA MARIA | Bucuresti(x) | BU001 Palatul Telefoanelor | Muntenia | 44 25 20.4 | 26 05 22.7 |  |  |  |  | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [17 empty] | DIEKAT |  | @ | 2001-09-01 | 2001-09-30 |  |  | Doru |  |  | 2001-06-28 |  |  |  | 2001-07-11 |  |  |  |  | 2001-06-28 | [47 empty] | ML 38 E 1+0 | Dr. Taberei | MW | [22 empty] | BU001 | PALATUL TELEFOANELOR | [61 empty] | 80
Phase_3 | CS | BU177 | SOSEAUA MAGURELE | Bucuresti | BU032 CNT_2 | Muntenia | 44 23 05.3 | 26 02 49.1 | [94 empty] | Dr. Taberei | MW | [22 empty] | BU079 | ALEXANDRIEI
Phase_3 | CS | BU178 | PROGRESULUI | Bucuresti | BU032 CNT_2 | Muntenia | 44 25 29.4 | 26 04 01.5 | [94 empty] | Dr. Taberei | MW | [22 empty] | BU184 | FACULTATEA ELTC
Phase_3 | CS | BU180 | SALAJ | Bucuresti | BU032 CNT_2 | Muntenia | 44 23 45.7 | 26 04 09.5 | [94 empty] | Dr. Taberei | MW | [22 empty] | BU079 | ALEXANDRIEI
Phase_3 | CS | BU182 | FINITEX | Bucuresti | BU032 CNT_2 | Muntenia | 44 24 19.6 | 26 05 08.8 | [94 empty] | Dr. Taberei | MW | [22 empty] | BU073 | NASAUD
Phase_3 | CS | BU183 | DR. FELIX | Bucuresti(x) | BU001 Palatul Telefoanelor | Muntenia | 44 27 05.8 | 26 04 50.4 |  |  |  |  | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [17 empty] | DIEKAT |  | @ | 2001-09-01 | 2001-09-30 |  |  | Doru |  |  | 2001-06-28 |  |  |  | 2001-07-11 |  |  |  |  | 2001-06-28 | [47 empty] | ML 38 E 1+0 | Dr. Taberei | MW | [22 empty] | BU001 | PALATUL TELEFOANELOR | [61 empty] | 81
Phase_3 | CS | BU184 | FACULTATEA ELTC | Bucuresti | BU032 CNT_2 | Muntenia | 44 26 02.2 | 26 03 26.1 | [94 empty] | Dr. Taberei | MW | [22 empty] | BU082 | Bdul. Timisoara
Phase_3 | CS | BU185 | IMGB | Bucuresti(x) | BU076 Popesti-Leordeni | Muntenia | 44 22 04.8 | 26 08 33.5 |  |  |  |  | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [17 empty] | DIEKAT* | [6 empty] | Doru* |  |  | 2001-06-07 |  |  |  | 2001-05-30 | [17 empty] | CTR | [34 empty] | ML 23 E 1+0 | Dr. Taberei | MW | [22 empty] | BU076 | POPESTI LEORDENI | [27 empty] | Petrica BURGHIU | Petrica BURGHIU | [42 empty] | 3 |  |  | missing
Phase_3 | CS | BU186 | CALARASILOR | Bucuresti(x) | BU010 Dacia | Muntenia | 44 25 58.1 | 26 06 40.3 |  |  |  |  | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [17 empty] | DIEKAT |  | @ | 2001-08-15 | 2001-08-30 |  |  | Doru |  |  | 2001-06-07 |  |  |  | 2001-05-30 | [53 empty] | Dr. Taberei | MW | [22 empty] | BU187 | TRAIAN | [27 empty] | Petrica BURGHIU | Petrica BURGHIU | [42 empty] | missing |  |  | missing
Phase_3 | CS | BU187 | TRAIAN | Bucuresti(x) | BU010 Dacia | Muntenia | 44 25 53.1 | 26 07 11.5 |  |  |  |  | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [17 empty] | DIEKAT |  | @ | 2001-08-15 | 2001-08-30 |  |  | Doru |  |  | 2001-06-07 |  |  |  | 2001-05-30 | [53 empty] | Dr. Taberei | MW | [22 empty] | BU055 | HYPERION | [27 empty] | Petrica BURGHIU | Petrica BURGHIU | [42 empty] | missing |  |  | missing
Phase_3 | CS | BU188 | POPA NAN | Bucuresti(x) | BU010 Dacia | Muntenia | 44 26 15.9 | 26 07 25.2 |  |  |  |  | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [17 empty] | DIEKAT* | [6 empty] | Doru* |  |  | 2001-06-07 |  |  |  | 2001-05-30 | [53 empty] | Dr. Taberei | MW | [22 empty] | BU189 | MOSILOR_2 | [27 empty] | Petrica BURGHIU | Petrica BURGHIU | [42 empty] | missing |  |  | missing
Phase_3 | CS | BU189 | MOSILOR_2 | Bucuresti(x) | BU010 Dacia | Muntenia | 44 26 40.7 | 26 07 14.7 |  |  | Calea Mosilor Nr 288, Bl 32, Sc A, Sect 2 |  | 2202 | M/E | C+C+C+ | 2/2/2 | 2202 | [17 empty] | DIEKAT | OK | DIEKAT | 2001-08-01 | 2001-08-20 |  |  | Doru |  |  | 2001-06-07 |  |  |  | 2001-05-30 | [53 empty] | Dr. Taberei | MW | [22 empty] | BU010 | DACIA | [27 empty] | Petrica BURGHIU | Petrica BURGHIU | [42 empty] | missing |  |  | missing
Phase_3 | CS | BU190 | LACUL TEI_3 | Bucuresti(x) | BU009 Baneasa_RTC | Muntenia | 44 27 42.9 | 26 07 07.3 |  |  |  |  | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [17 empty] | DIEKAT* | [6 empty] | Doru* |  |  | 2001-06-07 |  |  |  | 2001-05-30 | [53 empty] | Baneasa | MW | [22 empty] | BU116 | LACUL TEI_2 | [27 empty] | Petrica BURGHIU | Petrica BURGHIU | [42 empty] | missing |  |  | missing
Phase_3 | CS | BU191 | PIPERA | Bucuresti(x) | BU009 Baneasa_RTC | Muntenia | 44 28 48.1 | 26 06 03.2 |  |  |  |  | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [17 empty] | DIEKAT | OK | DIEKAT | 2001-08-01 | 2001-08-20 |  |  | Doru |  |  | 2001-06-07 |  |  |  | 2001-05-30 | [53 empty] | Baneasa | MW | [22 empty] | BU009 | ROMTELECOM BANEASA | [27 empty] | Petrica BURGHIU | Petrica BURGHIU | [42 empty] | missing |  |  | missing
Phase_3 | RS | BU192 | TUNARI | Bucuresti(x) | BU602 Afumati | Muntenia | 44 31 13.9 | 26 11 02.3 |  |  | SC MIKE SRL Tunari, Centura Bucuresti, Bucuresti |  | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | [11 empty] | SVF | OK | SVF | 2001-08-01 | 2001-08-30 |  |  | Doru |  |  | 2001-06-22 | [56 empty] | N/A | Dr. Taberei | RF | [12 empty] | N/A | [9 empty] | N/A | [25 empty] | N/A |  | N/A | N/A | Daniel BICIU | CSFT1802-REMOTE | BU602 | K 739 134 | 87 | 0 | 20 | 23 | 7/8" | K 739 714 | 80 | 0 | 17 | K 739 714 | 240 | 2 | 17 | 19 | 7/8" | 19 | 7/8" | 38
Phase_1 | CS | BU501 | OTOPENI | Road Buc-Bra | BU004 Pajura | Muntenia | 44 33 06.7 | 26 04 11.4 | 44 33 03.3 | 26 04 20.2 | Casa de Cultura Otopeni | Primarie/Mr. Marian Ghenea, 094.913.878 / 791.18.61 | 2202 | M | C+C+C+ | 2/2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | B | 11 | Pilonet 18m | ROOM | SVF | OK | SVF | OK | 2000-02-10 | YesV | OK | DRAGOS | 2000-02-10 | OK |  |  |  | 1999-11-19 | OK |  | OK | 2000-02-07 |  |  |  | N/A | YRO | SVF | 2000-02-10 | OK | OK | 2000-02-11 | 2000-02-18 |  | Yes | Cristian Croitor | 2000-02-28 | 2000-03-23 | 2000-03-23 | 2000-03-27 | OK | K 739 494 | 5 | 0 | 27.5 | K 739 494 | 180 | 2 | 27.5 | N/A | N/A | N/A | N/A |  |  |  |  | No | 35 | 35 | 7/8" | 35 | 35 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A | 140 | ML 23 E 1+0 | Dr. Taberei | MW | 205.5 | 0.6 | 18 | 40 | 23/56 |  | 4x2/8 | 2U-3 |  |  |  | Indoor Comteck | [9 empty] | 1 | BU093 | EPISCOP VULCAN | 25.5 | 0.6 | 32 |  | 23/58 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-10-11 |  |  | 2000-12-18 | 30N02 Pajura-Dr.Taberei |  | OK | DAN | DAN | CSFT1802-DONOR | BU801 | K 739 134 | 200 | 0 | 27 | 30 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | COUPLER | [11 empty] | 98 | Otopeni | Ilfov | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BU502 | BALOTESTI_RTC(OPTIMIZARE) | Road Buc-Bra | BU502 Balotesti_RTC | Muntenia | 26 04'24,1"E | 44 36'36,4"N | 44 36 34.1 | 26 04 22.6 | Oficiul Postal Balotesti | Romtelecom/ | 2202 | M | C+C+C+ | 2/2/2 | 2202 | BX613_Kogalniceanu1 | MAXITE | M | No | 2 | N/A | OK | N/A | N/A | Phase_1 | N/A | N/A | N/A | TN | 40 | New 40m tower | SHELTER | SVF | OK | SVF | OK | OK | YesV | OK | DRAGOS | 1999-12-21 | OK |  |  | 2001-06-14 | OK | OK |  | OK | 1999-12-16 |  |  |  | 2001-06-13 | ICOM | SVF | 2001-06-13 | 2001-06-13 | 2001-06-14 | 2001-06-17 | 2001-06-18 | PAUN | Yes | Alexandru Toma | 2001-06-19 | 2001-06-19 | 2001-06-19 | 2001-06-21 | 2001-07-11 | K 739 494 | 5 | 2 | 38 | K 739 494 | 100 | 2 | 39 | K 739 494 | 185 | 2 | 37 | N/A | N/A | N/A | N/A | N/A | 45 | 45 | 7/8" | 45 | 45 | 7/8" | 45 | 45 | 7/8" | N/A | N/A | N/A | 270 | N/A | Dr. Taberei | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | 2U-3 |  |  |  | Indoor Comteck | 10502 | 2000-04-19 | [7 empty] | 1 | BSC11 | DRUMUL TABEREI |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | 30N01 Balotesti-Dr.Taberei |  | 2001-12-19 | [23 empty] | 2000-02-01 | N/A | N/A | YRO | YRO | 2000-02-05 |  | 2000-02-10 | 2000-03-27 | 36612 | OK | 96 | Balotesti | Ilfov | [7 empty] | Site Near=Insertion Point
Phase_1 | CS | BU503 | TANCABESTI(OPTIMIZARE) | Road Buc-Bra | BU502 Balotesti_RTC | Muntenia | 44 40 09.8 | 26 04 39.2 | 44 40 06.4 | 26 04 37.0 | DRTV Tancabesti 012677003, 013132869 | DRTV/ | 2202 | M | C+C+C+ | 2/2/2 | N/A | Warehouse | MAXITE | M | No | 2 | N/A | OK |  | N/A | Phase_1 |  |  | N/A | TE | 40 | Existing 40m tower | ROOM | SVF | OK | SVF | OK | OK | YesV | OK | DRAGOS | 2000-01-07 | OK |  |  | 2001-06-29 | OK | 1999-11-04 |  | 1999-11-04 | 1999-11-19 |  |  |  | 2001-07-17 | ICOM | [7 empty] | Yes | [6 empty] | K 739 494 | 20 | 0 | 38 | K 739 494 | 185 | 0 | 38 | K 739 494 | 280 | 0 | 38 | N/A | N/A | N/A | N/A | N/A | 55 | 55 | 1 1/4" | 55 | 55 | 1 1/4" | 55 | 55 | 1 1/4" | N/A | N/A | N/A | 330 | ML 23 E 1+0 | Dr. Taberei | MW | 182.7 | 0.6 | 36.5 | 30 | 23/56 |  | 4x2/8 | 2U-3 |  |  |  | Indoor Comteck | [9 empty] | 1 | BU502 | BALOTESTI_RTC(OPTIMIZARE) | 2.7 | 0.6 | 36.5 | 65 | 23/58 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-05-24 |  |  | 2000-12-06 | 30N03 Balotesti-Dr.Taberei |  | 2001-06-19 | MIHAI C. | MIHAI C. | [21 empty] | OK | N/A | N/A | YRO | SVF | 2000-02-08 | Cristian Croitor | 2000-03-24 | 2000-03-24 | 2000-03-27 | OK | 100 | Tancabesti | Ilfov | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BU504 | CIOLPANI | Road Buc-Bra | BU502 Balotesti_RTC | Muntenia | 26 06'51,0"E | 44 43'57,0"N | 44 43 52.4 | 26 06 45.7 | Comuna Ciolpani, Judetul ILFOV | Private/ | MAXITE | M | No | 2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | TN | 32 | New 32m tower | SHELTER | SVF | OK | SVF | OK | 2000-02-10 | YesV | OK | DRAGOS | 2000-02-10 | 2000-01-30 |  |  |  | 1999-11-19 | OK |  | OK | 2000-01-14 |  |  |  | N/A | YRO | SVF | OK | OK | 2000-02-03 | 2000-02-03 | 2000-02-08 |  | Yes | Cristian Croitor | 2000-02-11 | 2000-03-23 | 2000-03-23 | 2000-03-27 | OK | AAU | 200 | 0 | 30 | AAU | 350 | 0 | 30 | N/A | N/A | N/A | N/A |  |  |  |  | MAXITE | 45 | 45 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 90 | ML 23 E 1+0 | Dr. Taberei | MW | 202.1 | 0.6 |  | 35 | 23/58 |  | 4x2/8 | 2U-3 |  |  |  | Indoor Comteck | [10 empty] | BU503 | TANCABESTI | 22.1 | 0.6 |  | 25 | 23/56 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-05-24 |  |  | 2000-05-31 | 30N01 Balotesti-Dr.Taberei |  | OK | DAN | DAN | [32 empty] | 101 | Ciolpani | Ilfov | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BU505 | POTIGRAFU_RTC(OPTIMIZARE) | Road Buc-Bra | BU502 Balotesti_RTC | Muntenia | 44 47 09.2 | 26 05 55.3 | 44 47 04.5 | 26 05 54.1 | ROMTELECOM POTIGRAFU | Romtelecom/PETRU NICOLAE, 044.474251 | 2202 | M | C+C+C+ | 2/2/2 | 2202 | Warehouse | MAXITE | M | No | 2 | N/A | OK |  | N/A | Phase_1 |  |  | N/A | TE | 30 | Existing 30m tower | ROOM | SVF | OK | SVF | OK | OK | YesV | OK | DRAGOS | 2000-01-07 | OK |  |  | 2001-07-12 | OK | 1999-11-04 |  | 1999-11-04 | 1999-11-23 |  |  |  | 2001-07-17 | ICOM | [7 empty] | Yes | [6 empty] | K 739 494 | 170 | 1 | 28 | K 739 494 | 250 | 1 | 28 | K 739 494 | 350 | 1 | 28 | N/A | N/A | N/A | N/A | N/A | 30 | 30 | 7/8" | 30 | 30 | 7/8" | 30 | 30 | 7/8" | N/A | N/A | N/A | 180 | ML 23 E 1+0 | Dr. Taberei | MW | 169.1 | 0.6 | 28 | 40 | 23/56 | N/A | 4x2/8 | 2U-3 |  |  | N/A | Indoor Comteck | [10 empty] | BU504 | CIOLPANI | 349.1 | 0.6 |  | 45 | 23/58 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-05-09 |  |  | 2000-07-05 | 30N01 Balotesti-Dr.Taberei |  | OK | MIHAI C. | MIHAI C. | [21 empty] | OK | N/A | N/A | YRO | SVF | 2000-02-08 | Cristian Croitor | 2000-03-23 | 2000-03-23 | 2000-03-27 | OK | 110 | Potigrafu | Prahova | [7 empty] | 1 |  |  | 1
Phase_2 | CS | BU506 | SNAGOV_RTC | Road Buc-Brasov(1) | BU502 Balotesti_RTC | Muntenia | 44 42 28.7 | 26 10 25.2 | 44 42 28.7 | 26 10 25.2 | Snagov Sat - RTC |  | 2202 | M | C+C+ | 2/2 | 2202 | [6 empty] | 2000-09-04 | N/A | N/A |  |  |  |  | B | 16 | 20m existing tower | Room | IMSAT | OK | PROFIL | 2000-07-26 | 2000-08-16 | YesV | 2000-08-16 | Doru | 2000-08-18 | 2000-08-18 |  |  |  | N/A | 2000-05-06 |  | 2000-07-02 | 2000-07-19 |  |  |  | 2000-08-21 | YRO | DIEKAT | 2000-08-18 | 2000-08-18 | 2000-08-21 | 2000-08-21 | 2000-08-23 |  | Yes | Cristian Croitor | 2000-09-10 | 2000-09-01 | 2000-09-02 | 2000-09-12 | 2000-09-21 | K 739 494 | 0 | 0 | 34 | K 739 494 | 230 | 0 | 33 | N/A | N/A | N/A | N/A |  |  |  |  | N/A | 46 | 46 | 1 1/4" | 46 | 46 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | 184 | ML 23 E 1+0 | Dr. Taberei | MW | 240 | 0.6 | 35/0.6 | 47 | 23/58 |  | 4x2/8 | 2U-3 | [14 empty] | BU503 | TANCABESTI_DRTV | 60 | 0.6 |  |  | 23/56 | [6 empty] | 1 | DIEKAT | 2000-08-21 | 136 | 2000-08-21 | 2000-08-21 | 2000-08-23 | VASILE | OK | 2000-09-01 |  | 2001-09-21 | 2000-10-04 | 30N03 Balotesti-Dr.Taberei |  | 2001-06-19 | Vasile MANEA | Cosmorom | [32 empty] | 92 | Snagov | Ilfov | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_1 | CS | BU601 | VOLUNTARI | Bucharest | BU602 Afumati | Muntenia | 44 29 19.0 | 26 10 21.0 | 44 29 19.0 | 26 10 21.0 | Strada Tudor Vladimirescu no 42, Voluntari, Ilfov | RTC/ | 2202 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | TE | N/A | Existing 40m tower | EXISTSHELT | ISAF | OK | ISAF | OK | 1999-10-18 | YesV | OK | AUREL | 1999-10-18 | 1999-10-22 |  |  |  | OK | 1999-10-04 |  | 1999-10-04 | 1999-10-01 |  |  |  | 99:0002 | ETR | N/A | OK | OK | 1999-11-18 | OK | 1999-11-19 |  | Yes | Cristian Croitor | 1999-12-13 | 2000-05-08 | 2000-05-08 | 2000-05-09 | OK | K 739 494 | 0 | 6 | 0 | K 739 494 | 120 | 8 | 0 | K 739 494 | 240 | 0 | 0 |  |  |  |  | N/A | 50 | 50 | 7/8" | 50 | 50 | 7/8" | 0 | 0 | N/A | N/A | N/A | N/A | 200 | N/A | Dr. Taberei | FO | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | [9 empty] | BU602 | AFUMATI |  | N/A |  |  | N/A | [6 empty] | OK | OK | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 30N01 Voluntari-Dr.Taberei |  | OK | COSMIN | COSMIN | [32 empty] | 85 | Voluntari | Ilfov | [7 empty] | Site Near=Insertion Point
Phase_1 | CS | BU602 | AFUMATI | Bucharest | BU602 Afumati | Muntenia | 44 31 24.0 | 26 14 57.0 | 44 31 24.0 | 26 14 57.0 | ROMTELECOM AFUMATI | RTC/ | 2202 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | TE |  |  | ROOM | SVF | OK | SVF | OK | 1999-10-18 | YesV | OK | DRAGOS | 1999-10-18 | 1999-10-22 |  |  | 2001-06-22 | OK | OK |  | OK | OK |  |  |  | 99:0002 | ETR | N/A | OK | OK | 2000-01-25 | 2000-01-25 | 2000-01-28 |  | Yes | Cristian Croitor | 2000-02-04 | 2000-05-03 | 2000-05-03 | 2000-05-04 | OK | K 739 494 | 0 | 0 | 0 | K 739 494 | 120 | 6 | 0 | K 739 494 | 240 | 0 | 0 |  |  |  |  | N/A | 85 | 85 | 1 1/4" | 85 | 85 | 1 1/4" | 0 | 0 | N/A | N/A | N/A | N/A | 340 | N/A | Dr. Taberei | FO | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | Indoor Comteck | N/A | [9 empty] | BSC11 | DRUMUL TABEREI |  | N/A |  |  | N/A | [6 empty] | OK | OK | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 30N01 Voluntari-Dr.Taberei |  | OK | COSMIN | COSMIN | CSFT1802-DONOR | BU192 | K 739 134 | 267 | 0 | 50 | 55 | 1 1/4" | [24 empty] | 75 | Afumati | Ilfov | [7 empty] | Site Near=Insertion Point
Phase_1 | CS | BU701 | PANTELIMON | Road Buc-Fet-Con | BU009 Baneasa_RTC | Muntenia | 44 27'07,1"N | 26 14'48,6"E | 44 27 07.1 | 26 14 42.5 | Comuna Pantelimon, Bd. Biruintei nr. 98 | Acumulatorul S.A./Director Hosbota Florin, 255.34.80; 255.01.23 | 2101 | M | C+ | 2 | 2101 | [6 empty] | OK |  | N/A |  |  |  | N/A | TN | 50 | New 50m tower | OUTDOOR | DUAL | OK | DUAL | OK | 2000-02-15 | YesV | OK | MUGUREL | 2000-02-15 | OK |  |  |  | 2000-01-18 | OK |  | OK | 2000-01-28 |  |  |  | N/A | YRO | HAR | 2000-02-11 | OK | 2000-02-14 | 2000-02-14 | 2000-02-22 |  | Yes | Theo Radoi | 2000-02-24 | 2000-04-25 | 2000-04-25 | 2000-04-26 | OK | K 739 494 | 90 | 6 | 50 | K 739 494 | 265 | 6 | 50 | N/A | N/A | N/A | N/A |  |  |  |  | K 63 55 8 | 55 | 55 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 110 | ML 15 E 1+0 | Baneasa | MW | 291.3 | 1.2 | 48.5 | 65 | 15/84 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [10 empty] | BU095 | COLENTINA-3 | 111.3 | 1.2 | 26.5 | 45 | 15/89 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-05-24 |  |  | 2000-05-31 | 30N02 Baneasa-Dr.Taberei |  | OK | SORIN UNTARU | SORIN UNTARU | [32 empty] | 71 | Pantelimon | Ilfov | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BU702 | BRANESTI(OPTIMIZARE) | Road Buc-Fet-Con | BU009 Baneasa_RTC | Muntenia | 44 27'16,4"N | 26 22'07,3"E | 44 27 42.1 | 26 19 46.0 | Comuna Branesti - RTC Branesti, Strada Sublocotenent Petre Ionel no 5 | Acumulatorul S.A./Director Hosbota Florin, 255.34.80; 255.01.23 | 2202 | M | C+C+C+ | 2/2/2 | 2202 | CJ193_CORPADEA | MAXITE | M | No | 2 | N/A | 2001-04-26 | N/A | N/A | Phase_1 | N/A | N/A | N/A | TN | 50 | New 50m tower | ROOM |  | OK |  |  |  | YesV |  |  |  |  | 2000-01-14 |  | 2001-05-16 | 1999-12-02 | 1999-12-08 |  | 1999-12-08 | 2000-01-12 |  |  |  | 2001-05-22 | ICOM | VECTOR | 2001-05-23 | 2001-05-23 | 2001-05-25 | 2001-05-26 | 2001-06-01 | VLAD | Yes | Mircea Mihut | 2001-06-01 | 2001-06-01 | 2001-06-01 | 2001-06-05 | 2001-06-19 | K 739 495 | 90 | 0 | 48 | K 739 495 | 265 | 0 | 48 | K 739 495 | 315 | 0 | 48 | N/A | N/A | N/A | N/A | N/A | 70 | 70 | 1 1/4" | 70 | 70 | 1 1/4" | 70 | 70 | 1 1/4" | N/A | N/A | N/A | 420 | ML 23 E 1+0 | Baneasa | MW | 260.8 | 0.6 |  | 60 | 23/58 |  | 4x2/8 | 2U-3 |  |  |  | Indoor Comteck | [10 empty] | BU701 | PANTELIMON | 80.82 | 0.6 |  | 60 | 23/56 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-05-15 |  |  | 2000-05-18 | 30N02 Baneasa-Dr.Taberei |  | OK | SORIN UNTARU | SORIN UNTARU | [22 empty] | N/A | N/A | YRO | HAR | 2000-02-04 | OK | 2000-02-25 | 2000-04-25 | 3-Mai-00 | OK | 70 | Branesti | Ilfov | [7 empty] | 1 |  |  | 1
Phase_2 | CS | BU800 | MALL | Bucuresti(19) | BU800 Mall | Muntenia | [6 empty] | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [7 empty] | N/A | N/A | [13 empty] | YesV | [7 empty] | OK | OK |  | OK | OK |  |  |  | NA | YRO | YRO | 2000-12-02 | 2000-12-03 | 2000-12-04 | 2000-12-05 | 2001-01-08 |  |  | Theo Radoi | 2001-01-15 | 2001-01-12 | 2001-01-12 | 2001-06-22 | 2001-07-11 | [9 empty] | 0 | 0 | 0 | [17 empty] | 0 | N/A | Dr. Taberei | HDSL | N/A | N/A | N/A | N/A | N/A |  | N/A | [15 empty] | BSC11 | DRUMUL TABEREI |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PAUN | OK | N/A |  | N/A | N/A | HDSL+30N01 Titan-Dr.Taberei |  | 2000-12-20 |  | Cosmorom | [42 empty] | Site Near=Insertion Point
Phase_2 | RS | BU801 | REPEATER POD BANEASA | Road Buc-Bra | BU004 Pajura | Muntenia | 44 32 03.98 | 26 03 57.29 | 44 32 03.98 | 26 03 57.29 | Vesta-langa podul Baneasa |  | N/A | N/A | N/A | N/A | N/A | [13 empty] | PN | 25 | 25m existing pylon | [14 empty] | 0 |  |  | N/A | N/A |  |  |  | N/A | YRO | N/A | 2000-11-17 | 2000-11-17 | 2000-11-18 | 2000-11-18 | 2000-11-21 |  |  | Alexandru Toma | 2001-05-29 | 2001-05-29 | 2001-05-29 | 2001-06-29 | 2001-07-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Dr. Taberei | RF | N/A | N/A | N/A | N/A | N/A |  | N/A | [15 empty] | N/A |  |  | N/A |  |  | N/A | [10 empty] | N/A | N/A | N/A | PAUN | OK | N/A |  |  |  | N/A |  | OK |  | Cosmorom | CSFT1802-REMOTE | BU501 | K 739 134 | 10 | 0 | 25 | 30 | 7/8" | K 739 494 | 180 | 0 | 25 | N/A | N/A | N/A | N/A | 30 | 7/8" | N/A | N/A | N/A | [21 empty] | Site Near=Insertion Point
Phase_3 | CS | BU802 | BLOC A | Bucuresti(x) | BU001 Palatul Telefoanelor | Muntenia | 44 26 00.5 | 26 05 51.3 |  |  |  |  | MAXITE | M | 1 | 2 | 2PBC | [17 empty] | SVF* | OK | [5 empty] | Doru* |  |  | 2001-06-13 |  |  |  | 2001-07-11 | [52 empty] | N/A | Dr. Taberei | HDSL | N/A | N/A | N/A | N/A | N/A |  | N/A | [15 empty] | BU001 | PALATUL TELEFOANELOR |  | N/A |  |  | N/A | [10 empty] | N/A | N/A | N/A |  |  | N/A | [6 empty] | Cosmorom | Ion BREZOI | [32 empty] | 80 | [9 empty] | missing |  |  | missing
Phase_2 | CS | BU804 | PUISOR1_RTC | Bucharest(OPTIMIZARE) | BU027 Puisor | Muntenia | 44 25 29.0 | 26 04 43.0 | 44 25 29.0 | 26 04 43.0 | Str.13 Septembrie, sec.5 | Romtelecom/ | MAXITE | M | 1 | 2 | 2PBC | [13 empty] | B |  | T3m | Room | SVF | OK | SVF | 2001-06-01 | 2001-06-02 | Yes |  | Doru |  |  | 2001-05-30 |  |  | N/A | N/A |  | OK | OK |  |  |  | 2001-05-24 | ICOM | SVF | 2001-05-24 | N/A | 2001-05-24 | 2001-05-28 | 2001-05-28 | DINCA |  | Bogdan Bogodai | 2001-05-30 | 2001-05-30 | 2001-05-30 |  |  | AAU | 0 | 0 | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 35 | 35 | 1/2'' | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 70 | N/A | Dr. Taberei | FO | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | Indoor Comteck | N/A | [9 empty] | BSC11 | DRUMUL TABEREI |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | DINCA | OK | N/A |  | N/A | N/A | 30N01 Puisor-Dr.Taberei |  | OK |  | Cosmorom | [33 empty] | Bucuresti | Bucuresti | [7 empty] | Site Near=Insertion Point
Phase_2 | RS | BU805 | REPEATER MARRIOTT Hotel (Parking Area) | Bucharest | BU032 CNT_2 | Muntenia | 44 25 29.0 | 26 04 43.0 | 44 25 29.0 | 26 04 43.0 | In spatele Hotelului Marriott |  | N/A | N/A | N/A | N/A | N/A | [13 empty] | B |  | Mast |  | SVF |  | @ | 2001-08-15 | 2001-08-30 |  |  | Doru |  |  | 2001-05-30 |  |  | N/A | N/A |  | N/A | N/A |  |  |  |  | ICOM | ICOM | 2001-05-29 | N/A | 2001-05-29 | 2001-05-29 | 2001-05-29 | DINCA |  | Bogdan Bogodai | 2001-06-01 | 2001-06-01 | 2001-06-01 | 2001-06-05 | 2001-06-19 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Dr. Taberei | RF | N/A | N/A | N/A | N/A | N/A |  | N/A | [15 empty] | BU081 | COTROCENI |  | N/A |  |  | N/A | [10 empty] | N/A | N/A | N/A | DINCA | OK | N/A | [7 empty] | Cosmorom | CSFT1802-REMOTE | BU081 | K 739 134 | 315 | 0 | 22 | 10 | 1/2" | K 739 494 | 120 | 0 | 30 | N/A | N/A | N/A | N/A | 10 | 1/2" | N/A | N/A | N/A | [6 empty] | ALEX T. | 2001-05-31 | 2001-05-31 | 37042 |  |  | Bucuresti | Bucuresti | [7 empty] | Site Near=Insertion Point
Phase_2 | RS | BU806 | M.J. MAILLIS | Buc-Buftea-Ploiesti | BU114 Mogosoia_RTC | Muntenia | 44 32 25.7 | 25 59 36 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | [17 empty] | SVF | OK | SVF | 2001-06-15 | 2001-06-20 | Yes |  | Doru |  |  | 2001-06-22 | [10 empty] | 2001-06-21 | ICOM | ICOM | 2001-06-20 | N/A | 2001-06-20 | 2001-06-20 | 2001-06-20 | PAUN |  | Mircea Mihut | 2001-06-21 | 2001-06-21 | 2001-06-21 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Dr. Taberei | RF | N/A | N/A | N/A | N/A | N/A |  | N/A | [15 empty] | N/A |  |  | N/A |  |  | N/A | [10 empty] | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A |  | N/A |  | Cosmorom | CSFT1802-REMOTE | BU114 | K 739 134 | [5 empty] | K 739 494 | 180 |  |  | N/A | N/A | N/A | N/A |  |  | N/A | N/A | N/A | [21 empty] | Site Near=Insertion Point
|  | BU808 | Smardan, nr15, et 2 |  | AA CONSTRUCT SRL 0216104548
Phase_2 | CS | BU999 | Site_Scoala | Bucuresti(19) | BU999 Site Scoala | Muntenia | 44 25 18.6 | 26 01 54.2 | 44 25 18.6 | 26 01 54.2 | CNT2 | RTC/ | 2202 | M | C+C+ | 2/2 | 2202 | [6 empty] | 2000-10-09 | Yes | N/A |  |  |  |  | B |  |  | Room | [5 empty] | YesV | [7 empty] | OK | OK |  | OK | 1999-09-15 |  |  |  | 2000-08-22 | YRO | SVF | 2000-08-22 | 2000-08-15 | 2000-08-22 | 2000-08-24 | 2000-08-24 |  |  | Alexandru Bucur | 2000-09-10 | 2000-09-01 | 2000-09-01 | 2000-10-04 | 2000-11-14 | K 739 494 | 0 | 0 | 23 | K 739 494 | 120 | 0 | 23 | N/A | N/A | N/A | N/A |  |  |  |  | N/A | 32 | 32 | 7/8" | 30 | 30 | 7/8" | N/A | N/A | N/A |  |  |  | 124 | N/A | Dr. Taberei | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | 2U-3 |  |  |  | TMR 9202 | [9 empty] | 1 | BSC11 | DRUMUL TABEREI |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | VASILE | OK | N/A |  | N/A | N/A |  |  | OK | Phase 1 | Cosmorom | [32 empty] | 88 | Bucuresti | Bucuresti | [7 empty] | Site Near=Insertion Point
|  | BU901 | Financial Plazza | [7 empty] | Magazinul Victoria (BANCOREX); Florin Acon-092321225, Adrian Toma-094258836
|  | BU902 | Financial Plazza
|  | BU903 | Financial Plazza
|  | BU904 | Financial Plazza
|  | BU905 | Financial Plazza
|  | BU906 | Financial Plazza
Phase_2 |  | BU907 | Egnatia Bank | [7 empty] | Str. General Budisteanu, Nr. 26C; Dan Amariei-096/678846, Dan Nache-092/623777, Poarta-3158108
Phase_1 | CS | BV001 | ROMTELECOM CTA | Brasov | BV001 Brasov_CTA | Transilvania | 45 38 38.0 | 25 35 30.0 | 45 38 38.0 | 25 35 30.0 | Bdul. Eroilor nr. 23, Romtelecom | RTC/Romtelecom Brasov | 2202 | M/E | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | B | 15 | P20m | ROOM | TRANSDATA | OK | TRANSDATA | OK | OK | YesV | OK | DORU | OK | OK |  |  |  | OK | 1999-10-11 |  | 1999-10-11 | 1999-10-11 |  |  |  | N/A | YRO | YRO | OK | OK | 1999-12-03 | OK | 1999-12-10 |  | Yes | Alexandru Bucur | 2000-01-27 | 2000-01-30 | 2000-01-30 | 2000-03-14 | OK | K 739 494 | 345 | 7 | 30 | K 739 494 | 120 | 0 | 30 | K 739 494 | 240 | 0 | 30 |  |  |  |  | N/A | 43 | 45 | 7/8" | 42 | 43 | 7/8" | 43 | 43 | 7/8" | N/A | N/A | N/A | 259 | N/A | Brasov | FO | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | TMR 9202 | 70001 | 2001-05-07 | [8 empty] | BSC12 | BSC BRASOV | N/A | N/A |  |  | N/A | [6 empty] | OK | OK | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 30N01 Conectare locala |  | OK | MIHAI C. | MIHAI C. | [32 empty] | 583 | Brasov | Brasov | [7 empty] | Site Near=Insertion Point
Phase_1 | CS | BV002 | ASTRA CTA | Brasov | BV002 Astra_CTA | Transilvania | 45 38 56.4 | 25 37 11.2 | 45 38 55.7 | 25 37 10.6 | Langa Spitalul Judetean Brasov | RTC/Romtelecom Brasov | 2202 | M/E | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | B | 15 | P12m | ROOM | TRANSDATA | OK | TRANSDATA | OK | OK | YesV | OK | DORU | OK | OK |  |  |  | OK | OK |  | OK | 1999-11-15 |  |  |  | N/A | YRO | YRO | OK | OK | 1999-12-03 | OK | 1999-12-10 |  | Yes | Alexandru Bucur | 2000-01-28 | 2000-01-28 | 2000-01-28 | 2000-03-14 | OK | K 739 494 | 0 | 0 | 30 | K 739 494 | 120 | 0 | 30 | K 739 494 | 240 | 0 | 30 |  |  |  |  | N/A | 26 | 26 | 7/8" | 26 | 26 | 7/8" | 25 | 25 | 7/8" | N/A | N/A | N/A | 154 | N/A | Brasov | FO | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | Indoor Comteck | 70002 | Phase_1 | [7 empty] | 1 | BSC12 | BSC BRASOV |  | N/A |  |  | N/A | [6 empty] | OK | OK | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 30N01 Astra-Brasov |  | OK | DAN | DAN | [32 empty] | 578 | Brasov | Brasov | [7 empty] | Site Near=Insertion Point
Phase_1 | CS | BV003 | MIHAI VITEAZUL CTA | Brasov | BV003 Mihai Viteazul_CTA | Transilvania | 45 39 48.0 | 25 36 01.0 | 45 39 32.6 | 25 36 00.9 | Strada Tebea | RTC/Romtelecom Brasov | 2202 | M/E | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | B | 15 | P15m | ROOM | TRANSDATA | OK | TRANSDATA | OK | OK | YesV | OK | DORU | OK | OK |  |  |  | OK | OK |  | OK | 1999-11-15 |  |  |  | N/A | YRO | YRO | OK | OK | 1999-12-03 | OK | 1999-12-10 |  | Yes | Alexandru Bucur | 2000-01-29 | 2000-01-29 | 2000-01-29 | 2000-03-14 | OK | K 739 494 | 0 | 0 | 30 | K 739 494 | 120 | 0 | 30 | K 739 494 | 240 | 4 | 30 |  |  |  |  | N/A | 36 | 33 | 7/8" | 32 | 34 | 7/8" | 36 | 33 | 7/8" | N/A | N/A | N/A | 204 | N/A | Brasov | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | 4U-1 |  |  |  | Indoor Comteck | 70003 | Phase_1 | [8 empty] | BSC12 | BSC BRASOV | N/A | N/A |  |  | N/A | [6 empty] | OK | OK | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 30N01 Mihai Viteazul-Brasov |  | OK | DAN | DAN | [32 empty] | 552 | Brasov | Brasov | [7 empty] | Site Near=Insertion Point
Phase_1 | CS | BV010 | PROIECT | Brasov | BV001 Brasov_CTA | Transilvania | 45 39 01.1 | 25 36 13.3 | 45 39 01.6 | 25 36 16.3 | Proiect Brasov SA, Strada Iuliu Maniu no 43 | Public/Terta Maria 068/415880 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | 2000-06-27 |  |  |  | 28 | B | 28 | T4m+T4m | OUTDOOR | TRANSDATA | OK | TRANSDATA | OK | 2000-02-04 | YesV | OK | DORU | 2000-02-04 | 2000-01-18 |  |  |  | 1999-10-28 | 1999-11-22 |  | 1999-11-22 | 1999-12-09 |  |  |  | N/A | YRO | ISAF | 2000-02-04 | OK | OK | 2000-02-14 | 2000-02-17 |  | Yes | Cristian Croitor | 2000-02-19 | 2000-02-08 | 2000-03-15 | 2000-03-15 | OK | K 739 494 | 0 | 0 | 30 | K 739 494 | 120 | 0 | 30 | K 739 494 | 240 | 0 | 30 |  |  |  |  | N/A | 22 | 22 | 7/8" | 22 | 22 | 7/8" | 22 | 22 | 7/8" | N/A | N/A | N/A | 132 | ML 38 E 1+0 | Brasov | MW | 234 | 0.3 | 28.5 |  | 38/18 |  | 4x2/8 | 4U-1 |  |  |  | RBS | [10 empty] | BV001 | ROMTELECOM CTA | 54 | 0.3 | 28.5 |  | 38/14 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-05-11 |  |  | 2000-05-31 | 30N02 conectare locala |  | OK | DAN | DAN | [32 empty] | 565 | Brasov | Brasov | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BV011 | TREATRUL_LIRIC | Brasov | BV003 Mihai Viteazul_CTA | Transilvania | 45 39 15.7 | 25 35 32.0 | 45 39 14.3 | 25 35 22.7 | Strada Bisericii Romane | Private/Ion MITOIUI 068/414490 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | 2000-06-27 |  |  |  |  | B | 12 | P9m | OUTDOOR | TRANSDATA | OK | TRANSDATA | OK | 2000-02-26 | YesV | OK | DORU | 2000-02-26 | 2000-02-10 |  |  |  | 1999-10-28 | OK |  | OK | 1999-12-13 |  |  |  | N/A | YRO | SVF | 2000-02-11 | OK | OK | 2000-02-12 | 2000-02-16 |  | Yes | Cristian Croitor | 2000-02-29 | 2000-03-14 | 2000-03-14 | 2000-03-15 | OK | K 739 494 | 0 | 0 | 19.5 | K 739 494 | 120 | 0 | 19.5 | K 739 494 | 240 | 0 | 19.5 |  |  |  |  | N/A | 45 | 45 | 7/8" | 48 | 48 | 7/8" | 20 | 20 | 7/8" | N/A | N/A | N/A | 226 |  | Brasov | MW | 340 | 0.3 | 18.5 |  | 38/14 |  | 4x2/8 | 4U-1 |  |  |  | RBS | [10 empty] | BV013 | MOARA | 160 | 0.3 | 24.5 |  | 38/18 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-05-09 |  |  | 2000-05-31 | 30N02 Mihai Viteazul-Brasov |  | OK | DAN | DAN | [32 empty] | 559 | Brasov | Brasov | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BV012 | FELDIOARA | Brasov | BV003 Mihai Viteazul_CTA | Transilvania | 45 39 32.8 | 25 34 16.2 | 45 39 48.0 | 25 34 09.5 | Pilon Drumuri Nationale, Strada Lanurilor no. 9, cartier Feldioara | Public/Drumuri Nationale, Costea Viorel, 068/163344 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | 2000-06-27 |  |  |  | N/A | TE | 36 | Tower_36 | OUTDOOR | TRANSDATA | OK | TRANSDATA | OK | 2000-02-04 | YesV | OK | DORU | 2000-02-04 | 2000-01-18 |  |  |  | 1999-10-28 | 1999-11-22 |  | 1999-11-22 | 1999-12-09 |  |  |  | N/A | YRO | SVF | 2000-02-11 | OK | OK | 2000-02-12 | 2000-02-16 |  | Yes | Cristian Croitor | 2000-02-19 | 2000-02-17 | 2000-03-14 | 2000-03-15 | OK | K 739 494 | 350 | 0 | 34 | K 739 494 | 120 | 4 | 34 | K 739 494 | 240 | 0 | 34 |  |  |  |  | N/A | 40 | 40 | 7/8" | 40 | 40 | 7/8" | 40 | 40 | 7/8" | N/A | N/A | N/A | 240 | ML 38 E 1+0 | Brasov | MW | 101 | 0.3 | 32.5 |  | 38/14 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [10 empty] | BV013 | MOARA | 282 | 0.3 | 24.5 |  | 38/18 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-05-11 |  |  | 2000-05-31 | 30N01 Mihai Viteazul-Brasov |  | OK | DAN | DAN | [32 empty] | 540 | Brasov | Brasov | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BV013 | MOARA | Brasov | BV003 Mihai Viteazul_CTA | Transilvania | 45 39 37.2 | 25 35 05.9 | 45 39 39.8 | 25 35 07.5 | Morarit si Panificatie POSTAVARUL SA, Strada Avram Iancu 98 | Private/Horia ISTUDIR, 068/162842 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | 2000-06-27 |  |  |  | 25 | B | 30 | C3m+C3m+C3m | OUTDOOR | TRANSDATA | OK | TRANSDATA | OK | OK | YesV | OK | DORU | 2000-01-31 | OK |  |  |  | 1999-10-28 | 1999-11-22 |  | 1999-11-22 | 1999-12-13 |  |  |  | N/A | YRO | ISAF | 2000-02-04 | OK | OK | 2000-02-14 | 2000-02-17 |  | Yes | Cristian Croitor | 2000-02-19 | 2000-02-17 | 2000-03-14 | 2000-03-15 | OK | K 739 494 | 0 | 0 | 26 | K 739 494 | 120 | 0 | 26 | K 739 494 | 240 | 0 | 26 |  |  |  |  | N/A | 30 | 30 | 7/8" | 30 | 30 | 7/8" | 20 | 20 | 7/8" | N/A | N/A | N/A | 160 |  | Brasov | MW | 100 | 0.3 | 24.5 | 30 | 38/18 | N/A | 4x2/8 | 4U-1 |  |  | N/A | Indoor Comteck | [9 empty] | 0 | BV003 | MIHAI VITEAZUL CTA | 280 | 0.3 | 28.5 | 45 | 38/14 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-05-11 |  |  | 2000-05-31 | 30N02 Mihai Viteazul-Brasov |  | OK | DAN | DAN | [32 empty] | 551 | Brasov | Brasov | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BV014 | GARA | Brasov | BV001 Brasov_CTA | Transilvania | 45 39 26.4 | 25 36 51.5 | 45 39 32.8 | 25 36 42.4 | Blvd. Victoriei no 2, bloc 40 | Private/MUSA Nicolae | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | 2000-06-27 |  |  |  | 26.7 | B | 26.7 | T3m+T3m | OUTDOOR | FIBEC | OK | FIBEC | OK | 1999-12-16 | YesV | OK | DORU | 1999-12-16 | 1999-12-14 |  |  |  | 1999-10-28 | 1999-11-10 |  | 1999-11-10 | 1999-11-16 |  |  |  | N/A | YRO | YRO | 2000-01-13 | OK | 2000-01-16 | 2000-01-17 | 2000-01-20 |  | Yes | Cristian Croitor | 2000-02-20 | 2000-02-20 | 2000-03-14 | 2000-03-15 | OK | K 739 494 | 10 | 0 | 28.4 | K 739 494 | 120 | 6 | 28.4 | K 739 494 | 240 | 7 | 28.4 |  |  |  |  | N/A | 42 | 42 | 7/8" | 42 | 42 | 7/8" | 32 | 32 | 7/8" | N/A | N/A | N/A | 232 | ML 38 E 1+0 | Brasov | MW | 210 | 0.3 | 27 |  | 38/14 |  | 4x2/8 | 4U-1 |  |  |  | RBS | [10 empty] | BV010 | PROIECT | 30 | 0.3 | 30.4 |  | 38/18 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-05-11 |  |  | 2000-05-31 | 30N02 conectare locala |  | OK | DAN | DAN | [32 empty] | 565 | Brasov | Brasov | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BV015 | ZIZINULUI | Brasov | BV002 Astra_CTA | Transilvania | 45 39 09.5 | 25 37 50.5 | 45 38 59.9 | 25 37 39.6 | Strada Zizinului no. 71, Bl. 104, Scara G | Private/Banu Eugen, 068/134924 | 2202 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | B | 34.3 | T3m+T3m+T3m | ROOM | FIBEC | OK | FIBEC | OK | 1999-12-16 | YesV | OK | DORU | 1999-12-16 | 1999-12-14 |  |  |  | 1999-10-28 | 1999-11-10 |  | 1999-11-10 | 1999-11-17 |  |  |  | N/A | YRO | YRO | 2000-01-13 | OK | OK | 2000-01-31 | 2000-02-02 |  | Yes | Cristian Croitor | 2000-02-20 | 2000-02-12 | 2000-03-15 | 2000-03-15 | OK | K 739 494 | 0 | 0 | 36 | K 739 494 | 110 | 0 | 36 | K 739 494 | 240 | 6 | 36 |  |  |  |  | N/A | 20 | 20 | 7/8" | 15 | 15 | 7/8" | 28 | 28 | 7/8" | N/A | N/A | N/A | 126 |  | Brasov | MW | 260 | 0.3 |  |  | 38/14 |  | 4X2/8 | 4U-1 |  |  |  | Indoor Comteck | [9 empty] | 1 | BV002 | ASTRA CTA | 80 | 0.3 |  |  | 38/18 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-05-10 |  |  | 2000-05-31 | 30N01 Astra-Brasov |  | OK | DAN | DAN | [32 empty] | 576 | Brasov | Brasov | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BV016 | SATURN | Brasov | BV002 Astra_CTA | Transilvania | 45 38 39.8 | 25 37 51.3 | 45 38 41.2 | 25 38 00.3 | Strada Saturn no 19, Bloc 66 Scara A | Private/Crisan Ion, 068/122256 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | 2000-06-27 |  |  |  | 25 | B | 25 | T3m+T3m+T3m | OUTDOOR | FIBEC | OK | FIBEC | OK | 1999-12-16 | YesV | OK | DORU | 1999-12-16 | 1999-12-14 |  |  |  | 1999-10-28 | 1999-11-10 |  | 1999-11-10 | 1999-11-17 |  |  |  | N/A | YRO | YRO | 2000-01-13 | OK | 2000-01-16 | 2000-01-17 | 2000-01-20 |  | Yes | Alexandru Bucur | 2000-01-28 | 2000-01-28 | 2000-01-28 | 2000-03-14 | OK | K 739 494 | 0 | 0 | 26.5 | K 739 494 | 120 | 0 | 26.5 | K 739 494 | 240 | 0 | 26.5 |  |  |  |  | N/A | 14 | 14 | 7/8" | 74 | 74 | 1 1/4" | 20 | 20 | 7/8" | N/A | N/A | N/A | 216 |  | Brasov | MW | 294 | 0.3 |  |  | 38/14 | YES | YES |  |  |  |  | RBS | [9 empty] | 1 | BV002 | ASTRA CTA | 114 | 0.3 |  |  | 38/18 | [6 empty] | OK/60* | OK/TRYLON | OK | OK/858 | OK/5/21/00 | OK | OK | OK | OK | 2000-05-23 | Dublare suplimentara ACC:20.06.01 | 2000-05-23 | 2001-05-31 | 30N02 Astra-Brasov |  | OK | DAN | DAN | [32 empty] | 585 | Brasov | Brasov | [6 empty] | 1 | 1 |  | 1 | 1
Phase_1 | CS | BV017 | CARPATILOR | Brasov | BV002 Astra_CTA | Transilvania | 45 38 25.2 | 25 37 15.7 | 45 38 16.2 | 25 37 11.0 | Strada Carpatilor no. 59A | Private/ | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | 2000-06-27 |  |  |  | 26 | B | 29 | T3m+T3m+T3m | OUTDOOR | FIBEC | OK | FIBEC | OK | 1999-12-16 | YesV | OK | DORU | 1999-12-16 | 1999-12-14 |  |  |  | 1999-10-28 | 1999-11-10 |  | 1999-11-10 | 1999-11-16 |  |  |  | N/A | YRO | YRO | 2000-01-13 | OK | 2000-01-16 | 2000-01-17 | 2000-01-20 |  | Yes | Alexandru Bucur | 2000-01-30 | 2000-01-30 | 2000-01-30 | 2000-03-14 | OK | K 739 494 | 0 | 4 | 30.7 | K 739 494 | 120 | 4 | 30.7 | K 739 494 | 240 | 0 | 30.7 |  |  |  |  | N/A | 16 | 16 | 7/8" | 11 | 11 | 7/8" | 20 | 20 | 7/8" | N/A | N/A | N/A | 94 |  | Brasov | MW | 80 | 0.3 |  |  | 38/14 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [9 empty] | 1 | BV020 | CALEA_BUCURESTI | 260 | 0.3 |  |  | 38/18 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-05-11 |  |  | 2000-05-31 | 30N03 Astra-Saturn |  | OK | DAN | DAN | [32 empty] | 588 | Brasov | Brasov | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BV018 | VALEA CETATII | Brasov | BV002 Astra_CTA | Transilvania | 45 38 09.2 | 25 36 37.7 | 45 38 18.5 | 25 36 43.7 | Strada Eftimie Murgu no 1, Bl. 5 | Private/Cazacu Ion, 068/310901 | 2202 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | B | 29.6 | C4m+C4m | ROOM | FIBEC | OK | FIBEC | OK | 1999-12-16 | YesV | OK | DORU | 1999-12-16 | 1999-12-14 |  |  |  | 1999-10-28 | 1999-11-10 |  | 1999-11-10 | 1999-11-16 |  |  |  | N/A | YRO | YRO | 2000-01-13 | OK | OK | 2000-01-31 | 2000-02-01 |  | Yes | Cristian Croitor | 2000-02-20 | 2000-02-15 | 2000-03-15 | 2000-03-15 | OK | K 739 494 | 0 | 0 | 31.5 | K 739 494 | 120 | 0 | 31.5 | K 739 494 | 240 | 0 | 31.5 |  |  |  |  | N/A | 35 | 35 | 7/8" | 35 | 35 | 7/8" | 16 | 16 | 7/8" | N/A | N/A | N/A | 172 |  | Brasov | MW | 97 | 0.3 |  |  | 38/18 |  | 4x2/8 | 4U-1 |  |  |  | Indoor Comteck | [9 empty] | 1 | BV017 | CARPATILOR | 260 | 0.3 |  |  | 38/14 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-05-09 |  |  | 2000-05-31 | 30N03 Astra-Saturn |  | OK | DAN | DAN | [32 empty] | 613 | Brasov | Brasov | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BV019 | INTERNAT | Brasov | BV001 Brasov_CTA | Transilvania | 45 38 03.1 | 25 34 54.0 | 45 38 01.6 | 25 34 49.6 | Strada Democratiei no. 24 bis | Public/Viorica IORDACHESCU, 068/142861 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | 2000-06-27 |  |  |  | 10 | B | 10 | P10m | OUTDOOR | FIBEC | OK | FIBEC | OK | OK | YesV | OK | DORU | 2000-01-07 | OK |  |  |  | 1999-10-28 | 1999-11-10 |  | 1999-11-10 | 1999-11-24 |  |  |  | N/A | YRO | YRO | 2000-01-13 | OK | OK | OK | 2000-02-02 |  | Yes | Cristian Croitor | 2000-02-20 | 2000-02-14 | 2000-03-15 | 2000-03-15 | OK | K 739 494 | 0 | 4 | 18 | K 739 494 | 120 | 0 | 18 | K 739 494 | 240 | 0 | 18 |  |  |  |  | N/A | 27 | 27 | 7/8" | 27 | 27 | 7/8" | 27 | 27 | 7/8" | N/A | N/A | N/A | 162 | ML 23 E 1+0 | Brasov | MW | 45 | 0.6 |  |  | 23/56 |  | 4X2/8 | 4U-1 |  |  |  | RBS | [10 empty] | BV010 | PROIECT | 255.4 | 0.6 |  |  | 23/58 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-05-11 |  |  | 2000-05-31 | 30N01 Conectare locala |  | OK | DAN | DAN | [32 empty] | 620 | Brasov | Brasov | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BV020 | CALEA_BUCURESTI | Brasov | BV002 Astra_CTA | Transilvania | 45 38 18.8 | 25 37 58.7 | 45 38 20.5 | 25 37 40.2 | Calea Bucuresti no. 92 | Private/Cornel MOLDOVAN, 068/181830 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | 2000-06-27 |  |  |  | 32 | B | 32 | T3m+T3m+T3m | OUTDOOR | FIBEC | OK | FIBEC | OK | 1999-12-16 | YesV | OK | DORU | 1999-12-16 | 1999-12-14 |  |  |  | 1999-10-28 | 1999-11-10 |  | 1999-11-10 | 1999-11-16 |  |  |  | N/A | YRO | YRO | 2000-01-13 | OK | 2000-01-16 | 2000-01-17 | 2000-01-20 |  | Yes | Alexandru Bucur | 2000-01-29 | 2000-01-29 | 2000-01-29 | 2000-03-14 | OK | K 739 494 | 350 | 6 | 33.7 | K 739 494 | 120 | 0 | 33.7 | K 739 494 | 240 | 6 | 33.7 |  |  |  |  | N/A | 6 | 7 | 7/8" | 33 | 33 | 7/8" | 21 | 22 | 7/8" | N/A | N/A | N/A | 122 |  | Brasov | MW | 35 | 0.3 |  |  | 38/18 |  | 4x2/8 | 4U-1 |  |  |  | RBS | [10 empty] | BV016 | SATURN | 215 | 0.3 |  |  | 38/14 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-05-11 |  |  | 2000-05-31 | 30N02 Astra-Brasov |  | OK | DAN | DAN | [32 empty] | 594 | Brasov | Brasov | [7 empty] | 1 |  |  | 1
Phase_2 | CS | BV025 | PREJMER | Road Bv-Miercurea C(9+3) | BV088 Sf. Gheorghe_RTC | Transilvania | 45 43 20 | 25 47 39.99 | 45 43 20 | 25 47 39.99 | Strada Mare nr.499 | Romtelecom - Ploiesti/Dl. Dorobantu, tel:482 700, 482 999 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-07-11 | N/A | N/A |  |  |  | 0 | TE | 30 | Existing 30m tower | N/A | IMSAT | OK | PROFIL | 2000-06-05 | 2000-06-10 | YesV | 2000-06-15 | Dragos | 2000-10-18 | 2000-06-19 |  |  |  | 2000-05-05 | 2000-05-10 |  | 2000-05-16 | 2000-06-05 |  |  |  | 2000-07-11 | YRO | SVF | 2000-07-10 | 2000-07-10 | 2000-07-12 | 2000-07-13 | 2000-07-20 |  | Yes | Mihai Constantin | 2000-09-28 | 2000-10-20 | 2000-10-20 | 2000-11-09 | 2000-11-29 | K 739 494 | 0 | 0 | 29 | K 739 494 | 120 | 0 | 29 | K 739 494 | 260 | 0 | 29 |  |  |  |  | N/A | 43 | 43 | 7/8" | 43 | 43 | 7/8" | 43 | 43 | 7/8" | N/A | N/A | N/A | 258 | ML 23 E 1+0 | Brasov | MW | 23 | 0.6 | 29.6 | 30 | 23/56 |  |  | 2U-3 |  |  |  | RBS | [9 empty] | 1 | BV026 | OZUNU | 203 | 0.6 | 40.3 | 28 | 23/58 | [6 empty] | 1/7 | SVF | 11.07/00-30.08.00 | 48//161 | 10.07.00-31.08.00 | 2000-07-13 | 2000-07-20 | PITURCESCU | OK | 2000-10-20 |  | 2000-11-20 | 2000-12-18 | 30N01 Sf. Gheorghe-Brasov |  | OK | Bogdan CRAIU | Cosmorom | [32 empty] | 516 | Prejmer | Brasov | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BV026 | OZUNU | Road Bv-Miercurea C(9+3) | BV088 Sf. Gheorghe_RTC | Transilvania | 45 47 52.44 | 25 50 16 | 45 47 54 | 25 50 34 | Siloz Cereale, Ozunu, jud. Covasna | Complex Agrosem Brasov/Neamtu Elena, tel: 068/417 335 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-08-16 | Yes | N/A |  |  |  | 37 | S | 50 | C2m+C3m | N/A | SVF | OK | SVF | 2000-08-10 | 2000-08-22 | YesV | 2000-08-25 | Dragos | 2000-09-04 | 2000-08-30 |  |  |  | 2000-05-05 | 2000-05-10 |  | 2000-07-17 | 2000-08-16 |  |  |  | 2000-08-30 | YRO | SVF | 2000-08-30 | 2000-08-30 | 2000-08-31 | 2000-08-31 | 2000-09-04 |  | Yes | Ionut Grigorescu | 2000-09-28 | 2000-09-22 | 2000-09-22 | 2000-11-09 | 2000-11-29 | K 739 494 | 50 | 0 | 53 | K 739 494 | 224 | 0 | 53.3 | K 739 494 | 338 | 0 | 53 |  |  |  |  | N/A | 22 | 22 | 7/8" | 22 | 22 | 7/8" | 30 | 30 | 7/8" | N/A | N/A | N/A | 168 | ML 23 E 1+0 | Brasov | MW | 326 | 1.2 | 40 | 29 | 23/58 |  |  | 2U-3 |  |  |  | RBS | [9 empty] | 1 | BV027 | SF.GHEORGHE_1 | 146 | 1.2 | 42 | 22 | 23/56 | [6 empty] | 2001-07-01 | SVF | 31.08.00-11.07/00 | 161/42 | 31.08.00-07.07.00 | 2000-08-31 | 2000-09-04 | PAUN | OK | 2000-09-22 |  | 2000-10-04 | 2000-12-06 | 30N01 Sf. Gheorghe-Brasov |  | OK | Bogdan CRAIU | Cosmorom | [32 empty] | 510 | Ozunu | Covasna | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BV027 | SF.GHEORGHE_1 | Road Bv-Miercurea C(9+3) | BV088 Sf. Gheorghe_RTC | Transilvania | 45 51 41 | 25 46 53 | 45 51 40 | 25 46 52 | Str. V.Goldis nr.5 Bl.2 | Asociatie de proprietari/Nyaguj Alexandru - Str. V.Goldis nr.5 Bl.2 tel:316 069 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-07-06 | 2000-07-07 | N/A |  |  |  | 35 | B | 38 | T4,5m+T4,5m | N/A | SVF | OK | SVF | 2000-06-22 | 2000-06-29 | YesV | 2000-06-30 | Dragos | 2000-07-03 | 2000-07-26 |  |  |  | 2000-05-05 | 2000-05-10 |  | 2000-05-19 | 2000-06-30 |  |  |  | 2000-07-11 | YRO | SVF | 2000-07-05 | 2000-07-05 | 2000-07-12 | 2000-07-13 | 2000-07-19 |  | Yes | Cristian Croitor | 2000-09-28 | 2000-09-06 | 2000-09-06 | 2000-09-12 | 2000-09-21 | K 739 494 | 10 | 0 | 41 | K 739 494 | 130 | 0 | 41 | K 739 494 | 250 | 0 | 41 |  |  |  |  | N/A | 26 | 26 | 7/8" | 26 | 26 | 7/8" | 21 | 21 | 7/8" | N/A | N/A | N/A | 146 | ML 38 E 1+0 | Brasov | MW | 80 | 0.3 | 42 | 27 | 38/13 |  |  | 2U-3 |  |  |  | RBS | [9 empty] | 1 | BV088 | SF.GHEORGHE_RTC | 260 | 0.3 | 30 | 50 | 38/17 | [6 empty] | 2001-01-02 | SVF | 11.07.00-18.07.00 | 42/62 | 7.07.00-18.0700 | 2000-07-13 | 2000-07-19 | PITURCESCU | OK | 2000-09-06 |  | 2000-09-21 | 2000-09-25 | 30N02 Sf. Gheorghe-Brasov |  | OK | Bogdan CRAIU | Cosmorom | [32 empty] | 556 | Sf.Gheorghe | Covasna | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BV028 | SF.GHEORGHE_2 | Road Bv-Miercurea C(9+3) | BV088 Sf. Gheorghe_RTC | Transilvania | 45 51 38.98 | 25 48 25.01 | 45 51 48.4 | 025 48 24.5 | Aleea Harniciei 12 Bl.31 Sc. A1 Ap.39 | Asociatie de locatari/Aga Ion - Presedinte de scara, tel:324 325 | 2202 | M/E | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-08-09 | N/A | N/A |  |  |  | 36 | B | 37.5 | C4.5m+C4.5m | Room | IMSAT | OK | PROFIL | 2000-06-05 | 2000-06-19 | YesV | 2000-06-19 | Dragos | 2000-08-03 | 2000-12-08 |  |  |  | 2000-05-08 | 2000-05-10 |  | 2000-06-06 | 2000-06-06 |  |  |  | 2000-08-07 | YRO | MIC | 2000-08-07 | 2000-08-03 | 2000-08-08 | 2000-08-08 | 2000-08-14 |  | Yes | Cristian Croitor | 2000-09-28 | 2000-09-06 | 2000-09-06 | 2000-10-04 | 2000-11-20 | K 739 494 | 10 | 0 | 38.5 | K 739 494 | 180 | 0 | 38.5 | K 739 494 | 275 | 0 | 38.5 |  |  |  |  | N/A | 40 | 40 | 7/8'' | 35 | 35 | 7/8'' | 35 | 35 | 7/8'' | N/A | N/A | N/A | 220 | ML 38 E 1+0 | Brasov | MW | 263.4 | 0.3 | 38.5 | 67 | 38/13 |  |  | 2U-3 |  |  |  | N/A | [9 empty] | 1 | BV088 | SF.GHEORGHE_RTC | 74 | 0.3 | 30 | 50 | 38/17 | [6 empty] | 2001-03-02 | U_ELECTRONICA/SVF | 7.08.00-18.07.00 | 106/62 | 20.07.00-18.07.00 | 2000-08-08 | 2000-08-14 | PITURCESCU | OK | 2000-09-06 |  | 2000-09-25 | 2000-10-03 | 30N02 Sf. Gheorghe-Brasov |  | OK | Bogdan CRAIU | Cosmorom | [32 empty] | 524 | Sf.Gheorghe | Harghita | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BV029 | BODOC | Road Bv-Miercurea C(9+3) | BV087 Tusnad_RTC | Transilvania | 45 57 38.02 | 25 51 27.65 | 45 57 36.02 | 25 51 28.8 | Str.Apa minerala nr.317 | Lunguly Bela-Str.Apa Minerala nr.317/Lunguly Bela-Str.Apa Minerala nr.317 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-08-08 | N/A | N/A |  |  |  |  | TN | 50 | 40m new tower | N/A | IMSAT | OK | TEHNOROB | 2000-06-07 | 2000-07-31 | YesV | 2000-08-01 | Dragos | 2000-08-03 | 2000-08-09 |  |  |  | 2000-05-08 | 2000-05-10 |  | 2000-05-16 | 2000-07-06 |  |  |  | 2000-08-07 | YRO | MIC | 2000-08-07 | 2000-08-03 | 2000-08-08 | 2000-08-09 | 2000-08-14 |  | Yes | Ionut Grigorescu | 2000-09-28 | 2000-09-28 | 2000-09-28 | 2000-12-05 | 2001-01-08 | K 739 494 | 197 | 0 | 39 | K 739 494 | 346 | 0 | 48 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 56 | 56 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 112 | ML 23 E 1+0 | Brasov | MW | 341 | 0.6 | 39.5 | 58 | 23/56 |  |  | 2U-3 |  |  |  | RBS | [10 empty] | BV030 | MALNAS | 161 | 0.6 | 48 | 67 | 23/58 | [6 empty] | 3 | U_ELECTRONICA | 2000-08-07 | 105 | 2000-08-07 | 2000-08-09 | 2000-08-14 | PITURCESCU | OK | 2000-09-28 | PENDING |  |  | 30N01 Tusnad-Brasov |  | OK | Bogdan CRAIU | Petrica BURGHIU | [32 empty] | 558 | Bodoc | Covasna | [7 empty] | 2 |  |  | 2
Phase_2 | CS | BV030 | MALNAS | Road Bv-Miercurea C(9+3) | BV087 Tusnad_RTC | Transilvania | 46 02 25.01 | 25 49 02.02 | 46 02 26.1 | 25 49 05.3 | Extravilan sat Micfalau | Primarie Malnas, sat Micfalau, te: 067/365 282/Mr Balog Gabor Csaba, tel: 094/ 510 086 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-08-09 | N/A | N/A |  |  |  |  | TN | 50 | 50m new tower | N/A | SVF | OK | SVF | 2000-06-15 | 2000-07-15 | YesV | 2000-08-01 | Dragos | 2000-08-04 | 2000-08-09 |  |  |  | 2000-05-05 | 2000-05-10 |  | 2000-05-16 | 2000-06-19 |  |  |  | 2000-08-07 | YRO | MIC | 2000-08-07 | 2000-08-03 | 2000-08-08 | 2000-08-09 | 2000-08-14 |  | Yes | Ionut Grigorescu | 2000-09-28 | 2000-09-27 | 2000-09-27 | 2000-12-05 | 2001-01-08 | K 739 494 | 20 | 0 | 49 | K 739 494 | 170 | 0 | 49 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 70 | 70 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 140 | ML 15 E 1+0 | Brasov | MW | 15 | 0.6 | 48 | 67 | 15/89 |  |  | 2U-3 |  |  |  | RBS | [10 empty] | BV031 | BAILE TUSNAD_DRTV |  | 0.6 | 18 | 27 | 15/84 | [6 empty] | 3 | ELECTOTRADE | 2000-08-07 | 105 | 2000-08-09 | 2000-08-09 | 2000-08-14 | PITURCESCU | OK | 2000-09-28 | PENDING |  |  | 30N01 Tusnad-Brasov |  | OK | Bogdan CRAIU | Cosmorom | [32 empty] | 676 | Micfalau | Brasov | [7 empty] | 2 |  |  | 2
Phase_2 | CS | BV031 | BAILE TUSNAD_DRTV | Road Bv-Miercurea C(9+3) | BV087 Tusnad_RTC | Transilvania | 46 08 59 | 25 51 39 | 46 09 06 | 25 52 00 | Baile Tusnad | D.R.T.V. Bucuresti/ | MAXITE | M | 1 | 2 | 2PBC | [6 empty] | 2000-07-18 | N/A | N/A |  |  |  |  | TN | 22 | Existing tower | N/A | SVF | OK | SVF | 2000-05-25 | 2000-06-05 | YesV | 2000-06-15 | Dragos | 2000-07-03 | 2000-07-04 |  |  |  | 2000-05-05 | 2000-05-10 |  | 2000-05-16 | 2000-05-30 |  |  |  | 2000-07-11 | YRO | SVF | 2000-07-04 | 2000-07-04 | 2000-07-12 | 2000-07-13 | 2000-07-18 |  | Yes | Ionut Grigorescu | 2000-09-28 | 2000-09-27 | 2000-09-27 | 2000-11-29 | 2000-12-05 | AAU | 30 | 0 | 19.5 | AAU | 190 | 0 | 19.5 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 28 | 28 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 56 | ML 38 E 1+0 | Brasov | MW | 269 | 0.3 | 18.5 | 27 | 38/13 |  |  | 4U-1 |  |  |  | TMR 9000 | [7 empty] | N/A/N/A |  | 1 | BV087 | TUSNAD_RTC | 88 | 0.3 | 8 | 20 | 38/17 | [6 empty] | 1/2 | SVF | 11.07.00-18.07.00 | 43/61 | 7.07.00-18.0700 | 2000-07-13 | 2000-07-18 | PITURCESCU | OK | 2000-09-28 |  | 2000-12-13 | 2001-01-08 | 30N01 Tusnad-Brasov |  | OK | Bogdan CRAIU | Petrica BURGHIU | [32 empty] | 692 | Baile Tusnad | Harghita | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BV032 | COZMENI | Road Bv-Miercurea C(9+3) | BV087 Tusnad_RTC | Transilvania | 46 13 49.81 | 25 56 39.71 | 46 13 47.8 | 25 56 45.2 | Societatea Agricola "Nyerges" | Societatea Agricola "Nyerges"/Vitos laslo, tel: 094/385 496 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-08-16 | N/A | N/A |  |  |  |  | TN | 50 | 50m new tower | N/A | IMSAT | OK | SVF | 2000-08-10 | 2000-08-31 | YesV | 2000-09-05 | Dragos | 2000-09-06 | 2000-09-13 |  |  |  | 2000-05-08 | 2000-05-10 |  | 2000-05-16 | 2000-07-31 |  |  |  | 2000-08-30 | YRO | SVF | 2000-08-30 | 2000-08-30 | 2000-08-31 | 2000-08-31 | 2000-09-04 |  | Yes | Ionut Grigorescu | 2000-09-28 | 2000-09-28 | 2000-09-28 | 2001-01-08 | 2001-02-08 | K 739 494 | 216 | 0 | 48.25 | K 739 494 | 319 | 0 | 48.25 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 57 | 57 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 114 | ML 15 E 1+0 | Brasov | MW | 214 | 0.6 | 50 | 54 | 15/89 |  |  | 2U-3 |  |  |  | RBS | [9 empty] | 1 | BV031 | BAILE TUSNAD_DRTV | 34 | 0.6 | 18 | 27 | 15/84 | [6 empty] | 7/1 | SVF | 31.08.00-11.07/00 | 160/43 | 31.08.00-07.07.00 | 2000-08-31 | 2000-09-04 | PAUN | OK | 2000-09-28 |  | 2000-10-04 | 2000-12-06 | 30N01 Tusnad-Brasov |  | OK | Bogdan CRAIU | COSMOROM | [32 empty] | 674 | Cozmeni | Harghita | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BV034 | MIERCUREA CIUC | Road Bv-Miercurea C(9+3) | BV086 Miercurea Ciuc_RTC | Transilvania | 46 21 20.02 | 25 48 44.99 | 46 21 21 | 25 48 41 | Miercurea Ciuc, B-dul. Fratiei nr.18,jud. Harghita | Asociatie de proprietari/Szegeti Iuliu - Str. Fratiei nr.18 ap.18, tel: 066/172 437 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-07-06 | 2000-07-07 | N/A |  |  |  | 33.5 | B | 36.3 | T4.5m+T4.5m | N/A | SVF | OK | SVF | 2000-06-16 | 2000-06-29 | YesV | 2000-06-30 | Dragos | 2000-07-03 | 2000-07-26 |  |  |  | 2000-05-15 | 2000-05-10 |  | 2000-05-16 | 2000-07-04 |  |  |  | 2000-07-11 | YRO | SVF | 2000-07-05 | 2000-07-05 | 2000-07-12 | 2000-07-13 | 2000-07-18 |  | Yes | Cristian Croitor | 2000-09-28 | 2000-09-07 | 2000-09-07 | 2000-09-21 | 2000-09-25 | K 739 494 | 20 | 0 | 39.5 | K 739 494 | 180 | 0 | 39.5 | K 739 494 | 300 | 0 | 39.5 |  |  |  |  | N/A | 20 | 20 | 7/8" | 21 | 21 | 7/8" | 21 | 21 | 7/8" | N/A | N/A | N/A | 124 | ML 38 E 1+1* | Brasov | MW | 301 | 0.3 | 41 | 20 | 38/13 |  |  | 2U-3 |  |  |  | RBS | [9 empty] | 1 | BV086 | MIERCUREA CIUC_RTC | 121 | 0.3 | 19.5 | 25 | 38/17 | [6 empty] | 1/2 | SVF | 11.07.00-18.07.00 | 44/60 | 7.07.00-18.0700 | 2000-07-13 | 2000-07-18 | PITURCESCU | OK | 2000-09-07 |  | 2000-09-21 | 2000-09-25 | 30N01 M. Ciuc-Brasov |  | OK | Bogdan CRAIU | Cosmorom | [32 empty] | 659 | Miercurea Ciuc | Harghita | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BV036 | CODLEA_RTC | Road Bv-Sibiu(11) | BV036 Codlea_RTC | Transilvania | 45 41 37.01 | 25 26 32 | 45 41 37.01 | 25 26 32 | Romtelecom Codlea | RTC Codlea, tel:068/ 931 111/ 068/251149 | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-07-11 | N/A | N/A |  |  |  | 8 | TN | 25 | 12m pylonet | Room | DIEKAT | OK | DIEKAT | 2000-06-12 | 2000-06-26 | YesV | 2000-06-27 | Mugur | 2000-06-29 | 2000-06-29 |  |  |  | N/A | 2000-05-06 |  | 2000-06-20 | 2000-06-22 |  |  |  | 2000-08-21 | YRO | DIEKAT | 2000-08-21 | 2000-08-21 | 2000-08-22 | 2000-08-23 | 2000-08-27 |  | Yes | Mihai Constantin | 2000-12-15 | 2000-11-28 | 2000-11-28 | 2001-02-08 | 2001-04-10 | K 739 494 | 20 | 0 | 26 | K 739 494 | 120 | 0 | 26 | K 739 494 | 240 | 0 | 26 |  |  |  |  | N/A | 32 | 32 | 7/8" | 32 | 32 | 7/8" | 32 | 32 | 7/8" | N/A | N/A | N/A | 192 | N/A | Brasov | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | [12 empty] | 15/Yes |  |  | BSC12 | BSC BRASOV |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PITURCESCU | OK | N/A |  | N/A | N/A | 30N01 Codlea-Brasov |  | OK | Mihai CONSTANTIN | COSMOROM | [32 empty] | 559 | Codlea | Brasov | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | BV037 | FERMA | Road Bv-Sibiu(11) | BV041 Fagaras_RTC | Transilvania | 45 44 49.6 | 25 25 31 | 45 44 47.3 | 25 24 59.4 | E68 Brasov-Sibiu, borna Km. 191, intre Codlea si Vladeni Km10 | Primaria Codlea/Dl. Primar Dragu - 068/ 251 202 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-10-20 | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | DIEKAT | OK | DIEKAT | 2000-10-12 | 2000-11-11 | YesV | 2000-11-28 | Mugur | 2000-11-15 | 2000-12-07 |  |  |  |  | 2000-07-03 |  | 2000-09-18 | 2000-10-12 |  |  |  | 2000-11-10 | ICOM | DIEKAT | 2000-11-10 | 2000-11-10 | 2000-11-13 | 2000-11-13 | 2000-11-14 |  | Yes | Alexandru Toma | 2001-03-07 | 2001-03-07 | 2001-03-07 |  |  | K 739 494 | 120 | 0 | 49 | K 739 494 | 300 | 0 | 49 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 62 | 62 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 124 | ML 23 E 1+0 | Brasov | MW | 273 | 1.2 | 47 | 70 | 23/56 |  |  | 4U-1 |  |  |  | RBS | [9 empty] | 1 | BV038 | HOMOROD | 93 | 1.2 | 41.5 | 58 | 23/58 | [6 empty] | 18 | TRYLON | 2000-11-30 | 418 | 2000-11-30 | 2000-11-30 | 2000-12-10 | IVAN | OK | 2001-03-07 |  | 2001-03-21 | 2001-04-06 | 30N02 Fagaras-Brasov |  | OK | Mihai CONSTANTIN | Cosmorom | [32 empty] | 579 | Codlea | Brasov | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BV038 | HOMOROD | Road Bv-Sibiu(11) | BV041 Fagaras_RTC | Transilvania | 45 45 04.37 | 25 17 33.12 | 45 45 06.2 | 25 17 32.9 | Extravilan Dealul Cioi, tarla 48, parcela 1649 | Finghis Gheorghe - sat Persani nr.46, com. Sinca/Finghis Gheorghe - sat Persani nr.46, com. Sinca | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-12-11 | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | DIEKAT | OK | DIEKAT | 2000-10-27 | 2000-11-28 | YesV | 2000-11-28 | Mugur | 2000-11-27 | 2000-12-07 |  |  |  |  | 2000-05-05 |  | 2000-10-23 | 2000-11-09 |  |  |  | 2000-11-30 | ICOM | TRY | 2000-11-23 | 2000-11-23 | 2000-11-30 | 2000-11-28 | 2000-12-04 |  | Yes | Alexandru Toma | 2001-03-07 | 2001-03-07 | 2001-03-07 |  |  | K 739 494 | 70 | 0 | 49 | K 739 494 | 300 | 0 | 49 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 62 | 62 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 124 | ML 15 E 1+0 | Brasov | MW | 299 | 0.6 | 47 | 65 | 15/84 |  |  | 4U-1 |  |  |  | RBS | [9 empty] | 1 | BV039 | PERSANI | 119 | 0.6 |  | 65 | 15/89 | [6 empty] | 18 | TRYLON | 2000-11-30 | 419 | 2000-11-30 | 2000-11-30 | 2000-12-10 | IVAN | OK | 2001-03-07 |  | 2001-03-21 | 2001-04-06 | 30N02 Fagaras-Brasov |  | OK | Mihai CONSTANTIN | Cosmorom | [32 empty] | 600 | Homorod | Brasov | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BV039 | PERSANI | Road Bv-Sibiu(11) | BV041 Fagaras_RTC | Transilvania | 45 47 16 | 25 11 50.9 | 45 46 43.5 | 25 11 53.01 | Teren extravilan Persani, Dealul Slatinii | Borosnov Alecu Ioan - Persani 176, Com. Sinca Veche/Alecu Gheorghe (fiu) - 094/ 516 281 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-10-20 | N/A | N/A |  |  |  |  | TN | 50 | Tower | N/A | IMSAT | OK | ROMPSAR | 2000-09-15 | 2000-11-09 | YesV | 2000-11-28 | Mugur | 2001-01-19 | 2000-12-07 |  |  |  |  | 2000-05-05 |  | 2000-07-18 | 2000-08-11 |  |  |  | 2000-11-10 | ICOM | DIEKAT | 2000-11-10 | 2000-11-10 | 2000-11-13 | 2000-11-14 | 2000-11-15 |  | Yes | Mihai Constantin | 2001-02-10 | 2001-02-10 | 2001-02-10 |  |  | K 739 494 | 130 | 0 | 48.5 | K 739 494 | 310 | 0 | 48.5 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 65 | 65 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 130 | ML 15 E 1+1 | Brasov | MW | 289 | 1.2 | 47.5 | 61 | 15/89 | YES | 4x2/8 | 4U-1+2U-3 |  |  |  | N/A | [10 empty] | BV040 | MANDRA | 109 | 1.2 | 47.5 | 60 | 15/84 | [6 empty] | 12 | DIEKAT | 2000-11-10 | 282/417 | 17.11.00-30.11.00 | 2000-11-21 | 2000-11-24 | IVAN | OK | 2001-02-10 | PENDING |  |  | 30N02 Fagaras-Brasov |  | OK | Mihai CONSTANTIN | Cosmorom | [32 empty] | 520 | Persani | Brasov | [6 empty] | 1 | 2 |  | 1 | 2
Phase_2 | CS | BV040 | MANDRA | Road Bv-Sibiu(11) | BV041 Fagaras_RTC | Transilvania | 45 49 18.95 | 25 03 47.54 | 45 49 19.2 | 25 03 51.0 | Deal la intrarea dinspre Brasov in Mindra, langa targul de animale | Zara Ioan - Mindra 241, 068/ 404 820/ | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-07-25 | N/A | N/A |  |  |  |  | TN | 50 | Tower | N/A | IMSAT | OK | ROMPSAR | 2000-09-15 | 2000-11-13 | YesV | Respins | Mugur | 2001-01-19 |  |  |  |  | 2000-06-21 | 2000-05-05 |  | 2000-07-18 | 2000-08-11 |  |  |  | 2000-11-10 | ICOM | DIEKAT | 2000-11-10 | 2000-11-10 | 2000-11-13 | 2000-11-13 | 2000-11-15 |  | Yes | Bogdan Bogodai | 2001-02-01 | 2001-02-01 | 2001-02-01 |  |  | K 739 494 | 80 | 0 | 48.5 | K 739 494 | 280 | 0 | 48.5 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+1 | Brasov | MW | 290 | 0.6 | 47.5 | 60 | 15/84 | YES | 4x2/8 | 4U-1 |  |  |  | RBS | [10 empty] | BV041 | FAGARAS | 110 | 0.6 | 28 | 35 | 15/89 | [6 empty] | 3* | DIEKAT | 2000-12-08 | 283/416 | 21.11.00-30.11.00 | 2000-11-21 | 2000-11-24 | IVAN | OK | 2001-02-10 |  | 2001-02-27 | 2001-03-02 | 30N02 Fagaras-Brasov |  | OK | Mihai CONSTANTIN | Cosmorom | [32 empty] | 444 | Mindra | Sibiu | [5 empty] | 1 | 1 | 2 | 1 | 1 | 2
Phase_2 | CS | BV041 | FAGARAS | Road Bv-Sibiu(11) | BV041 Fagaras_RTC | Transilvania | 45 50 39.01 | 24 58 05.99 | 45 50 38 | 24 58 11.7 | Cladire Romtelecom/Posta Fagaras | Romtelecom/Dragne Marin - sef centru zona, tel: 068/ 21 44 11 | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-09-19 | N/A | N/A |  |  |  | 20 | B | 20 | 12m pylonet | Room | IMSAT | OK | ROMPSAR | 2000-08-10 | 2000-09-08 | YesV | 2000-09-19 | Mugur | 2000-09-12 | 2000-09-22 |  |  |  | 2000-05-15 | 2000-05-06 |  | 2000-07-06 | 2000-07-31 |  |  |  | 2000-09-15 | YRO | ISAF | 2000-09-15 | 2000-09-15 | 2000-09-19 | 2000-09-22 | 2000-09-25 |  | Yes | Mihai Constantin | 2000-12-15 | 2000-12-08 | 2000-12-08 |  |  | K 739 494 | 0 | 0 | 29 | K 739 494 | 120 | 0 | 29 | K 739 494 | 240 | 0 | 29 |  |  |  |  | N/A | 33 | 33 | 7/8" | 33 | 33 | 7/8" | 33 | 33 | 7/8" | N/A | N/A | N/A | 198 | N/A | Brasov | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | 4U-1+2U-3 |  |  |  | Indoor Comteck | 70041 | [6 empty] | 20/Indoor |  | 1 | BSC12 | BSC BRASOV |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | IVAN | OK | N/A |  | N/A | N/A | 30N01 Fagaras-Brasov |  | OK | Mihai CONSTANTIN | Cosmorom | [32 empty] | 433 | Fagaras | Sibiu | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | BV042 | VOILA | Road Bv-Sibiu(11) | BV041 Fagaras_RTC | Transilvania | 45 49 06 | 26 50 38.9 | 45 49 25.3 | 24 52 47.4 | DRTV Voila | DRTV Voila/ | 2202 | M | C+C+ | 2/2 | 2202 | [6 empty] | 2000-07-26 | N/A | N/A |  |  |  |  | TN | 50 | Existing 48.5m tower | Room | SVF | OK | ISAF | 2000-06-20 | 2000-07-05 | YesV | 2000-07-14 | Mugur | 2000-08-02 | 2000-07-20 |  |  |  | 2000-05-15 | 2000-05-06 |  | 2000-05-23 | 2000-06-07 |  |  |  | 2000-08-08 | YRO | SVF | 2000-07-21 | 2000-08-02 | 2000-08-10 | 2000-08-12 | 2000-08-15 |  | Yes | Mihai Constantin | 2000-12-15 | 2000-12-10 | 2000-12-10 |  |  | K 739 494 | 80 | 0 | 48.5 | K 739 494 | 260 | 0 | 48.5 | N/A | N/A | N/A | N/A |  |  |  |  | N/A | 66 | 66 | 1 1/4" | 66 | 66 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | 264 | ML 23 E 1+0 | Brasov | MW | 72 | 0.6 | 48 | 62 | 23/56 |  |  | 2U-3 | [13 empty] | 1 | BV041 | FAGARAS | 253 | 0.6 | 28 | 35 | 23/58 | [6 empty] | 2 | ISAF | 2000-09-15 | 203 | 2000-09-15 | 2000-08-12 | 2000-08-15 | PITURCESCU | OK | 2000-12-08 |  | 2001-02-05 | 2001-02-06 | 30N01 Fagaras-Brasov |  | OK | Mihai CONSTANTIN | Cosmorom | [32 empty] | 425 | Voila | Brasov | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BV044 | CORBI | Road Bv-Sibiu(11) | BV046 Avrig_RTC | Transilvania | 45 46 16.64 | 24 41 41.07 | 45 47 15.5 | 24 41 56.9 | DN 1 Km 256+850 | /Irimie Gheorghita - viceprimar | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-07-26 | N/A | N/A |  |  |  |  | TN | 50 | New 50m tower | N/A | SVF | OK | VECTOR | 2000-06-10 | 2000-07-10 | YesV | 2000-07-14 | Mugur | 2000-08-04 | 2000-07-20 |  |  |  | 2000-05-15 | 2000-05-06 |  | 2000-05-24 | 2000-06-27 |  |  |  | 2000-08-08 | YRO | SVF | 2000-08-08 | 2000-08-02 | 2000-08-10 | 2000-08-12 | 2000-08-15 |  | Yes | Mihai Constantin | 2001-02-10 | 2001-02-10 | 2001-02-10 | 2001-03-25 | 2001-04-10 | K 739 494 | 80 | 0 | 49.5 | K 739 494 | 270 | 0 | 49.5 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 70 | 70 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 140 | ML 15 E 1+0 | Brasov | MW | 255 | 1.2 | 47.5 | 68 | 15/84 |  |  | 2U-3 |  |  |  | RBS | [9 empty] | 1 | BV045 | SCOREIU | 75.29 | 1.2 | 47.5 | 67 | 15/89 | [6 empty] | 2 | ISAF | 2000-09-15 | 204 | 2000-09-15 | 2000-08-12 | 2000-08-15 | PITURCESCU | OK | 2001-02-10 |  | 2001-02-27 | 2001-03-02 | 30N01 Avrig-Brasov |  | OK | Mihai CONSTANTIN | COSMOROM | [32 empty] | 417 | Corbi | Brasov | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BV045 | SCOREIU | Road Bv-Sibiu(11) | BV046 Avrig_RTC | Transilvania | 45 45 36.04 | 24 31 43.02 | 45 45 35.3 | 24 32 25.2 | DN 1 Km 271+450, intravilan Scoreiu | Pampu Constantin, loc. Scoreiu nr. 350/ | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-09-19 | N/A | N/A |  |  |  |  | TN | 50 | New 50m tower | N/A | SVF | OK | SETRACO | 2000-06-20 | 2000-08-04 | YesV | 2000-08-08 | Mugur | 2000-09-12 | 2000-08-14 |  |  |  | 2000-05-15 | 2000-05-06 |  | 2000-05-24 | 2000-06-27 |  |  |  | 2000-09-15 | YRO | ISAF | 2000-08-22 | 2000-08-22 | 2000-09-19 | 2000-09-20 | 2000-09-21 |  | Yes | Mihai Constantin | 2000-12-15 | 2000-12-11 | 2000-12-11 |  |  | K 739 494 | 80 | 0 | 49.5 | K 739 494 | 270 | 0 | 49.5 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 70 | 70 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 140 | ML 15 E 1+0 | Brasov | MW | 254 | 1.2 | 47.5 | 67 | 15/89 |  |  | 2U-3 |  |  |  | RBS | [9 empty] | 1 | BV046 | AVRIG_RTC | 75 | 1.2 | 46.2 | 72 | 15/84 | [6 empty] | 11 | SVF | 2000-10-24 | 284 | 2000-10-24 | 2000-09-16 | 2000-09-20 | DINCA | OK | 2001-02-10 |  | 2001-01-22 | 2001-01-22 | 30N01 Avrig-Brasov |  | OK | Mihai CONSTANTIN | Cosmorom | [32 empty] | 439 | Scoreiu | Sibiu | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BV046 | AVRIG_RTC | Road Bv-Sibiu(11) | BV046 Avrig_RTC | Transilvania | 45 43 42 | 24 22 31 | 45 43 35.9 | 24 22 28.8 | RTc Avrig Str. Gheorghe Lazar nr.6 | Dir.ge. Hanea - RTc Sibiu, 069/211 033/404 192/Popovici Gheorghe - RTC Avrig Str.b Gh. Lazar nr.6 | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-10-20 | N/A | N/A |  |  |  | 17 | TN | 45 |  | Room | ISAF | OK | SVF | 2000-09-01 | 2000-10-15 | YesV | 2000-11-13 | Mugur | 2000-10-24 | 2000-12-07 |  |  |  | 2000-05-12 | 2000-05-06 |  | 2000-07-11 | 2000-09-07 |  |  |  | 2000-10-23 | ICOM | SVF | 2000-10-23 | 2000-10-23 | 2000-10-24 | 2000-11-02 | 2000-11-09 |  | Yes | Mihai Constantin | 2000-12-15 | 2000-11-29 | 2000-11-29 | 2001-01-16 | 2001-01-26 | K 739 494 | 0 | 0 | 44.4 | K 739 494 | 120 | #N/A | 44.4 | K 739 494 | 240 | 0 | 44.4 |  |  |  |  | N/A | 70 | 70 | 1 1/4" | 70 | 70 | 1 1/4" | 70 | 70 | 1 1/4" | N/A | N/A | N/A | 420 | N/A | Brasov | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | 4U-1 |  |  |  |  | 71146 | [8 empty] | 1 | BSC12 | BSC BRASOV | N/A | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | IVAN | OK | N/A |  | N/A | N/A | 30N01 Avrig-Brasov |  | OK | Mihai CONSTANTIN | #N/A | [32 empty] | 386 | Avrig | Sibiu | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | BV047 | VESTEM | Road Bv-Sibiu(11) | BV049 Dumbrava_RTC | Transilvania | 45 43 11.17 | 24 14 18.75 | 45 43 26.9 | 24 13 22.6 | Com. Vestem, Sos. E15A | Baciu Viorel - Com. Vestem nr.65, tel: 069/565 026/D-nul primar Tatu Ion - Com. Vestem nr.193, tel: 069/565 107, 094/640 860 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-08-09 | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | ISAF | OK | ISAF | 2000-06-05 | 2000-07-09 | YesV | 2001-01-26 | Mugur | 2000-08-04 |  |  |  |  | 2000-05-12 | 2000-05-06 |  | 2000-05-16 | 2000-06-05 |  |  |  | 2000-08-08 | YRO | SVF | 2000-08-08 | 2000-08-02 | 2000-08-10 | 2000-08-12 | 2000-08-15 |  | Yes | Mihai Constantin | 2000-12-15 | 2000-12-16 | 2000-12-16 | 2001-01-22 | 2001-01-26 | K 739 494 | 100 | 0 | 50 | K 739 494 | 320 | 0 | 50 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 60 | ML 23 E 1+0 | Brasov | MW | 319 | 0.6 | 49 | 62 | 23/56 |  |  | 2U-3 |  |  |  | RBS | [9 empty] | 1 | BV049 | DUMBRAVA_RTC | 138 | 0.6 | 37 | 21.5 | 23/58 | [6 empty] | 13/ | DIEKAT/ | 17.11.00- | 302 | 2000-11-17 | 2000-11-21 | 2000-11-24 | PITURCESCU | OK | 2000-12-11 |  | 2001-01-22 | 2001-01-22 | HDSL+30N02 Dumbrava-Balcescu-Brasov |  | OK | Mihai CONSTANTIN | Cosmorom | [32 empty] | 394 | Com. Vestem | Sibiu | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BV048 | NICOLAE_BALCESCU | Sibiu(9) | BV048 Balcescu_RTC | Transilvania | 45 47 37.28 | 24 09 00.12 | 45 47 41.2 | 24 09 02 | Nicolae Balcescu nr.13, Sibiu | Romtelecom Sibiu - Calea Dumbravii nr.17, tel: 069/404 196/Bicer Adrian - statia frecventa, str. Oncesti bl.17 ap.31, sibiu, tel: 069/404 143 | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-06-28 | N/A | N/A |  |  |  |  | B | 19 | T3.5m+T3.5m | Room | IMSAT | OK | IMSAT | 2000-05-28 | 2000-06-08 | YesV | 2000-06-12 | Relu | 2000-06-16 | 2000-06-16 |  |  |  | 2000-05-17 | 2000-05-06 |  | 2000-05-26 | 2000-06-29 |  |  |  | NA | YRO | NA | 2000-06-29 | 2000-06-30 | 2000-07-03 | 2000-07-03 | 2000-07-06 |  | Yes | Theo Radoi | 2000-09-10 | 2000-09-05 | 2000-09-05 | 2000-09-18 | 2000-10-04 | K 739 494 | 0 | 0 | 22.5 | K 739 494 | 120 | 0 | 24 | K 739 494 | 240 | 0 | 22.5 |  |  |  |  | N/A | 26 | 26 | 7/8" | 28 | 28 | 7/8" | 26 | 26 | 7/8" | N/A | N/A | N/A | 160 | N/A | Brasov | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | 2U-3 |  |  |  | Indoor Comteck | 70048 | Livrat/Instalat | [7 empty] | 1 | BSC12 | BSC BRASOV |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | DINCA | OK | N/A |  | N/A | N/A | 30N01 Nicolae Balcescu-Brasov |  | OK | Mihai CONSTANTIN | Cosmorom | [32 empty] | 439 | Sibiu | Sibiu | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | BV049 | DUMBRAVA_RTC | Sibiu(9) | BV049 Dumbrava_RTC | Transilvania | 45 46 56.98 | 24 09 02.91 | 45 47 14 | 24 08 58.6 | Calea Dumbravii nr.17 | Romtelecom - Directia de Telecomunicatii Sibiu, Calea Dumbravii nr.17, tel: 069/ 211 033 - secretariat/Ing. Cufteac - Sef serviciu comercial/ D-na. Manzat - Dir. Comercial, tel: 069/ 404 333 sau 069/ 404 380 | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-06-28 | N/A | N/A |  |  |  |  | B | 21 | 16m existing tower | Room | IMSAT | OK | IMSAT | 2000-06-07 | 2000-06-19 | YesV | 2000-06-19 | Relu | 2000-07-06 | 2000-07-11 |  |  |  | N/A | 2000-05-06 |  | 2000-06-05 | 2000-06-22 |  |  |  | NA | YRO | NA | 2000-07-03 | 2000-06-30 | 2000-07-26 | 2000-07-26 | 2000-07-31 |  | Yes | Theo Radoi | 2000-09-10 | 2000-09-06 | 2000-09-06 | 2000-10-04 | 2000-10-13 | K 739 494 | 0 | 0 | 37 | K 739 494 | 120 | 0 | 37 | K 739 494 | 240 | 0 | 37 |  |  |  |  | N/A | 20 | 20 | 7/8" | 20 | 20 | 7/8" | 20 | 20 | 7/8" | N/A | N/A | N/A | 120 | N/A | Brasov | HDSL | N/A | N/A | N/A | N/A | N/A |  | N/A | 4U-1(TMR9202) |  |  |  | TMR 9202 | 70049 | [8 empty] | 1 | BSC12 | BSC BRASOV |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | DINCA | OK | N/A |  | N/A | N/A | HDSL+30N03 Dumbrava-Balcescu-Brasov |  | OK | Mihai CONSTANTIN | Cosmorom | [32 empty] | 442 | Sibiu | Sibiu | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | BV051 | COMPA | Sibiu(9) | BV049 Dumbrava_RTC | Transilvania | 45 47 17.99 | 24 08 11.67 | 45 47 02.1 | 24 08 15 | Bd. Victorie nr.42-47 | COMPA SA - Pazgu Ion, 069/ 212 820, 069/ 210 589/Nicoara Octavian | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-10-11 | Yes | N/A |  |  |  | 16.3 | B | 16.3 | Pylonet 12 m | N/A | IMSAT | OK | IMSAT | 2000-09-10 | 2000-10-02 | YesV | 2000-10-12 | Relu | 2000-10-18 | 2000-10-13 |  |  |  |  | 2000-05-06 |  | 2000-08-23 | 2000-09-11 |  |  |  | 2000-10-03 | YRO | ISAF | 2000-10-03 | 2000-10-03 | 2000-10-04 | 2000-10-06 | 2000-10-11 |  | Yes | Mihai Constantin | 2000-10-18 | 2000-10-20 | 2000-10-20 | 2000-12-08 | 2000-12-18 | K 739 494 | 0 | 0 | 27.5 | K 739 494 | 120 | 0 | 27.5 | K 739 494 | 240 | 0 | 27.5 |  |  |  |  | N/A | 14 | 14 | 7/8" | 14 | 14 | 7/8" | 14 | 14 | 7/8" | N/A | N/A | N/A | 84 |  | Brasov | MW | 124 | 0.6 | 27/0.3 | 14 | 38/13 |  |  | 4U-1 |  |  |  | RBS | [9 empty] | 1 | BV049 | DUMBRAVA_RTC | 304 | 0.6 | 37 | 21.5 | 38/17 | [6 empty] | 3/ | ISAF/ | 3.10.00- | 255 | 2000-03-10 | 2000-10-13 | 2000-10-13 | DINCA | OK | 2000-10-18 |  | 2001-02-21 | 2001-03-02 | HDSL+30N02 Dumbrava-Balcescu-Brasov |  | OK | Mihai CONSTANTIN | COSMOROM | [32 empty] | 452 | Sibiu | Sibiu | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BV052 | TEREZIAN_RTC | Sibiu(9) | BV052 Terezian_RTC | Transilvania | 45 48 05.98 | 24 08 30.02 | 45 48 04.6 | 24 08 32.5 | Of. Telefonic nr.5 - Terezian - str. Lunga nr.1 | Romtelecom Sibiu/Dl. Traian Gusan - sef admin., tel: 094/ 963 555 | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-07-14 | N/A | N/A |  |  |  |  | B | 15 | C1.5m+C1.5m+C1.5m | Room | IMSAT | OK | IMSAT | 2000-05-31 | 2000-06-08 | YesV | 2000-06-12 | Relu | 2000-06-16 | 2000-06-16 |  |  |  | 2000-05-19 | 2000-05-06 |  | 2000-05-30 | 2000-06-16 |  |  |  | NA | YRO | NA | 2000-06-29 | 2000-06-30 | 2000-07-03 | 2000-07-03 | 2000-07-06 |  | Yes | Theo Radoi | 2000-09-10 | 2000-09-06 | 2000-09-06 | 2000-09-18 | 2000-09-21 | K 739 494 | 0 | 0 | 15 | K 739 494 | 120 | 0 | 15 | K 739 494 | 240 | 0 | 15 |  |  |  |  | N/A | 39 | 39 | 7/8" | 39 | 39 | 7/8" | 12 | 12 | 7/8" | N/A | N/A | N/A | 141 | N/A | Brasov | FO | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | Indoor Comteck | [7 empty] | 60/ |  |  | BSC12 | BSC BRASOV |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | DINCA | OK | N/A |  | N/A | N/A | 30N04 Terezian-Balcescu-Brasov |  | OK | Mihai CONSTANTIN | Cosmorom | [32 empty] | 433 | Sibiu | Sibiu | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | BV054 | COOPERATIVA | Sibiu(9) | BV048 Balcescu_RTC | Transilvania | 45 48 01.85 | 24 09 45.93 | 45 48 01.85 | 24 09 45.93 | Cooperativa "Arta Sibiului" - Calea Gusteritei nr.1 (langa RTC) | Presedinte "Arta Sibiului" - Dl. Ioan Hambasan, str. Laurian Augustus nr.1, tel: 094/ 588 305/Dl. Dragos Padureanu - Administrator, tel: 094/ 502 286 | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-08-02 | N/A | N/A |  |  |  | 4 | B | 15.3 | T3m+T3m | Room | IMSAT | OK | VECTOR | 2000-06-20 | 2000-07-07 | YesV | 2000-07-14 | Relu | 2000-07-27 | 2000-10-06 |  |  |  | 2000-05-19 | 2000-05-06 |  | 2000-06-22 | 2000-07-10 |  |  |  | NA | YRO | NA | 2000-07-27 | 2000-07-27 | 2000-07-30 | 2000-08-03 | 2000-08-08 |  | Yes | Ionut Grigorescu | 2000-09-10 | 2000-09-29 | 2000-09-29 | 2000-12-08 | 2001-01-08 | K 739 494 | 0 | 0 | 16.8 | K 739 494 | 120 | 0 | 16.8 | K 739 494 | 240 | 0 | 16.8 |  |  |  |  | N/A | 36 | 36 | 7/8" | 43 | 43 | 7/8" | 36 | 36 | 7/8" | N/A | N/A | N/A | 182 | N/A | Brasov | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | [12 empty] | 25/ |  |  | BV048 | NICOLAE_BALCESCU |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | DINCA | OK | N/A |  | N/A | N/A | 30N01 Nicolae Balcescu-Brasov |  | OK | Mihai CONSTANTIN | COSMOROM | [32 empty] | 428 | Sibiu | Sibiu | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | BV055 | GHEATA | Sibiu(9) | BV049 Dumbrava_RTC | Transilvania | 45 47 18.39 | 24 09 49.57 | 45 47 22.7 | 24 09 54.7 | Str. Victor Hugo nr.2 | SC GHEATA SRL, str. Victor Hugo nr.2, tel: 069/213 160/Greavu Gheorghe | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-09-19 | Yes | N/A |  |  |  | 20.5 | B | 22.8 | T4.5m+T4.5m | N/A | IMSAT | OK | VECTOR | 2000-08-08 | 2000-09-14 | YesV | 2000-09-19 | Relu | 1906-01-30 | 2000-09-22 |  |  |  | 2000-05-17 | 2000-05-06 |  | 2000-06-08 | 2000-07-27 |  |  |  | 2000-09-15 | YRO | ISAF | 2000-09-15 | 2000-09-15 | 2000-09-19 | 2000-09-20 | 2000-09-21 |  | Yes | Theo Radoi | 2000-10-05 | 2000-10-06 | 2000-10-06 | 2000-10-25 | 2000-11-09 | K 739 494 | 0 | 0 | 23.55 | K 739 494 | 120 | 0 | 23.55 | K 739 494 | 240 | 0 | 23.55 |  |  |  |  | N/A | 8 | 8 | 7/8" | 6 | 6 | 7/8" | 8 | 8 | 7/8" | N/A | N/A | N/A | 44 | ML 38 E 1+0 | Brasov | MW | 237 | 0.6 | 22.8 | 8 | 38/13 |  |  | 2U-3 |  |  |  | RBS | [9 empty] | 1 | BV049 | DUMBRAVA_RTC | 57 | 0.6 | 37 | 21.5 | 38/17 | [6 empty] | 2/ | ISAF/ | 15.09.00- | 205 | 2000-09-18 | 2000-09-19 | 2000-09-21 | DINCA | OK | 2000-10-06 |  | 2000-09-25 | 2000-10-25 | HDSL+30N02 Dumbrava-Balcescu-Brasov |  | OK | Mihai CONSTANTIN | Cosmorom | [32 empty] | 440 | Sibiu | Sibiu | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BV056 | SILOZ | Sibiu(9) | BV049 Dumbrava_RTC | Transilvania | 45 47 40.50 | 24 07 17.06 | 45 47 41.3 | 24 06 18.5 | str. Alba Iulia nr.100B, (Statia de conditionare a semintelor Sibiu) | Agrosem Sibiu - Str. Alba Iulia nr. 100b, tel: 069/ 964 225/Dir. Arsenie I. - Str. Alba Iulia nr. 100B, tel: 092/ 711 709 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-06-28 | 2000-07-24 | MIC |  |  |  | 28 | B | 40 | T4m+T4m | N/A | ISAF | OK | ISAF | 2000-06-05 | 2000-06-19 | YesV | 2000-06-19 | Relu | 2000-07-06 | 2000-07-11 |  |  |  | 2000-05-11 | 2000-05-06 |  | 2000-05-19 | 2000-06-05 |  |  |  | NA | YRO | NA | 2000-07-07 | 2000-06-30 | 2000-07-26 | 2000-07-31 | 2000-08-02 |  | Yes | Ionut Grigorescu | 2000-09-10 | 2000-09-29 | 2000-09-29 | 2000-11-20 | 2001-01-08 | K 739 494 | 0 | 0 | 42.5 | K 739 494 | 120 | 0 | 42.5 | K 739 494 | 240 | 0 | 42.5 |  |  |  |  | N/A | 31 | 31 | 7/8" | 31 | 31 | 7/8" | 23 | 23 | 7/8" | N/A | N/A | N/A | 170 | ML 38 E 1+0 | Brasov | MW | 95 | 0.6 | 44.5 | 29 | 38/13 |  |  | 4U-1+2U-3 |  |  |  | N/A | [9 empty] | 1 | BV049 | DUMBRAVA_RTC | 300 | 0.6 | 38 | 22.5 | 38/17 | [6 empty] | N/A | YRO | N/A | 45/46 | 2000-07-10 | 2000-07-31 | 2000-08-02 | DINCA | OK | 2000-09-29 |  | 2000-11-20 | 2001-01-10 | HDSL+30N03 Dumbrava-Balcescu-Brasov |  | OK | Mihai CONSTANTIN | Cosmorom | [32 empty] | 452 | Sibiu | Sibiu | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BV057 | CRISTIAN | Road Sibiu-Miercurea Sibiului(3+1) | BV049 Dumbrava_RTC | Transilvania | 45 47 12.32 | 24 01 24.89 | 45 47 10 | 24 01 00.58 | DN-E15A | D-nul Bradescu - Str. 11 nr.119 com. Cristian, tel: 069/ 579 346/D-nul Bradescu - Str. 11 nr.119 com. Cristian, tel: 069/ 579 346 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-08-08 | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | ISAF | OK | ISAF | 2000-06-05 | 2000-07-09 | YesV | 2000-07-25 | Relu | 2000-08-04 | 2000-08-03 |  |  |  | 2000-05-11 | 2000-05-06 |  | 2000-05-19 | 2000-06-05 |  |  |  | 2000-08-08 | YRO | SVF | 2000-08-08 | 2000-08-02 | 2000-08-10 | 2000-08-12 | 2000-08-15 |  | Yes | Constantin Mihai | 2000-12-15 | 2000-12-11 | 2000-12-11 | 2001-06-19 | 2001-07-11 | K 739 494 | 90 | 0 | 47 | K 739 494 | 270 | 0 | 47 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 60 | ML 23 E 1+0 | Brasov | MW | 84.5 | 0.6 | 50 | 70 | 23/58 |  |  | 2U-3 |  |  |  | RBS | [7 empty] | N/A/N/A |  | 1 | BV056 | SILOZ | 100 | 0.6 | 44.5 | 62 | 23/56 | [6 empty] | 4/* | SVF/* | 2000-08-08 | 108 | 2000-08-08 | 2000-08-12 | 2000-08-15 | AUREL | OK | 2000-12-11 |  | 2001-01-22 | 2001-01-22 | HDSL+30N03 Dumbrava-Balcescu-Brasov |  | OK | Mihai CONSTANTIN | Cosmorom | [32 empty] | 464 | Com. Cristian | Sibiu | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BV059 | MIERCUREA SIBIULUI | Road Sibiu-Miercurea Sibiului(3+1) | BV060 Miercurea Sibiului_RTC | Transilvania | 45 53 11.01 | 23 47 35 | 45 52 48.4 | 23 47 49.9 | Restaurant Miercurea Deal, DN 1Km 343+500 | SC RESPOLD SRL - com. Miercurea Sibiului DN 1Km 343+500, tel: 069/533 418/Dan Ioan - com. Miercurea Sibiului DN 1Km 343+500, tel: 094/387 864 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-09-19 | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | PROTELCO | OK | EL-MONT | 2000-07-06 | 2000-08-04 | YesV | 2000-08-11 | Relu | 2000-08-18 | 2000-08-14 |  |  |  | 2000-06-11 | 2000-05-05 |  | 2000-06-20 | 2000-07-10 |  |  |  | 2000-08-21 | YRO | DIEKAT | 2000-08-21 | 2000-08-21 | 2000-08-22 | 2000-08-23 | 2000-08-31 |  | Yes | Mihai Constantin | 2000-12-15 | 2000-12-12 | 2000-12-12 | 2001-07-05 | 2001-07-11 | K 739 494 | 110 | 0 | 48 | K 739 494 | 300 | 0 | 48 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 65 | 65 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 130 | ML 38 E 1+0 | Brasov | MW | 335 | 0.3 | 47.5 | 65 | 38/14 |  |  | 2U-3 |  |  |  | RBS | [9 empty] | 1 | BV060 | MIERCUREA SIBIULUI_RTC | 156 | 0.3 | 22 | 65 | 38/18 | [6 empty] | 2001-02-04 | DIEKAT |  | 143/180 | 8/21/00-9/9/00 | 2000-08-23 | 2000-08-31 | OK | OK | 2000-12-10 |  | 2001-01-22 | 2001-01-22 | 30N01 M. Sibiului-Brasov |  | OK | Mihai CONSTANTIN | Cosmorom | [32 empty] | 320 | Miercurea Sibiului | Sibiu | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | TM | BV060 | MIERCUREA SIBIULUI_RTC | Road Sibiu-Miercurea Sibiului(3+1) | BV060 Miercurea Sibiului_RTC | Transilvania | 45 53 11.01 | 23 47 35 | 45 53 13.4 | 23 47 33.9 | Oficiu Romtelecom, com. Miercurea Sibiului | Romtelecom Sibiu/Jurca Adriana (sef centru Miercurea Sibiului 069/533115), Sibiu - 0692111033 | N/A | N/A | N/A | N/A | N/A | [7 empty] | N/A | N/A |  |  |  | N/A | TE | 25 | 25m existing tower | Room | PROTELCO | OK | EL-MONT | 2000-07-20 | 2000-08-21 | YesV | 2000-08-24 | Relu | 2000-09-06 | 2000-08-30 |  |  |  |  | 2000-05-05 |  | 2000-08-07 | 2000-09-04 |  |  |  | 2000-09-08 | YRO | DIEKAT | N/A | N/A | 2000-09-09 | N/A | N/A |  | Yes | N/A | 2000-12-15 | 2000-12-12 | 2000-12-12 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Brasov | FO | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | TMR 9202 | 70060 | [6 empty] | 15/ |  | 1 | BSC12 | BSC BRASOV | N/A | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | DINCA | OK | N/A |  | N/A | N/A | N/A |  | OK | Mihai CONSTANTIN | Cosmorom | [32 empty] | 317 | Miercurea Sibiului | Sibiu | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | BV070 | SALCONSERV | Medias(3+1) | BV085 Medias_RTC | Transilvania | 46 09 53 | 24 21 29.5 | 46 09 53.6 | 24 21 29.5 | Str. Horea nr.6, Fabrica de Mezeluri | Fabrica de Mezeluri/Dir. G. Cuculas - 069/ 845 493 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-10-13 | Yes | N/A |  |  |  | 44 | B | 48 | C4m+S4m | N/A | ISAF | OK | DUAL | 2000-10-18 | 2000-10-25 | YesV | 2000-11-02 | Dragos | 2000-11-22 | 2000-11-10 |  |  |  | 2000-05-22 | 2000-05-20 |  | 2000-09-04 | 2000-10-19 |  |  |  | 2000-10-20 | ICOM | DIEKAT | 2000-10-16 | 2000-10-16 | 2000-10-23 | 2000-10-24 | 2000-10-25 |  | Yes | Durugy Iosif | 2000-11-30 | 2000-11-27 | 2000-11-27 | 2000-12-05 | 2000-12-18 | K 739 494 | 85 | 0 | 51 | K 739 494 | 180 | 0 | 52 | K 739 494 | 325 | 0 | 51 |  |  |  |  | N/A | 15 | 15 | 7/8" | 31 | 31 | 7/8" | 15 | 15 | 7/8" | N/A | N/A | N/A | 122 | ML 23 E 1+0 | Tg. Mures | MW | 270 | 0.6 | 52 | 23 | 23/58 |  | N/A | 4U-1 |  |  | N/A | RBS | [9 empty] | 1 | BV085 | MEDIAS_RTC | 89 | 0.6 | 20 | 80 | 23/56 | [6 empty] | 8 | DIEKAT | 2000-10-20 | 277 | 2000-10-13 | 2000-10-24 | 2000-10-25 | VLAD | Yes | 2000-11-27 | PENDING |  |  |  |  | OK | Bogdan CRAIU | Cosmorom | [32 empty] | 320 | Medias | Sibiu | [7 empty] | 2 |  |  | 2
Phase_2 | CS | BV071 | TURN ROMGAZ | Medias(3+1) | BV085 Medias_RTC | Transilvania | 46 09 09.8 | 24 20 57.1 | 46 09 09.8 | 24 20 57.1 | Cartier Gloria | Romgaz/Maistru Pepene - directia Romgaz Medias, 069/ 845 598 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-10-13 | N/A | N/A |  |  |  | 0 | TE | 50 |  | N/A | ISAF | OK | DUAL | 2000-10-02 | 2000-10-25 | YesV | 2000-11-02 | Dragos | 2001-06-06 | 2001-01-22 |  |  |  | 2000-05-21 | 2000-05-20 |  | 2000-05-22 | 2000-06-06 |  |  |  | 2000-10-20 | ICOM | DIEKAT | 2000-10-09 | 2000-10-09 | 2000-10-23 | 2000-10-24 | 2000-10-25 |  | Yes | Mircea Mihut | 2001-05-10 | 2001-05-10 | 2001-05-10 |  |  | K 739 494 | 95 | 0 | 45 | K 739 494 | 205 | 0 | 45 | K 739 494 | 325 | 0 | 45 |  |  |  |  | N/A | 56 | 56 | 1 1/4" | 56 | 56 | 1 1/4" | 56 | 56 | 1 1/4" | N/A | N/A | N/A | 336 | ML 23 E 1+0 | Tg. Mures | MW | 354 | 0.6 | 45 | 56 | 23/58 |  |  | 4U-1 |  |  |  | RBS | [9 empty] | 1 | BV085 | MEDIAS_RTC | 174 | 0.6 | 20/0.6 | 85 | 23/56 | [6 empty] | 8 | DIEKAT | 2000-10-20 | 278 / 892 | 2000-10-13 | 2000-10-24 | 2000-10-25 | VLAD | OK | 2001-05-10 |  | 2001-05-23 | 2001-05-25 |  |  | OK | Bogdan CRAIU | Cosmorom | [32 empty] | 400 | Medias | Sibiu | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BV072 | 1 DECEMBRIE | Medias(3+1) | BV085 Medias_RTC | Transilvania | 46 09 59 | 24 20 01.6 | 46 09 59 | 24 20 01.6 | Str. 1 Decembrie nr.32 Bl.13 Sc.B | Asociatie de locatari/Stanca Simion - Et.1, 069/ 833 945 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-09-19 | Yes | N/A |  |  |  | 33 | B | 36.3 | T4m+T4m | N/A | ISAF | OK | DUAL | 2000-08-01 | 2000-08-07 | YesV | 2000-08-08 | Dragos | 2000-09-07 | 2000-08-14 |  |  |  | 2000-05-22 | 2000-05-20 |  | 2000-05-23 | 2000-07-27 |  |  |  | 2000-09-08 | YRO | DIEKAT | 2000-08-25 | 2000-08-26 | 2000-09-09 | 2000-09-10 | 2000-09-11 |  | Yes | Durugy Iosif | 2000-11-30 | 2000-12-09 | 2000-12-09 |  |  | K 739 494 | 100 | 0 | 35 | K 739 494 | 230 | 0 | 35 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 25 | 25 | 7/8" | 25 | 25 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A | 100 | ML 23 E 1+0 | Tg. Mures | MW | 100 | 0.6 | 33.8 | 25 | 23/58 |  |  | 2U-3 |  |  |  | RBS | [9 empty] | 1 | BV085 | MEDIAS_RTC | 280 | 0.6 | 20 | 80 | 23/56 | [6 empty] | 4 | DIEKAT | 2000-09-08 | 182 | 2000-09-08 | 2000-09-09 | 2000-09-11 | DINCA | OK | 2000-12-09 |  | 2000-12-21 | 2001-01-10 |  |  | OK | Bogdan CRAIU | #N/A | [32 empty] | 330 | Medias | Sibiu | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BV073 | BARSA | Road Bv-Tg. Mures(13) | BV001 Brasov_CTA | Transilvania | 45 46 04.9 | 25 35 10.2 | 45 45 43.9 | 25 35 05.7 | Teren proprietate CF nr.6096 TOP 1301, Com. Feldioara | Bogdan Magdalena - Str. Birsei 22, com. Feldioara, 188 din centrala colonie BOD/Bogdan Magdalena - Str. Birsei 22, com. Feldioara, 188 din centrala colonie BOD | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-12-11 | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | IMSAT | OK | IMSAT | 2000-11-03 | 2001-02-07 | YesV | 2001-02-21 | Marin | 2001-07-06 | 2001-02-28 |  |  |  |  | 2000-10-04 |  | 2000-10-25 | 2000-11-07 | [6 empty] | 2001-02-09 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 0 | 0 | 48.25 | K 739 494 | 185 | 0 | 48.25 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 |  | Brasov | MW | 176 |  | 41.5 | 50 | [7 empty] | RBS | [10 empty] | BV112 | TAMPA | [26 empty] | OK | Petrica BURGHIU | Petrica BURGHIU | [32 empty] | 501 | Barsa | Brasov | [7 empty] | 2 |  |  | missing
Phase_2 | CS | BV074 | MAIERUS | Road Bv-Tg. Mures(13) | BV001 Brasov_CTA | Transilvania | 45 54 18.2 | 25 32 19.4 | 45 54 18.6 | 25 32 16.4 | Teren arabil, tarla 40, parcela 522/64, com. Maierus | Nemes Arpad/Nemes Arpad | MUTAT | M | C+ | 2 | 2101 | [6 empty] | 2000-11-17 | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | IMSAT | OK | IMSAT | 2000-10-15 | 2000-11-17 | YesV | 2000-11-28 | Dragos | 2001-03-14 | 2000-12-13 | [6 empty] | 2000-10-04 | 2000-10-19 |  |  |  | 2000-11-20 | ICOM | Interactive | 2000-11-20 | 2000-11-20 | 2000-11-21 | 2000-11-28 | 2000-11-28 |  | Yes |  | 2101 MOVED TO CJ183 |  |  |  |  | K 739 494 | 180 | 0 | 48.25 | K 739 494 | 270 | 0 | 48.25 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Brasov | MW | 166 | 1.2 | 30/1.2 | 38 | [7 empty] | N/A | [10 empty] | BV073 | BARSA | 347 |  | 41.5 | 50 | [22 empty] | OK | Petrica BURGHIU | Cosmorom | [32 empty] | 512 | Maierus | Mures | [7 empty] | 2 |  |  | 2
Phase_2 | CS | BV075 | DEALUL CU STEJARI_DRTV | Road Bv-Tg. Mures(13) | BV001 Brasov_CTA | Transilvania | 45 58 58 | 25 27 08.4 | 45 52 58 | 25 27 08.4 | DN13(Intrarea in Padurea Bogatii) | DRTV/ | 2202 | M | C+C+ | 2/2 | 2202 | [6 empty] | 2000-10-11 | N/A | N/A |  |  |  | 0 | TE |  |  | Room | IMSAT | OK | IMSAT | 2000-08-17 | 2000-09-14 | YesV | 2000-10-10 | Dragos | 2000-09-28 | 2000-10-13 |  |  |  |  | 2000-08-07 |  | 2000-08-07 | 2000-08-07 |  |  |  | 2000-10-03 | YRO | SVF | 2000-10-02 | 2000-10-02 | 2000-10-04 | 2000-10-06 | 2000-10-09 |  | Yes | Bogdan Bogodai | 2001-05-13 | 2001-05-14 | 2001-05-14 |  |  | K 739 494 | 60 | 0 | 22 | K 739 494 | 316 | 0 | 22 | N/A | N/A | N/A | N/A |  |  |  |  | N/A | 30 | 30 | 7/8" | 30 | 30 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A | 120 |  | Brasov | MW | 158 | 1.8 | 27/1.8 | 50 | 15/84 |  |  | 4U-1 |  |  |  | Indoor Comteck | [9 empty] | 1 | BV112 | TAMPA | 337 | 1.2 |  | 60 | 15/89 | [6 empty] | 62* | TRYLON | 2001-05-02 | 767 | 2001-05-03 | 2001-05-04 | 2001-05-07 | PAUN | OK | 2001-05-14 | PENDING |  |  | 30N05 conectare locala |  | OK | Petrica BURGHIU | Cosmorom | [32 empty] | 812 | DRTv Acatari | Mures | [6 empty] | 1 | 2 |  |  | 2
Phase_2 | CS | BV076 | BOGATA | Road Bv-Tg. Mures(13) | BV001 Brasov_CTA | Transilvania | 45 58 37.4 | 25 20 10.2 | 45 57 55.3 | 25 21 01.6 | Extravilan sat Bogata, zona "Fata lui Topot", tarla 69, parcela 1317/23 | Leuca v. Victor, sat Bogata, com. Hoghiz, str. Principala 120/Leuca v. Victor, sat Bogata, com. Hoghiz, str. Principala 120 - 43A prin centrala Hoghiz | MAXITE | M | 1 | 2 | 2PBC | [6 empty] | 2000-12-11 | N/A | N/A |  |  |  |  | TN | 50 |  |  | IMSAT | OK | IMSAT | 2000-11-03 | 2001-04-07 | YesV | 2001-05-28 | Marin | 2001-05-07 | 2001-05-30 |  |  |  |  | 2000-10-05 |  | 2000-10-25 | 2001-02-12 |  |  |  | 2001-04-03 | ICOM | TRY | 2001-04-03 | 2001-04-03 | 2001-04-05 | 2001-04-06 | 2001-04-09 |  | Yes | Bogdan Bogodai | 2001-05-13 | 2001-05-13 | 2001-05-13 | 2001-06-19 | 2001-07-11 | K 739 494 | 0 | 0 | 48.25 | K 739 494 | 185 | 0 | 48.25 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+1 (PS) | Brasov | MW | 139 | 1.2 | 50/1.2 | 60 | 15/89 | YES | 4x2/8 |  |  |  | YES | TMR 9000 | [9 empty] | 1 | BV075 | DEALUL CU STEJARI_DRTV | 319 | 0.6 | 27-28/1.2 | 40 | 15/84 | [6 empty] | 62* | TRYLON | 2001-05-02 | 875 | 2001-05-03 | 2001-05-04 | 2001-05-07 | VLAD | OK | 2001-05-14 |  | 2001-05-23 | 2001-05-25 | 30N05 conectare locala |  | OK | Petrica BURGHIU | Petrica BURGHIU | [32 empty] | 600 | Bogata | Brasov | [5 empty] | 1 | 1 | 2 | 1 | 1 | 2
Phase_2 | CS | BV077 | RUPEA | Road Bv-Tg. Mures(13) | BV001 Brasov_CTA | Transilvania | 46 02 42.9 | 25 13 08.8 | 46 02 22.5 | 25 12 47.9 | Rupea, langa Cetate | Borcoman Vasile - Rupea, 068/ 260 666/Viceprimar cons. Loc. Rupea, Comaniciu Pompiliu, 094/ 525 336 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-10-13 | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | ORION | OK | ORION | 2000-09-26 | 2000-10-27 | YesV | 2000-11-01 | Dragos | 2000-10-27 | 2000-11-10 |  |  |  |  | 2000-07-09 |  | 2000-09-27 | 2000-10-17 |  |  |  | 2000-10-20 | ICOM | ORION | 2000-10-13 | 2000-10-13 | 2000-11-09 | 2000-11-15 | 2000-11-17 |  | Yes | Bogdan Bogodai | 2001-05-13 | 2001-05-14 | 2001-05-14 | 2001-05-25 | 2001-06-19 | K 739 494 | 110 | 0 | 49 | K 739 494 | 300 | 0 | 49 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 70 | 70 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 140 | ML 15 E 1+0 | Brasov | MW | 128 | 0.6 | 45/1.2 | 60 | 15/84 |  |  | 4U-1 |  |  |  | RBS | [9 empty] | 1 | BV076 | BOGATA | 308 | 0.6 | 48/1.2 | 60 | 15/89 | [6 empty] | 53* | TRYLON | 2001-04-03 | 819 | 2001-04-05 | 2001-05-05 | 2001-05-07 | PITURCESCU | OK | 2001-05-14 | PENDING |  |  | 30N05 conectare locala |  | OK | Petrica BURGHIU | Cosmorom | [32 empty] | 530 | Rupea | Brasov | [7 empty] | 2 |  | 1 | 2
Phase_2 | CS | BV078 | FISER | Road Bv-Tg. Mures(13) | BV001 Brasov_CTA | Transilvania | 46 04 41.3 | 25 08 28.8 | 46 04 36.1 | 25 08 51.5 | Fisher | Bercan Ion, Com. Fisher nr. 62/Viceprimar Consiliul local Rupea - Comaniciu Pompiliu, 094/ 525 336 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-10-13 | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | ORION | OK | ORION | 2000-09-26 | 2000-10-25 | YesV | 2000-11-01 | Dragos | 2000-10-27 | 2000-11-10 |  |  |  |  | 2000-09-07 |  | 2000-09-20 | 2000-10-09 |  |  |  | 2000-10-20 | ICOM | ORION | 2000-10-13 | 2000-10-13 | 2000-11-09 | 2000-11-10 | 2000-11-14 |  | Yes | Bogdan Bogodai | 2001-05-13 | 2001-05-14 | 2001-05-14 | 2001-05-25 | 2001-06-19 | K 739 494 | 126 | 0 | 50 | K 739 494 | 315 | 0 | 50 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 70 | 70 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 140 | ML 23 E 1+0 | Brasov | MW | 127 | 0.6 | 10 | 25 | 23/58 |  |  | 4U-1 |  |  |  | RBS | [9 empty] | 1 | BV077 | RUPEA | 307 | 0.6 | 30/0.6 | 45 | 23/56 | [6 empty] | 8 | ORION | 2000-10-20 | 314 | 2000-10-13 | 2000-11-10 | 2000-11-17 | PITURCESCU | OK | 2001-05-14 |  | 2001-05-23 | 2001-05-25 | 30N05 conectare locala |  | OK | Petrica BURGHIU | Cosmorom | [32 empty] | 559 | Fisher | Brasov | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BV079 | ROADES | Road Bv-Tg. Mures(13) | BV001 Brasov_CTA | Transilvania | 46 07 31.1 | 26 04 40.7 | 46 07 31.11 | 25 04 40.6 | Roades, com. Bunesti | Consiliul local Bunesti/Viceprimar Consiliul local Bunesti, Palasanu Mircea, 068/ 260 681 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-10-13 | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | ORION | OK | ORION | 2000-09-26 | 2000-10-25 | YesV | 2000-11-01 | Dragos | 2000-10-26 | 2000-11-10 |  |  |  |  | 2000-07-05 |  | 2000-09-27 | 2000-10-17 |  |  |  | 2000-10-20 | ICOM | ORION | 2000-10-13 | 2000-10-13 | 2000-11-09 | 2000-11-15 | 2000-11-17 |  | Yes | Bogdan Bogodai | 2001-05-14 | 2001-05-14 | 2001-05-14 | 2001-05-25 | 2001-06-19 | K 739 494 | 130 | 0 | 50 | K 739 494 | 290 | 0 | 50 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 70 | 70 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 140 | ML 15 E 1+0 | Brasov | MW | 132 | 1.2 | 30 | 40 | 15/89 |  |  | 4U-1 |  |  |  | RBS | [9 empty] | 1 | BV077 | RUPEA | 312 | 1.2 | 45 | 60 | 15/84 | [6 empty] | 8 | ORION | 2000-10-20 | 313 | 2000-10-20 | 2000-11-20 | 2000-11-21 | PITURCESCU | OK | 2001-05-14 | PENDING |  |  | 30N05 conectare locala |  | OK | Petrica BURGHIU | Cosmorom | [32 empty] | 722 | Roades, com. Bunesti | Brasov | [7 empty] | 2 |  |  | 2
Phase_2 | CS | BV080 | SASCHIZ | Road Bv-Tg. Mures(13) | BV001 Brasov_CTA | Transilvania | 46 10 57 | 24 57 36.3 | 46 14 53.1 | 24 57 40.6 | Com. Saschiz, tarla 114, parcela 3309/1 | Flesar I. Viorica si Valcu Maria, com. Saschiz/Flesar I. Viorica si Valcu Maria, com. Saschiz | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | ORION | OK | ORION | 2000-11-01 | 2000-11-30 | YesV | 2000-12-06 | Dragos | 2001-03-08 | 2000-12-13 |  |  |  |  | 2000-08-05 |  | 2000-10-06 | 2000-12-05 |  |  |  | 2000-11-08 | ICOM | ORION | 2000-11-08 | 2000-11-08 | 2000-11-09 | 2000-11-20 | 2000-11-21 |  | Yes | Bogdan Bogodai | 2001-05-14 | 2001-05-14 | 2001-05-14 | 2001-05-25 | 2001-06-19 | K 739 494 | 0 | 0 | 49 | K 739 494 | 150 | 0 | 49 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 70 | 70 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 140 | ML 15 E 1+0 | Brasov | MW | 125 | 0.6 | 30/1.2 | 40 | 15/84 |  |  | 2U-3 |  |  |  | RBS | [9 empty] | 1 | BV079 | ROADES | 305 | 0.6 | 45/1.2 | 55 | 15/89 | [6 empty] | * | INTERACTIVE | 2000-11-17 | 380 | 2000-11-17 | 2000-11-20 | 2000-11-21 | PITURCESCU | OK | 2001-05-14 | PENDING |  |  | 30N05 conectare locala |  | OK | Petrica BURGHIU | Cosmorom | [32 empty] | 479 | Saschiz | Mures | [7 empty] | 2 |  |  | 2
Phase_2 | CS | BV081 | VINATORI | Road Bv-Tg. Mures(13) | CJ079 Sighisoara_RTC | Transilvania | 46 14 33.6 | 24 38 30.4 | 46 10 57 | 24 57 36.3 | Extravilan com. Vanatori | Toth Ioan -064/ 411 946/Toth Ioan -064/ 411 946 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-10-13 | N/A | N/A |  |  |  | 0 | TN | 50 |  | N/A | ORION | OK | ORION | 2000-10-16 | 2000-11-10 | YesV | 2000-11-14 | Dragos | 2000-10-26 | 2000-12-07 |  |  |  |  | 2000-09-07 |  | 2000-10-06 | 2000-11-06 |  |  |  | 2000-10-20 | ICOM | ORION | 2000-10-13 | 2000-10-13 | 2000-11-09 | 2000-11-15 | 2000-11-17 |  | Yes | Ion Soare | 2001-04-11 | 2001-04-11 | 2001-04-11 |  |  | K 739 494 | 40 | 0 | 50 | K 739 494 | 190 | 0 | 50 | K 739 494 | 280 | 0 | 50 |  |  |  |  | N/A | 70 | 70 | 1 1/4" | 70 | 70 | 1 1/4" | 70 | 70 | 1 1/4" | N/A | N/A | N/A | 420 | ML 15 E 1+0 | Tg. Mures | MW | 263 | 1.2 | 30/1.2 | 50 | 15/89 |  |  | 4U-1 |  |  |  | RBS | [9 empty] | 1 | CJ040 | TURN DEALUL GARII | 82 | 1.2 | 30/1.2 | 45 | 15/84 | [6 empty] | 5* | ORION | 2000-12-11 | 451 | 2000-12-11 | 2001-01-10 | 2001-03-06 | PITURCESCU | OK | 2001-04-11 |  | 2001-05-03 | 2001-05-11 |  |  | 2000-11-01 | Ionut GRIGORESCU | Cosmorom | [32 empty] | 396 | Vinatori | Mures | [7 empty] | 2 |  |  | 2
Phase_2 | CS | BV082 | HETIUR | Road Bv-Tg. Mures(13) | CJ026 Tg. Mures_RTC | Transilvania | 46 16 33.8 | 24 44 09 | 46 16 34 | 24 44 05.5 | Extravilan Dealul Neadesului | Primaria com. Nades/Primar Alexandru Cirnu - str. Principala 343, Nades - 094/ 619 004 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-12-11 | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | IMSAT | OK | GIRARDOT | 2000-11-03 | 2001-04-05 | YesV | 2001-05-14 | Marin | 2001-05-07 | 2001-05-16 |  |  |  |  | 2000-10-05 |  | 2000-10-25 | 2000-11-16 | [6 empty] | 2001-04-09 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 130 | 0 | 48.25 | K 739 494 | 340 | 0 | 48.25 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Tg. Mures | MW | 347 | 1.2 | 30/1.2 | 44 | [7 empty] | RBS | [10 empty] | BV083 | CHENDU | 167 | 1.2 | 30/1.2 | 44 | [23 empty] | Petrica BURGHIU | Cosmorom | [32 empty] | 525 | Nades | Mures | [7 empty] | 2 |  |  | 2
Phase_2 | CS | BV083 | CHENDU | Road Bv-Tg. Mures(13) | CJ026 Tg. Mures_RTC | Transilvania | 46 21 59.6 | 24 42 20.8 | 46 21 59.6 | 24 42 20.8 | Pasunea comunala Chendu Mare (langa padurea Ceria) | Primaria com. Balauseri/Dl. Primar ing. Mate Ianos si dl. Vice-primar Szalma Ianos | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-11-17 | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | IMSAT | OK | GIRARDOT | 2000-10-16 | 2001-01-24 | YesV | 2001-03-03 | Marin | 2001-02-07 | 2001-03-14 |  |  |  |  | 2000-07-05 |  | 2000-09-26 | 2000-10-20 | [6 empty] | 2001-02-01 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 162 | 0 | 48.25 | K 739 494 | 337 | 0 | 48.25 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Tg. Mures | MW | 343 | 0.6 | 30/0.6 | 44 | [7 empty] | RBS | [10 empty] | BV084 | CEUAS | 163 | 1.2 | 30/1.2 | 41 | [23 empty] | Petrica BURGHIU | CATALINA CIOCAN | [32 empty] | 493 | Chendu | Mures | [7 empty] | 2 |  |  | 2
Phase_2 | CS | BV084 | CEUAS | Road Bv-Tg. Mures(13) | CJ026 Tg. Mures_RTC | Transilvania | 46 24 46.6 | 24 41 07.5 | 46 24 46.6 | 24 41 07.5 | Teren arabil com. Balauseri, sat Balauseri | Primaria com. Balauseri/Dl. Primar Mate Ianos; dl. Viceprimar Szalmanenyhert Ianos | MUTAT | M | C+ | 2 | 2101 | [6 empty] | 2000-11-17 | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | IMSAT | OK | PROFIL | 2000-10-16 | 2000-12-18 | YesV | 2001-02-06 | Marin | 2001-02-26 | 2001-02-07 | [6 empty] | 2000-10-04 | 2000-10-20 |  |  |  | 2000-12-18 | ICOM | SVF | 2000-12-18 | 2000-12-18 | 2000-12-19 | 2001-01-08 | 2001-01-11 |  | Yes |  | 2101 MOVED TO CR142 |  |  |  |  | K 739 494 | 152 | 0 | 48.25 | K 739 494 | 330 | 0 | 48.25 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Tg. Mures | MW | 338 | 1.2 | 45/1.2 | 58 | [7 empty] | N/A | [10 empty] | BV090 | ACATARI | 154 | 1.2 | 30/1.2 | 40 | [23 empty] | Petrica BURGHIU | CATALINA CIOCAN | [32 empty] | 423 | Ceuas | Mures | [7 empty] | 2 |  |  | 2
Phase_2 | TM | BV085 | MEDIAS_RTC | Medias(3+1) | BV085 Medias_RTC | Transilvania | 46 09 53 | 24 20 50.3 | 46 09 53 | 24 20 50.3 | Romtelecom, Medias | Romtelecom/ | N/A | N/A | N/A | N/A | N/A | [7 empty] | N/A | N/A |  |  |  | N/A | B | 20 | C3m | Room | ISAF | OK | DUAL | 2000-08-01 | 2000-08-07 | YesV | 2000-08-08 | Dragos | 2000-09-07 | 2000-08-14 |  |  |  | 2000-06-06 | 2000-05-20 |  | 2000-06-07 | 2000-07-18 |  |  |  | 2000-09-08 | YRO | DIEKAT | N/A | N/A | 2000-09-09 | N/A | N/A |  | Yes | N/A | 2000-11-30 | 2000-11-27 | 2000-11-27 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Tg. Mures | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | 2U-3 |  |  |  | TMR 9202 | 70085 | 2001-05-07 | [7 empty] | 1 | BSC14 | BSC TG. MURES | N/A | N/A | N/A | N/A | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | DINCA | OK | N/A |  | N/A | N/A |  |  | OK | Bogdan CRAIU | Cosmorom | [32 empty] | 318 | Medias | Sibiu | [7 empty] | Site Near=Insertion Point
Phase_2 | TM | BV086 | MIERCUREA CIUC_RTC | Road Bv-Miercurea C(9+3) | BV086 Miercurea Ciuc_RTC | Transilvania | 46 21 28.8 | 25 48 22.3 | 46 21 28.8 | 25 48 22.3 | Oficiul nr.2 | Romtelecom/ | N/A | N/A | N/A | N/A | N/A | [7 empty] | N/A | N/A |  |  |  | N/A | B | 20 |  | Room | SVF | OK | SVF | 2000-07-20 | 2000-07-25 | YesV | 2000-08-01 | Dragos | 2000-08-02 | 2000-08-09 |  |  |  | N/A | 2000-05-20 |  | 2000-07-11 | 2000-07-25 |  |  |  | 2000-07-20 | YRO | SVF | N/A | N/A | 2000-07-20 | N/A | N/A |  | Yes | N/A | 2000-09-28 | 2000-09-07 | 2000-09-07 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Brasov | FO | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | TMR 9202 | 70086 | [9 empty] | BSC12 | BSC BRASOV | N/A | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PITURCESCU | OK | N/A |  | N/A | N/A | N/A |  | OK | Ionut GRIGORESCU | Cosmorom | [32 empty] | 650 | Miercurea Ciuc | Harghita | [7 empty] | Site Near=Insertion Point
Phase_2 | TM | BV087 | TUSNAD_RTC | Road Bv-Miercurea C(9+3) | BV087 Tusnad_RTC | Transilvania | 46 08 56.7 | 25 51 33.5 | 46 08 56.7 | 25 51 33.5 | Baile Tusnad | Romtelecom/ | N/A | N/A | N/A | N/A | N/A | [7 empty] | N/A | N/A |  |  |  | N/A | B | 10 |  | Room | SVF | OK | SVF | 2000-07-20 | 2000-07-25 | YesV | 2000-08-01 | Dragos | 2000-08-02 | 2000-08-09 |  |  |  | N/A | 2000-05-20 |  | 2000-07-11 | 2000-07-25 |  |  |  | 2000-07-20 | YRO | SVF | N/A | N/A | 2000-07-20 | N/A | N/A |  | Yes | N/A | 2000-09-28 | 2000-09-27 | 2000-09-27 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Brasov | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | 2U-3 |  |  |  | N/A | 70087 | 2001-04-06 | [7 empty] | 1 | BSC12 | BSC BRASOV | N/A | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PITURCESCU | OK | N/A |  | N/A | N/A | 30N01 Tusnad-Brasov |  | OK | Bogdan CRAIU | Cosmorom | [32 empty] | 639 | Tusnad | Harghita | [7 empty] | Site Near=Insertion Point
Phase_2 | TM | BV088 | SF.GHEORGHE_RTC | Road Bv-Miercurea C(9+3) | BV088 Sf. Gheorghe_RTC | Transilvania | 45 51 41.3 | 25 47 44.2 | 45 51 41.3 | 25 47 44.2 | Romtelecom - Sf.Gheorghe | Romtelecom/ | N/A | N/A | N/A | N/A | N/A | [7 empty] | N/A | N/A |  |  |  | N/A | TE | 48.5 |  | Room | SVF | OK | SVF | 2000-07-20 | 2000-07-25 | YesV | 2000-08-01 | Dragos | 2000-08-02 | 2000-08-09 |  |  |  | N/A | 2000-05-20 |  | 2000-07-11 | 2000-07-25 |  |  |  | 2000-07-20 | YRO | SVF | N/A | N/A | 2000-07-20 | N/A | N/A |  | Yes | N/A | 2000-09-28 | 2000-09-06 | 2000-09-06 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Brasov | FO | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | TMR 9202 | 70088 | [8 empty] | 1 | BSC12 | BSC BRASOV |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PITURCESCU | OK | N/A |  | N/A | N/A | N/A |  | OK | Bogdan CRAIU | Cosmorom | [32 empty] | 533 | Sf.Gheorghe | Covasna | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | BV090 | ACATARI | Road Bv-Tg. Mures(13) | CJ026 Tg. Mures_RTC | Transilvania | 46 29 47.1 | 24 37 40.1 | 46 29 50.1 | 24 37 31.1 | Extravilan com. Acatari (Dealul Stejaris) | Kerekes Ildiko, com. Acatari/Kerekes Ildiko, com. Acatari - sat Roteni nr.271 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-12-11 | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | IMSAT | OK | PROFIL | 2000-11-03 | 2001-01-25 | YesV | 2001-02-14 | Marin | 2001-02-21 | 2001-02-26 |  |  |  |  | 2000-10-05 |  | 2000-10-25 | 2001-01-12 | [6 empty] | 2001-01-30 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 165 | 0 | 48.3 | K 739 494 | 330 | #N/A | 48.3 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Tg. Mures | MW | 320 | 1.2 | 30/1.2 | 40 | [7 empty] | RBS | [10 empty] | CJ027 | PANDURILOR | 140 |  | 35 | 15 | [23 empty] | Petrica BURGHIU | #N/A | [32 empty] | 440 | Acatari | Mures | [7 empty] | 2 |  |  | 2
Phase_2 | CS | BV091 | DUMBRAVENI | Road Sigisoara-Medias(2) | BV085 Medias_RTC | Transilvania | 46 13 55.3 | 24 35 00.3 | 46 13 55.3 | 24 35 00.3 | Uzina de apa Dumbraveni, str. Hotar | Primarie/Petri Ioan - Str. Salcamilor nr.33, 094/ 610 312 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-10-20 | N/A | N/A |  |  |  | 0 | B | 10 | T4.5m | N/A | DIEKAT | OK | VECTOR | 2000-11-01 | 2000-11-17 | YesV | 2000-12-06 | Doru | 2001-01-19 | 2000-12-13 |  |  |  |  | 2000-08-17 |  | 2000-09-26 | 2000-10-30 |  |  |  | 2000-11-20 | ICOM | Interactive | 2000-11-20 | 2000-11-20 | 2000-11-21 | 2000-11-29 | 2000-11-30 |  | Yes | Bogdan Bogodai | 2001-01-30 | 2001-01-30 | 2001-01-30 |  |  | K 739 494 | 110 | 0 | 13.5 | K 739 494 | 235 | 0 | 13.5 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 20 | 20 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 40 | ML 15 E 1+0 | Tg. Mures | MW | 247 | 0.6 | 12/0.6 | 20 | 15/89 |  |  | 4U-1 |  |  |  | RBS | [9 empty] | 1 | BV092 | ALMA | 67 | 0.6 | 30/0.6 | 40 | 15/84 | [6 empty] | 7* | ORION | 2000-12-14 | 471 | 2000-12-14 | 2000-12-19 | 2001-01-01 | PITURCESCU | OK | 2001-01-30 | PENDING |  |  |  |  | OK | Petrica BURGHIU | Cosmorom | [32 empty] | 361 | Dumbraveni | Sibiu | [7 empty] | 2 |  |  | 2
Phase_2 | CS | BV092 | ALMA | Road Sigisoara-Medias(2) | BV085 Medias_RTC | Transilvania | 46 11 55 | 24 28 08 | 46 11 55 | 24 28 08 | Com. Atel, Sat Alma 182, sos. Medias-Sighisoara (DN14) | Muntean Doina - com. Atel nr.182/Muntean Doina - com. Atel nr.182 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-10-20 | N/A | N/A |  |  |  | 0 | TN | 50 |  | N/A | DIEKAT | OK | VECTOR | 2000-10-15 | 2000-12-12 | YesV | 2000-12-13 | Doru | 2001-01-19 | 2000-12-20 |  |  |  |  | 2000-08-17 |  | 2000-09-18 | 2000-10-11 |  |  |  | 2000-12-14 | ICOM | ORION | 2000-12-13 | 2000-12-15 | 2000-12-19 | 2000-12-21 | 2000-12-28 |  | Yes | Bogdan Bogodai | 2001-01-30 | 2001-01-30 | 2001-01-30 |  |  | K 739 494 | 80 | 0 | 49 | K 739 494 | 230 | 0 | 49 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Tg. Mures | MW | 246 | 0.6 | 30/0.6 | 40 | 15/84 |  |  | 4U-1 |  |  |  | RBS | [9 empty] | 1 | BV070 | SALCONSERV | 66 | 0.6 | 52/0.6 | 23 | 15/89 | [6 empty] | 7* | ORION | 2000-12-14 | 472 | 2000-12-14 | 2000-12-19 | 2000-12-28 | PITURCESCU | OK | 2001-01-30 | PENDING |  |  |  |  | OK | Petrica BURGHIU | #N/A | [32 empty] | 360 | Alma | Sibiu | [7 empty] | 2 |  |  | 2
Phase_2 | CS | BV093 | COPSA MICA_RTC | Road Medias-Sibiu(4) | BV093 Copsa Mica_RTC | Transilvania | 46 06 45.3 | 24 13 53.8 | 46 06 48.5 | 24 13 42.2 | Oficiul Romtelecom, str. Sibiului nr.3 | Romtelecom/Pop Coriolan - primar; Terza Vasile - inspector urbanism | 2202 | M | C+C+ | 2/2 | 2202 | [7 empty] | N/A |  |  |  |  | 5 | TN | 40 |  | Room | DIEKAT | OK | VECTOR | 2001-02-01 | 2001-02-28 | YesV | 2001-03-14 | Doru | 2001-03-06 | 2001-03-21 |  |  |  |  | 2000-11-10 |  | 2000-11-29 | 2001-02-01 |  |  |  | 2001-03-01 | ICOM | VECTOR | 2001-03-01 | 2001-03-01 | 2001-03-02 | 2001-03-03 | 2001-03-06 |  | Yes | Theo Radoi | 2001-04-07 | 2001-04-07 | 2001-04-07 | 2001-04-17 | 2001-04-23 | K 739 494 | 60 | 0 | 38.5 | K 739 494 | 215 | 0 | 39 | N/A | N/A | N/A | N/A |  |  |  |  | N/A | 55 | 55 | 7/8" | 55 | 55 | 7/8'' | N/A | N/A | N/A | N/A | N/A | N/A | 220 | N/A | Tg. Mures | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | 2U-3 |  |  |  |  | 70093 | [6 empty] | 20/outdoor |  | 1 | BSC32 | BSC ORADEA | N/A | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PRUNARU | OK | N/A |  | N/A | N/A | 30N01 |  | 2001-03-30 | Denis CIUCU | COSMOROM | [32 empty] | 293 | Copsa Mica | Sibiu | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | BV094 | SEICA MARE | Road Medias-Sibiu(4) | BV093 Copsa Mica_RTC | Transilvania | 46 01 11.5 | 24 09 18 | 46 01 11.5 | 24 09 18 | Sat Seica Mare, Str.. Sibiului nr371A, sos. Sibiu-Medias (DN14) | Trandafir Nicolae - Sieca Mare, nr.371a, str. Sibiului/Trandafir Nicolae - Sieca Mare, nr.371a, str. Sibiului | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-10-19 | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | DIEKAT | OK | DUAL | 2000-10-16 | 2001-01-20 | YesV | 2001-02-01 | Doru | 2001-02-05 | 2001-02-01 |  |  |  |  | 2000-08-17 |  | 2000-09-18 | 2000-10-11 |  |  |  | 2001-04-04 | ICOM | SVF | 2001-01-26 | 2001-01-26 | 2001-04-05 | 2001-04-06 | 2001-04-09 | PAUN | Yes | Mihai Constantin | 2001-04-09 | 2001-04-10 | 2001-04-10 |  |  | K 739 494 | 22 | 0 | 49 | K 739 494 | 190 | 0 | 48 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 58 | 58 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 116 | ML 15 E 1+0 | Tg. Mures | MW | 30 | 1.2 | 49/1.2 | 60 | 15/89 |  |  | 2U-3 |  |  |  | RBS | [9 empty] | 1 | BV093 | COPSA MICA_RTC | 208 | 1.2 | 37.5/1.2 | 54 | 15/84 | [6 empty] | 54* | INTRACOM | 2001-04-04 | 823 | 2001-04-06 | 2001-04-06 | 2001-04-09 | PAUN | OK | 2001-04-10 | PENDING |  |  | 30N01 |  | 2001-03-30 | Petrica BURGHIU | Cosmorom | [32 empty] | 363 | Seica Mare | Sibiu | [7 empty] | 2 |  |  | 2
Phase_2 | CS | BV095 | SLIMNIC | Road Medias-Sibiu(4) | BV093 Copsa Mica_RTC | Transilvania | 45 56 12.1 | 24 09 45.6 | 45 56 12.1 | 24 09 45.6 | Com. Ciocanesti - siloz baza Ciocanesti | Primaria Slimnic - Str. Principala nr.6, 069/ 210 132/Plopaceanu Ioan - Str. Rusilor nr.46, 069/ 404 943 int 220B | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | DIEKAT | OK | DIEKAT | 2000-11-22 | 2001-01-20 | YesV | 2000-12-22 | Doru | 2001-01-09 | 2001-01-19 |  |  |  |  | 2000-08-17 |  | 2000-11-10 | 2000-11-29 |  |  |  | 2001-04-04 | ICOM | SVF | 2001-01-26 | 2001-01-26 | 2001-04-05 | 2001-04-06 | 2001-04-09 | PAUN | Yes | Mihai Constantin | 2001-04-10 | 2001-04-10 | 2001-04-10 |  |  | K 739 494 | 180 | 0 | 49 | K 739 494 | 350 | 0 | 49 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Tg. Mures | MW | 359 | 0.6 | 41.5 | 50 | 15/84 |  |  | 2U-3 |  |  |  | RBS | [9 empty] | 1 | BV094 | SEICA MARE | 179 | 0.6 | 49/0.6 | 60 | 15/89 | [6 empty] | 54* | INTRACOM | 2001-04-04 | 568 | 2001-04-06 | 2001-04-06 | 2001-04-09 | PAUN | OK | 2001-04-10 |  | 2001-05-10 | 2001-05-25 | 30N01 |  | 2001-03-30 | Petrica BURGHIU | Cosmorom | [32 empty] | 579 | Slimnic | Sibiu | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BV096 | SURA MARE | Road Medias-Sibiu(4) | BV049 Dumbrava_RTC | Transilvania | 45 50 28.5 | 24 09 08.1 | 45 50 28.6 | 24 09 08.1 | Sura Mare | Ghirlif Gheorghe - sat Sura Mare nr.417/Ranga Ion - Str. Viile Sibiului nr.21, 069/ 222 553 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-10-19 | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | DIEKAT | OK | DIEKAT | 2000-10-15 | 2000-11-29 | YesV | 2000-12-06 | Doru | 2000-12-04 | 2000-12-13 |  |  |  |  | 2000-08-17 |  | 2000-09-25 | 2000-10-12 |  |  |  | 2000-12-15 | ICOM | DIEKAT | 2000-11-30 | 2000-12-15 | 2000-12-19 | 2001-02-06 | 2001-02-08 |  | Yes | Alexandru Toma | 2001-02-28 | 2001-02-28 | 2001-02-28 | 2001-03-12 | 2001-03-15 | K 739 494 | 10 | 0 | 49 | K 739 494 | 185 | 0 | 49 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Brasov | MW | 215 | 0.6 | 15/0.6 | 25 | 15/84 |  |  | 4U-1 |  |  |  | RBS | [9 empty] | 1 | BV056 | SILOZ | 35 | 0.6 | 44/0.6 | 60 | 15/89 | [6 empty] | 7* | DIEKAT | 2000-12-14 | 421 | 2000-12-15 | 2001-02-06 | 2001-02-14 | DINCA | OK | 2001-02-28 |  | 2001-03-21 | 2001-04-06 | HDSL+30N05 Dumbrava-Balcescu-Brasov |  | 2001-02-28 | Petrica BURGHIU | Cosmorom | [32 empty] | 455 | Sura Mare | Sibiu | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BV097 | DARSTE | Brasov(2+2) | BV002 Astra_CTA | Muntenia | 45 36 58.08 | 25 38 19.84 | 45 36 59.2 | 25 38 40.1 | Str. Prunului nr.10, bl.E3, sc.A | Asociatie de proprietari/D-na. Anca Smeu - pres. , Sc.B, Et.5, 068/ 337 680, 095/ 255 090 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-10-20 | YES |  |  |  |  | 27.5 | B | 31.8 | S3m+S3m+S3m | N/A | PROTELCO | OK | FIBEC | 2001-02-22 | 2001-03-10 | YesV | 2001-04-30 | Marin | 2001-05-07 | 2001-05-03 |  |  |  |  | 2000-09-25 |  | 15/00 | 2001-03-27 |  |  |  | 2001-03-15 | ICOM | TRY | 2001-03-13 | 2001-03-13 | 2001-03-20 | 2001-03-21 | 2001-03-23 | DINCA | Yes | Mircea Mihut | 2001-05-09 | 2001-05-09 | 2001-05-09 | 2001-05-23 | 2001-05-31 | K 739 494 | 0 | 0 | 35.3 | K 739 494 | 120 | 0 | 35.3 | K 739 494 | 260 | 0 | 35.3 |  |  |  |  | N/A | 18 | 18 | 7/8" | 15 | 15 | 7/8" | 10 | 10 | 7/8" | N/A | N/A | N/A | 86 | ML 23 E 1+0 | Brasov | MW | 319 | 0.6 | 35/0.6 | 14.5 | 23/58 |  |  | 2U-3 |  |  |  | RBS | [10 empty] | BV017 | CARPATILOR | 139 | 0.6 | 28/0.6 |  | 23/56 | [6 empty] | 43* | TRYLON | 2001-02-01 | 722 | 2001-03-20 | 2001-03-20 | 2001-03-23 | VLAD | OK | 2001-05-09 | PENDING |  |  | 30N04 Astra-Saturn |  | 2001-02-21 | Ionut GRIGORESCU | Cosmorom | [32 empty] | 634 | Brasov | Brasov | [7 empty] | 2 |  |  | 2
Phase_2 | CS | BV111 | TRIAJ | Brasov(2+2) | BV002 Astra_CTA | Transilvania | 45 40 31.44 | 25 38 47.64 | 45 40 32.8 | 25 38 48 | Str. Harmanului nr.65, bl.B1, Cartier Triaj | Asociatie de proprietari Harmanului 65/Dl. Precu Marius - 068/ 334 344 | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [7 empty] | N/A | N/A |  |  |  | 27.4 | B | 30.2 | S3m+S3m+S3m | Room | PROTELCO | OK | FIBEC | 2001-01-12 | 2001-02-16 | YesV | 2001-04-30 | Marin | 2001-04-06 | 2001-05-03 |  |  |  |  | 2000-11-10 |  | 2000-12-04 | 2000-12-14 |  |  |  | 2001-02-19 | ICOM | VECTOR | 2001-02-19 | 2001-02-19 | 2001-02-20 | 2001-02-22 | 2001-02-23 | VLAD | Yes | Alexandru Toma | 2001-03-06 | 2001-03-06 | 2001-03-06 | 2001-04-17 | 2001-04-23 | K 739 494 | 40 | 0 | 32.3 | K 739 494 | 140 | 0 | 32.3 | K 739 494 | 260 | 0 | 32.3 |  |  |  |  | N/A | 20 | 20 | 7/8" | 28 | 28 | 7/8" | 15 | 15 | 7/8" | N/A | N/A | N/A | 126 |  | Brasov | MW | 206 | 0.6 | 31.5 | 25 | 38/18 |  |  | 2U-3 | [13 empty] | 1 | BV015 | ZIZINULUI | 26 | 0.6 |  | 45 | 38/14 | [6 empty] | 29* | VECTOR | 2001-02-19 | 653 | 2001-02-20 | 2001-02-21 | 2001-02-23 | VLAD | OK | 2001-03-06 | PENDING |  |  | 30N04 Astra-Saturn |  | 2001-02-21 | Denis CIUCU | Cosmorom | [32 empty] | 559 | Brasov | Brasov | [7 empty] | 2 |  |  | 2
Phase_2 | TM | BV112 | TAMPA | Brasov(2+2) | BV001 Brasov_CTA | Muntenia | 45 38 06 | 25 35 38 | 45 38 07.7 | 25 35 48.9 | Statia DRTV - Tampa | DRTv/Ing. Danila Dan-sef statieRR, tel. 092221486 si 068476882 | N/A | N/A | N/A | N/A | N/A | [7 empty] | N/A | N/A |  |  |  | 5 | B | 20 | S | N/A | IMSAT | OK | IMSAT | 2000-12-01 | 2000-12-14 | YesV | Respins | Marin | 2001-02-19 |  |  |  |  | N/A | N/A |  | 2000-11-30 | 2000-12-22 |  |  |  | 2000-11-25 | ICOM | IMSAT | N/A | N/A | 2000-11-26 | N/A | N/A |  | Prov | N/A | 2001-02-09 | 2001-02-09 | 2001-02-09 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | ML 38 E 1+1 | Brasov | MW | 3 | 0.3 | 26 | 30 | 38/14 | YES | 8x2 | 4U-1(TMR9202) |  |  |  | TMR 9202 | [7 empty] | 15/ |  | 1 | BV001 | BRASOV_RTC | 183 | 0.3 | 24 | 40 | 38/18 | [6 empty] | 6 | IMSAT | 2000-11-27 | 370 | 2000-11-27 | 2000-11-27 | 2000-12-13 | DINCA | OK | 2001-01-10 | PENDING |  |  | N/A |  | OK | Cosmorom | Cosmorom | [32 empty] | 868 | Brasov - Tampa | Brasov | [7 empty] | 2 |  |  | 2
Phase_2 | CS | BV114 | MIHAI VITEAZU | Sibiu(9) | BV049 Dumbrava_RTC | Transilvania | 45 46 38 | 24 09 28 | 45 46 41.8 | 24 09 26.9 | Str. Mihai Viteazu bl.29 | Asociatie de locatari/Dl. Isbasoiu Constantin - Bl.29, sc.B, ap.78, 069/ 425 068 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | YES |  |  |  |  | 40 | B | 43.45 | C4.5m+C4.5m | N/A | ROMPSAR | OK | ALMO | 2001-01-18 | 2001-03-05 | YesV | 2001-03-14 | Marin | 2001-03-15 | 2001-03-21 |  |  |  |  | 2000-11-10 |  | 2000-12-08 | 2001-02-12 |  |  |  | 2001-03-13 | ICOM | CAMUSAT | 2001-03-07 | 2001-03-07 | 2001-03-14 | 2001-03-15 | 2001-03-19 |  | Yes | Mihai Constantin | 2001-04-09 | 2001-04-10 | 2001-04-10 | 2001-05-28 | 2001-06-19 | K 739 494 | 30 | 0 | 40.6 | K 739 494 | 220 | 0 | 40.6 | K 739 494 | 290 | 0 | 40.6 |  |  |  |  | N/A | 18 | 18 | 7/8" | 9 | 9 | 7/8" | 20 | 20 | 7/8" | N/A | N/A | N/A | 120 |  | Brasov | MW | 318 | 0.3 | 39 | 18 | 38/14 |  |  | 2U-3 |  |  |  | RBS | [9 empty] | 1 | BV049 | DUMBRAVA_RTC | 137 | 0.3 | 21/0.3 | 25 | 38/18 | [6 empty] | 41* | CAMUSAT | 2001-03-13 | 709 | 2001-03-14 | 2001-03-16 | 2001-03-19 | DINCA | OK | 2001-04-10 |  | 2001-05-10 | 2001-05-25 | HDSL+30N06 Dumbrava-Balcescu-Brasov |  | 2001-02-28 | Denis CIUCU | Cosmorom | [32 empty] | 454 | Sibiu | Sibiu | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BV115 | VALEA AURIE | Sibiu(9) | BV049 Dumbrava_RTC | Transilvania | 45 46 05 | 24 07 33 | 45 46 04.6 | 24 07 34 | Str. Ludus nr.8 bl.31 | Dl. Piciorus - str. Ludus nr.8 bl.31, 069/ 240 178/Dl. Piciorus - str. Ludus nr.8 bl.31, 069/ 240 178 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | Yes | N/A |  |  |  | 35 | B | 35 | C3m+C3m+C3m | N/A | ROMPSAR | OK | ALMO | 2000-12-05 | 2001-01-26 | YesV | 2001-02-21 | Marin | 2001-02-02 | 2001-02-28 |  |  |  |  | 2000-11-10 |  | 2000-11-22 | 2001-01-25 |  |  |  | 2001-02-01 | ICOM | TRY | 2001-02-01 | 2001-02-01 | 2001-02-05 | 2001-02-07 | 2001-02-08 |  | Yes | Alexandru Toma | 2001-02-28 | 2001-02-28 | 2001-02-28 | 2001-03-12 | 2001-03-15 | K 739 494 | 0 | 0 | 36.3 | K 739 494 | 120 | 0 | 36.3 | K 739 494 | 240 | 0 | 36.3 |  |  |  |  | N/A | 28 | 28 | 7/8" | 18 | 18 | 7/8" | 18 | 18 | 7/8" | N/A | N/A | N/A | 128 | ML 38 E 1+0 | Brasov | MW | 50 | 0.6 | 35.75 | 28 | 38/14 |  |  | 2U-3 |  |  |  | RBS | [9 empty] | 1 | BV049 | DUMBRAVA_RTC | 230 | 0.6 |  |  | 38/18 | [6 empty] | 22* | TRYLON | 2001-02-01 | 583 | 2001-02-02 | 2001-02-05 | 2001-02-08 | DINCA | OK | 2001-02-28 | PENDING |  |  | HDSL+30N05 Dumbrava-Balcescu-Brasov |  | 2001-02-28 | Denis CIUCU | Cosmorom | [32 empty] | 469 | Sibiu | Sibiu | [7 empty] | 2 |  |  | 2
Phase_2 | CS | BV118 | PALTINIS_RTC | Road Paltinis-Sibiu(1) | BV048 Balcescu_RTC | Transilvania | 45 39 24.2 | 23 55 56.6 | 45 39 24.2 | 23 55 56.6 | Statiunea Paltinis | Romtelecom/ | MAXITE | M | 1 | 2 | 2PBC | [7 empty] | N/A | N/A |  |  |  | 0 | TE | 32 | T3m | Room | ROMPSAR | OK | ROMPSAR | 2000-12-06 | 2000-12-20 | YesV | 2001-03-20 | Marin | 2001-01-19 | 2001-03-21 |  |  |  | N/A | 2000-11-10 |  | 2000-11-20 | 2001-01-23 |  |  |  | 2000-12-28 | ICOM | TRY | 2000-12-20 | 2000-12-21 | 2001-01-11 | 2001-01-15 | 2001-01-19 |  | Yes | Bogdan Bogodai | 2001-04-13 | 2001-04-13 | 2001-04-13 | 2001-05-31 | 2001-06-19 | AAU | 40 | 0 | 34 | AAU | 240 | 0 | 34 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 40 | 40 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 80 | N/A | Brasov | HDSL | N/A | N/A | N/A | N/A | N/A |  | N/A | [15 empty] | BV048 | NICOLAE_BALCESCU | [11 empty] | N/A |  | N/A |  | 2001-04-02 | 2001-04-02 | 2001-04-03 | VLAD | OK | 2001-04-13 |  | N/A | N/A | HDSL+RR+30N01 Nicolae Balcescu-Brasov |  | 2001-03-12 | Cristi CROITOR | Cosmorom | [32 empty] | 1382 | Paltinis | Sibiu | [7 empty] | 2 |  |  | 2
Phase_2 | CS | BV120 | DEDA_RTC | Road Reghin-Gheorghieni(1) | CJ034 Reghin_RTC | Transilvania | 46 56 46.9 | 24 52 19.1 | 46 56 46.9 | 24 52 19.1 | Com. Deda, Romtelecom | Romtelecom/Eros Csaba - sef retea urbana Reghin - RTC Reghin, 095/ 823 199 | MAXITE | M | 1 | 2 | 2PBC | [7 empty] | N/A | N/A |  |  |  | 0 | TE | 25.25 |  | Room | PROTELCO | OK | KEN-KEN | 2001-01-15 | 2001-02-05 | YesV | 2001-02-15 | Andrei | 2001-02-13 | 2001-02-26 |  |  |  | N/A | 2001-07-13 |  | 2000-12-12 | 2001-01-16 |  |  |  | 2001-02-06 | ICOM | TRY | 2001-02-06 | 2001-02-05 | 2001-02-07 | 2001-02-09 | 2001-02-10 |  | Yes |  | CW ZJ250 |  |  |  |  | AAU | 60 | 0 | 23.75 | AAU | 230 | 0 | 23.75 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 32 | 32 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 64 | ML 23 E 1+0 | Tg. Mures | MW | 220 | 0.6 | 25/0.6 | [8 empty] | N/A | XC60034 | [6 empty] | 35/Outdoor |  |  | ZJ250 | RUSII MUNTI | 40 | 0.6 | 45/0.6 | [12 empty] | 2001-02-07 | 2001-02-07 | 2001-02-09 | [6 empty] | 30N02 |  | OK | Cosmorom | Cosmorom | [32 empty] | 470 | Deda | Mures | [7 empty] | 2 |  |  | 2
Phase_3 | CS | BV122 | POPLACA | Road Paltinis-Sibiu(2) | BV049 Dumbrava_RTC | Transilvania | 45 43 27.1 | 24 04 13.3 |  |  |  |  | 2101 | M | C+ | 2 | 2101 | [49 empty] | RBS 2101 | [30 empty] | N/A | N/A | N/A |  |  | Brasov | MW | 44 | [21 empty] | BV049 | DUMBRAVA_RTC | [27 empty] | Bogdan CRAIU | [33 empty] | 562 | [9 empty] | 3 |  |  | missing
Phase_3 | CS | BV124 | CULMENI | Miercurea Ciuc | BV086 Miercurea Ciuc_RTC | Transilvania | 46 21 56.1 | 25 48 33.7 | 46 21 56.1 | 25 48 33.7 | str. Culmei nr.17, Loc.Miercurea Ciuc, Jud. Harghita | Antal Carol, str. Culmei, nr.17, ap. 22, et.5, tel 095/563876 si 066/123993 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | YES |  |  |  |  | 33.5 | B | 36.3 | S4m+S4m+S4m | N/A | SVF | OK | SVF | 2001-05-05 | 2001-05-15 | YesV | 2001-06-15 | Andrei |  | 2001-06-26 | 2001-02-16 |  |  | 2001-03-20 | 2001-05-22 |  | OK | 2001-05-14 |  |  | 1902-08-31 | 2001-05-14 | ICOM | SVF | 2001-05-14 |  | 2001-05-15 | 2001-05-17 | 2001-05-19 | IVAN |  | Bogdan Bogodai | 2001-06-05 | 2001-06-05 | 2001-06-05 | 2001-06-21 | 2001-07-11 | K 739 494 | 0 | 0 | 38 | K 739 494 | 180 | 0 | 37.8 | K 739 494 | 250 | 0 | 38 |  |  |  |  | N/A | 19 | 19 | 7/8" | 23 | 23 | 7/8" | 23 | 23 | 7/8" | N/A | N/A | N/A | 130 | ML 38 E 1+0 | Brasov | MW | 172 | 0.3 | 40 | 25 | 38/18 |  |  | 2U-3 | [13 empty] | 1 | BV034 | MIERCUREA CIUC | 329 | 0.3 |  | 25 | 38/14 | [6 empty] | 70* | ICOM | 2001-05-23 | 946 | 2001-05-24 | 2001-05-24 | 2001-05-26 | IVAN | 2001-05-31 | 2001-06-05 |  | 2001-06-19 | 2001-07-10 | 30N01 M. Ciuc-Brasov |  | OK | Florin BELEA | Andrei DUMITRESCU | [33 empty] | Miercurea Ciuc | Harghita | [7 empty] | 3 |  |  | 2
Phase_3 | CS | BV125 | MOACSA | Road Brasov-Onesti(9) | BV126 Tg. Secuiesc_RTC | Transilvania | 45 53 58.1 | 26 00 20.6 | 45 54 08 | 26 00 19 | Loc. Moacsa | Vas Arpad - str. Oltului nr.40, Sf.Gheorghe, 067/ 313 220 | MAXITE | M | 1 | 2 | 2PBC | [12 empty] | 0 | TN | 50 |  | N/A/TMR9000 | ISAF | OK | AQUA | 2001-06-20 | 2001-08-18 | in exec |  | Andrei | [5 empty] | 2001-04-17 | 2001-04-06 |  | 2001-05-09 | 2001-06-14 | [14 empty] | MAXITE |  |  |  |  | AAU | 10 | 0 | 48.9 | AAU | 220 | 0 | 48.7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | 56 | 56 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 112 | ML 15 E 1+0 | Brasov | MW | 42 | 1.2 | 30 | 36 | [18 empty] | BV126 | TG. SACUIESC_RTC | 222 | 1.2 | 20 | 25 | [23 empty] | Dragos BICIU | CATALINA CIOCAN | [32 empty] | 604 | Moacsa | Covasna | [7 empty] | 3 |  |  | 3
Phase_3 | CS | BV126 | TG. SACUIESC_RTC | Road Brasov-Onesti(9) | BV126 Tg. Secuiesc_RTC | Transilvania | 45 59 48.7 | 26 07 52.2 | 45 59 48.7 | 26 07 52.2 | Str. GH. Doja, nr. 31 | Romtelecom/D-ul Imre Kadar, tel. 095/836821 | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [12 empty] | 0/parter | B | 13 | TE-32m | Room/TMR9202 | ISAF | OK | ISAF | 2001-05-22 | 2001-05-31 | YesV |  | Andrei |  |  | 2001-03-19 |  |  | N/A | 2001-04-06 |  | 2001-04-17 | 2001-05-07 |  |  | 1902-10-30 | 2001-06-06 | ICOM | INTERACTIVE | 2001-06-04 |  | 2001-06-07 | 2001-06-07 | 2001-06-10 | RADU |  | Bogdan Bogodai | 2001-06-19 | 2001-06-19 | 2001-06-19 | 2001-06-29 | 2001-07-11 | K 739 494 | 90 | 0 | 30 | K 739 494 | 230 | 0 | 30 | K 739 494 | 350 | 0 | 30 |  |  |  |  | N/A | 35 | 35 | 7/8" | 35 | 35 | 7/8" | 35 | 35 | 7/8" | N/A | N/A | N/A | 210 | N/A | Brasov | FO | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | Indoor Comteck | 70126 | [6 empty] | 10m/50m/16pInd/16pOut |  |  | BSC12 | BSC BRASOV | N/A | N/A |  |  | N/A | [10 empty] | N/A | N/A | N/A | RADU |  | N/A |  |  |  | 30N01 Tg. Secuiesc-Brasov |  | 2001-06-19 | Dragos BICIU | CATALINA CIOCAN | [33 empty] | Tg. Secuiesc | Covasna | [7 empty] | Site Near=Insertion Point
Phase_3 | CS | BV127 | TUFALAU | Road Brasov-Onesti(9) | BV126 Tg. Secuiesc_RTC | Transilvania | 45 50 10.5 | 26 01 39.7 | 45 50 16.8 | 26 01 43.6 | Loc Tufalau | Csiki Iren, Tufalau, nr.72 | MAXITE | M | 1 | 2 | 2PBC | [12 empty] | 0 | TN | 50 |  | N/A/TMR9000 | ISAF | OK | AXA | 2001-06-20 | 2001-07-17 | Yes |  | Andrei | [5 empty] | 2001-04-17 | 2001-04-06 |  | 2001-05-03 | 2001-06-14 | [14 empty] | MAXITE |  |  |  |  | AAU | 90 | 0 | 49 | AAU | 260 | 0 | 49 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | 54 | 54 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 108 | ML 15 E 1+0 | Brasov | MW | 85 | 1.2 | 49 | 54 | [18 empty] | BV128 | COVASNA_RTC | 265 | 1.2 | 30 | 22 | [23 empty] | Dragos BICIU | CATALINA CIOCAN | [32 empty] | 525.3 | Tufalau | Covasna | [7 empty] | 3 |  |  | 3
Phase_3 | CS | BV128 | COVASNA_RTC | Road Brasov-Onesti(9) | BV126 Tg. Secuiesc_RTC | Transilvania | 45 50 43.1 | 26 10 17.8 | 45 50 43.1 | 26 10 17.8 | Str. Libertatii, nr.1 | Romtelecom/D-ul Vlaicu, tel 094/337287 | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [12 empty] | 10 | B | 13m | TE-52m | Room/TMR9202 | ISAF | OK | ISAF | 2001-05-22 | 2001-05-31 | Yes |  | Andrei | [5 empty] | N/A | 2001-04-06 |  | 2001-04-17 | 2001-05-07 | [6 empty] | 2001-06-04 |  |  |  |  | NO-CIPRIAN |  |  | CW BV125 |  |  |  |  | K 739 494 | 10 | 0 | 45 | K 739 494 | 110 | 0 | 45 | K 739 494 | 250 | 0 | 42 |  |  |  |  | N/A | 45 | 45 | 7/8" | 45 | 45 | 7/8" | 45 | 45 | 7/8" | N/A | N/A | N/A | 270 | ML 15 E 1+0 | Brasov | MW | 295 | 1.2 | 45 | 33 | [18 empty] | BV125 | MOACSA | 115 | 1.2 | 30 | 36 | [23 empty] | Catalina Ciocan | Dragos BICIU | [33 empty] | Covasna | Covasna | [7 empty] | 3 |  |  | 3
Phase_3 | CS | BV129 | LUNGA | Road Brasov-Onesti(9) | BV126 Tg. Secuiesc_RTC | Transilvania | 46 01 49.7 | 26 13 52.4 |  |  |  |  | MAXITE | M | 1 | 2 | 2PBC | [17 empty] | ISAF |  | DUAL | 2001-08-01 | 2001-09-10 |  |  | Andrei | [6 empty] | 2001-04-06 | [17 empty] | MAXITE | [30 empty] | N/A | N/A | N/A |  | ML 15 E 1+0 | Brasov | MW | 224 | [21 empty] | BV126 | TG. SACUIESC_RTC | 64 | 1.2 | 25 | 30 | [23 empty] | Dragos BICIU | CATALINA CIOCAN | [42 empty] | 3 |  |  | 3
Phase_3 | CS | BV130 | BRETCU | Road Brasov-Onesti(9) | BV126 Tg. Secuiesc_RTC | Transilvania | 46 03 13.7 | 26 21 58.9 | 46 03 13.7 | 26 21 59.9 | Loc Bretcu | Toth Gizella, sat Bretcu, nr662 | MAXITE | M | 1 | 2 | 2PBC | [12 empty] | 0 | TN | 50 | 2C2m+2C1.5m | N/A/TMR9000 | ISAF | OK | DUAL | 2001-07-12 | 2001-08-10 | in exec |  | Andrei | [5 empty] | 2001-04-17 | 2001-04-06 |  | 2001-05-09 | 2001-06-14 | [14 empty] | MAXITE |  |  |  |  | AAU | 40 | 0 | 49 | AAU | 260 | 0 | 49 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | 54 | 54 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 108 | ML 15 E 1+0 | Brasov | MW | 256 | 1.2 | 46 | 54 | [18 empty] | BV129 | LUNGA | 76 | [26 empty] | Dragos BICIU | CATALINA CIOCAN | [32 empty] | 923 | Bretcu | Covasna | [7 empty] | 3 |  |  | 3
Phase_3 | CS | BV131 | CABANA VALEA OLTULUI | Road Rm. Valcea-Talmaciu(9) | BV049 Dumbrava_RTC | Transilvania | 45 34 56.7 | 24 15 13.7 |  |  |  |  | MAXITE | M | 1 | 2 | 2PBC | [17 empty] | DIEKAT | OK | DIEKAT | 2001-08-01 | 2001-09-10 |  |  | Mugur |  |  | 2001-05-16 |  |  |  | 2001-05-16 | [17 empty] | MAXITE | [30 empty] | N/A | N/A | N/A |  |  | Brasov | MW | [22 empty] | BV132 | TURNU ROSU | [27 empty] | Dragos BICIU | Daniel BICIU | [42 empty] | missing |  |  | missing
Phase_3 | CS | BV132 | TURNU ROSU | Road Rm. Valcea-Talmaciu(9) | BV049 Dumbrava_RTC | Transilvania | 45 36 18.1 | 24 16 15.1 |  |  |  |  | 2101 | M | C+ | 2 | 2101 | [17 empty] | DIEKAT | OK | DIEKAT | 2001-08-01 | 2001-09-10 |  |  | Mugur |  |  | 2001-05-16 |  |  |  | 2001-05-16 | [17 empty] | RBS 2101 | [30 empty] | N/A | N/A | N/A |  |  | Brasov | MW | [22 empty] | BV133 | BOITA | [27 empty] | Dragos BICIU | Daniel BICIU | [42 empty] | missing |  |  | missing
Phase_3 | CS | BV133 | BOITA | Road Rm. Valcea-Talmaciu(9) | BV049 Dumbrava_RTC | Transilvania | 45 39 10.4 | 24 16 16.2 |  |  |  |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [17 empty] | DIEKAT | OK | DIEKAT | 2001-08-01 | 2001-09-10 |  |  | Mugur |  |  | 2001-05-16 |  |  |  | 2001-05-16 | [17 empty] | CTR | [30 empty] | N/A | N/A | N/A |  |  | Brasov | MW | [22 empty] | BV047 | VESTEM | [27 empty] | Dragos BICIU | Daniel BICIU | [42 empty] | missing |  |  | missing
Phase_3 | CS | BV134 | SICULENI | Road Gheorghieni-M.Ciuc | BV086 Miercurea Ciuc_RTC | Transilvania | 46 26 31.14 | 25 44 52.2 |  |  |  |  | MAXITE | M | 1 | 2 | 2PBC | [27 empty] | 2001-07-12 | [8 empty] | 2001-07-12 | [47 empty] | ML 15 E 1+0* | Brasov | MW | [22 empty] | BV124 | CULMEI | [27 empty] | Petrica BURGHIU | Calin ACHIM
Phase_3 | CS | BV135 | SANDOMINIC | Road Gheorghieni-M.Ciuc | BV086 Miercurea Ciuc_RTC | Transilvania | 46 34 21.79 | 25 48 14.07 |  |  |  |  | MAXITE | M | 1 | 2 | 2PBC | [27 empty] | 2001-07-12 | [8 empty] | 2001-07-12 | [47 empty] | ML 15 E 1+0* | Brasov | MW | [22 empty] | BV134 | SICULENI | [27 empty] | Petrica BURGHIU | Calin ACHIM
Phase_3 | CS | BV136 | IZVORUL MURESULUI | Road Gheorghieni-M.Ciuc | YV140 Gheorghieni_RTC | Transilvania | 46 37 30.89 | 25 42 56.42 |  |  |  |  | MAXITE | M | 1 | 2 | 2PBC | [27 empty] | 2001-07-12 |  |  |  | 2001-07-13 |  |  |  |  | 2001-07-12 | [47 empty] | ML 15 E 1+0 | Brasov | MW | [22 empty] | BV137 | SUSENI | [27 empty] | Petrica BURGHIU | Calin ACHIM
Phase_3 | CS | BV137 | SUSENI | Road Gheorghieni-M.Ciuc | YV140 Gheorghieni_RTC | Transilvania | 46 37 04.18 | 25 34 05.12 |  |  |  |  | MAXITE | M | 1 | 2 | 2PBC | [27 empty] | 2001-07-12 |  |  |  | 2001-07-13 |  |  |  |  | 2001-07-12 | [47 empty] | ML 15 E 1+0 | Brasov | MW | [22 empty] | BV141 | JOSENI | [27 empty] | Petrica BURGHIU | Calin ACHIM
Phase_3 | CS | BV138 | GHEORGHIENI TURN APA | Road Gheorghieni-M.Ciuc | YV140 Gheorghieni_RTC | Transilvania | 46 43 02.9 | 25 34 40.7 |  |  |  |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [27 empty] | 2001-07-12 |  |  |  | 2001-07-13 |  |  |  |  | 2001-07-12 | [47 empty] | ML 38 E 1+1 | Brasov | MW | [22 empty] | YV140 | GHEORGHIENI_RTC | [27 empty] | Petrica BURGHIU | Calin ACHIM
Phase_3 | CS | BV139 | GHEORGHIENI HOTEL | Road Gheorghieni-M.Ciuc | YV140 Gheorghieni_RTC | Transilvania | 46 43 22.7 | 25 35 45.1 |  |  |  |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [27 empty] | 2001-07-12 |  |  |  | 2001-07-13 |  |  |  |  | 2001-07-12 | [47 empty] | ML 23 E 1+0 | Brasov | MW | [22 empty] | BV138 | GHEORGHIENI TURN APA | [27 empty] | Petrica BURGHIU | Calin ACHIM
Phase_3 | CS | BV141 | JOSENI | Road Gheorghieni-M.Ciuc | YV140 Gheorghieni_RTC | Transilvania | 46 42 07.26 | 25 30 09.28 |  |  |  |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [27 empty] | 2001-07-12 |  |  |  | 2001-07-13 |  |  |  |  | 2001-07-12 | [47 empty] | ML 23 E 1+0 | Brasov | MW | [22 empty] | BV138 | GHEORGHIENI TURN APA | [27 empty] | Petrica BURGHIU | Calin ACHIM
Phase_3 | CS | BV142 | REMETEA | Road Gheorghieni-Reghin | YV140 Gheorghieni_RTC | Transilvania | 46 47 54.18 | 25 26 59.81 |  |  |  |  | MAXITE | M | 1 | 2 | 2PBC | [27 empty] | 2001-07-12 |  |  |  | 2001-07-13 |  |  |  |  | 2001-07-12 | [47 empty] | ML 15 E 1+0 | Brasov | MW | [22 empty] | BV141 | JOSENI | [27 empty] | Petrica BURGHIU | Calin ACHIM
Phase_3 | CS | BV143 | SARMAS | Road Gheorghieni-Reghin | BV145 Toplita_RTC | Transilvania | 46 53 06.3 | 25 26 13.19 |  |  |  |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [27 empty] | 2001-07-12 | [8 empty] | 2001-07-12 | [47 empty] | ML 15 E 1+0* | Brasov | MW | [22 empty] | BV145 | TOPLITA_RTC | [27 empty] | Petrica BURGHIU | Calin ACHIM
Phase_3 | CS | BV145 | TOPLITA_RTC | Road Gheorghieni-Reghin | BV145 Toplita_RTC | Transilvania | 46 55 29.79 | 25 21 12.81 |  |  |  |  | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [27 empty] | 2001-07-12 | [8 empty] | 2001-07-12 | [47 empty] | N/A | Brasov | FO | [22 empty] | BSC12 | BSC BRASOV | [27 empty] | Petrica BURGHIU | Calin ACHIM
Phase_3 | CS | BV146 | TOPLITA EDILTOP | Road Gheorghieni-Reghin | BV145 Toplita_RTC | Transilvania | 46 55 50.06 | 25 20 53.4 |  |  |  |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [27 empty] | 2001-07-12 | [8 empty] | 2001-07-12 | [47 empty] | ML 38 E 1+0* | Brasov | MW | [22 empty] | BV145 | TOPLITA_RTC | [27 empty] | Petrica BURGHIU | Calin ACHIM
Phase_3 | CS | BV151 | BISTRA MURESULUI | Road Gheorghieni-Reghin | CJ034 Reghin_RTC | Transilvania | 46 58 42.23 | [5 empty] | MAXITE | M | 1 | 2 | 2PBC | [27 empty] | 2001-07-12 |  |  |  | 2001-07-13 |  |  |  |  | 2001-07-12 | [47 empty] | ML 23 E 1+0 | Tg. Mures | MW | [22 empty] | BV120 | DEDA_RTC | [27 empty] | Petrica BURGHIU | Calin ACHIM
Phase_3 | CS | BV152 | FLORILOR | Miercurea Ciuc | BV086 Miercurea Ciuc_RTC | Transilvania | 46 21 42.6 | 25 47 53.5 | [94 empty] | Brasov | MW | [22 empty] | BV124 | CULMEI
Phase_1 | CS | BV501 | TIMISU DE SUS | Road Buc-Bra | BV001 Brasov_CTA | Transilvania | 25 35'20,7"E | 45 32'19,5"N | 45 33 00.5 | 25 35 19.6 | Teren Primarie pe dreapta drumului spre Brasov, langa Halta Timisu de Sus | Primarie/ | 2101 | M | C+ | 2 | 2101 | [6 empty] | OK |  | N/A |  |  |  | N/A | TN | 40 | New 40m tower | OUTDOOR | IMSAT | OK | IMSAT | OK | 2000-03-15 | YesV | OK | AUREL | OK | OK |  |  |  | 1999-11-30 | 2000-03-02 |  | 2000-03-02 | OK |  |  |  | 00:0009 | ETR | Electotrade | OK | OK | 2000-03-14 | 2000-03-21 | 2000-03-23 |  | Yes | Cristian Croitor | 2000-03-30 | 2000-03-30 | 2000-03-30 | 2000-04-10 | OK | K 739 494 | 5 | 0 | 39.7 | K 739 494 | 210 | 0 | 39.7 | N/A | N/A | N/A | N/A |  |  |  |  | K 63 55 8 | 45 | 45 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 90 | ML 23 E 1+0 | Brasov | MW | 323 | 0.6 |  |  | 23/56 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [9 empty] | 1 | BV505 | POSTAVARU | 143 | 0.6 |  |  | 23/58 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-10-03 |  |  | 2000-10-03 | 30N03 conectare locala |  | OK | DAN | DAN | [32 empty] | 823 | Timisul de Sus | Brasov | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BV504 | SACELE | Road Buc-Bra | BV001 Brasov_CTA | Transilvania | 25 39'54,3"E | 45 36'33,0"N | 45 36 36.5 | 25 39 47.7 | Str. Noua, jud. Brasov | Paul Becheanu, 068.415.691; Str. Dealul de Jos/Paul Becheanu, 092.499.299; 068.415.691 | 2202 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | TN | 40 | New 40 m tower | SHELTER | IMSAT | OK | IMSAT | OK | OK | YesV | OK | AUREL | 2000-03-03 | OK |  |  |  | 1999-11-24 | OK |  | OK | 2000-01-20 |  |  |  | 00:0009 | YRO | ISAF | OK | OK | OK | OK | 2000-03-03 |  | Yes | Cristian Croitor | 2000-03-09 | 2000-03-16 | 2000-03-16 | 2000-03-21 | OK | K 739 494 | 90 | 0 | 35 | K 739 494 | 230 | 0 | 35 | K 739 494 | 320 | 6 | 35 |  |  |  |  | No | 45 | 45 | 7/8" | 45 | 45 | 7/8" | 45 | 45 | 7/8" | N/A | N/A | N/A | 270 | ML 23 E 1+0 | Brasov | MW | 238 | 0.6 |  |  | 23/56 |  | 4x2/8 | 4U-1(TMR9202) |  |  |  | TMR 9202 | [9 empty] | 1 | BV505 | POSTAVARU | 57.9 | 0.6 |  |  | 23/58 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-05-09 |  |  | 2000-05-31 | 30N03 conectare locala |  | OK | DAN | DAN | [32 empty] | 665 | Sacele | Brasov | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BV505 | POSTAVARU | Road Buc-Bra | BV001 Brasov_CTA | Transilvania | 25 34'19,0"E | 45 34'05,0"N | 45 34 07.6 | 25 34 09.1 | DRTV Postavarul | /Sebestien, 092.221.485 | 2202 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | TE | 12 | T3m+T3m+T3m+C4m | ROOM | IMSAT | OK | IMSAT | OK | OK | YesV | OK | AUREL | 2000-02-18 | 2000-02-10 |  |  |  | 1999-11-30 | OK |  | OK | 2000-02-16 |  |  |  | N/A | ETR | Electotrade | 2000-02-18 | OK | 2000-02-21 | 2000-02-21 | 2000-02-25 |  | Yes | Cristian Croitor | 2000-02-26 | 2000-06-23 | 2000-07-18 | 2000-06-23 | 2000-07-19 | K 739 494 | 80 | -8 | 14 | K 739 494 | 160 | -8 | 14 | K 739 494 | 330 | 0 | 14 |  |  |  |  | No | 30 | 30 | 7/8" | 30 | 30 | 7/8" | 30 | 30 | 7/8" | N/A | N/A | N/A | 180 |  | Brasov | MW | 13 | 0.6 | 20 | 40 | 15/89 | YES | 8x2 | 4U-1 |  |  |  | Indoor Comteck | [9 empty] | 1 | BV112 | TAMPA | 193 | 1.2 | 22 | 30 | 15/84 | [6 empty] | 6 | IMSAT |  | 371 | 2000-11-27 | OK | OK | OK | OK | 2001-02-10 |  | 2001-02-21 | 2001-03-02 | 30N04 conectare locala |  | OK | DAN | DAN | [32 empty] | 1799 | Brasov | Brasov | [7 empty] | 2 | 1 | 1 | 2
Phase_1 | CS | BV510 | POIANA BRASOV | Brasov | BV001 Brasov_CTA | Transilvania | 45 35 39.9 | 25 32 56.0 | 45 35 39.9 | 25 32 56.0 | Hotel Piatra Mare, Poiana Brasov | Private/Dorin Sovaila (director), 068.262.320 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | 2000-06-27 |  |  |  |  | B |  |  | OUTDOOR | SVF | OK | SVF | OK | OK | YesV | OK | DRAGOS | 1999-12-21 | OK |  |  |  | 1999-11-24 | OK |  | OK | 1999-12-15 | IP devine BV001 Brasov_RTC |  |  | N/A | YRO | YRO | 2000-01-13 | OK | OK | OK | 2000-02-05 |  | Yes | Cristian Croitor | 2000-02-19 | 2000-03-24 | 2000-03-25 | 2000-03-27 | OK | K 739 494 | 90 | 0 | 0 | K 739 494 | 180 | 0 | 0 | N/A | N/A | N/A | N/A |  |  |  |  | N/A | 30 | 30 | 7/8" | 30 | 30 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A | 120 |  | Brasov | MW | 60 | 0.6 |  |  | 23/56 | [6 empty] | RBS | [9 empty] | 1 | BV511 | POIANA BRASOV_FAVORIT | 240 | 0.6 |  |  | 23/58 | ZV001 | [5 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-05-09 |  | 2000-09-25 | 2000-10-03 |  |  | N/A | MIHAI C. | MIHAI C. | [32 empty] | 1035 | Poiana Brasov | Brasov | [7 empty] | 1 |  |  | 1
Phase_1 | TM | BV511 | POIANA BRASOV_FAVORIT | Brasov | BV001 Brasov_CTA | Transilvania | 45 35 45.8 | 25 33 11.0 | 45 35 45.8 | 25 33 11.0 | Restaurant Erotic Show in complexul Favorit, Strada Vulturului no 2, Poiana Brasov, Jud. Brasov | Private/Sanda ZAMFIR, patron SC ROMELI , Strada Vulturului no 2 Poiana Brasov, 068/312016 | N/A | N/A | N/A | N/A | N/A | [8 empty] | N/A |  |  |  | N/A | B | 8 | Suport 1m | N/A | SVF | OK | SVF | OK | OK | YesV | OK | DRAGOS | OK | OK |  |  |  | 2000-02-14 | 2000-02-14 |  | 2000-02-14 | 2000-02-15 | Se anuleaza |  |  | OK | YRO | SVF | N/A | N/A | N/A | N/A | N/A |  | Yes | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | N/A | Brasov | FO | N/A | N/A | N/A | N/A | N/A |  | 4x2/8 | 2U-3 |  |  |  | Indoor Comteck | [10 empty] | BSC12 | BSC BRASOV | N/A | N/A |  |  | N/A | [6 empty] | OK | OK | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2000-05-09 |  |  | 2000-05-31 |  |  | N/A | DAN | DAN | [32 empty] | 1017 | Poiana Brasov | Brasov | [7 empty] | Site Near=Insertion Point
Phase_1 | TM | BV512 | POIANA_BRASOV_PTT | Brasov | BV001 Brasov_CTA | Transilvania | 45 35 45.8 | 25 33 11.0 | 45 35 45.8 | 25 33 11.0 | Oficiul Postal Poiana Brasov | RTC/Florin MUNTEANU sau Marius SOPORAN, tel 068/262300 | N/A | N/A | N/A | N/A | N/A | [8 empty] | N/A |  |  |  | N/A | B | 8 | Nimic | ROOM | SVF | OK | SVF | OK | OK | YesV | OK | DRAGOS | OK | OK |  |  |  | 2000-02-14 | 2000-02-14 |  | 2000-02-14 | 2000-02-15 | Se anuleaza |  |  | OK | YRO | SVF | N/A | N/A | N/A | N/A | N/A |  | Yes | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | N/A | Brasov | FO | N/A | N/A | N/A | N/A | N/A |  | 4x2/8 | 2U-3 |  |  |  | Indoor Comteck | 70512 | 2000-02-16 | [7 empty] | 1 | BSC12 | BSC BRASOV | N/A | N/A |  |  | N/A | [6 empty] | OK | OK | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2000-05-09 |  |  | 2000-05-31 |  |  | N/A | DAN | DAN | [32 empty] | 1017 | Poiana Brasov | Brasov | [7 empty] | Site Near=Insertion Point
Phase_3 | CS | BV900 | PIATA SFATULUI | Brasov | BV001 Brasov_CTA | Transilvania | 45 38 50 | 25 35 26 |  |  |  |  | MAXITE | M | 1 | 2 | 2PBC | [13 empty] | B |  | Drapel |  | ISAF |  | FIBEC | 2001-08-01 | 2001-09-10 |  |  | Andrei | [6 empty] | 2001-04-17 | [17 empty] | MAXITE | [30 empty] | N/A | N/A | N/A |  | N/A | Brasov | HDSL | N/A | N/A | N/A | N/A | N/A |  | N/A | [15 empty] | BV001 | ROMTELECOM CTA |  | N/A |  |  | N/A | [10 empty] | N/A | N/A | N/A |  |  | N/A |  |  |  | N/A |  | OK | Dragos BICIU | Dragos BICIU | [42 empty] | 3 |  |  | missing
Phase_1 | CS | BX001 | ROMTELECOM CTA | Constanta | BX001 Constanta_CTA | Dobrogea | 44 10 46.3 | 28 38 58.5 | 44 10 46.3 | 28 38 58.5 | Bdul. Tomis 79-81 - Romtelecom CTA Constanta | RTC/ | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | 2000-06-27 |  |  |  | N/A | B |  |  | OUTDOOR | ORION | OK | ORION | OK | 1999-10-21 | YesV | OK | MUGUREL | 1999-10-21 | 1999-10-26 |  |  |  | OK | OK |  | OK | 1999-10-06 |  |  |  | 99:0003 | ETR | N/A | OK | OK | 1999-11-22 | OK | 1999-11-26 |  | Yes | Theo Radoi | 28-IAN-00 | 2000-03-15 | 2000-03-15 | 2000-03-23 | OK | K 739 494 | 5 | 6 | 0 | K 739 494 | 190 | 8 | 0 | K 739 494 | 240 | 6 | 0 |  |  |  |  | N/A | 43 | 43 | 7/8" | 42 | 42 | 7/8" | 43 | 43 | 7/8" | N/A | N/A | N/A | 256 | N/A | Constanta | FO | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | TMR 9202 | 30001 | Phase_1 | [7 empty] | 1 | BSC13 | BSC CONSTANTA |  | N/A |  |  | N/A | [6 empty] | OK | OK | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 30N01 RTC-Constanta |  | OK | MIHAI C. | MIHAI C. | [32 empty] | 37 | Constanta | Constanta | [7 empty] | Site Near=Insertion Point
Phase_1 | CS | BX002 | TOMIS NORD | Constanta | BX002 Tomis Nord | Dobrogea | 44 12 02.8 | 28 37 38.6 | 44 12 01.4 | 28 37 40.4 | Bd-ul Tomis nr.318 | RTC/ | 2202 | M/E | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | B |  |  | ROOM | ORION | OK | ORION | OK | 1999-10-21 | YesV | OK | MUGUREL | 1999-10-21 | 1999-10-26 |  |  |  | OK | OK |  | OK | 1999-10-06 |  |  |  | 99:0003 | ETR | N/A | OK | OK | 1999-11-22 | OK | 1999-11-26 |  | Yes | Theo Radoi | 2000-02-09 | 2000-03-14 | 2000-03-14 | 2000-03-23 | OK | K 739 494 | 0 | 7 | 0 | K 739 494 | 100 | 6 | 0 | K 739 494 | 250 | 4 | 0 |  |  |  |  | N/A | 25 | 25 | 7/8" | 25 | 25 | 7/8" | 25 | 25 | 7/8" | N/A | N/A | N/A | 150 | N/A | Constanta | FO | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | Indoor Comteck | 30002 | Phase_1 | [7 empty] | 1 | BSC13 | BSC CONSTANTA |  | N/A |  |  | N/A | [6 empty] | OK | OK | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 30N03 Tomis Nord-Constanta |  | OK | MIHAI C. | MIHAI C. | [32 empty] | 25 | Constanta | Constanta | [7 empty] | Site Near=Insertion Point
Phase_1 | CS | BX003 | MAMAIA CTA | Constanta | BX003 Mamaia_CTA | Dobrogea | 44 13 58.9 | 28 37 38.1 | 44 13 58.9 | 28 37 38.1 | Bdul. Tomis - Romtelecom CTA Mamaia | RTC/ | 2202 | M | C+C+C+ | 2/2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | B |  | PILONET 12m | ROOM | SVF | OK | SVF | OK | OK | YesV | OK | DRAGOS | 2000-02-21 | OK |  |  |  | OK | 1999-10-11 |  | 1999-10-11 | OK |  |  |  | 00:0009 | ETR | Electotrade | OK | OK | 2000-02-23 | 2000-02-23 | 2000-03-05 |  | Yes | Cristian Croitor | 2000-04-22 | 2000-04-22 | 2000-04-22 | 2000-04-24 | OK | K 739 494 | 160 | 5 | 34 | K 739 494 | 350 | 3 | 34 | N/A | N/A | N/A | N/A |  |  |  |  | N/A | 25 | 25 | 7/8" | 25 | 25 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A | 100 | N/A | Constanta | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | 4U-1(TMR9202) |  |  |  | TMR 9202 | XC30003 | 2001-07-10 | YES | [6 empty] | 1 | BSC13 | BSC CONSTANTA |  | N/A |  |  | N/A | [6 empty] | OK | OK | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 30N01 Mamaia-Constanta |  | OK | MIHAI C. | MIHAI C. | [32 empty] | 1 | Mamaia | Constanta | [7 empty] | Site Near=Insertion Point
Phase_1 | CS | BX004 | NAVODARI CTA | Constanta | BX004 Navodari_CTA | Dobrogea | 44 19 22.0 | 28 36 47.9 | 44 19 22.0 | 28 36 47.9 | Centrala Telefonica Navodari | RTC/ | 2202 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | B |  |  | ROOM | SERACOM | OK | SERACOM | OK | OK | YesV | OK | DRAGOS | 2000-01-07 | 1999-12-22 |  |  |  | OK | OK |  | OK | OK |  |  |  | 00:0008 | ETR | N/A | 2000-01-10 | OK | 2000-01-11 | 2000-01-12 | 2000-01-25 |  | Yes | Theo Radoi | 2000-03-30 | 2000-03-30 | 2000-03-30 | 2000-04-06 | OK | K 739 494 | 0 | 0.5 | 0 | K 739 494 | 110 | 5.5 | 0 | K 739 494 | 250 | 0.5 | 0 |  |  |  |  | N/A | 25 | 25 | 7/8" | 25 | 25 | 7/8" | 25 | 25 | 7/8" | N/A | N/A | N/A | 150 | N/A | Constanta | FO | N/A | N/A | N/A | N/A | N/A | [6 empty] | Indoor Comteck | 30003 | 2001-05-03 | YES | [6 empty] | 1 | BSC13 | BSC CONSTANTA |  | N/A |  |  | N/A | [6 empty] | OK | OK | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 30N01 Navodari-Constanta |  | OK | MIHAI C. | MIHAI C. | [32 empty] | 10 | Navodari | Constanta | [7 empty] | Site Near=Insertion Point
Phase_1 | CS | BX005 | POPORULUI CTA | Constanta | BX005 Poporului_CTA | Dobrogea | 44 11 06.2 | 28 37 06.6 | 44 11 03.3 | 28 38 01.7 | Str. Ion Nenitescu nr.2 | RTC/ | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | 2000-06-27 |  |  |  | N/A | B |  |  | OUTDOOR | ORION | OK | ORION | OK | 1999-11-08 | YesV | OK | MUGUREL | 1999-11-08 | 1999-10-26 |  |  |  | OK | OK |  | OK | 1999-10-06 |  |  |  | 99:0003 | ETR | N/A | OK | OK | 1999-11-22 | OK | 1999-11-29 |  | Yes | Theo Radoi | 2000-02-10 | 2000-03-14 | 2000-03-14 | 2000-03-23 | OK | K 739 494 | 10 | 8 | 0 | K 739 494 | 120 | 8 | 0 | K 739 494 | 235 | 8 | 0 |  |  |  |  | N/A | 25 | 25 | 7/8" | 25 | 25 | 7/8" | 25 | 25 | 7/8" | N/A | N/A | N/A | 150 | N/A | Constanta | FO | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | RBS | N/A | [9 empty] | BSC13 | BSC CONSTANTA |  | N/A |  |  | N/A | [6 empty] | OK | OK | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 30N01 Poporului-Constanta |  | OK | MIHAI C. | MIHAI C. | [32 empty] | 53 | Constanta | Constanta | [7 empty] | Site Near=Insertion Point
Phase_1 | CS | BX006 | BRATIANU CTA | Constanta | BX006 Bratianu_CTA | Dobrogea | 44 10 32.3 | 28 37 14.1 | 44 10 29.1 | 28 37 16.1 | Str. I.L. Caragiale nr.14 | RTC/ | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | 2000-06-27 |  |  |  | N/A | B |  |  | OUTDOOR | ORION | OK | ORION | OK | OK | YesV | OK | MUGUREL | OK | 1999-11-01 |  |  |  | OK | OK |  | OK | 1999-10-06 |  |  |  | 99:0005 | ETR | N/A | OK | OK | 1999-11-22 | 1999-11-23 | 1999-11-30 |  | Yes | Theo Radoi | 2000-02-10 | 2000-03-14 | 2000-03-14 | 2000-03-23 | OK | K 739 494 | 0 | 6 | 0 | K 739 494 | 110 | 6 | 0 | K 739 494 | 240 | 6 | 0 |  |  |  |  | N/A | 22 | 22 | 7/8" | 22 | 22 | 7/8" | 22 | 22 | 7/8" | N/A | N/A | N/A | 132 | N/A | Constanta | FO | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | RBS | 30006 | Phase_1 | [7 empty] | 1 | BSC13 | BSC CONSTANTA | N/A | N/A |  |  | N/A | [6 empty] | OK | OK | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 30N01 Bratianu-Constanta |  | OK | MIHAI C. | MIHAI C. | [32 empty] | 45 | Constanta | Constanta | [7 empty] | Site Near=Insertion Point
Phase_1 | CS | BX010 | BD_TOMIS | Constanta | BX002 Tomis Nord | Dobrogea | 44 11 35.7 | 28 38 08.7 | 44 11 46.6 | 28 37 56.3 | Bulevardul Tomis no 235, Bl. C Sc. 1, Constanta | Private/Gheorghe CRISTEA, Bd. Tomis no 235 Bl. C, et 7 apt. 35, Constanta, 041/635172 | 2202 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | B | 30 | T3m+T3m+T4m | Room |  | OK | IMSAT | OK | OK | YesV | OK |  | 2000-03-07 | 2000-02-08 |  |  |  | 2000-01-17 | 2000-01-18 |  | 2000-01-18 | 2000-02-03 |  |  |  | 00:0009 | ETR | Electotrade | OK | OK | 2000-02-07 | OK | 2000-02-12 |  | Yes | Theo Radoi | 2000-03-30 | 2000-03-30 | 2000-03-30 | 2000-04-06 | OK | K 739 494 | 10 | 8 | 29.7 | K 739 494 | 130 | 4 | 34 | K 739 494 | 240 | 4 | 29.7 |  |  |  |  | N/A | 40 | 40 | 7/8" | 8 | 8 | 7/8" | 25 | 25 | 7/8" | N/A | N/A | N/A | 146 |  | Constanta | MW | 322 | 0.3 |  |  | 38/14 |  | 4x2/8 | 4U-1 |  |  |  | Indoor Comteck | [9 empty] | 1 | BX002 | TOMIS NORD | 142 | 0.3 |  |  | 38/18 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-10-03 |  |  | 2000-10-03 | 30N03 Tomis Nord-Constanta |  | OK | MIHAI C. | MIHAI C. | [32 empty] | 17 | Constanta | Constanta | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BX011 | CARAGIALE | Constanta | BX002 Tomis Nord | Dobrogea | 44 10 49.7 | 28 38 09.4 | 44 10 47.3 | 28 38 06.7 | Str. IL Caragiale no.1 Bl. L26 | Private/Popa Nicolae, Str. IL Caragiale no.1 Bl. L26 | 2202 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | N/A |  |  |  |  | B | 38 |  | ROOM | IMSAT | OK | IMSAT | OK | 2000-02-09 | YesV | OK |  | 2000-02-09 | 2000-01-06 |  |  |  | 1999-12-01 | OK |  | OK | OK |  |  |  | 00:0009 | ETR | Electotrade | OK | OK | OK | OK | 2000-02-12 |  | Yes | Theo Radoi | 2000-03-30 | 2000-03-30 | 2000-03-30 | 2000-04-06 | OK | K 739 494 | 0 | 8 | 0 | K 739 494 | 145 | 6 | 0 | K 739 494 | 225 | 4 | 0 |  |  |  |  | N/A | 25 | 25 | 7/8" | 25 | 25 | 7/8" | 25 | 25 | 7/8" | N/A | N/A | N/A | 150 |  | Constanta | MW | 352 | 0.6 |  |  | 23/58 |  | 4x2/8 | 4U-1 |  |  |  | Indoor Comteck | [9 empty] | 1 | BX010 | BD_TOMIS | 172 | 0.6 |  |  | 23/56 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-10-03 |  |  | 2000-10-03 | 30N02 Tomis Nord-Constanta |  | OK | MIHAI C. | MIHAI C. | [32 empty] | 41 | Constanta | Constanta | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BX012 | BD_MAMAIA | Constanta | BX001 Constanta_CTA | Dobrogea | 44 11 31.5 | 28 39 01.9 | 44 11 14.8 | 28 38 57.3 | Bulevardul Mamaia no 87, bl. BI LS7 | Private/Bulevardul Mamaia no 87, bl. BI LS7, Vasilescu Marieta , apt 7, tel 041/669700 | 2202 | M | C+C+C+ | 2/2/2 | Yes | [6 empty] | OK |  | N/A |  |  |  | 30 | B | 30 | C2.5m+C2.5m+C2.5m | ROOM | ISAF | OK | ISAF | OK | OK | YesV | OK | AUREL | 2000-03-07 | OK |  |  |  | 1999-12-28 | 2000-01-20 |  | 2000-01-20 | 2000-02-09 |  |  |  | 00:0009 | ETR | Electotrade | 2000-02-03 | OK | 2000-03-08 | 2000-03-08 | 2000-03-09 |  | Yes | Theo Radoi | 2000-03-30 | 2000-03-30 | 2000-03-30 | 2000-04-06 | OK | K 739 494 | 335 | 5 | 32 | K 739 494 | 130 | 5 | 32 | K 739 494 | 240 | 3 | 32 |  |  |  |  | N/A | 20 | 20 | 7/8" | 13 | 13 | 7/8" | 22 | 22 | 7/8" | N/A | N/A | N/A | 110 |  | Constanta | MW | 178 | 0.3 |  |  | 38/18 |  | 4x2/8 |  |  |  |  | RBS | [9 empty] | 1 | BX001 | ROMTELECOM CTA | 360 | 0.3 |  |  | 38/14 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-10-03 |  |  | 2000-10-03 | 30N03 RTC-Constanta |  | OK | DAN | DAN | [32 empty] | 29 | Constanta | Constanta | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BX013 | CASIN | Constanta | BX001 Constanta_CTA | Dobrogea | 44 12 23.2 | 28 38 48.8 | 44 12 24.8 | 28 38 56.7 | Strada Casin no. 17,bl. G2B Sc. A | Private/Viorel Alexandru, Strada Casin no. 17,bl. G2B Sc. A, Apt. 17 | 2202 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | B | 15 | Pilonet 15 m | ROOM | SVF | OK | SVF | OK | OK | YesV | OK | DRAGOS | 1999-12-10 | 1999-11-29 |  |  |  | OK | OK |  | OK | 1999-11-15 |  |  |  | 99:0006 | ETR | N/A | OK | OK | 2000-01-11 | 2000-01-12 | 2000-01-28 |  | Yes | Theo Radoi | 2000-03-23 | 2000-03-30 | 2000-03-30 | 2000-04-19 | OK | K 739 494 | 10 | 6 | 25 | K 739 494 | 115 | 6 | 25 | K 739 494 | 240 | 2 | 25 |  |  |  |  | N/A | 35 | 35 | 7/8" | 35 | 35 | 7/8" | 35 | 35 | 7/8" | N/A | N/A | N/A | 210 |  | Constanta | MW | 179 | 0.3 |  |  | 38/14 |  | 4x2/8 | 4U-1 |  |  |  | Indoor Comteck | [9 empty] | 1 | BX012 | BD_MAMAIA | 359 | 0.3 |  |  | 38/18 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-10-03 |  |  | 2000-10-03 | 30N03 RTC-Constanta |  | OK | DAN | DAN | [32 empty] | 6 | Constanta | Constanta | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BX014 | DOBRILA | Constanta | BX002 Tomis Nord | Dobrogea | 44 12 32.8 | 28 37 29.8 | 44 12 24.8 | 28 37 24.4 | Str. Dobrila Eugeniu no 2, bl. H | Private/Gheorghe Popescu, Str. Dobrila Eugeniu no 2, bl. H, sc. B, apt 73. | 2202 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | B | 30 | T3m+T3m+T3m | ROOM | SVF | OK | SVF | OK | OK | YesV | OK | DRAGOS | 1999-12-10 | 1999-11-29 |  |  |  | OK | OK |  | OK | 1999-11-11 |  |  |  | 99:0006 | ETR | N/A | 1999-11-29 | OK | 2000-01-11 | 2000-01-12 | 2000-01-28 |  | Yes | Theo Radoi | 2000-02-25 | 2000-03-14 | 2000-03-14 | 2000-03-23 | OK | K 739 494 | 0 | 2 | 32 | K 739 494 | 105 | 4 | 32 | K 739 494 | 240 | 3 | 32 |  |  |  |  | N/A | 15 | 15 | 7/8" | 15 | 15 | 7/8" | 35 | 35 | 7/8" | N/A | N/A | N/A | 130 |  | Constanta | MW | 153 | 0.3 |  |  | 38/14 |  | 4x2/8 | [14 empty] | 1 | BX002 | TOMIS NORD | 333 | 0.3 |  |  | 38/18 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-10-03 |  |  | 2000-10-03 | 30N01 Tomis Nord-Constanta |  | OK | DAN | DAN | [32 empty] | 24 | Constanta | Constanta | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BX015 | PERLA | Constanta | BX002 Tomis Nord | Dobrogea | 44 13 16.1 | 28 37 58.8 | 44 13 13.4 | 28 37 53.3 | Hotel Perla, Mamaia | Private/Catalin lazarescu, 041.831.730 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | 2000-06-27 |  |  |  | 45 | B | 45 | T4m+T4m+T4m | OUTDOOR | SVF | OK | SVF | OK | 2000-02-01 | YesV | OK | DRAGOS | 2000-02-01 | 1999-12-22 |  |  |  | 1999-11-11 | OK |  | OK | 1999-12-11 |  |  |  | 00:0008 | ETR | N/A | 2000-01-10 | OK | 2000-01-11 | 2000-01-12 | 2000-01-20 |  | Yes | Theo Radoi | 2000-02-25 | 2000-03-14 | 2000-03-14 | 2000-03-23 | OK | K 739 494 | 130 | 5 | 46 | K 739 494 | 220 | 5 | 46 | K 739 494 | 340 | 3 | 46 |  |  |  |  | N/A | 12 | 12 | 7/8" | 32 | 32 | 7/8" | 20 | 20 | 7/8" | N/A | N/A | N/A | 128 |  | Constanta | MW | 203 | 0.3 |  |  | 38/13 |  | 4x2/8 | 4U-1 |  |  |  | RBS | [9 empty] | 1 | BX014 | DOBRILA | 23 | 0.3 |  |  | 38/17 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-10-03 |  |  | 2000-10-03 | 30N01 Tomis Nord-Constanta |  | OK | DAN | DAN | [32 empty] | 1 | Constanta | Constanta | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BX016 | 1_DECEMBRIE | Constanta | BX002 Tomis Nord | Dobrogea | 44 10 18.0 | 28 38 11.2 | 44 10 03.0 | 28 38 12.1 | Bd. 1 Decembrie 1918, no2C bl. I1 | Private/Bd. 1 Decembrie 1918, no2C bl. I1 | 2202 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | B | 35 | C3m+C2.5m+C2.5m | ROOM | ISAF | OK | ISAF | OK | OK | YesV | OK | AUREL | 2000-02-18 | OK |  |  |  | OK | 2000-01-23 |  | 2000-01-23 | 2000-02-09 |  |  |  | 00:0009 | ETR | Electotrade | OK | OK | OK | OK | OK |  | Yes | Cristian Croitor | 2000-04-20 | 2000-04-20 | 2000-04-20 | 2000-04-24 | OK | K 739 494 | 335 | 6 | 49.5 | K 739 494 | 130 | 8 | 49.5 | K 739 494 | 235 | 4 | 49.5 |  |  |  |  | N/A | 35 | 35 | 7/8" | 28 | 28 | 7/8" | 22 | 22 | 7/8" | N/A | N/A | N/A | 170 |  | Constanta | MW | 354 | 0.3 |  |  | 38/14 |  | 4x2/8 |  |  |  |  | Indoor Comteck | [9 empty] | 1 | BX011 | CARAGIALE | 174 | 0.3 |  |  | 38/18 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-10-03 |  |  | 2000-10-03 | 30N02 Tomis Nord-Constanta |  | OK | DAN | DAN | [32 empty] | 40 | Constanta | Constanta | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BX017 | PIATA_FARULUI | Constanta | BX001 Constanta_CTA | Dobrogea | 44 09 40.1 | 28 37 52.9 | 44 09 28.1 | 28 37 47.8 | Strada Dunarii np. 9 bloc PF4, Scara B | Private/Strada Dunarii no. 9 bloc PF4, Scara C etaj 4, apt 53, Galan Eliana | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | 2000-06-27 |  |  |  | N/A | B | 33 | T3m+T4m+T4m | OUTDOOR | ISAF | OK | ISAF | OK | OK | YesV | OK | AUREL | 2000-02-18 | OK |  |  |  | OK | 2000-01-23 |  | 2000-01-23 | 2000-02-09 |  |  |  | 00:0009 | ETR | Electotrade | OK | OK | OK | OK | 2000-03-02 |  | Yes | Cristian Croitor | 2000-03-05 | 2000-04-20 | 2000-04-20 | 2000-04-24 | OK | K 739 494 | 15 | 6 | 24.5 | K 739 494 | 135 | 8 | 23.5 | K 739 494 | 245 | 4 | 24.5 |  |  |  |  | N/A | 15 | 15 | 7/8" | 20 | 20 | 7/8" | 33 | 33 | 7/8" | N/A | N/A | N/A | 136 |  | Constanta | MW | 33 | 0.6 |  |  | 23/58 |  | 4x2/8 |  |  |  |  | RBS | [9 empty] | 1 | BX001 | ROMTELECOM CTA | 213 | 0.6 |  |  | 23/56 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-10-03 |  |  | 2000-10-03 | 30N01 RTC-Constanta |  | OK | DAN | DAN | [32 empty] | 27 | Constanta | Constanta | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BX018 | ARCULUI | Constanta | BX001 Constanta_CTA | Dobrogea | 44 09 07.7 | 28 37 36.8 | 44 08 55.2 | 28 37 29.2 | Strada Arcului no. 20, bl. A9, scara A | Private/Strada Arcului no. 20, bloc A9 scaraA | 2202 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | B | 30 | T4m+T4m+T4m | ROOM | ORION | OK | ORION | OK | OK | YesV | OK | MUGUREL | 2000-03-01 | 2000-02-07 |  |  |  | OK | 2000-01-19 |  | 2000-01-19 | 2000-01-17 |  |  |  | 00:0009 | ETR | Electotrade | OK | OK | 2000-02-07 | OK | 2000-02-12 |  | Yes | Cristian Croitor | 2000-04-21 | 2000-04-21 | 2000-04-21 | 2000-04-24 | OK | K 739 494 | 0 | 4 | 39 | K 739 494 | 100 | 8 | 39 | K 739 494 | 230 | 2 | 39 |  |  |  |  | N/A | 20 | 20 | 7/8" | 20 | 20 | 7/8" | 20 | 20 | 7/8" | N/A | N/A | N/A | 120 |  | Constanta | MW | 21 | 0.3 |  |  | 38/14 |  | 4x2/8 |  |  |  |  | Indoor Comteck | [9 empty] | 1 | BX017 | PIATA_FARULUI | 201 | 0.3 |  |  | 38/18 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-10-03 |  |  | 2000-10-03 | 30N02 RTC_Constanta |  | OK | DAN | DAN | [32 empty] | 42 | Constanta | Constanta | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BX019 | AUREL_VLAICU | Constanta | BX006 Bratianu_CTA | Dobrogea | 44 09 24.0 | 28 36 56.9 | 44 09 21.6 | 28 36 51.4 | Bd. Aurel Vlaicu no. 41, Bloc PC1, Scara C | Private/Sarpe Felicia, administrator, apt 24, cheia la Stoichita Marian, apt 89 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | 2000-06-27 |  |  |  | 30 | B | 30 | T4m+T4m | OUTDOOR | ORION | OK | ORION | OK | OK | YesV | OK |  | 2000-02-21 | 2000-02-07 |  |  |  | 1999-12-08 | 2000-01-19 |  | 2000-01-19 | 2000-01-17 |  |  |  | 00:0009 | ETR | Electotrade | OK | OK | OK | OK | 2000-02-12 |  | Yes | Theo Radoi | 2000-03-05 | 2000-03-17 | 2000-03-17 | 2000-03-23 | OK | K 739 494 | 0 | 5 | 33 | K 739 494 | 140 | 2 | 33.5 | K 739 494 | 230 | 2 | 33.5 |  |  |  |  | N/A | 20 | 20 | 7/8" | 30 | 30 | 7/8" | 30 | 30 | 7/8" | N/A | N/A | N/A | 160 | ML 38 E 1+0 | Constanta | MW | 342 | 0.3 |  |  | 38/18 |  | 4x2/8 | 4U-1 |  |  |  | RBS | [9 empty] | 1 | BX021 | BRATIANU | 162 | 0.3 |  |  | 38/14 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-10-03 |  |  | 2000-10-03 | 30N02 Bratianu-Constanta |  | OK | DAN | DAN | [32 empty] | 48 | Constanta | Constanta | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BX020 | SOS_MANGALIEI | Constanta | BX001 Constanta_CTA | Dobrogea | 44 08 31.9 | 28 37 40.5 | 44 08 28.5 | 28 37 22.0 | Soseaua Mangaliei no. 181 bl. PD | Private/Soseaua Mangaliei no. 181 bl. PD | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | 2000-06-27 |  |  |  | 30 | B | 30 | T6m+T5m+C6m | OUTDOOR | ORION | OK | ORION | OK | OK | YesV | OK | MUGUREL | 2000-01-21 | OK |  |  |  | OK | 1999-11-22 |  | 1999-11-22 | 2000-01-17 |  |  |  | 00:0009 | ETR | Electotrade | 2000-01-31 | OK | OK | OK | 2000-02-05 |  | Yes | Cristian Croitor | 2000-04-21 | 2000-04-21 | 2000-04-21 | 2000-04-24 | OK | K 739 494 | 0 | 3 | 30.5 | K 739 494 | 100 | 2 | 30.5 | K 739 494 | 230 | 1 | 30.5 |  |  |  |  | N/A | 35 | 35 | 7/8" | 20 | 20 | 7/8" | 35 | 35 | 7/8" | N/A | N/A | N/A | 180 |  | Constanta | MW | 10 | 0.3 |  |  | 38/18 |  | 4x2/8 | 4U-1 |  |  |  | RBS | [9 empty] | 1 | BX018 | ARCULUI | 190 | 0.3 |  |  | 38/14 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-10-03 |  |  | 2000-10-03 | 30N02 RTC_Constanta |  | OK | DAN | DAN | [32 empty] | 30 | Constanta | Constanta | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BX021 | BRATIANU | Constanta | BX006 Bratianu_CTA | Dobrogea | 44 10 12.3 | 28 36 28.1 | 44 10 13.8 | 28 36 28.5 | Bd. Bratianu no. 106, bl. SR1A | Private/Bd. Bratianu no. 106, bl. SR1A | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | 2000-06-27 |  |  |  | 45 | B | 30 | T6m+T5m+T5m | OUTDOOR | ORION | OK | ORION | OK | OK | YesV | OK | MUGUREL | 2000-01-15 | 1999-12-15 |  |  |  | OK | OK |  | OK | 1999-11-15 |  |  |  | 00:0009 | ETR | Electotrade | 2000-01-31 | OK | OK | OK | 2000-02-05 |  | Yes | Cristian Croitor | 2000-03-05 | 2000-04-19 | 2000-04-19 | 2000-04-24 | OK | K 739 494 | 10 | 2 | 45 | K 739 494 | 130 | 2 | 45 | K 739 494 | 240 | 2 | 45 |  |  |  |  | N/A | 15 | 15 | 7/8" | 20 | 20 | 7/8" | 30 | 30 | 7/8" | N/A | N/A | N/A | 130 | ML 38 E 1+0 | Constanta | MW | 65 | 0.3 |  |  | 38/18 |  | 4x2/8 | 4U-1 |  |  |  | RBS | [9 empty] | 1 | BX006 | BRATIANU CTA | 245 | 0.3 |  |  | 38/14 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-10-11 |  |  | 2000-12-08 | 30N02 Bratianu-Constanta |  | OK | MIHAI C. | MIHAI C. | [32 empty] | 48 | Constanta | Constanta | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BX022 | STEFAN_STANCA | Constanta | BX006 Bratianu_CTA | Dobrogea | 44 10 11.1 | 28 35 22.6 | 44 10 08.0 | 28 35 21.1 | Str. Stefan Stanca no. 8 | Private/Str. Stefan Stanca no. 8 | 2202 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | TN |  | New 50m tower | SHELTER | ORION | OK | ORION | OK | OK | YesV | OK | MUGUREL | 2000-01-14 | 1999-11-25 |  |  |  | OK | OK |  | OK | 1999-12-21 |  |  |  | 99:0005 | ETR | N/A | 1999-11-30 | OK | 2000-01-11 | 2000-01-12 | 2000-01-20 |  | Yes | Theo Radoi | 2000-03-05 | 2000-03-16 | 2000-03-16 | 2000-03-23 | OK | K 739 494 | 0 | 4.5 | 30 | K 739 494 | 270 | 1 | 30 | N/A | N/A | N/A | N/A |  |  |  |  | N/A | 40 | 40 | 7/8" | 40 | 40 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A | 160 |  | Constanta | MW | 83 | 0.3 |  |  | 38/14 |  | 4x2/8 |  |  |  |  | Indoor Comteck | [9 empty] | 1 | BX021 | BRATIANU | 263 | 0.3 |  |  | 38/18 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-10-03 |  |  | 2000-10-03 | 30N01 Bratianu-Constanta |  | OK | MIHAI C. | MIHAI C. | [32 empty] | 59 | Constanta | Constanta | [7 empty] | 1 |  |  | 1
Phase_2 | CS | BX042 | AGIGEA | Constanta shore(14) | BX042 Agigea_RTC | Dobrogea | 44 05 34.40 | 28 36 42.42 | 44 05 34.3 | 28 36 40.2 | Oficiul Comercial Romtelecom, Agigea, jud. Constanta | Romtelecom/ | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-06-19 | 2000-06-13 | SVF |  |  |  | 12 | B | 12 | 9 m guided pylonet | N/A | SVF | OK | SVF | 2000-05-03 | 2000-05-10 | YesV | 2000-05-10 | Dragos | 2000-05-16 | 2000-05-10 |  |  |  | 2000-04-04 | 2000-03-22 |  | 2000-04-20 | 2000-04-27 |  |  |  | NA | YRO | NA | 2000-05-17 | 2000-05-18 | 2000-05-22 | 2000-05-22 | 2000-05-26 |  | Yes | Alexandru Bucur | 2000-05-29 | 2000-06-10 | 2000-06-10 | 2000-06-16 | 2000-06-28 | K 739 494 | 0 | 0 | 20.5 | K 739 494 | 140 | 0 | 20.5 | K 739 494 | 250 | 0 | 20.5 |  |  |  |  | N/A | 19 | 19 | 7/8" | 19 | 19 | 7/8" | 19 | 19 | 7/8" | N/A | N/A | N/A | 114 | N/A | Constanta | FO | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | RBS | N/A | [6 empty] | 20/2 pairs - outdoor |  |  | BSC13 | BSC CONSTANTA |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | DINCA | OK | N/A |  | N/A | N/A | 30N01 Agigea-Constanta |  | OK | SORIN UNTARU | #N/A | [32 empty] | 19 | AGIGEA | Constanta | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | BX043 | FREE ZONE | Constanta shore(14) | BX044 Eforie-Nord-RTC | Dobrogea | 44 05 44.59 | 28 39 26.89 | 44 05 55.60 | 28 39 18.40 | Portul Constanta, Zona Libera | Administratia Portului Constanta/Graur Laurentiu tel. 041/602221 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-08-09 | 2000-08-02 | NA |  |  |  | 21.50 | B | 18 | T6m+T6m | N/A | SVF | OK | SVF | 2000-06-14 | 2000-06-29 | YesV | 2000-07-05 | Dragos | 2000-08-02 | 2000-07-26 |  |  |  | OK | 2000-05-03 |  | 2000-05-16 | 2000-06-22 |  |  |  | 2000-08-03 | YRO | SVF | 2000-08-03 | 2000-08-03 | 2000-08-04 | 2000-08-04 | 2000-08-18 |  | Yes | Cristian Croitor | 2000-09-10 | 2000-09-04 | 2000-09-04 | 2000-09-12 | 2000-09-21 | K 739 494 | 0 | 0 | 26.2 | K 739 494 | 120 | 0 | 26 | K 739 494 | 240 | 0 | 26 |  |  |  |  | N/A | 14 | 14 | 7/8" | 14 | 14 | 7/8" | 14 | 14 | 7/8" | N/A | N/A | N/A | 84 | ML 23 E 1+0 | Constanta | MW | 202 | 0.6 | 27.2 | 20 | 23/56 |  |  | 2U-3 |  |  |  | RBS | [9 empty] | 1 | BX044 | EFORIE NORD-optimizare AZ. 270 | 22 | 0.6 | 43.2 | 55 | 23/58 | [6 empty] | 3 | SVF | 2000-08-03 | 100 | 2000-08-03 | 2000-08-04 | 2000-08-18 | RADU | OK | 2000-09-04 |  | 2000-10-04 | 2001-01-10 | 30N02 Eforie-Constanta |  | OK | SORIN UNTARU | Cosmorom | [33 empty] | FREE ZONE | Constanta | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BX044 | EFORIE NORD-optimizare AZ. 270 | Constanta shore(14) | BX044 Eforie-Nord-RTC | Dobrogea | 44 03 49.12 | 28 38 07.30 | 44 03 49.12 | 28 38 07.30 | Romtelecom Eforie Nord | Romtelecom/Adetu Marian, 092 82 71 96 | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-06-19 | N/A | N/A |  |  |  | N/A | TE | 42 |  | Room | SVF | OK | EL-MONT | 2000-05-09 | 2000-05-15 | YesV | 2000-05-18 | Dragos | [5 empty] | OK |  |  | OK | OK |  |  |  | NA | ICOM | SVF | 2001-04-05 | N/A | 2001-04-06 | 2001-04-07 | 2001-04-08 |  | Yes | Valentin C-tinescu | 2001-06-20 | 2001-06-20 | 2001-06-20 |  |  | K 739 494 | 0 | 0 | 30 | K 739 494 | 180 | 0 | 30 | K 739 494 | 270 | 2 | 30 | N/A | N/A | N/A | N/A | N/A | 35 | 35 | 7/8" | 38 | 38 | 7/8" | 41 | 41 | 7/8" | N/A | N/A | N/A | 228 | N/A | Constanta | FO | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | TMR 9202 | [7 empty] | N/A/N/A |  | 1 | BSC13 | BSC CONSTANTA |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | OK | N/A |  | N/A | N/A | 30N01 Eforie-Constanta |  | OK | SORIN UNTARU | Cosmorom | [23 empty] | N/A | YRO | N/A | 2000-05-24 |  | 2001-06-07 | 2001-06-07 | 37058 | 37061 | 20 | EFORIE NORD | Constanta | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | BX045 | TECHIRGHIOL | Constanta shore(14) | BX042 Agigea_RTC | Dobrogea | 44 03 14.90 | 28 36 03.76 | 44 03 13.00 | 28 36 00.02 | Str. Victiriei nr. 6,bl.A1,sc.A, Techirghiol, Jud. Constanta | /Groza Viorel 093. 470 907 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-06-19 | 2000-06-13 | SVF |  |  |  | 15.5 | B |  |  | N/A | SVF | OK | EL-MONT | 2000-05-09 | 2000-05-18 | YesV | 2000-05-18 | Dragos | 2000-06-16 | 2000-06-02 |  |  |  | 2000-04-04 | OK |  | 2000-04-21 | 2000-05-15 |  |  |  | NA | YRO | NA | 2000-05-29 | 2000-05-29 | 2000-05-30 | 2000-05-31 | 2000-06-05 |  | Yes | Ionut Grigorescu | 2000-06-10 | 2000-06-11 | 2000-06-11 | 2000-06-16 | 2000-06-28 | K 739 494 | 0 | 0 | 20 | K 739 494 | 130 | 0 | 20 | K 739 494 | 240 | 0 | 20 |  |  |  |  | N/A | 20 | 20 | 7/8" | 23 | 23 | 7/8" | 20 | 20 | 7/8" | N/A | N/A | N/A | 126 | N/A | Constanta | FO | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | RBS | N/A | [6 empty] | N/A/N/A |  |  | BX042 | AGIGEA |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PITURCESCU | OK | N/A |  | N/A | N/A | 30N01Techirghiol-Agigea+30N01 Agige-Constanta |  | OK | SORIN UNTARU | Cosmorom | [32 empty] | 19 | TECHIRGHIOL | Constanta | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | BX046 | EFORIE SUD | Constanta shore(14) | BX044 Eforie-Nord-RTC | Dobrogea | 44 01 40.31 | 28 38 50.79 | 44 01 50.9 | 28 38 88.1 | Strada M. Eminescu nr. 6, Bl. B, Sc. B | Asoc. Proprietari/Lica Maria 041/748494 (ap. 35) | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-06-19 | 2000-06-13 | SVF |  |  |  | 13.5 | B | 13.5 | 9 m guided pylonet | N/A | SVF | OK | EL-MONT | 2000-05-09 | 2000-05-30 | YesV | 2000-05-30 | Dragos | 2000-06-16 | 2000-06-02 |  |  |  | 2000-04-04 | 2000-05-03 |  | 2000-04-21 | 2000-05-15 |  |  |  | NA | YRO | NA | 2000-05-29 | 2000-05-29 | 2000-05-30 | 2000-05-31 | 2000-06-05 |  | Yes | Alexandru Bucur | 2000-06-06 | 2000-06-08 | 2000-06-08 | 2000-06-16 | 2000-06-28 | K 739 494 | 0 | 0 | 21.3 | K 739 494 | 120 | 0 | 21.3 | K 739 494 | 220 | 0 | 21.3 |  |  |  |  | N/A | 24 | 24 | 7/8" | 24 | 24 | 7/8" | 24 | 24 | 7/8" | N/A | N/A | N/A | 144 | ML 23 E 1+0 | Constanta | MW | 347 | 0.6 | 19.3 | 24 | 23/56 |  |  | 2U-3 |  |  |  | RBS | [7 empty] | N/A/N/A |  |  | BX044 | EFORIE NORD-optimizare AZ. 270 | 167 | 0.6 | 43.2 | 52 | 23/58 | [6 empty] | * | YRO | 2000-05-30 | 440 | 2000-05-30 | 2000-05-22 | 2000-05-26 | DINCA | OK | 2000-06-14 |  | 2000-06-28 | 2000-07-05 | 30N01 Eforie-Constanta |  | OK | SORIN UNTARU | Cosmorom | [33 empty] | EFORIE SUD | Constanta | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BX047 | TUZLA | Constanta shore(14) | BX044 Eforie-Nord-RTC | Dobrogea | 43 59 28.52 | 28 38 27.79 | 43 59 27.20 | 28 37 35.80 | Sectia de Mecanizare - Multiserv - Mangalia, com. Tuzla | /Sibianu Cornel 041/731094 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-06-19 | N/A | N/A |  |  |  | N/A | TN | 30 | New 30m tower | N/A | ISAF | OK | ISAF | 2000-05-12 | 2000-06-07 | YesV | 2000-06-07 | Dragos | 2000-06-16 | 2000-06-08 |  |  |  | 2000-04-27 | OK |  | 2000-05-11 | 2000-05-18 |  |  |  | NA | YRO | NA | 2000-06-05 | 2000-06-05 | 2000-06-06 | 2000-06-07 | 2000-06-08 |  | Yes | Alexandru Bucur | 2000-06-09 | 2000-06-10 | 2000-06-10 | 2000-06-16 | 2000-06-28 | K 739 494 | 20 | 0 | 28.9 | K 739 494 | 200 | 0 | 28.9 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 40 | 40 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 80 | ML 23 E 1+0 | Constanta | MW | 24 | 0.6 | 28.3 | 40 | 23/58 |  |  | 2U-3 |  |  |  | RBS | [7 empty] | N/A/N/A |  |  | BX046 | EFORIE SUD | 204 | 0.6 | 19.3 | 24 | 23/56 | [6 empty] | * | YRO |  | 452 | 2000-06-07 | 2000-06-08 | 2000-06-09 | DINCA | OK | 2000-06-16 |  | 2000-06-28 | 2000-07-05 | 30N01 Eforie-Constanta |  | OK | SORIN UNTARU | Cosmorom | [32 empty] | 39 | TUZLA | Constanta | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BX048 | COSTINESTI | Constanta shore(14) | BX049 23_August_RTC | Dobrogea | 43 56 52.81 | 28 37 58.92 | 43 56 54.02 | 28 37 59.00 | RTC COSTINESTI | /RTC | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-06-19 | N/A | N/A |  |  |  | N/A | B | B |  | ROOM | ISAF | OK | ISAF | 2000-05-05 | 2000-05-15 | YesV | 2000-05-18 | Dragos | 2000-05-19 | 2000-05-19 |  |  |  | 2000-04-04 | OK |  | 2000-04-24 | 2000-05-10 |  |  |  | NA | YRO | NA | 2000-05-18 | 2000-05-18 | 2000-05-19 | 2000-05-19 | 2000-05-23 |  | Yes | Alexandru Bucur | 2000-05-29 | 2000-06-09 | 2000-06-09 | 2000-06-16 | 2000-06-28 | K 739 494 | 0 | 0 | 49.7 | K 739 494 | 120 | 0 | 49.7 | K 739 494 | 240 | 0 | 49.7 |  |  |  |  | N/A | 64 | 64 | 1 1/4" | 64 | 64 | 1 1/4" | 64 | 64 | 1 1/4" | N/A | N/A | N/A | 384 | N/A | Constanta | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | [5 empty] | N/A | [6 empty] | 25/2 p indoor |  |  | BX049 | 23_AUGUST |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | ARANYOSI | OK | N/A |  | N/A | N/A | 30N01 Costinesti-23 August+30N01 23 August-Constanta+DXX |  | OK | SORIN UNTARU | COSMOROM | [32 empty] | 12 | COSTINESTI | Constanta | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | BX049 | 23_AUGUST | Constanta shore(14) | BX049 23_August_RTC | Dobrogea | 43 55 02.52 | 28 34 56.68 | 43 55 03.00 | 28 34 54.99 | Comuna 23 August, jud. Constanta | RTC/RTC | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-08-09 | N/A | N/A |  |  |  | 7 | B | B | 12m pylonet | ROOM | ISAF | OK | ISAF | 2000-05-05 | 2000-05-15 | YesV | 2000-05-18 | Dragos | 2000-06-16 | 2000-06-02 |  |  |  | 2000-04-04 | OK |  | 2000-04-24 | 2000-05-10 |  |  |  | NA | YRO | NA | 2000-05-17 | 2000-05-18 | 2000-05-22 | 2000-05-22 | 2000-05-26 |  | Yes | Alexandru Bucur | 2000-05-29 | 2000-06-16 | 2000-06-16 | 2000-06-28 | 2000-07-04 | K 739 494 | 0 | 0 | 20 | K 739 494 | 120 | #N/A | 20 | K 739 494 | 240 | 0 | 20 |  |  |  |  | N/A | 30 | 30 | 7/8'' | 30 | 30 | 7/8'' | 30 | 30 | 7/8'' | N/A | N/A | N/A | 180 | N/A | Constanta | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | [5 empty] | N/A | [6 empty] | 30/2 p indoor |  |  | BSC13 | BSC CONSTANTA |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | DINCA | OK | N/A |  | N/A | N/A | 30N01 23 August-Constanta+DXX |  | OK | SORIN UNTARU | #N/A | [32 empty] | 22 | 23_AUGUST | Constanta | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | BX051 | NEPTUN_RTC | Constanta shore(14) | BX051 Neptun_RTC | Dobrogea | 43 51 54.51 | 28 35 48.82 | 43 51 55.01 | 28 35 50.00 | RTC NEPTUN | RTC-Neptun/ | 2202 | M/E | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-06-19 | N/A | N/A |  |  |  | 8 | B | B | 6m guided pylonet | Room | DIEKAT | OK | DIEKAT | 2000-04-25 | 2000-05-10 | YesV | 2000-05-10 | Dragos | 2000-06-16 | 2000-05-10 |  |  |  | OK | OK |  | 2000-04-22 | 2000-04-24 |  |  |  | NA | YRO | NA | 2000-05-17 | 2000-05-18 | 2000-05-19 | 2000-05-19 | 2000-05-25 |  | Yes | Alexandru Bucur | 2000-05-29 | 2000-06-07 | 2000-06-07 | 2000-06-16 | 2000-06-28 | K 739 494 | 20 | 0 | 20 | K 739 494 | 120 | 0 | 20 | K 739 494 | 240 | 0 | 20 |  |  |  |  | N/A | 25 | 25 | 7/8" | 25 | 25 | 7/8" | 25 | 25 | 7/8" | N/A | N/A | N/A | 150 | N/A | Constanta | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | 2U-3 |  |  |  | TMR 9202 | 30051 | 2001-04-26 | [7 empty] | 1 | BSC13 | BSC CONSTANTA | N/A | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | 30N01 Neptun-Constanta |  | 2001-05-22 | SORIN UNTARU | Cosmorom | [32 empty] | 14 | Neptun | Constanta | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | BX052 | MANGALIA_RTC | Constanta shore(14) | BX052 Mangalia_RTC | Dobrogea | 43 48 55.30 | 28 34 59.51 | 43 48 38 | 28 34 50 | RTC Mangalia | RTC/RTC | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-06-19 | N/A | N/A |  |  |  |  | B | B | 9m pylonet | Room | DIEKAT | OK | DIEKAT | 2000-05-15 | 2000-05-30 | YesV | 2000-05-30 | Dragos | 2000-06-02 | 2000-06-02 | 2000-03-24 |  |  | N/A | OK |  | 2000-04-21 | 2000-05-18 |  |  |  | NA | YRO | NA | 2000-05-29 | 2000-05-29 | 2000-05-30 | 2000-05-31 | 2000-06-05 |  | Yes | Alexandru Bucur | 2000-06-10 | 2000-06-11 | 2000-06-11 | 2000-06-16 | 2000-06-28 | K 739 494 | 0 | 0 | 25 | K 739 494 | 120 | 0 | 25 | K 739 494 | 240 | 0 | 25 |  |  |  |  | N/A | 30 | 30 | 7/8" | 25 | 25 | 7/8" | 25 | 25 | 7/8" | N/A | N/A | N/A | 160 | N/A | Constanta | FO | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | TMR 9202 | 30052 | 2001-07-09 | NO | [7 empty] | BSC13 | BSC CONSTANTA |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PAUN | OK | N/A |  | N/A | N/A | 30N01 Mangalia-Constanta |  | OK | SORIN UNTARU | Cosmorom | [32 empty] | 3 | Mangalia | Constanta | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | BX053 | MANGALIA_1 | Constanta shore(14) | BX052 Mangalia_RTC | Dobrogea | 43 49 23 | 28 35 02 | 43 49 17 | 28 35 04 | str. Ion Creanga, nr. 8, C3, sc. C, Mangalia, jud. Constanta | Asoc. Proprietari nr. 23/1) Dan Adrian (admin.) tel. 041/753576; 2) Alexandru Mocanu-sef scara (ap 45) tel. 041/759419 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-06-19 | 2000-06-13 | N/A |  |  |  | 15 | B | 15 | T4.5m+T4.5m+T3m | N/A | ISAF | OK | ORION | 2000-05-17 | 2000-06-07 | YesV | 2000-06-07 | Dragos | 2000-06-16 | 2000-06-08 |  |  |  | 2000-04-05 | OK |  | 2000-04-21 | 2000-05-16 |  |  |  | NA | YRO | NA | 2000-06-05 | 2000-06-05 | 2000-06-06 | 2000-06-07 | 2000-06-10 |  | Yes | Alexandru Bucur | 2000-06-12 | 2000-06-15 | 2000-06-15 | 2000-06-28 | 2000-07-04 | K 739 494 | 0 | 0 | 16.5 | K 739 494 | 120 | 0 | 16.6 | K 739 494 | 240 | 0 | 16.6 |  |  |  |  | N/A | 16 | 16 | 7/8" | 19 | 19 | 7/8" | 14 | 14 | 7/8" | N/A | N/A | N/A | 98 | ML 38 E 1+0 | Constanta | MW | 200.1 | 0.3 | 16.5 | 18 | 38/14 |  |  | 2U-3 |  |  |  | RBS | [7 empty] | N/A/N/A |  |  | BX052 | MANGALIA_RTC | 19 | 0.3 | 39 | 20 | 38/18 | [6 empty] | N/A | YRO | N/A | 450 | 2000-06-05 | 2000-06-07 | 2000-06-10 | PAUN | OK | 2000-06-15 |  | 2000-06-28 | 2000-07-05 | 30N02 Mangalia-Constanta |  | OK | SORIN UNTARU | Cosmorom | [32 empty] | 7 | Mangalia | Constanta | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BX054 | MANGALIA_2 | Constanta shore(14) | BX052 Mangalia_RTC | Dobrogea | 43 48 52 | 28 34 08 | 43 48 55 | 28 34 08 | Str Oituz nr.90 Bl.P1 Sc.A | Asoc. Proprietari nr. 30/Presedinte: Dancov Nicolas, tel: 041 756533, Sef Scara: Herciu Mariana Sc B Ap.10, tel: 041 756086, Sef Scara (2) Musat Ramona Sc.A Ap.5 tel: 041 755110 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-06-19 | 2000-06-13 | N/A |  |  |  | 11 | B | 11 | T4.5m+T4.5m | N/A | ISAF | OK | ORION | 2000-05-17 | 2000-06-07 | YesV | 2000-06-07 | Dragos | 2000-06-16 | 2000-06-08 |  |  |  | 2000-04-05 | OK |  | 2000-04-24 | 2000-05-11 |  |  |  | NA | YRO | NA | 2000-06-05 | 2000-06-05 | 2000-06-06 | 2000-06-07 | 2000-06-10 |  | Yes | Alexandru Bucur | 2000-06-12 | 2000-06-15 | 2000-06-15 | 2000-06-28 | 2000-07-04 | K 739 494 | 0 | 0 | 14 | K 739 494 | 120 | 0 | 14 | K 739 494 | 240 | 0 | 14 |  |  |  |  | N/A | 16 | 16 | 7/8" | 15 | 15 | 7/8" | 15 | 15 | 7/8" | N/A | N/A | N/A | 92 | ML 38 E 1+0 | Constanta | MW | 118 | 0.3 | 13.5 | 20 | 38/14 |  |  | 2U-3 |  |  |  | RBS | [7 empty] | N/A/N/A |  |  | BX052 | MANGALIA_RTC | 295 | 0.3 | 19.5 | 20 | 38/18 | [6 empty] | N/A | YRO | N/A | 449 | 2000-06-05 | 2000-06-07 | 2000-06-10 | PAUN | OK | 2000-06-15 |  | 2000-06-28 | 2000-07-05 | 30N02 Mangalia-Constanta |  | OK | SORIN UNTARU | Cosmorom | [32 empty] | 20 | Mangalia | Constanta | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BX056 | OLIMP | Constanta shore(14) | BX051 Neptun_RTC | Dobrogea | 43 53 11.98 | 28 36 31.99 | 43 53 12 | 28 36 32 | Hotel "Oltenia", Olimp |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-06-19 | 2000-06-13 | SVF |  |  |  | 47 | B | 47 | C2.9m+C2.9m | N/A | SVF | OK | ESROM | 2000-05-24 | 2000-06-07 | YesV | 2000-06-07 | Dragos | 2000-06-16 | 2000-06-08 |  |  |  | 2000-04-04 | OK |  | 2000-05-23 | 2000-05-24 |  |  |  | NA | YRO | NA | 2000-06-05 | 2000-06-05 | 2000-06-06 | 2000-06-07 | 2000-06-09 |  | Yes | Alexandru Bucur | 2000-06-09 | 2000-06-09 | 2000-06-09 | 2000-06-16 | 2000-06-28 | K 739 494 | 100 | 0 | 49 | K 739 494 | 230 | 0 | 49 | K 739 494 | 340 | 0 | 48.5 |  |  |  |  | N/A | 9 | 9 | 7/8" | 12 | 12 | 7/8" | 11 | 11 | 7/8" | N/A | N/A | N/A | 64 | ML 38 E 1+0 | Constanta | MW | 202 | 0.3 | 49 | 20 | 38/13 |  |  | 4U-1 |  |  |  | RBS | [9 empty] | 1 | BX051 | NEPTUN_RTC | 21.5 | 0.3 |  |  | 38/17 | [6 empty] | N/A | YRO | N/A | 454 | 2000-06-07 | 2000-06-08 | 2000-06-09 | YRO | OK | 2000-06-16 |  | 2000-06-28 | 2000-07-05 | 30N02 Neptun-Constanta |  | OK | SORIN UNTARU | Cosmorom | [32 empty] | 3 | OLIMP | Constanta | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BX057 | VENUS | Constanta shore(14) | BX052 Mangalia_RTC | Dobrogea | 43 50 46.99 | 28 35 51.01 | 43 50 46.62 | 28 35 51.36 | Hotel Zamfira, Venus | /Elena Popa - Dir. Gen; tel.: 094581581 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-06-19 | 2000-06-13 | SVF |  |  |  | 11.5 | B | 11.5 | T 4.5 m + T 6 m | N/A | SVF | OK | ESROM | 2000-05-12 | 2000-05-30 | YesV | 2000-05-30 | Dragos | 2000-06-16 | 2000-06-02 |  |  |  | 2000-04-04 | 2000-05-03 |  | 2000-04-24 | 2000-05-15 |  |  |  | NA | YRO | NA | 2000-05-29 | 2000-05-29 | 2000-05-30 | 2000-05-31 | 2000-06-05 |  | Yes | Alexandru Bucur | 2000-06-10 | 2000-06-11 | 2000-06-11 | 2000-06-16 | 2000-06-28 | K 739 494 | 10 | 0 | 15 | K 739 494 | 120 | 0 | 15 | K 739 494 | 240 | 0 | 15 |  |  |  |  | N/A | 13 | 13 | 7/8" | 13 | 13 | 7/8" | 30 | 30 | 7/8" | N/A | N/A | N/A | 112 | ML 23 E 1+0 | Constanta | MW | 199 | 0.6 | 16 | 75 | 23/56 |  |  | 2U-3 |  |  |  | RBS | [7 empty] | N/A/N/A |  |  | BX052 | MANGALIA_RTC | 11 | 0.6 | 40 | 20 | 23/58 | [6 empty] | N/A | YRO | N/A | 431 | 2000-05-29 | 2000-05-22 | 2000-05-26 | IVAN | OK | 2000-06-15 |  | 2000-06-28 | 2000-07-05 | 30N01 Mangalia-Constanta |  | OK | SORIN UNTARU | Cosmorom | [32 empty] | 7 | VENUS | Constanta | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BX059 | PLOIESTI_1 | Ploiesti(6) | BX059 Ploiesti_1 | Muntenia | 44 56 28.99 | 26 01 24.99 | 44 56 33.6 | 26 01 21.9 | Prefectura Ploiesti - Str. Republicii nr.2 | Prefectura Ploiesti - Str. Republicii nr.2/Dl. Lamba - adm. | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-10-20 | Yes | N/A |  |  |  | 40 | B | 40 | C4m+C4m+C4m | N/A | IMSAT | OK | SETRACO | 2000-10-20 | 2000-10-30 | YesV | 2000-11-03 | Relu | 2000-11-10 | 2000-11-10 |  |  |  | 2000-05-08 | 2000-05-12 |  | 2000-05-24 | 2000-08-31 |  |  |  | 2000-10-31 | ICOM | Electotrade | 2000-09-15 | 2000-09-15 | 2000-11-01 | 2000-11-01 | 2000-11-02 |  | Yes | Bogdan Bogodai | 2001-01-24 | 2001-01-24 | 2001-01-24 | 2001-01-26 | 2001-02-08 | K 739 494 | 40 | 0 | 44 | K 739 494 | 160 | 0 | 44 | K 739 494 | 280 | 0 | 44 |  |  |  |  | N/A | 25 | 25 | 7/8" | 18 | 18 | 7/8" | 27 | 27 | 7/8" | N/A | N/A | N/A | 140 | N/A | Baneasa | HDSL | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | RBS | [7 empty] | 100/ |  |  | BSC11 | DRUMUL TABEREI |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PAUN | OK | N/A |  | N/A | N/A | HDSL+30N04 Ploiesti Centru-Dr.Taberei |  | OK | Liviu CHIRCA | Cosmorom | [32 empty] | 170 | Ploiesti | Prahova | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | BX060 | PLOIESTI_2 | Ploiesti(6) | BX523 Ploiesti Vest_CTA | Muntenia | 44 55 05.2 | 26 01 57.9 | 44 55 06.9 | 26 02 02.8 | B-dul. Bucuresti nr.22 Bl.2B | Negoita Gheorghe, ap. 7, et. 2, tel. 0722695999, 0244174104 | 2102 | M/E | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-09-15 | Yes | N/A |  |  |  | 34 | B | 34 | C3m+C4.5m+C4.5m | N/A | IMSAT | OK | VECTOR | 2000-08-03 | 2000-08-21 | YesV | 2000-09-05 | Relu | 2000-09-15 | 2000-09-13 |  |  |  | 2000-05-08 | 2000-05-12 |  | OK | 2000-07-21 |  |  |  | 2000-09-15 | YRO | Electotrade | 2000-09-15 | 2000-09-15 | 2000-09-18 | 2000-09-19 | 2000-09-20 |  | Yes | Alexandru Bucur | 2000-09-25 | 2000-09-29 | 2000-09-29 | 2001-01-08 | 2001-01-10 | K 739 494 | 40 | 0 | 36 | K 739 494 | 160 | 0 | 39.5 | K 739 494 | 280 | 0 | 39.5 |  |  |  |  | N/A | 15 | 15 | 7/8" | 25.5 | 25.5 | 7/8" | 29.5 | 29.5 | 7/8" | N/A | N/A | N/A | 140 | ML 23 E 1+0 | Baneasa | MW | 290 | 0.6 | 42.7 | 30 | 23/56 |  |  | 2U-3 |  |  |  | RBS | XC30523/1 | [8 empty] | 1 | BX503 | PLOIESTI VEST |  | 0.6 |  |  | 23/58 | [6 empty] | 2 | RADCOM | 2000-09-15 | 207 | 2000-09-15 | 2000-09-16 | 2000-09-20 | RADU | OK | 2000-09-29 |  | 2000-10-04 | 2000-12-18 | mutat pe 30N07 Ploiesti Vest-Dr.Taberei |  | OK | Liviu CHIRCA | Cosmorom | [32 empty] | 145 | Ploiesti | Prahova | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BX061 | PLOIESTI_3 | Ploiesti(6) | BX523 Ploiesti Vest_CTA | Muntenia | 44 57 26 | 26 00 18.02 | 44 57 27.3 | 26 00 23 | Str. Rapsodiei nr.2 Bl.144 Sc.A | Admin. Locatari/Adm.: Filon Stelian, tel: 044 133780 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-06-19 | 2000-06-22 | N/A |  |  |  | 30 | B | 30 | T4m+T4.5m | N/A | IMSAT | OK | TEHNOROB | 2000-05-29 | 2000-06-09 | YesV | 2000-06-15 | Relu | 2000-06-16 | 2000-06-19 |  |  |  | OK | 2000-05-12 |  | 2000-05-18 | 2000-05-18 |  |  |  | 2000-06-19 | YRO | MIC | 2000-06-19 | 2000-06-19 | 2000-06-20 | 2000-06-20 | 2000-06-23 |  | Yes | Cristian Croitor | 2000-08-22 | 2000-08-20 | 2000-08-22 | 2000-09-12 | 2000-09-21 | K 739 494 | 40 | 0 | 32.5 | K 739 494 | 160 | 0 | 32.5 | K 739 494 | 280 | 0 | 32.5 |  |  |  |  | N/A | 12 | 12 | 7/8" | 34 | 34 | 7/8" | 12 | 12 | 7/8" | N/A | N/A | N/A | 116 | ML 38 E 1+0 | Baneasa | MW | 209 | 0.3 | 34.7 |  | 38/17 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [7 empty] | N/A/N/A |  |  | BX503 | PLOIESTI VEST | 29 | 0.3 |  |  | 38/13 | [6 empty] | * | U-ELECTRONICA/YRO | 19.06.00-N/A | 14/116 | 6/19/00-8/10/00 | 2000-06-23 | 2000-07-23 | PAUN | OK | 2000-08-23 |  | 2000-09-12 | 2000-09-25 | 30N03 Ploiesti Vest-Dr.Taberei |  | OK | Liviu CHIRCA | Cosmorom | [32 empty] | 179 | Ploiesti | Prahova | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BX062 | PLOIESTI_4 | Ploiesti(6) | BX523 Ploiesti Vest_CTA | Muntenia | 44 56 22 | 26 02 58.01 | 44 56 21.7 | 26 02 57.6 | Str. Sabinelor nr.2 Bl.2 Sc.A | Admin. Locatari/Prersedinte: Vasiloaie Constantin, Adm: Stoica Radu, Ap.2, tel: 044 116579 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-08-16 | 2000-08-02 | N/A |  |  |  | 33 | B | 33 | T4.5m+T4.5m | N/A | IMSAT | OK | SERACOM | 2000-06-19 | 2000-07-12 | YesV | 2000-07-20 | Relu | 2000-07-21 | 2000-07-21 |  |  |  | OK | 2000-05-12 |  | 2000-06-02 | 2000-06-20 |  |  |  | 2000-08-03 | YRO | SVF | 2000-07-24 | 2000-07-24 | 2000-08-04 | 2000-08-06 | 2000-08-11 |  | Yes | Cristian Croitor | 2000-08-22 | 2000-08-20 | 2000-08-23 | 2000-10-04 | 2000-10-13 | K 739 494 | 40 | 0 | 35.9 | K 739 494 | 160 | 0 | 35.9 | K 739 494 | 280 | 0 | 39.4 |  |  |  |  | N/A | 12 | 12 | 7/8" | 12 | 12 | 7/8" | 15 | 15 | 7/8" | N/A | N/A | N/A | 78 | ML 23 E 1+0 | Baneasa | MW | 301 | 0.6 | 39.15 | 15 | 23/56 |  |  | 2U-3 |  |  |  | RBS | [10 empty] | BX061 | PLOIESTI_3 | 121 | 0.6 |  | 50 | 23/58 | [6 empty] | N/A | YRO | N/A | 115 | 2000-08-10 | 2000-08-06 | 2000-08-11 | RADU | OK | 2000-08-23 |  | 2000-09-12 | 2000-09-25 | 30N03 Ploiesti Vest-Dr.Taberei |  | OK | Liviu CHIRCA | Cosmorom | [32 empty] | 161 | Ploiesti | Prahova | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BX063 | INDEPENDENTEI_RTC | Braila(8) | BX063 Independentei_RTC | Moldova | 45 15 54 | 27 58 08.9 | 45 15 54 | 27 58 08.9 | B-dul. Independentei nr.6 | DRTV/ | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-10-11 | N/A | N/A |  |  |  | 20 | TE | 60 | 60m existing tower | Room | DIEKAT | OK | ROMPSAR | 2000-08-10 | 2000-09-15 | YesV | 2000-09-20 | Dragos | 2000-09-22 | 2000-09-26 |  |  |  | N/A | 2000-05-25 |  | 2000-06-19 | 2000-07-27 |  |  |  | 2000-09-28 | YRO | DIEKAT | 2000-09-28 | 2000-09-28 | 2000-09-29 | 2000-09-30 | 2000-10-01 |  | Yes | Theo Radoi | 2000-11-27 | 2000-11-21 | 2000-11-21 | 2000-12-13 | 2000-12-18 | K 739 494 | 0 | 0 | 40 | K 739 494 | 120 | 0 | 40 | K 739 494 | 240 | 0 | 40 |  |  |  |  | N/A | 40 | 40 | 7/8" | 44 | 44 | 7/8" | 44 | 44 | 7/8" | N/A | N/A | N/A | 256 | N/A | Galati | FO | N/A | N/A | N/A | N/A | N/A |  | 4x2/8 | 4U-1 | [11 empty] | 35/ |  | 1 | BSC22 | BSC GALATI |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | VLAD | OK | N/A |  | N/A | N/A |  |  | OK | Bogdan CRAIU | Cosmorom | [32 empty] | 18 | Braila | Braila | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | BX064 | LICEUL PROGRESU | Braila(8) | BX065 Braila_RTC3 | Moldova | 45 18 19.4 | 27 57 47 | 45 48 19.4 | 27 57 47 | Calea Galati nr.331, Bl.5 | Asociatie de locatari/Burete Ion - administrator, Et.6, Ap.45, 039/ 616 699 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-10-09 | Yes | N/A |  |  |  | 24 | B | 27.7 | T3.5m+T3.5m | N/A | DIEKAT | OK | ROMPSAR | 2000-07-21 | 2000-09-10 | YesV | 2000-09-13 | Dragos | 2000-11-10 | 2000-12-08 |  |  |  | 2000-06-01 | 2000-05-25 |  | 2000-07-03 | 2000-08-21 |  |  |  | 2000-09-12 | YRO | TRY | 2000-09-12 | 2000-09-12 | 2000-09-13 | 2000-09-14 | 2000-09-18 |  | Yes | Cristian Croitor | 2000-11-27 | 2000-11-22 | 2000-11-22 | 2000-12-27 | 2001-01-08 | K 739 494 | 95 | 0 | 31.2 | K 739 494 | 145 | 0 | 31.2 | K 739 494 | 285 | 0 | 31.2 |  |  |  |  | N/A | 28 | 28 | 7/8" | 26 | 26 | 7/8" | 26 | 26 | 7/8" | N/A | N/A | N/A | 160 | ML 23 E 1+0 | Galati | MW | 164 | 0.6 | 30.2 | 27 | 23/58 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [9 empty] | 1 | BX065 | BRAILA_RTC3 | 343 | 0.6 | 31 | 31 | 23/56 | [6 empty] | 5 | TRYLON | 2000-09-12 | 189 | 2000-09-12 | 2000-09-14 | 2000-09-18 | IVAN | OK | 2000-11-21 |  | 2000-12-06 | 2000-12-18 |  |  | OK | Bogdan CRAIU | Cosmorom | [32 empty] | 27 | Braila | Braila | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BX065 | BRAILA_RTC3 | Braila(8) | BX065 Braila_RTC3 | Moldova | 45 17 18.8 | 27 58 12.8 | 45 17 18.8 | 27 58 12.8 | CTA3 Braila,Calea Galati, jud. Braila |  | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-10-09 | N/A | N/A |  |  |  | 5 | B | 17 | 14.5m new pylon | Room | DIEKAT | OK | ROMPSAR | 2000-07-21 | 2000-09-10 | YesV | 2000-09-13 | Dragos | 2000-11-10 | 2000-12-08 |  |  |  | N/A | 2000-05-25 |  | 2000-06-14 | 2000-07-07 |  |  |  | 2000-09-12 | YRO | TRY | 2000-09-12 | 2000-09-12 | 2000-09-13 | 2000-09-14 | 2000-09-18 |  | Yes | Theo Radoi | 2000-11-27 | 2000-11-21 | 2000-11-21 | 2000-12-08 | 2001-02-08 | K 739 494 | 30 | 0 | 30 | K 739 494 | 170 | 0 | 30 | K 739 494 | 300 | 0 | 30 |  |  |  |  | N/A | 30 | 30 | 7/8" | 30 | 30 | 7/8" | 30 | 30 | 7/8" | N/A | N/A | N/A | 180 | N/A | Galati | FO | N/A | N/A | N/A | N/A | N/A |  | 4x2/8 | 4U-1(TMR9202) |  |  |  | TMR 9202 | [9 empty] | 1 | BSC22 | BSC GALATI |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A |  |  | OK | Bogdan CRAIU | Petrica BURGHIU | [32 empty] | 13 | Braila | Braila | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | BX066 | TURN CFR | Braila(8) | BX063 Independentei_RTC | Moldova | 45 16 55.9 | 27 57 23.7 | 45 16 55.9 | 27 57 23.7 | Str. Garii nr.230 | SNCFR - Dir. Telecomunicatii/Ing. Zinca Ion, tel: 036/ 460 321; 092/ 693 140 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-10-09 | N/A | N/A |  |  |  | 0 | TE | 42 | Tower | N/A | DIEKAT | OK | DIEKAT | 2000-09-01 | 2000-09-21 | YesV | 2000-09-28 | Dragos | 2000-11-10 | 2000-10-03 |  |  |  |  | 2000-05-25 |  | 2000-06-11 | 2000-08-18 |  |  |  | 2000-10-04 | YRO | ORION | 2000-10-03 | 2000-10-03 | 2000-10-05 | 2000-10-10 | 2000-10-11 |  | Yes | Theo Radoi | 2000-11-27 | 2000-11-23 | 2000-11-23 | 2000-12-06 | 2000-12-18 | K 739 494 | 60 | 0 | 38 | K 739 494 | 205 | 0 | 38 | K 739 494 | 305 | 0 | 38 |  |  |  |  | N/A | 45 | 45 | 7/8" | 45 | 45 | 7/8" | 45 | 45 | 7/8" | N/A | N/A | N/A | 270 | ML 23 E 1+0 | Galati | MW | 153 | 0.6 | 39 | 45 | 23/56 |  | 4x2/8 | 4U-1 |  |  |  | RBS | [9 empty] | 1 | BX063 | INDEPENDENTEI_RTC | 333 | 0.6 | 42 | 50 | 23/58 | [6 empty] | N/A | YRO | N/A | 300 | 2000-10-24 | 2000-10-24 | 2000-10-30 | VLAD | OK | 2000-11-22 |  | 2000-12-06 | 2000-12-18 |  |  | OK | Bogdan CRAIU | Cosmorom | [32 empty] | 16 | Braila | Braila | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_3 | CS | BX067 | ROMGAZ | Braila | BX065 Braila_RTC3 | Moldova | 45 17 15.4 | 27 57 40.3 |  |  |  |  | 2101 | M | C+ | 2 | 2101 | [17 empty] | ROMPSAR |  | @ | 2001-09-01 | 2001-09-30 |  |  | Bogdan |  |  | 2001-07-10 | [8 empty] | 2001-07-10 | [47 empty] | ML 38 E 1+0* | Galati | MW | [22 empty] | BX065 | BRAILA_RTC3 | [27 empty] | Theo RADOI | Theo RADOI
Phase_2 | CS | BX068 | DOROBANTI | Braila(8) | BX063 Independentei_RTC | Moldova | 45 16 18.3 | 27 57 21 | 45 16 18.2 | 27 57 21.6 | Str. 1 Decembrie 1918 nr.62 |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-09-05 | Yes | N/A |  |  |  | 33.2 | B | 36 | C4m+C4m | N/A | DIEKAT | OK | DIEKAT | 2000-07-15 | 2000-07-31 | YesV | 2000-08-04 | Dragos | 2000-12-08 | 2000-08-09 |  |  |  | OK | 2000-05-25 |  | 2000-07-04 | 2000-07-13 |  |  |  | 2000-09-12 | YRO | TRY | 2000-08-23 | 23-08-00 | 2000-09-13 | 2000-09-14 | 2000-09-18 |  | Yes | Theo Radoi | 2000-11-27 | 2000-11-23 | 2000-11-23 | 2000-12-06 | 2000-12-18 | K 739 494 | 60 | 0 | 38.8 | K 739 494 | 160 | 0 | 38.8 | K 739 494 | 300 | 0 | 38.8 |  |  |  |  | N/A | 22 | 22 | 7/8" | 22 | 22 | 7/8" | 17 | 17 | 7/8" |  |  |  | 122 | ML 38 E 1+0 | Galati | MW | 126 | 0.6 | 39 | 21 | 38/13 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [9 empty] | 1 | BX063 | INDEPENDENTEI_RTC | 306 | 0.6 | 42 | 50 | 38/17 | [6 empty] | 6 | DIEKAT | 2000-09-28 | 247 | 2000-09-28 | 2000-09-14 | 2000-09-18 | IVAN | OK | 2000-11-23 |  | 2000-12-06 | 2000-12-18 |  |  | OK | Bogdan CRAIU | Cosmorom | [32 empty] | 8 | Braila | Braila | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BX069 | PIATA DOROBANTI | Braila(8) | BX063 Independentei_RTC | Moldova | 45 15 26 | 27 57 32.4 | 45 15 31.9 | 27 57 37.8 | Str. Calarasilor Bl.15 Sc.2 | Asociatie de proprietari/Dl. Duwal - adm. Sc.1, 039/ 636 335 | 2102 | M/E | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-09-05 | Yes | N/A |  |  |  | 25.7 | B | 29 | T6m | N/A | DIEKAT | OK | DIEKAT | 2000-07-25 | 2000-08-04 | YesV | 2000-08-16 | Dragos | 2000-09-06 | 2000-08-21 |  |  |  |  | 2000-07-05 |  | 2000-07-20 | 2000-07-31 |  |  |  | 2000-09-12 | YRO | TRY | 2000-08-25 | 25-08-00 | 2000-09-13 | 2000-09-14 | 2000-09-18 |  | Yes | Alexandru Toma | 2000-11-27 | 2000-12-08 | 2000-12-08 |  |  | K 739 494 | 60 | 0 | 33.5 | K 739 494 | 210 | 0 | 33.5 | K 739 494 | 320 | 0 | 33 |  |  |  |  | N/A | 25 | 25 | 7/8" | 25 | 25 | 7/8" | 25 | 25 | 7/8" |  |  |  | 150 | ML 23 E 1+0 | Galati | MW | 351 | 0.6 | 34.5 | 26 | 23/58 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [9 empty] | 1 | BX068 | DOROBANTI | 171 | 0.6 | 39 | 21 | 23/56 | [6 empty] | 5 | TRYLON | 2000-09-15 | 190 | 2000-09-12 | 2000-09-14 | 2000-09-18 | IVAN | OK | 2000-12-08 |  | 2000-12-13 | 2000-12-18 |  |  | OK | Bogdan CRAIU | Cosmorom | [32 empty] | 6 | Braila | Braila | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BX070 | CALARASILOR | Braila(8) | BX063 Independentei_RTC | Moldova | 45 14 48.3 | 27 57 00 | 45 14 52.1 | 27 57 02.4 | Calea Calarasilor nr.24 |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-09-06 | Yes | N/A |  |  |  | 32 | B | 35 | C4m+C4m+C4m | N/A | DIEKAT | OK | DIEKAT | 2000-07-15 | 2000-08-04 | YesV | 2000-08-16 | Dragos |  | 2000-08-21 |  |  |  | 2000-06-01 | 2000-05-25 |  | 2000-07-06 | 2000-07-14 |  |  |  | 2000-09-12 | YRO | TRY | 2000-08-25 | 25-08-00 | 2000-09-13 | 2000-09-14 | 2000-09-18 |  | Yes | Theo Radoi | 2000-11-27 | 2000-11-23 | 2000-11-23 |  |  | K 739 494 | 60 | 0 | 36.8 | K 739 494 | 205 | 0 | 36.8 | K 739 494 | 300 | 0 | 36.8 |  |  |  |  | N/A | 15 | 15 | 7/8" | 15 | 15 | 7/8" | 31 | 31 | 7/8" |  |  |  | 122 | ML 23 E 1+0 | Galati | MW | 37 | 0.6 | 37.5 | 14 | 23/56 |  | 4x2/8 | 4U-1 |  |  |  | RBS | [9 empty] | 1 | BX063 | INDEPENDENTEI_RTC | 217 | 0.6 | 42 | 45 | 23/58 | [6 empty] | 6 | DIEKAT | 2000-09-28 | 246 | 2000-09-28 | 2000-09-14 | 2000-09-18 | IVAN | OK | 2000-11-22 |  | 2000-12-06 | 2000-12-18 |  |  | OK | Bogdan CRAIU | CATALINA CIOCAN | [32 empty] | 8 | Braila | Braila | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BX071 | BUZAULUI | Braila(8) | BX063 Independentei_RTC | Moldova | 45 14 48.4 | 27 56 14.1 | 45 14 48.4 | 27 56 13.8 | Buzaului nr.17 bl.B30 |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-09-06 | Yes | N/A |  |  |  | 28.2 | B | 28.2 | T3.5m+T3.5m | N/A | DIEKAT | OK | DIEKAT | 2000-07-21 | 2000-07-28 | YesV | 2000-08-04 | Dragos |  | 2000-08-09 |  |  |  | 2000-06-01 | 2000-05-25 |  | 2000-06-21 | 2000-07-11 |  |  |  | 2000-09-12 | YRO | TRY | 2000-08-25 | 25-08-00 | 2000-09-13 | 2000-09-14 | 2000-09-18 |  | Yes | Theo Radoi | 2000-11-27 | 2000-11-22 | 2000-11-22 | 2000-12-06 | 2000-12-18 | K 739 494 | 60 | 0 | 35 | K 739 494 | 220 | 0 | 35 | K 739 494 | 340 | 0 | 35 |  |  |  |  | N/A | 11 | 11 | 7/8" | 13 | 13 | 7/8" | 13 | 13 | 7/8" |  |  |  | 74 | ML 23 E 1+0 | Galati | MW | 84 | 0.6 | 35 | 11 | 23/58 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [9 empty] | 1 | BX070 | CALARASILOR | 263.81 | 0.6 | 37.5 | 14 | 23/56 | [6 empty] | 5 | TRYLON | 2000-09-12 | 191 | 2000-09-12 | 2000-09-14 | 2000-09-18 | IVAN | OK | 2000-11-23 |  | 2000-12-06 | 2000-12-18 |  |  | OK | Bogdan CRAIU | Cosmorom | [32 empty] | 10 | Braila | Braila | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BX072 | OTELARILOR | Galati | BX080 Central_RTC | Moldova | 45 24 37.7 | 28 00 56 | 45 24 38.8 | 28 00 52.3 | Str. Otelarilor nr.27 | Asociatie de locatari nr.27/Dl. Ionescu - sef scara, 036/ 479 463 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-10-11 | Yes | N/A |  |  |  | 27 | B | 33.5 | C4.5m+C4.5m | N/A | DIEKAT | OK | CRIS-CORI | 2000-08-10 | 2000-09-14 | YesV | 2000-10-27 | Dragos | 2000-12-11 | 2000-10-31 |  |  |  |  | 2000-05-05 |  | 2000-07-18 | 2000-07-31 |  |  |  | 2000-10-04 | YRO | ORION | 2000-10-04 | 2000-10-04 | 2000-10-05 | 2000-10-06 | 2000-10-09 |  | Yes | Alexandru Toma | 2000-11-30 | 2000-11-24 | 2000-11-24 | 2001-02-08 | 2001-02-16 | K 739 494 | 15 | 0 | 34 | K 739 494 | 180 | 0 | 34 | K 739 494 | 260 | 0 | 34 |  |  |  |  | N/A | 15 | 15 | 7/8" | 28 | 28 | 7/8" | 28 | 28 | 7/8" |  |  |  | 142 | ML 23 E 1+0 | Galati | MW | 349 | 0.6 | 35 | 19 | 23/58 |  | 4x2/8 | 4U-1 |  |  |  | RBS | [9 empty] | 1 | BX073 | BRAILEI_1 | 169 | 0.6 | 44.5 | 20 | 23/56 | [6 empty] | 7 | ORION | 2000-10-04 | 257 | 2000-10-04 | 2000-10-04 | 2000-10-09 | RADU | OK | 2000-11-24 |  | 2000-12-06 | 2000-12-18 |  |  | OK | Bogdan CRAIU | Cosmorom | [32 empty] | 41 | Galati | Galati | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BX073 | BRAILEI_1 | Galati | BX080 Central_RTC | Moldova | 45 25 04.3 | 28 00 48.8 | 45 25 04.3 | 28 00 48.8 | Sos. Brailei nr.210 Bl.C4 | Asociatie de locatari/Dl. Caprita Dobre - Sos. Brailei nr.365 Bl.C6, 036/ 322 415 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-10-11 | Yes | N/A |  |  |  | 35 | B | 38.5 | T6m | N/A | DIEKAT | OK | CRIS-CORI | 2000-08-03 | 2000-09-14 | YesV | 2000-10-12 | Dragos | 2000-11-27 | 2000-10-13 |  |  |  | 2000-06-09 | 2000-05-05 |  | 2000-07-03 | 2000-07-20 |  |  |  | 2000-10-04 | YRO | ORION | 2000-10-04 | 2000-10-04 | 2000-10-05 | 2000-10-06 | 2000-10-10 |  | Yes | Alexandru Toma | 2000-11-30 | 2000-11-22 | 2000-11-22 | 2001-02-08 | 2001-02-16 | K 739 494 | 115 | 0 | 43.5 | K 739 494 | 235 | 0 | 43.5 | K 739 494 | 350 | 0 | 43.5 |  |  |  |  | N/A | 19 | 19 | 7/8" | 19 | 19 | 7/8" | 19 | 19 | 7/8" |  |  |  | 114 | ML 23 E 1+1 | Galati | MW | 59 | 0.6 | 44.5 | 20 | 23/56 |  | 4x2/8 | 4U-1 |  |  |  | RBS | [6 empty] | Trebuie dublat link-ul |  |  | 1 | BX080 | CENTRAL_RTC | 239 | 0.6 | 48 | 24 | 23/58 | [6 empty] | 7 | ORION | 2000-10-04 | 261 | 2000-10-04 | 2000-10-04 | 2000-10-10 | RADU | OK | 2000-11-22 |  | 2000-12-06 | 2000-12-18 |  |  | OK | Bogdan CRAIU | Petrica BURGHIU | [32 empty] | 41 | Galati | Galati | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BX074 | GHE. ASACHI | Galati | BX080 Central_RTC | Moldova | 45 25 41 | 28 00 57.5 | 45 25 43.8 | 28 01 01.7 | Str. Ghe. Asachi Bl.B3 Sc.3 | Asociatie de locatari/Coman Iordache - presedinte, 036/ 327 774 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-10-11 | Yes | N/A |  |  |  | 14.4 | B | 14.4 | 15m new pylonet | N/A | DIEKAT | OK | GIRARDOT | 2000-08-03 | 2000-09-10 | YesV | 2000-09-13 | Dragos | 2000-09-27 | 2000-12-08 |  |  |  | 2000-06-06 | 2000-05-05 |  | 2000-07-03 | 2000-07-18 |  |  |  | 2000-09-12 | YRO | Interactive | 2000-09-12 | 2000-09-12 | 2000-09-13 | 2000-09-14 | 2000-09-18 |  | Yes | Alexandru Toma | 2000-11-30 | 2000-12-07 | 2000-12-07 | 2001-02-08 | 2001-02-16 | K 739 494 | 12 | 0 | 29.4 | K 739 494 | 115 | 0 | 29.4 | K 739 494 | 210 | 0 | 29.4 |  |  |  |  | N/A | 25 | 25 | 7/8" | 25 | 25 | 7/8" | 25 | 25 | 7/8" |  |  |  | 150 | ML 23 E 1+0 | Galati | MW | 193 | 0.6 | 22.4 | 17 | 23/58 |  | 4x2/8 | 4U-1 |  |  |  | RBS | [9 empty] | 1 | BX073 | BRAILEI_1 | 13 | 0.6 | 44.5 | 20 | 23/56 | [6 empty] | 7 | ORION | 2000-10-04 | 258 | 2000-10-04 | 2000-10-04 | 2000-10-06 | IVAN | OK | 2000-12-07 |  | 2000-12-06 | 2000-12-18 |  |  | OK | Bogdan CRAIU | Cosmorom | [32 empty] | 41 | Galati | Galati | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BX075 | SIDERURGISTILOR | Galati(13) | BX078 Ghe. Doja_RTC | Moldova | 45 26 16.5 | 28 01 08 | 45 26 24.7 | 28 01 13.4 | Str. Siderurgistilor Bl. M3 A, Sc.5 | Asociatie de locatari/Adm. Voicu Elena - Str. Siderurgistilor Bl.SD1/A Sc.2 Ap.36, 476 525/ 456 456 | 2102 | M/E | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-09-06 | Yes | N/A |  |  |  | 19.2 | B | 19.2 | 6m new pylonet | N/A | DIEKAT | OK | GIRARDOT | 2000-07-10 | 2000-07-28 | YesV | 2000-08-03 | Dragos | 2000-09-27 | 2000-08-09 |  |  |  | 2000-06-09 | 2000-05-05 |  | 2000-06-21 | 2000-07-04 |  |  |  | 2000-09-28 | YRO | DIEKAT | 2000-08-23 | 23/08/00 | 2000-09-29 | 2000-09-30 | 2000-10-02 |  | Yes | Alexandru Toma | 2000-11-30 | 2000-12-10 | 2000-12-10 | 2000-12-18 | 2000-12-21 | K 739 494 | 0 | 0 | 25 | K 739 494 | 120 | 0 | 25 | K 739 494 | 240 | 0 | 25 |  |  |  |  | N/A | 11 | 11 | 7/8" | 11 | 11 | 7/8" | 11 | 11 | 7/8" |  |  |  | 66 | ML 23 E 1+0 | Galati | MW | 121 | 0.6 | 25 | 11 | 23/56 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [9 empty] | 1 | BX078 | GHE. DOJA_RTC | 301 | 0.6 | 25.5 | 36 | 23/58 | [6 empty] | 6 | DIEKAT | 2000-09-28 | 248 | 2000-09-28 | 2000-09-29 | 2000-10-01 | RADU | OK | 2000-12-10 |  | 2000-12-13 | 2000-12-18 |  |  | OK | Bogdan CRAIU | Cosmorom | [32 empty] | 39 | Galati | Galati | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BX076 | FEROVIARILOR | Galati | BX080 Central_RTC | Moldova | 45 26 55.9 | 28 01 03.6 | 45 27 02.1 | 28 01 05.2 | Str. Feroviarilor nr.2 Bl.C1 Sc.3 | Asociatie de locatari/Apostel Ionel - sef scara, 036/ 422 284 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-10-11 | Yes | N/A |  |  |  | 16.4 | B | 16.4 | T6m | N/A | DIEKAT | OK | ROMPSAR | 2000-08-05 | 2000-09-29 | YesV | 2000-10-12 | Dragos | 2000-11-10 | 2000-10-13 |  |  |  |  | 2000-05-05 |  | 2000-07-03 | 2000-07-20 |  |  |  | 2000-10-04 | YRO | ORION | 2000-10-04 | 2000-10-04 | 2000-10-05 | 2000-10-13 | 2000-10-16 |  | Yes | Alexandru Toma | 2000-11-30 | 2000-12-07 | 2000-12-07 | 2001-02-08 | 2001-02-16 | K 739 494 | 12 | 0 | 22.3 | K 739 494 | 135 | 0 | 22.3 | K 739 494 | 240 | 0 | 22.3 |  |  |  |  | N/A | 24 | 24 | 7/8" | 24 | 24 | 7/8" | 24 | 24 | 7/8" |  |  |  | 144 | ML 23 E 1+0 | Galati | MW | 184 | 0.6 | 23.3 | 25 | 23/58 |  | 4x2/8 | 4U-1 |  |  |  | RBS | [9 empty] | 1 | BX073 | BRAILEI_1 | 4 | 0.6 | 44.5 | 20 | 23/56 | [6 empty] | 7 | ORION | 2000-10-04 | 259 | 2000-10-04 | 2000-10-04 | 2000-10-16 | RADU | OK | 2000-12-07 |  | 2000-12-13 | 2000-12-18 |  |  | OK | Bogdan CRAIU | Cosmorom | [32 empty] | 40 | Galati | Galati | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BX077 | SATURN | Galati | BX080 Central_RTC | Moldova | 45 26 58.7 | 28 01 34.7 | 45 25 18.5 | 28 01 42.7 | Str. Saturn nr.34 Bl.17 | Asociatie de locatari/Dl. Viorel - 036/ 310 624 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-10-11 | Yes | N/A |  |  |  | 31 | B | 31 | T4.5m+T4.5m | N/A | DIEKAT | OK | ROMPSAR | 2000-08-05 | 2000-09-29 | YesV | 2000-10-12 | Dragos | 2000-11-27 | 2000-10-13 |  |  |  |  | 2000-05-05 |  | 2000-07-11 | 2000-07-25 |  |  |  | 2000-10-04 | YRO | ORION | 2000-10-04 | 2000-10-04 | 2000-10-05 | 2000-10-13 | 2000-10-16 |  | Yes | Alexandru Toma | 2000-11-30 | 2000-11-21 | 2000-11-21 | 2000-12-06 | 2000-12-18 | K 739 494 | 0 | 0 | 34.5 | K 739 494 | 80 | 0 | 34.5 | K 739 494 | 225 | 0 | 34.5 |  |  |  |  | N/A | 20 | 20 | 7/8" | 16 | 16 | 7/8" | 20 | 20 | 7/8" |  |  |  | 112 | ML 23 E 1+0 | Galati | MW | 48 | 0.6 | 35.5 | 17 | 23/56 |  | 4x2/8 | 4U-1 |  |  |  | RBS | [9 empty] | 1 | BX080 | CENTRAL_RTC | 227 | 0.6 | 48 | 26 | 23/58 | [6 empty] | 7 | ORION | 2000-10-04 | 262 | 2000-10-04 | 2000-10-04 | 2000-10-16 | RADU | OK | 2000-11-21 |  | 2000-12-06 | 2000-12-18 |  |  | OK | Bogdan CRAIU | Cosmorom | [32 empty] | 40 | Galati | Galati | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BX078 | GHE. DOJA_RTC | Galati(13) | BX078 Ghe. Doja_RTC | Moldova | 45 26 00.8 | 28 01 38.4 | 45 26 00.8 | 28 01 38.4 | Str. Ghe. Doja | Romtelecom/ | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-09-06 | N/A | N/A |  |  |  | 17 | B | 17 | 9m Pylonet | Room | DIEKAT | OK | DIEKAT | 2000-07-06 | 2000-07-28 | YesV | 2000-08-03 | Dragos | 2000-08-17 | 2000-08-09 |  |  |  | N/A | 2000-05-05 |  | 2000-06-14 | 2000-07-03 |  |  |  | 2000-09-05 | YRO | DIEKAT | 2000-08-23 | 2000-08-23 | 2000-09-05 | 2000-09-07 | 2000-09-08 |  | Yes | Alexandru Toma | 2000-11-30 | 2000-11-24 | 2000-11-24 | 2001-02-15 | 2001-02-16 | K 739 494 | 0 | 0 | 25 | K 739 494 | 120 | 0 | 25 | K 739 494 | 235 | 0 | 25 |  |  |  |  | N/A | 36 | 36 | 7/8" | 36 | 36 | 7/8" | 36 | 36 | 7/8" |  |  |  | 216 | N/A | Galati | FO | N/A | N/A | N/A | N/A | N/A |  | 4x2/8 | 4U-1 |  |  |  | N/A | [9 empty] | 1 | BSC11 | DRUMUL TABEREI | N/A | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A |  |  | OK | Bogdan CRAIU | Cosmorom | [32 empty] | 42 | Galati | Galati | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | BX079 | PODUL INALT | Galati(13) | BX078 Ghe. Doja_RTC | Moldova | 45 26 35.7 | 28 01 34.8 | 45 26 42.8 | 28 01 41.2 | Str. Podul Inalt Bl.U14A Sc.1 | Asociatie de locatari/Fam. Rusu - Et.1 Ap.13, 036/ 481 796 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-09-06 | Yes | N/A |  |  |  | 15.8 | B | 15.8 | 6m pylonet | N/A | DIEKAT | OK | DIEKAT | 2000-07-06 | 2000-07-28 | YesV | 2000-08-03 | Dragos | 2000-12-08 | 2000-08-09 |  |  |  | 2000-06-09 | 2000-05-05 |  | 2000-06-21 | 2000-07-07 |  |  |  | 2000-10-03 | YRO | DIEKAT | 2000-10-02 | 2000-10-02 | 2000-10-04 | 2000-10-05 | 2000-10-06 |  | Yes | Alexandru Toma | 2000-11-30 | 2000-12-10 | 2000-12-10 | 2001-02-08 | 2001-04-10 | K 739 494 | 120 | 0 | 20 | K 739 494 | 240 | 0 | 20 | K 739 494 | 345 | 0 | 20 |  |  |  |  | N/A | 16 | 16 | 7/8" | 16 | 16 | 7/8" | 16 | 16 | 7/8" |  |  |  | 96 | ML 23 E 1+0 | Galati | MW | 227 | 0.6 | 21 | 17 | 23/58 |  | 4x2/8 | 4U-1 |  |  |  | RBS | [9 empty] | 1 | BX075 | SIDERURGISTILOR | 47 | 0.6 | 25 | 11 | 23/56 | [6 empty] | 7 | DIEKAT | 2000-10-03 | 253 | 2000-10-03 | 2000-10-04 | 2000-10-06 | RADU | OK | 2000-12-10 |  | 2000-12-13 | 2000-12-18 |  |  | OK | Bogdan CRAIU | Cosmorom | [32 empty] | 39 | Galati | Galati | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BX080 | CENTRAL_RTC | Galati | BX080 Central_RTC | Moldova | 45 25 41.2 | 28 02 17.8 | 45 25 41.2 | 28 02 17.8 | Romtelecom Galati | Romtelecom/ | 2102 | M/E | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-08-29 | Yes | NA |  |  |  | 36 | B | 52 | 16m Pylonet | N/A | DIEKAT | OK | DIEKAT | 2000-07-06 | 2000-07-28 | YesV | 2000-08-03 | Dragos | 2000-08-17 | 2000-08-09 |  |  |  | N/A | 2000-05-05 |  | 2000-06-15 | 2000-08-03 |  |  |  | 2000-08-23 | YRO | ORION | 2000-08-23 | 2000-08-21 | 2000-08-24 | 2000-08-29 | 2000-08-31 |  | Yes | Alexandru Toma | 2000-11-30 | 2000-11-21 | 2000-11-21 | 2000-12-06 | 2000-12-18 | K 739 494 | 0 | 0 | 44 | K 739 494 | 120 | 0 | 44 | K 739 494 | 240 | 0 | 44 |  |  |  |  | N/A | 25 | 25 | 7/8" | 23 | 23 | 7/8" | 21 | 21 | 7/8" |  |  |  | 138 | N/A | Galati | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | 4U-1 | 2U-3 |  |  | RBS | [7 empty] | 50/ |  | 1 | BSC22 | BSC GALATI |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A |  |  | OK | Bogdan CRAIU | CATALINA CIOCAN | [32 empty] | 39 | Galati | Galati | [7 empty] | Site Near=Insertion Point
Phase_3 | CS | BX082 | URSUS | Buzau(2) | BX088 Buzau_RTC | Moldova | 45 09 47.3 | 26 47 13.4 |  |  |  |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [17 empty] | D&D |  | @ | 2001-08-15 | 2001-08-30 |  |  | Doru |  |  | 2001-05-30 |  |  |  | 2001-05-30 | [17 empty] | CTR | [35 empty] | Galati | MW | [22 empty] | BX089 | BD.GARII | [27 empty] | SORIN UNTARU | SORIN UNTARU | [42 empty] | missing |  |  | missing
Phase_2 | CS | BX083 | DEPOZIT_RTC | Galati | BX080 Central_RTC | Moldova | 45 27 59.6 | 28 02 04.1 | 45 27 59.6 | 28 02 04.1 | Str. Traian nr.399 | Romtelecom/ | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-09-06 | N/A | N/A |  |  |  | 24 | B | 28 | C4m+C4m | Room | DIEKAT | OK | DIEKAT | 2000-07-15 | 2000-08-21 | YesV | 2000-08-25 | Dragos | 2000-09-04 | 2000-08-30 |  |  |  | N/A | 2000-05-05 |  | 2000-07-11 | 2000-07-27 |  |  |  | 2000-09-05 | YRO | DIEKAT | 2000-08-29 | 2000-08-29 | 2000-09-05 | 2000-09-09 | 2000-09-10 |  | Yes | Alexandru Toma | 2000-11-30 | 2000-11-24 | 2000-11-24 | 2001-02-15 | 2001-02-16 | K 739 494 | 0 | 0 | 30 | K 739 494 | 135 | 0 | 30 | K 739 494 | 240 | 0 | 30 |  |  |  |  | N/A | 23 | 23 | 7/8" | 23 | 23 | 7/8" | 28 | 28 | 7/8" |  |  |  | 148 | ML 23 E 1+0 | Galati | MW | 176 | 0.6 | 31 | 29 | 23/56 |  | 4x2/8 | 2U-3 |  |  |  | N/A | [9 empty] | 1 | BX080 | CENTRAL_RTC | 356 | 0.6 | 48 | 26 | 23/58 | [6 empty] | 3 | DIEKAT | 2000-09-05 | 171 | 2000-09-05 | 2000-09-09 | 2000-09-10 | PITURCESCU | OK | 2000-11-24 |  | 2000-12-06 | 2000-12-18 |  |  | OK | Bogdan CRAIU | Cosmorom | [32 empty] | 40 | Galati | Galati | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BX084 | BRAILEI_2 | Galati | BX080 Central_RTC | Moldova | 45 25 56.7 | 28 02 54.5 | 45 25 56.4 | 28 02 54.4 | Str. Brailei Bl.BR1C Sc.1 | Asociatie de locatari/Dl. Vasiliu - Ap.15, 036/ 414 971 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-08-29 | Yes | N/A |  |  |  | 28.8 | B | 35.4 | C45m+C4m | N/A | DIEKAT | OK | DIEKAT | 2000-08-03 | 2000-08-23 | YesV | 2000-08-25 | Dragos | 2000-09-04 | 2000-08-30 |  |  |  |  | 2000-05-05 |  | 2000-07-18 | 2000-08-03 |  |  |  | 2000-08-29 | YRO | ORION | 2000-08-29 | 2000-08-29 | 2000-08-30 | 2000-08-29 | 2000-08-31 |  | Yes | Alexandru Toma | 2000-11-30 | 2000-11-22 | 2000-11-22 |  |  | K 739 494 | 0 | 0 | 35 | K 739 494 | 105 | 0 | 35 | K 739 494 | 230 | 0 | 35 |  |  |  |  | N/A | 20 | 20 | 7/8" | 16 | 16 | 7/8" | 16 | 16 | 7/8" |  |  |  | 104 | ML 38 E 1+0 | Galati | MW | 239.04 | 0.3 | 36 | 20 | 38/13 |  | 4x2/8 | 4U-1 |  |  |  | RBS | [9 empty] | 1 | BX080 | CENTRAL_RTC | 59 | 0.3 | 48 | 28 | 38/17 | [6 empty] | 4 | ORION | 2000-08-29 | 157 | 2000-08-29 | 2000-08-29 | 2000-08-31 | PITURCESCU | OK | 2000-11-22 |  | 2000-12-06 | 2000-12-18 |  |  | OK | Bogdan CRAIU | Petrica BURGHIU | [32 empty] | 34 | Galati | Galati | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BX085 | PROIECT GALATI | Galati | BX080 Central_RTC | Moldova | 45 26 03.3 | 28 03 29 | 45 25 55.2 | 28 03 39.2 | B-dul. Brailei nr.20 | PROIECT Galati - 036/ 411 779/Dl Dir. Chiriac - 036/ 411 779 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-09-06 | Yes | N/A |  |  |  | 32 | B | 32 | T4m | N/A | DIEKAT | OK | DIEKAT | 2000-08-03 | 2000-09-04 | YesV | 2000-09-13 | Dragos | 2000-09-04 | 2000-12-08 |  |  |  |  | 2000-05-05 |  | 2000-07-20 | 2000-08-03 |  |  |  | 2000-09-05 | YRO | DIEKAT | 2000-09-05 | 2000-09-05 | 2000-09-05 | 2000-09-07 | 2000-09-08 |  | Yes | Alexandru Toma | 2000-11-30 | 2000-11-22 | 2000-11-22 | 2001-02-15 | 2001-02-16 | K 739 494 | 60 | 0 | 35 | K 739 494 | 235 | 0 | 35 | K 739 494 | 345 | 0 | 35 |  |  |  |  | N/A | 12 | 12 | 7/8" | 12 | 12 | 7/8" | 12 | 12 | 7/8" |  |  |  | 72 | ML 23 E 1+0 | Galati | MW | 272 | 0.6 | 36 | 13 | 23/58 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [7 empty] | 50/ |  | 1 | BX084 | BRAILEI_2 | 93 | 0.6 | 36 | 21 | 23/56 | [6 empty] | 3 | DIEKAT | 2000-09-05 | 172 | 2000-09-05 | 2000-11-17 | 2000-11-23 | PITURCESCU | OK | 2000-11-22 |  | 2000-12-06 | 2000-12-18 |  |  | OK | Bogdan CRAIU | Cosmorom | [32 empty] | 6 | Galati | Galati | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BX086 | MIHAI BRAVU | Galati | BX080 Central_RTC | Moldova | 45 26 50.7 | 28 03 20.9 | 45 26 50.7 | 28 03 20.9 | Str. Mihai Bravu nr.11 | Telecomunicatii CFR4 - Galati/ | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-10-11 | N/A | N/A |  |  |  | 0 | TE | 62 | Tower | N/A | DIEKAT | OK | DIEKAT | 2000-09-01 | 2000-09-21 | YesV | 2000-09-28 | Dragos | 2000-11-10 | 2000-10-03 |  |  |  | 2000-06-09 | 2000-05-05 |  | 2000-07-05 | 2000-08-18 |  |  |  | 2000-10-03 | YRO | DIEKAT | 2000-10-03 | 2000-10-03 | 2000-10-04 | 2000-10-06 | 2000-10-10 |  | Yes | Alexandru Toma | 2000-11-30 | 2000-11-28 | 2000-11-28 | 2000-12-06 | 2000-12-18 | K 739 494 | 0 | 0 | 46 | K 739 494 | 120 | 0 | 46 | K 739 494 | 240 | 0 | 46 |  |  |  |  | N/A | 60 | 60 | 1 1/4" | 60 | 60 | 1 1/4" | 60 | 60 | 1 1/4" |  |  |  | 360 | ML 23 E 1+0 | Galati | MW | 166 | 0.6 | 46 | 60 | 23/56 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [9 empty] | 1 | BX085 | PROIECT GALATI | 346 | 0.6 |  | 15 | 23/58 | [6 empty] | 13 | TRYLON | 2000-11-16 | 369 | 2000-11-16 | 2000-11-17 | 2000-11-23 | RADU | OK | 2000-12-01 |  | 2000-12-06 | 2000-12-18 |  |  | OK | Bogdan CRAIU | Cosmorom | [32 empty] | 39 | Galati | Galati | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_3 | CS | BX087 | FABRICA DE ULEI | Buzau(2) | BX088 Buzau_RTC | Moldova | 45 08 07.3 | 26 50 17.2 |  |  |  |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [17 empty] | D&D |  | @ | 2001-08-01 | 2001-08-20 |  |  | Doru |  |  | 2001-05-30 |  |  |  | 2001-05-30 | [17 empty] | CTR | [35 empty] | Galati | MW | [22 empty] | BX092 | MARGHILOMAN | [27 empty] | SORIN UNTARU | SORIN UNTARU | [42 empty] | missing |  |  | missing
Phase_2 | CS | BX088 | BUZAU_RTC | Buzau(7) | BX088 Buzau_RTC | Moldova | 45 09 09.2 | 26 49 07.2 | 45 09 09.2 | 26 49 07.2 | Str. Ostrovului nr.1, RTC Buzau | Romtelecom/ | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-09-19 | N/A | N/A |  |  |  | 20 | TE | 45 |  | Room | SVF | OK | EL-MONT | 2000-07-28 | 2000-08-18 | YesV | 2000-08-18 | Bogdan | 2000-08-17 | 2000-08-30 |  |  |  | N/A | 2000-07-19 |  | 2000-07-13 | 2000-07-31 |  |  |  | 2000-09-07 | YRO | SVF | 2000-08-25 | 2000-09-07 | 2000-09-08 | 2000-09-12 | 2000-09-14 |  | Yes | Theo Radoi | 2000-12-02 | 2000-11-28 | 2000-11-28 | 2001-02-08 | 2001-02-16 | K 739 494 | 340 | 0 | 43.3 | K 739 494 | 100 | 0 | 43.3 | K 739 494 | 210 | 0 | 43.3 |  |  |  |  | N/A | 62 | 62 | 1 1/4" | 62 | 62 | 1 1/4" | 62 | 62 | 1 1/4" |  |  |  | 372 | N/A | Galati | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | 4U-1 |  |  |  | N/A | [9 empty] | 1 | BSC22 | BSC GALATI |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | RADU | OK | N/A |  | N/A | N/A |  |  | OK | Ionut GRIGORESCU | [33 empty] | 100 | Buzau | Buzau | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | BX089 | BD. GARII | Buzau(7) | BX088 Buzau_RTC | Moldova | 45 09 43.9 | 26 48 59.5 | 45 09 43.9 | 26 48 59.5 | Bd. Unirii Bl.H2, MICRO 3 CONEL BUZAU 038/725531 | Asociatie de locatari/Sava Elena - responsabil bloc H2 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-11-17 | Yes | N/A |  |  |  | 32 | B | 37.85 | C4.5m+C4.5m | N/A | SVF | OK | EL-MONT | 2000-10-20 | 2000-10-23 | YesV | 2000-10-30 | Bogdan | 2000-12-08 | 2000-11-02 |  |  |  |  | 2000-07-19 |  | 2000-10-05 | 2000-10-24 |  |  |  | 2000-10-26 | ICOM | TRY | 2000-10-26 | 2000-10-27 | 2000-10-28 | 2000-10-28 | 2000-10-31 |  | Yes | Theo Radoi | 2000-12-02 | 2000-11-24 | 2000-11-24 | 2000-12-08 | 2001-01-08 | K 739 494 | 15 | 0 | 40.45 | K 739 494 | 110 | 0 | 39.65 | K 739 494 | 225 | 0 | 40.35 |  |  |  |  | N/A | 31 | 31 | 7/8" | 22 | 22 | 7/8" | 31 | 31 | 7/8" |  |  |  | 168 | ML 23 E 1+0 | Galati | MW | 171 | 0.6 | 41.05 | 22 | 23/58 |  | 4x2/8 | 4U-1 |  |  |  | RBS | [9 empty] | 1 | BX088 | BUZAU_RTC | 351 | 0.6 | 35 | 56 | 23/56 | [6 empty] | 10 | TRYLON | 2000-10-26 | 347 | 2000-10-26 | 2000-10-28 | 2000-10-31 | VLAD | OK | 2000-11-24 |  | 2000-12-06 | 2000-12-10 |  |  | OK | Ionut GRIGORESCU | Petrica BURGHIU | [32 empty] | 108 | Buzau | Buzau | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BX090 | UNIRII | Buzau(7) | BX088 Buzau_RTC | Moldova | 45 08 37.7 | 26 48 38.4 | 45 08 37.7 | 26 48 38.4 | Bd. Unirii Bl.B16, Sc B | Asociatie de locatari/Dl. Neacsu - 095/ 047748, 038/ 424 924 | 2102 | M/E | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-10-11 | Yes | N/A |  |  |  | 31 | B | 36 | T4m+C3m | N/A | SVF | OK | EL-MONT | 2000-09-05 | 2000-09-15 | YesV | 2000-09-19 | Bogdan | 2000-09-18 | 2000-09-22 |  |  |  |  | 2000-07-19 |  | 2000-08-21 | 2000-08-22 |  |  |  | 2000-09-28 | YRO | DIEKAT | 2000-09-21 | 2000-09-21 | 2000-09-29 | 2000-10-03 | 2000-10-04 |  | Yes | Theo Radoi | 2000-12-02 | 2000-11-25 | 2000-11-25 | 2001-02-13 | 2001-02-16 | K 739 494 | 20 | 0 | 33.9 | K 739 494 | 135 | 0 | 37.5 | K 739 494 | 230 | 0 | 37.4 |  |  |  |  | N/A | 10 | 10 | 7/8" | 28 | 28 | 7/8" | 28 | 28 | 7/8" |  |  |  | 132 | ML 23 E 1+0 | Galati | MW | 33 | 0.6 | 34.4 | 12 | 23/58 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [9 empty] | 1 | BX088 | BUZAU_RTC | 215 | 0.6 | 35 | 59 | 23/56 | [6 empty] | 6 | DIEKAT | 2000-09-28 | 250 | 2000-09-28 | 2000-10-04 | 2000-10-04 | YRO | OK | 2000-11-25 |  | 2000-12-06 | 2000-12-18 |  |  | OK | Petrica BURGHIU | Cosmorom | [32 empty] | 96 | Buzau | Buzau | [7 empty] | 2 | 1 |  | 2
Phase_2 | CS | BX091 | GARA BUZAU | Buzau(7) | BX088 Buzau_RTC | Moldova | 45 08 34.9 | 26 49 30.2 | 45 08 34.9 | 26 49 30.2 | B-dul. 1 Decembrie Gara Centrala Buzau | /Dl. Zinca - 036/ 460 361, 092/ 693 140 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-10-20 | N/A | N/A |  |  |  | 0 | TE | 42 | Existed tower 42m | N/A | SVF | OK | EL-MONT | 2000-09-12 | 2000-09-22 | YesV | 2000-09-29 | Bogdan | 2000-11-02 | 2000-10-03 |  |  |  |  | 2000-07-19 |  | 2000-08-07 | 2000-08-30 |  |  |  | 2000-10-20 | ICOM | TRY | 2000-10-03 | 2000-10-03 | 2000-10-24 | 2000-10-24 | 2000-10-26 |  | Yes | Theo Radoi | 2000-12-02 | 2000-11-27 | 2000-11-27 | 2000-12-13 | 2001-01-08 | K 739 494 | 100 | 0 | 41 | K 739 494 | 240 | 0 | 41 | K 739 494 | 345 | 0 | 41 |  |  |  |  | N/A | 45 | 45 | 7/8'' | 45 | 45 | 7/8'' | 45 | 45 | 7/8" |  |  |  | 270 | ML 23 E 1+0 | Galati | MW | 334 | 0.6 | 27 | 36 | 23/58 |  | 4x2/8 | 4U-1 |  |  |  | RBS | [9 empty] | 1 | BX088 | BUZAU_RTC | 155 | 0.6 | 35 | 62 | 23/56 | [6 empty] | 9 | TRYLON | 2000-10-20 | 279 | 2000-10-13 | 2000-10-14 | 2000-10-18 | VLAD | OK | 2000-11-25 |  | 2000-12-06 | 2000-12-18 |  |  | OK | Ionut GRIGORESCU | Cosmorom | [32 empty] | 97 | Buzau | Buzau | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BX092 | MARGHILOMAN | Buzau(7) | BX088 Buzau_RTC | Moldova | 45 08 47 | 26 50 18.5 | 45 08 47 | 26 50 18.5 | Str. Al. Marghiloman Bl.17 Sc. B | Asociatia de locatari/Dl. Moise | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-10-13 | Yes | N/A |  |  |  | 35.25 | B | 35.25 | C2m+C2m | N/A | SVF | OK | EL-MONT | 2000-10-02 | 2000-10-15 | YesV | 2000-10-30 | Bogdan | 2000-11-10 | 2000-11-03 |  |  |  |  | 2000-07-19 |  | 2000-08-21 | 2000-09-04 |  |  |  | 2000-10-20 | ICOM | TRY | 2000-10-13 | 2000-10-13 | 2000-10-24 | 2000-10-24 | 2000-10-26 |  | Yes | Theo Radoi | 2000-12-02 | 2000-11-27 | 2000-11-27 | 2001-02-13 | 2001-02-16 | K 739 494 | 135 | 0 | 37 | K 739 494 | 245 | 0 | 36.75 | K 739 494 | 350 | 0 | 36.85 |  |  |  |  | N/A | 15 | 15 | 7/8" | 15 | 15 | 7/8" | 12 | 12 | 7/8" |  |  |  | 84 | ML 23 E 1+0 | Galati | MW | 250 | 0.6 | 37.85 | 16 | 23/56 |  | 4x2/8 | 4U-1 |  |  |  | RBS | [9 empty] | 1 | BX091 | GARA BUZAU | 70 | 0.6 | 27 | 36 | 23/58 | [6 empty] | 9 | TRYLON | 2000-10-20 | 280 | 2000-10-13 | 2000-10-14 | 2000-10-18 | VLAD | OK | 2000-11-26 |  | 2000-12-06 | 2000-12-18 |  |  | OK | Ionut GRIGORESCU | Cosmorom | [32 empty] | 98 | Buzau | Buzau | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BX093 | BROSTENI | Buzau(7) | BX088 Buzau_RTC | Moldova | 45 09 16.5 | 26 49 50.2 | 45 09 16.5 | 26 49 50.2 | Str. Brosteni Bl.F4 | Romtelecom/ | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-09-09 | Yes | N/A |  |  |  | 14.25 | B | 14.25 | 9m pylonet | N/A | SVF | OK | SVF | 2000-07-26 | 2000-08-15 | YesV | 2000-08-16 | Bogdan | 2000-08-17 | 2000-08-21 |  |  |  | 2000-07-11 | 2000-07-19 |  | 2000-07-20 | 2000-07-20 |  |  |  | 2000-09-07 | YRO | SVF | 2000-08-25 | 2000-09-07 | 2000-09-08 | 2000-09-12 | 2000-09-14 |  | Yes | Theo Radoi | 2000-12-02 | 2000-11-25 | 2000-11-25 | 2001-02-21 | 2001-03-06 | K 739 494 | 0 | 0 | 22.85 | K 739 494 | 110 | 0 | 22.85 | K 739 494 | 230 | 0 | 22.85 |  |  |  |  | N/A | 19 | 19 | 7/8" | 19 | 19 | 7/8" | 19 | 19 | 7/8" |  |  |  | 114 | ML 23 E 1+0 | Galati | MW | 307 | 0.6 | 21.35 | 18 | 23/56 |  | 4x2/8 | 4U-1 |  |  |  | RBS | [9 empty] | 1 | BX089 | BD. GARII | 127 | 0.6 | 40.65 | 22 | 23/58 | [6 empty] | 10 | TRYLON | 2000-10-26 | 348 | 2000-10-26 | 2000-10-28 | 2000-10-31 | RADU | OK | 2000-11-25 |  | 2000-12-06 | 2000-12-18 |  |  | OK | Ionut GRIGORESCU | Petrica BURGHIU | [32 empty] | 106 | Buzau | Buzau | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BX094 | GRIGORE BASTAN | Buzau(7) | BX088 Buzau_RTC | Moldova | 45 09 03.7 | 26 47 55.2 | 45 09 05.7 | 26 47 55.2 | Str. Grigore Bastan Bl.52 Sc.B | Asociatie de locatari/Dl. Moraru Stefan - 038/ 438 012 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-09-09 | Yes | N/A |  |  |  | 31.35 | B | 33.75 | 2 x suport zid | N/A | SVF | OK | SVF | 2000-07-26 | 2000-08-15 | YesV | 2000-08-16 | Bogdan | 2000-09-06 | 2000-08-21 |  |  |  |  | 2000-07-19 |  | 2000-07-20 | 2000-08-11 |  |  |  | 2000-09-07 | YRO | SVF | 2000-08-30 | 2000-09-07 | 2000-09-08 | 2000-09-10 | 2000-09-11 |  | Yes | Theo Radoi | 2000-12-02 | 2000-11-26 | 2000-11-26 | 2001-02-21 | 2001-04-10 | K 739 494 | 50 | 0 | 39.3 | K 739 494 | 140 | 0 | 39.5 | K 739 494 | 315 | 0 | 39.5 |  |  |  |  | N/A | 25 | 25 | 7/8" | 25 | 25 | 7/8" | 21 | 21 | 7/8" |  |  |  | 142 | ML 23 E 1+0 | Galati | MW | 130 | 0.6 | 38.1 | 25 | 23/56 |  | 4x2/8 | 4U-1 |  |  |  | RBS | [9 empty] | 1 | BX090 | UNIRII | 310 | 0.6 | 38.5 | 30 | 23/58 | [6 empty] | 6 | DIEKAT | 2000-09-28 | 249 | 2000-09-28 | 2000-09-29 | 2000-10-04 | RADU | OK | 2000-11-26 |  | 2000-12-06 | 2000-12-18 |  |  | OK | Ionut GRIGORESCU | Cosmorom | [32 empty] | 100 | Buzau | Buzau | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BX095 | RM. SARAT_DRTV | Rm. Sarat(3+1) | BX098 Rm. Sarat_RTC | Moldova | 45 22 41.2 | 27 02 35.6 | 45 22 41.2 | 27 02 35.6 | Str. Constantin Brancoveanu nr.34 | DRTV/ | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-09-19 | N/A | N/A |  |  |  | 0 | TE | 110.5 | Tower | N/A | SVF | OK | ORION | 2000-08-03 | 2000-08-24 | YesV | 2000-08-25 | Andrei | 2000-09-06 | 2000-08-30 |  |  |  | N/A | 2000-06-21 |  | 2000-07-13 | 2000-07-27 |  |  |  | 2000-09-12 | YRO | Interactive | 2000-08-31 | 2000-08-31 | 2000-09-13 | 2000-09-14 | 2000-09-15 |  | Yes | Theo Radoi | 2000-12-04 | 2000-11-30 | 2000-11-30 | 2000-12-06 | 2000-12-18 | K 739 494 | 5 | 0 | 75 | K 739 494 | 120 | 0 | 46 | K 739 494 | 230 | 0 | 75 |  |  |  |  | N/A | 80 | 80 | 1 1/4" | 56 | 56 | 1 1/4" | 75 | 75 | 1 1/4" |  |  |  | 422 | ML 38 E 1+0 | Galati | MW | 350 | 0.6 | 30 | 55 | 38/14 |  | 4x2/8 | 4U-1 |  |  |  | RBS | [9 empty] | 1 | BX098 | RM. SARAT_RTC | 174 | 0.6 | 15 | 40 | 38/18 | [6 empty] | 9 | TRYLON | 2000-10-20 | 317 | 2000-10-16 | 2000-10-17 | 2000-10-30 | RADU | OK | 2000-11-30 | PENDING |  |  |  |  | OK | Ionut GRIGORESCU | Cosmorom | [32 empty] | 141 | Rm. Sarat | Buzau | [7 empty] | 2 |  |  | 2
Phase_2 | CS | BX096 | COSTIENI | Rm. Sarat(3+1) | BX098 Rm. Sarat_RTC | Moldova | 45 22 19.8 | 27 03 24.8 | 45 22 19.8 | 27 03 24.8 | Str. Aleea Scanteii Bl.8 | Asociatia de locatari/Dl. Slujitoru Serban - 038/ 565 530 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-09-19 | Yes | N/A |  |  |  | 32 | B | 32 | C3m+C3m | N/A | SVF | OK | ORION | 2000-08-10 | 2000-09-09 | YesV | 2000-09-13 | Andrei | 2000-09-07 | 2000-12-08 |  |  |  |  | 2000-06-21 |  | 2000-07-24 | 2000-08-07 |  |  |  | 2000-09-12 | YRO | Interactive | 2000-09-12 | 2000-09-12 | 2000-09-13 | 2000-09-14 | 2000-09-17 |  | Yes | Theo Radoi | 2000-12-04 | 2000-11-30 | 2000-11-30 | 2000-12-08 | 2001-01-08 | K 739 494 | 0 | 0 | 37.6 | K 739 494 | 120 | 0 | 37.6 | K 739 494 | 250 | 0 | 37.4 |  |  |  |  | N/A | 17 | 17 | 7/8" | 21 | 21 | 7/8" | 21 | 21 | 7/8" |  |  |  | 118 | ML 23 E 1+0 | Galati | MW | 302 | 0.6 | 37 | 25 | 23/58 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [9 empty] | 1 | BX095 | RM. SARAT_DRTV | 120 | 0.6 | 40 |  | 23/56 | [6 empty] | 7 | INTERACTIVE | 2000-09-12 | 188 | 2000-09-12 | 2000-10-26 | 2000-10-30 | RADU | OK | 2000-11-29 |  | 2000-12-06 | 2000-12-18 |  |  | OK | Petrica BURGHIU | COSMOROM | [32 empty] | 126 | Rm. Sarat | Buzau | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BX097 | VICTORIEI | Rm. Sarat(3+1) | BX098 Rm. Sarat_RTC | Moldova | 45 23 02.2 | 27 02 30 | 45 23 02.2 | 27 02 30 | Str.Victoriei, Bl.A1 | Asociatia de locatari/Pavel Nicolae Str.Victoriei, Bl.A1 038/ 56 27 97 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-10-13 | Yes | N/A |  |  |  | 40.5 | B | 40.5 | T3m+C2m | N/A | SVF | OK | ORION | 2000-09-12 | 2000-10-19 | YesV | 2000-10-27 | Andrei | 2000-10-20 | 2000-10-31 |  |  |  |  | 2000-06-21 |  | 2000-08-29 | 2000-09-11 |  |  |  | 2000-10-20 | ICOM | TRY | 2000-10-13 | 2000-10-13 | 2000-10-24 | 2000-10-26 | 2000-10-30 |  | Yes | Theo Radoi | 2000-12-04 | 2000-11-30 | 2000-11-30 | 2000-12-06 | 2000-12-18 | K 739 494 | 5 | 0 | 42.5 | K 739 494 | 130 | 0 | 42.5 | K 739 494 | 240 | 0 | 42.5 |  |  |  |  | N/A | 14 | 14 | 7/8" | 14 | 14 | 7/8" | 22 | 22 | 7/8" |  |  |  | 100 | ML 38 E 1+0 | Galati | MW | 138 | 0.6 | 42.5 | 22 | 38/14 |  | 4x2/8 | 4U-1 |  |  |  | RBS | [9 empty] | 1 | BX096 | COSTIENI | 318 | 0.6 | 38 | 25 | 38/18 | [6 empty] | 9 | TRYLON | 2000-10-20 | 316 | 2000-10-16 | 2000-10-26 | 2000-10-30 | DINCA | OK | 2000-11-30 |  | 2000-12-06 | 2000-12-18 |  |  | OK | Ionut GRIGORESCU | Cosmorom | [32 empty] | 142 | Rm.Sarat | Buzau | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | TM | BX098 | RM. SARAT_RTC | Rm. Sarat(3+1) | BX098 Rm. Sarat_RTC | Moldova | 45 22 51.6 | 27 02 34.2 | 45 22 51.6 | 27 02 34.2 | RTC Rm. Sarat | Romtelecom/ | N/A | N/A | N/A | N/A | N/A | [7 empty] | N/A | N/A |  |  |  | N/A | B | 15 | C1.5m | Room | SVF | OK | ORION | 2000-08-05 | 2000-08-24 | YesV | 2000-08-25 | Andrei | 2000-10-23 | 2000-08-30 |  |  |  | N/A | 2000-06-21 |  | 2000-07-18 | 2000-08-02 |  |  |  | 2000-10-20 | ICOM | TRY | N/A | N/A | 2000-10-24 | N/A | N/A |  | Yes | N/A | 2000-12-04 | 2000-11-30 | 2000-11-30 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A | Galati | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | 4U-1 |  |  |  | N/A | [7 empty] | 20/ |  | 1 | BSC11 | DRUMUL TABEREI | N/A | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A |  |  | OK | Ionut GRIGORESCU | Cosmorom | [32 empty] | 141 | Rm.Sarat | Buzau | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | BX099 | TECUCI_RTC | Tecuci(2) | BX099 Tecuci_RTC | Moldova | 45 50 33.7 | 27 25 49.5 | 45 50 33.7 | 27 25 49.5 | Romtelecom Central Tecuci | Romtelecom/ | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-10-11 | N/A | N/A |  |  |  | 0 | TE | 50 | 50m existing tower | N/A | SVF | OK | KEN-KEN | 2000-08-10 | 2000-08-30 | YesV | 2000-08-30 | Andrei | 2000-11-10 | 2000-09-04 |  |  |  | N/A | OK |  | 2000-07-13 | 2000-08-02 |  |  |  | 2000-10-20 | ICOM | TRY | 2000-09-21 | 2000-09-21 | 2000-10-24 | 2000-10-26 | 2000-10-30 |  | Yes | Alexandru Toma | 2000-12-04 | 2000-11-27 | 2000-11-27 |  |  | K 739 494 | 0 | 0 | 48 | K 739 494 | 150 | 0 | 48 | K 739 494 | 210 | 0 | 48 |  |  |  |  | N/A | 60 | 60 | 1 1/4" | 60 | 60 | 1 1/4" | 60 | 60 | 1 1/4" |  |  |  | 360 | N/A | Galati | FO | N/A | N/A | N/A | N/A | N/A |  | 4x2/8 | 2U-3 |  |  |  | RBS | [7 empty] | 85/8p |  | 1 | BSC11 | DRUMUL TABEREI | N/A | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A |  |  | OK | Ionut GRIGORESCU | Cosmorom | [32 empty] | 39 | Tecuci | Galati | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | BX100 | GHE.PATRASCU | Tecuci(2) | BX099 Tecuci_RTC | Moldova | 45 50 53.4 | 27 25 01.6 | 45 50 53.4 | 27 25 01.6 | Str.Ghe.Petrascu nr.58, Bl.A2A,sc5 | Asociatia de locatari/Mocanu Vasile Str.Ghe.Petrascu nr.58, Bl.A2A, sc.5 036/ 81 32 40, 036/ 81 65 45 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-10-20 | Yes | N/A |  |  |  | 35 | B | 37.73 | T6m+T6m | N/A | SVF | OK | KEN-KEN | 2000-10-19 | 2000-11-08 | YesV | 2000-11-16 | Andrei | 2000-11-10 | 2000-11-22 |  |  |  |  | OK |  | 2000-08-29 | 2000-09-11 |  |  |  | 2000-11-09 | ICOM | TRY | 2000-11-09 | 2000-11-09 | 2000-11-09 | 2000-11-10 | 2000-11-13 |  | Yes | Alexandru Toma | 2000-12-04 | 2000-12-01 | 2000-12-01 | 2000-12-27 | 2001-01-08 | K 739 494 | 0 | 0 | 42.28 | K 739 494 | 120 | 0 | 42.08 | K 739 494 | 280 | 0 | 42.08 |  |  |  |  | N/A | 30 | 30 | 7/8" | 30 | 30 | 7/8" | 30 | 30 | 7/8" |  |  |  | 180 | ML 38 E 1+0 | Galati | MW | 120 | 0.3 | 43.53/0.3 | 20 | 38/18 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [9 empty] | 1 | BX099 | TECUCI_RTC | 300 | 0.3 | 41/0.3 | 55 | 38/14 | [6 empty] | 13 | TRYLON | 2000-11-16 | 372 | 2001-11-17 | 2000-11-17 | 2000-11-24 | DINCA | OK | 2000-12-01 |  | 2000-12-06 | 2001-01-10 |  |  | OK | Ionut GRIGORESCU | Cosmorom | [32 empty] | 44 | Tecuci | Galati | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BX101 | COSTESTI | Road Urziceni-Tecuci(12) | BX102 Mihailesti_RTC | Moldova | 45 02 33.9 | 26 45 50.4 | 45 02 33.9 | 26 45 50.4 | Loc. Costesti, tarla 30, parcela 387 | Barbu T. Nicolae - com. Costesti/Barbu T. Nicolae - com. Costesti | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-11-17 | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | SVF | OK | DUAL | 2000-10-16 | 2001-01-30 | YesV | 2001-02-08 | Andrei | 2001-02-05 | 2001-02-15 |  |  |  | 2000-08-05 | 2000-06-20 |  | 2000-09-25 | 2000-10-18 |  |  |  |  | ICOM |  | 2001-02-02 |  |  |  |  | GATA-2101 | Prov |  | RBS 2101 |  |  |  |  | K 739 494 | 10 | 0 | 49 | K 739 494 | 205 | 0 | 49 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 70 | 70 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 140 |  | Galati | MW | 207 | 1.2 | 30/1.2 | 40 | [7 empty] | RBS | [10 empty] | BX102 | MIHAILESTI_RTC | 25 | 0.6 | 38/0.6 | 52 | [22 empty] | 2001-01-26 | Petrica BURGHIU | COSMOROM | [32 empty] | 82 | Costesti | Buzau | [7 empty] | 2 |  |  | 2
Phase_2 | CS | BX102 | MIHAILESTI_RTC | Road Urziceni-Tecuci(12) | BX102 Mihailesti_RTC | Moldova | 44 54 57.6 | 26 40 21.7 | 44 54 57.6 | 26 40 21.7 | Romtelecom Mihailesti | Romtelecom/ | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-09-19 | N/A | N/A |  |  |  | 0 | TE | 52.4 | 50m existing tower | N/A | SVF | OK | DUAL | 2000-07-27 | 2000-08-20 | YesV | 2000-08-25 | Andrei | 2000-09-07 | 2000-08-30 |  |  |  | N/A | 2000-06-20 |  | 2000-07-06 | 2000-07-20 |  |  |  | 2000-09-12 | YRO | Interactive | 2000-08-30 | 2000-08-30 | 2000-09-13 | 2000-09-14 | 2000-09-21 |  | Yes | Bogdan Bogodai | 2001-02-07 | 2001-02-07 | 2001-02-07 | 2001-02-13 | 2001-02-16 | K 739 494 | 24 | 0 | 51 | K 739 494 | 163 | 0 | 51 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 65 | 65 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 130 | N/A | Galati | FO | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | RBS | [10 empty] | BSC22 | BSC GALATI |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A |  |  | 2001-01-26 | Ionut GRIGORESCU | Cosmorom | [32 empty] | 70 | Mihailesti | Buzau | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | BX103 | CIOCARLIA | Road Urziceni-Tecuci(12) | BX102 Mihailesti_RTC | Moldova | 44 47 55.3 | 26 40 03.2 | 44 47 55.6 | 26 40 12.6 | Loc. Ciocarlia | Primaria com. Ciocarlia/Dl. Primar Dragomir Raducanu, dl. Viceprimar Voicila Eugen | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-11-17 | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | SVF | OK | DUAL | 2000-10-16 | 2001-01-30 | YesV | 2001-02-08 | Andrei | 2001-02-05 | 2001-02-15 |  |  |  |  | 2000-06-20 |  | 2000-09-25 | 2000-10-18 | [6 empty] | 2001-02-02 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 10 | 0 | 49 | K 739 494 | 190 | 0 | 49 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 70 | 70 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 140 |  | Galati | MW | 2 | 1.2 | 30/1.2 | 50 | [7 empty] | RBS | [10 empty] | BX102 | MIHAILESTI_RTC | 180 | 0.6 | 38/0.6 | 52 | [22 empty] | 2001-01-26 | Ionut GRIGORESCU | CATALINA CIOCAN | [32 empty] | 61 | Ciocarlia | Ialomita | [7 empty] | 2 |  |  | 2
Phase_2 | CS | BX104 | SMA FUNDENI | Road Urziceni-Tecuci(12) | BX098 Rm. Sarat_RTC | Moldova | 45 17 25.5 | 26 53 14.6 | 45 17 30.1 | 26 53 21.4 | Com. Zarnesti, SMA Fundeni | Primaria Zarnesti - 519 175/Costica Stroe - primaria Zarnesti, 092/ 475 640 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-10-20 | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | SVF | OK | FIBEC | 2000-09-15 | 2000-11-20 | YesV | 2000-12-06 | Andrei | 2001-01-11 | 2000-12-13 |  |  |  |  | 2000-06-21 |  | 2000-09-07 | 2000-09-18 |  |  |  | 2000-11-20 | ICOM | TRY | 2000-11-20 | 2000-11-20 | 2000-11-21 | 2000-11-23 | 2000-11-25 |  | Yes | Alexandru Toma | 2001-03-10 | 2001-03-09 | 2001-03-09 | 2001-05-15 | 2001-05-25 | K 739 494 | 55 | 0 | 48 | K 739 494 | 190 | 0 | 48 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 70 | 70 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 140 | ML 15 E 1+0 | Galati | MW | 51 | 1.2 | 30/1.2 | 50 | 15/89 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [9 empty] | 1 | BX095 | RM. SARAT_DRTV | 230 | 1.2 | 40/1.2 | 55 | 15/84 | [6 empty] | 5* | ORION | 2000-12-11 | 450 | 2000-12-12 | 2000-12-14 | 2001-02-14 | PAUN | OK | 2001-03-09 | PENDING |  |  |  |  | OK | Ionut GRIGORESCU | Cosmorom | [32 empty] | 243 | Zarnesti | Buzau | [7 empty] | 2 |  |  | 2
Phase_2 | CS | BX105 | COSMESTI_RTC | Road Urziceni-Tecuci(12) | BX105 Cosmesti_RTC | Moldova | 45 51 56 | 27 18 21.7 | 45 51 56 | 27 18 21.7 | Romtelecom Cosmesti | Romtelecom/ | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-09-19 | N/A | N/A |  |  |  | 0 | TE | 40 |  | N/A | SVF | OK | IMSAT | 2000-08-03 | 2000-08-31 | YesV | 2000-08-30 | Andrei | 2000-08-31 | 2000-09-04 |  |  |  | 2000-07-07 | 2000-06-28 |  | 2000-07-14 | 2000-07-26 |  |  |  | 2000-09-12 | YRO | Interactive | 2000-09-12 | 2000-09-12 | 2000-09-13 | 2000-09-14 | 2000-09-15 |  | Yes | Bogdan Bogodai | 2001-02-06 | 2001-02-06 | 2001-02-06 | 2001-03-06 | 2001-04-10 | K 739 494 | 90 | 0 | 38 | K 739 494 | 240 | 0 | 38 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 50 | 50 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 100 | N/A | Galati | FO | N/A | N/A | N/A | N/A | N/A |  | 4x2/8 | 4U-1 |  |  |  | RBS | XC30105 | [8 empty] | 1 | BSC22 | BSC GALATI |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | 30N01 Cosmesti-Galati |  | 2001-01-26 | Ionut GRIGORESCU | COSMOROM | [32 empty] | 74 | Cosmesti | Galati | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | BX107 | SENDRENI | Road Galati-Tecuci(6) | BX108 Piscu_RTC | Moldova | 45 25 07.6 | 27 55 21.2 | 45 25 07.5 | 27 55 21.2 | Comuna Sendreni, jud. Galati |  | 2202 | M | C+C+ | 2/2 | 2202 | [6 empty] | 2000-07-26 | N/A | N/A |  |  |  | 0 | TE | 50 | Tower 50m | Room | DIEKAT | OK | ORION | 2000-07-10 | 2000-07-14 | YesV | 2000-07-21 | Dragos | 2000-07-25 | 2000-07-21 |  |  |  | 2000-06-09 | 2000-05-20 |  | 2000-06-09 | 2000-07-03 |  |  |  | 2000-08-23 | YRO | ORION | 2000-08-15 | 2000-08-15 | 2000-08-24 | 2000-08-29 | 2000-08-31 |  | Yes | Alexandru Toma | 2000-12-04 | 2000-11-25 | 2000-11-25 | 2000-12-08 | 2001-04-10 | K 739 494 | 135 | 0 | 49 | K 739 494 | 274 | 0 | 49 | N/A | N/A | N/A | N/A |  |  |  |  | N/A | 60 | 60 | 1 1/4" | 60 | 60 | 1 1/4" | N/A | N/A | N/A |  |  |  | 240 | N/A | Galati | FO | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | [6 empty] | 120/ |  |  | BX108 | PISCU_RTC |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | 30N01 Sendreni-Piscu |  | OK | Bogdan CRAIU | Cosmorom | [32 empty] | 36 | Sendreni | Galati | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | BX108 | PISCU | Road Galati-Tecuci(6) | BX108 Piscu_RTC | Moldova | 45 30 32.4 | 27 43 25.3 | 45 30 32.4 | 27 43 25.3 | Piscu, jud Galati | Romtelecom/ | 2202 | M | C+C+ | 2/2 | 2202 | [6 empty] | 2000-07-26 | N/A | N/A |  |  |  | 0 | TE | 50 |  | Room | DIEKAT | OK | ORION | 2000-07-10 | 2000-07-14 | YesV | 2000-07-21 | Dragos | 2000-07-25 | 2000-07-21 |  |  |  | OK | 2000-05-20 |  | 2000-06-12 | 2000-07-04 |  |  |  | 2000-08-23 | YRO | ORION | 2000-08-15 | 2000-08-15 | 2000-08-24 | 2000-08-29 | 2000-08-31 |  | Yes | Alexandru Toma | 2000-12-04 | 2000-11-25 | 2000-11-25 | 2001-04-27 | 2001-05-15 | K 739 494 | 143 | 0 | 45 | K 739 494 | 315 | 0 | 45 | N/A | N/A | N/A | N/A |  |  |  |  | N/A | 55 | 55 | 1 1/4" | 55 | 55 | 1 1/4" | N/A | N/A | N/A |  |  |  | 220 | N/A | Galati | FO | N/A | N/A | N/A | N/A | N/A |  | 4x2/8 | 4U-1 |  |  |  | N/A | 30108 | [8 empty] | 1 | BSC11 | DRUMUL TABEREI | N/A | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | 30N01 Piscu-Galati |  | OK | Bogdan CRAIU | Cosmorom | [32 empty] | 35 | Piscu | Galati | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | BX109 | HANUL CONACHI | Road Galati-Tecuci(6) | BX109 Hanul Conachi_RTC | Moldova | 45 35 19.8 | 27 35 36.9 | 45 35 19.8 | 27 35 36.9 | Hanul Conachi | Romtelecom/ | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-08-02 | N/A | N/A |  |  |  | 0 | TE | 36 |  | N/A | DIEKAT | OK | ORION | 2000-07-10 | 2000-07-14 | YesV | 2000-07-21 | Dragos | 2000-07-25 | 2000-07-21 |  |  |  | OK | 2000-05-20 |  | 2000-06-12 | 2000-07-03 |  |  |  | 2000-08-23 | YRO | ORION | 2000-08-14 | 2000-08-14 | 2000-08-24 | 2000-08-29 | 2000-08-31 |  | Yes | Alexandru Toma | 2000-12-04 | 2000-11-28 | 2000-11-28 | 2000-12-18 | 2001-01-08 | K 739 494 | 125 | 0 | 32 | K 739 494 | 315 | 0 | 32 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 36 | 36 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 72 | N/A | Galati | FO | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | RBS | [7 empty] | 20/2 p outdoor |  |  | BSC22 | BSC GALATI |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PITURCESCU | OK | N/A |  | N/A | N/A | 30N01 Hanul Conachi-Galati |  | OK | Bogdan CRAIU | Cosmorom | [32 empty] | 21 | Com. Hanul Conachi | Galati | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | BX110 | IVESTI | Road Galati-Tecuci(6) | BX109 Hanul Conachi_RTC | Moldova | 45 40 19.3 | 27 31 19.9 | 45 40 19.3 | 27 31 19.9 | Comuna Ivesti |  | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-08-02 | N/A | N/A |  |  |  | 0 | TE | 36 |  | N/A | DIEKAT | OK | ORION | 2000-07-10 | 2000-07-14 | YesV | 2000-07-21 | Dragos | 2000-07-25 | 2000-08-09 |  |  |  | OK | 2000-05-20 |  | 2000-06-12 | 2000-07-04 |  |  |  | 2000-08-23 | YRO | ORION | 2000-08-14 | 2000-08-14 | 2000-08-24 | 2000-08-29 | 2000-08-31 |  | Yes | Alexandru Toma | 2000-12-04 | 2000-11-29 | 2000-11-29 | 2000-12-18 | 2001-01-08 | K 739 494 | 168 | 0 | 32 | K 739 494 | 336 | 0 | 32 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 36 | 36 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 72 | N/A | Galati | FO | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | RBS | [7 empty] | 60/2 p outdoor |  |  | BX109 | HANUL CONACHI |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PITURCESCU | OK | N/A |  | N/A | N/A | 30N01 Ivesti-Hanul Conachi |  | OK | Bogdan CRAIU | Cosmorom | [32 empty] | 26 | Ivesti | Galati | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | BX111 | BARCEA | Road Galati-Tecuci(6) | BX109 Hanul Conachi_RTC | Moldova | 45 45 13.3 | 27 28 28.4 | 45 45 13.3 | 27 28 28.4 | Barcea | Romtelecom/ | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-08-02 | N/A | N/A |  |  |  | 0 | TE | 36 |  | N/A | DIEKAT | OK | ORION | 2000-07-10 | 2000-07-14 | YesV | 2000-07-21 | Dragos | 2000-07-25 | 2000-07-21 |  |  |  | OK | 2000-05-20 |  | 2000-06-12 | 2000-07-07 |  |  |  | 2000-08-23 | YRO | ORION | 2000-08-14 | 2000-08-14 | 2000-08-24 | 2000-08-29 | 2000-08-31 |  | Yes | Alexandru Toma | 2000-12-04 | 2000-11-29 | 2000-11-29 | 2000-12-27 | 2001-01-08 | K 739 494 | 156 | 0 | 32 | K 739 494 | 341 | 0 | 32 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 36 | 36 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 72 | N/A | Galati | FO | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | RBS | [7 empty] | 15/2 p outdoor |  |  | BX110 | HANUL CONACHI |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PITURCESCU | OK | N/A |  | N/A | N/A | 30N01 Barcea-Ivesti |  | OK | Bogdan CRAIU | Petrica BURGHIU | [32 empty] | 38 | Com. Barcea | Galati | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | BX112 | VASILE ALECSANDRI | Road Galati-Tecuci(6) | BX108 Piscu_RTC | Moldova | 45 27 12 | 27 47 52 | 45 27 15 | 27 47 54.8 | Sat Vasile Alexandri, Com. Braniste | Dna. Racovita Maria/Racovita Aurel - 094/ 828 627, 036/ 827 213 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-10-13 | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | SVF | OK | FIBEC | 2000-09-27 | 2000-11-13 | YesV | 2000-12-07 | Dragos | 2000-12-11 | 2000-12-13 |  |  |  |  | 2000-05-20 |  | 2000-09-20 | 2000-09-28 |  |  |  | 2000-10-20 | ICOM | TRY | 2000-10-13 | 2000-10-13 | 2000-10-24 | 2000-10-26 | 2000-11-02 |  | Yes | Alexandru Toma | 2000-12-04 | 2000-12-20 | 2000-12-20 | 2001-01-08 | 2001-01-10 | K 739 494 | 113 | 0 | 49 | K 739 494 | 310 | 0 | 49 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 70 | 70 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 140 | ML 15 E 1+0 | Galati | MW | 316 | 1.2 | 47/0.6 | 70 | 15/89 |  | 4x2/8 | 4U-1 |  |  |  | RBS | [9 empty] | 1 | BX108 | PISCU | 136 | 1.2 | 47/1.2 | 55 | 15/84 | [6 empty] | 9 | TRYLON | 2000-10-20 | 312 | 2000-10-16 | 2000-10-17 | 2000-10-20 | VLAD | OK | 2000-12-20 |  | 2001-02-05 | 2001-03-02 | 30N01 Piscu-Galati |  | OK | Petrica BURGHIU | Cosmorom | [32 empty] | 15 | Vasile Alecsandri | Galati | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BX113 | PLEVNA | Road Lehliu-Calarasi(4) | BX116 Calarasi_RTC | Muntenia | 44 21 57.26 | 26 59 12.7 | 44 21 50.3 | 26 59 23.5 | Intravilan com. Lupsanu, sat Plevna, tarla 4, parcela 66 | Gavrila Ion/Gavrila Ion | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-12-11 | N/A | N/A |  |  |  |  | TN | 40 |  | N/A | ORION | OK | ORION | 2000-10-26 | 2000-12-08 | YesV | 2001-01-10 | Mugur | 2001-01-19 | 2001-01-11 |  |  |  |  | 2000-10-04 |  | 1902-10-20 | 2000-11-15 |  |  |  | 2000-12-11 | ICOM | ORION | 2000-12-08 | 2000-12-13 | 2000-12-14 | 2000-12-15 | 2000-12-22 |  | Yes | Bogdan Bogodai | 2001-03-22 | 2001-03-22 | 2001-03-22 |  |  | K 739 494 | 110 | 0 | 40 | K 739 494 | 300 | 0 | 40 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 45 | 45 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 90 | ML 15 E 1+0 | Baneasa | MW | 110 | 0.6 | 40/1.2 | 55 | 15/89 |  |  | 2U-3 |  |  |  | RBS | [9 empty] | 1 | BX114 | VLAD TEPES | 290 | 0.6 | 38/1.2 | 55 | 15/84 | [6 empty] | 4 | ORION | 2000-12-11 | 442 | 2000-12-12 | 2001-01-08 | 2001-01-12 | IVAN | OK | 2001-03-22 |  | 2001-05-10 | 2001-05-25 | 30N02 Calarasi-Baneasa |  | 2001-03-01 | Cristian CROITOR | Cosmorom | [32 empty] | 40 | Plevna | Calarasi | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BX114 | VLAD TEPES | Road Lehliu-Calarasi(4) | BX116 Calarasi_RTC | Muntenia | 44 20 13.1 | 27 06 05.3 | 44 20 17.8 | 27 06 10 | Vlad Tepes - tarla 126, parcela 3 | Ciulian State - com. Vlad Tepes, 143-int centrala comuna/Ciulian State - com. Vlad Tepes, 143-int centrala comuna | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-11-17 | N/A | N/A |  |  |  |  | TN | 40 |  | N/A | ORION | OK | ORION | 2000-10-16 | 2000-12-08 | YesV | 2000-12-13 | Mugur | 2001-01-19 | 2000-12-20 |  |  |  |  | 2000-10-04 |  | 2000-10-05 | 2000-10-30 |  |  |  | 2000-12-11 | ICOM | ORION | 2000-12-08 | 2000-12-13 | 2000-12-14 | 2000-12-15 | 2000-12-22 |  | Yes | Bogdan Bogodai | 2001-03-22 | 2001-03-22 | 2001-03-22 | 2001-04-27 | 2001-05-15 | K 739 494 | 130 | 0 | 40 | K 739 494 | 300 | 0 | 40 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 45 | 45 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 90 | ML 15 E 1+0 | Baneasa | MW | 130 | 0.6 | 38/1.2 | 55 | 15/84 |  |  | 2U-3 |  |  |  | RBS | [9 empty] | 1 | BX115 | INTERSECTIA CALARASI | 309 | 0.6 | 48/1.2 | 62 | 15/89 | [6 empty] | 31* | DIEKAT | 2001-02-26 | 657 | 2001-02-27 | 2001-03-01 | 2001-03-06 | IVAN | OK | 2001-03-22 |  | 2001-04-11 | 2001-04-17 | 30N02 Calarasi-Baneasa |  | 2001-03-01 | Cristian CROITOR | Cosmorom | [32 empty] | 40 | Vlad Tepes | Calarasi | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BX115 | INTERSECTIA CALARASI | Road Lehliu-Calarasi(4) | BX116 Calarasi_RTC | Muntenia | 44 14 53.4 | 22 12 15 | 44 14 53.4 | 27 12 15 | DN3 Km 110, com. Cuza Voda, MT-AND Constanta, SDN Calarasi | MT-AND Constanta, SDN-Calarasi, District Cuza Voda/ | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-12-11 | N/A | N/A |  |  |  | 0 | TN | 50 |  | N/A | ISAF | OK | ISAF | 2000-11-15 | 2001-02-16 | YesV | 2001-03-06 | Mugur | 2001-03-06 | 2001-03-13 |  |  |  |  | 2000-09-27 |  | 2000-10-16 | 2000-11-15 |  |  |  | 2001-02-19 | ICOM | KEN KEN | 2001-02-19 | 2001-02-19 | 2001-02-20 | 2001-03-03 | 2001-03-06 |  | Yes | Bogdan Bogodai | 2001-03-20 | 2001-03-20 | 2001-03-20 | 2001-04-19 | 2001-05-15 | K 739 494 | 110 | 0 | 50 | K 739 494 | 230 | 0 | 50 | K 739 494 | 300 | 0 | 50 |  |  |  |  | N/A | 60 | 60 | 1 1/4" | 60 | 60 | 1 1/4" | 60 | 60 | 1 1/4" |  |  |  | 360 | ML 15 E 1+0 | Baneasa | MW | 133 | 0.6 | 48/1.2 | 62 | 15/89 |  |  | 4U-1 |  |  |  | RBS | [9 empty] | 1 | BX116 | CALARASI_RTC | 313 | 0.6 | 60/1.2 | 115 | 15/84 | [6 empty] | 31* | DIEKAT | 2001-02-26 | 658 | 2001-02-27 | 2001-03-01 | 2001-03-06 | IVAN | OK | 2001-03-20 |  | 2001-04-11 | 2001-04-20 | De mutat de pe 30N01 Calarasi-Baneasa pe 30N02 Calarasi-Baneasa |  | 2001-03-01 | Cristian CROITOR | Cosmorom | [32 empty] | 40 | Geacu | Calarasi | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BX116 | CALARASI_RTC | Road Lehliu-Calarasi(4) | BX116 Calarasi_RTC | Muntenia | 44 14 53.7 | 27 15 14.4 | 44 11 23.5 | 27 19 57.8 | Str. 1 Decembrie 1918 nr.22-24 | Romtelecom Calarasi/Romtelecom | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-11-17 | N/A | N/A |  |  |  | 5 | TE | 60 |  | Room | ISAF | OK | ISAF | 2000-11-01 | 2000-12-15 | YesV | 2001-06-05 | Mugur | 2001-01-09 | 2001-06-14 |  |  |  | N/A | 2000-09-28 |  | 2000-10-09 | 2000-11-06 |  |  |  | 2000-12-15 | ICOM | DIEKAT | 2000-12-14 | 2000-12-14 | 2000-12-19 | 2001-03-02 | 2001-03-03 |  | Yes | Bogdan Bogodai | 2001-03-19 | 2001-03-19 | 2001-03-19 |  |  | K 739 494 | 0 | 0 | 61 | K 739 494 | 210 | 0 | 61 | K 739 494 | 330 | 0 | 59 |  |  |  |  | N/A | 110 | 110 | 1 1/4" | 103 | 103 | 1 1/4" | 108 | 108 | 1 1/4" |  |  |  | 642 | N/A | Baneasa | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | 4U-1(TMR9202) |  |  |  | TMR 9202 | XC30116 | 2001-06-25 | [7 empty] | 1 | BSC21 | BSC BANEASA |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | IVAN | OK | N/A |  | N/A | N/A | 30N01 Calarasi-Baneasa |  | 2001-03-01 | Cristian CROITOR | CATALINA CIOCAN | [32 empty] | 18 | Calarasi | Calarasi | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | BX117 | FRUMUSANI | Road Bucuresti-Oltenita(4+1) | YX138 Oltenita_RTC | Muntenia | 44 18 20.31 | 26 17 55.35 | 44 18 24 | 26 18 00 | Frumusani, tarla 51, parcela 40 | Voinea A. Stefan, Comuna Frumusani/Voinea Gheorghe, Str. Adrian Cirstea, nr.22, bl. 15C, sc. 1, et. 2, ap. 15 Bucuresti, tel. 092213941 si 3506563 | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | ROMPSAR | OK | SVF | 2001-01-29 | 2001-03-07 | YesV | 2001-03-21 | Mugur | 2001-04-20 | 2001-03-29 |  |  |  |  | 2000-10-04 |  | 2001-01-17 | 2001-03-01 | [6 empty] | 2001-03-07 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 120 | 0 | 48.5 | K 739 494 | 320 | 0 | 48.5 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Baneasa | MW | 117 | 1.2 | 47.5/1.2 | 50 | [7 empty] | RBS | [10 empty] | BX118 | SILOZ BUDESTI | [24 empty] | new01 Oltenita-Baneasa |  |  | Cristian CROITOR | Cosmorom | [32 empty] | 60 | Frumusani | Calarasi | [7 empty] | 2 |  |  | 2
Phase_2 | CSH | BX118 | SILOZ BUDESTI | Road Bucuresti-Oltenita(4+1) | YX138 Oltenita_RTC | Muntenia | 44 14 43.44 | 26 27 43.49 |  |  |  |  | 2101 | M | C+ | 2 | 2101 | [17 empty] | ROMPSAR* |  | ROMPSAR* |  |  |  |  | Doru | 2001-06-06 | [23 empty] | RBS 2101 | [13 empty] | 0 | 0 | 0 |  |  |  |  | Yes | [12 empty] | 0 | ML 15 E 1+0 | Baneasa | MW | [11 empty] | RBS | [10 empty] | BX119 | CURCANI | 298 | 0.6 | 47.5/0.6 | 50 | [20 empty] | new01 Oltenita-Baneasa |  |  | Cristian CROITOR | Cosmorom | [32 empty] | 34 | [9 empty] | 2 |  |  | 2
Phase_2 | CS | BX119 | CURCANI | Road Bucuresti-Oltenita(4+1) | YX138 Oltenita_RTC | Muntenia | 44 11 47.52 | 26 34 36.28 | 44 12 23 | 26 33 55 | Sat Salcioara, com. Curcani | Bumbacaru Valeria-sat Salcioara, com. Curcani/Bumbacaru Valeria, sat Salcioara, comuna , Curcani | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | ROMPSAR | OK | ROMPSAR | 2001-02-12 | 2001-04-17 | YesV | 2001-06-21 | Doru |  | 2001-06-26 |  |  |  |  | 2000-10-23 |  | 2001-01-23 | 2001-02-12 | [6 empty] | 2001-05-03 | 2001-05-03 |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 140 | 0 | 48.5 | K 739 494 | 320 | 0 | 48.5 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Baneasa | MW | 151 | 1.2 | 47/1.2 | 50 | [7 empty] | RBS | [10 empty] | BX120 | SILOZ OLTENITA | [24 empty] | new01 Oltenita-Baneasa |  |  | Cristian CROITOR | Cosmorom | [32 empty] | 26 | Salcioara | Calarasi | [7 empty] | 2 |  |  | 2
Phase_2 | CSH | BX120 | SILOZ OLTENITA | Road Bucuresti-Oltenita(4+1) | YX138 Oltenita_RTC | Muntenia | 44 05 36.47 | 26 39 03.41 |  |  |  |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [17 empty] | ROMPSAR* |  | MMK* |  |  |  |  | Doru | [24 empty] | CTR | [13 empty] | 0 | 0 | 0 | [17 empty] | 0 | ML 23 E 1+0 | Baneasa | MW | [11 empty] | RBS | [10 empty] | YX138 | OLTENITA_RTC | 51 | 0.3 | 19/0.3 | 30 | [20 empty] | new01 Oltenita-Baneasa |  |  | Cristian CROITOR | Cosmorom | [32 empty] | 16 | [9 empty] | 2 |  |  | 2
Phase_2 | CS | BX121 | SLOBOZIA_2 | Road Buc-Constanta(4) | BX615 Slobozia_RTC | Dobrogea | 44 33 54.1 | 27 22 52.46 | 44 33 54.1 | 27 22 52.5 | B-dul. Matei Basarab Bl. MB13 sc.A | Asociatia de proprietari 36 MB13 Basarab/Dl. Matei Dumitru - 043/ 219 078 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-12-11 | Yes | N/A |  |  |  | 35 | B | 35 | 9m new pylonet | N/A | ORION | OK | ORION | 2000-11-07 | 2000-12-08 | YesV | 2000-12-13 | Andrei | 2000-12-08 | 2000-12-20 |  |  |  |  | 2000-08-05 |  | 2000-10-30 | 2000-11-20 |  |  |  | 2000-12-18 | ICOM | ORION | 2000-12-08 | 2000-12-13 | 2000-12-14 | 2000-12-15 | 2000-12-22 |  | Yes | Bogdan Bogodai | 2001-02-22 | 2001-02-22 | 2001-02-22 | 2001-05-31 | 2001-06-19 | K 739 494 | 65 | 0 | 35 | K 739 494 | 170 | 0 | 35 | K 739 494 | 250 | 0 | 35 |  |  |  |  | N/A | 20 | 20 | 7/8" | 20 | 20 | 7/8" | 20 | 20 | 7/8" |  |  |  | 120 | ML 38 E 1+0 | Dr. Taberei | MW | 270 | 0.3 | 30/0.3 | 20 | 38/13 |  |  | 2U-3 |  |  |  | RBS | [9 empty] | 1 | BX610 | SLOBOZIA | 89 | 0.3 | 20 | 15 | 38/17 | [6 empty] | 9* | ORION | 2000-12-18 | 443 | 2000-12-18 | 2001-01-05 | 2001-01-23 | PAUN | OK | 2001-02-22 | PENDING |  |  | 30N02 Slobozia-Dr. Taberei |  | OK | Theo RADOI | Cosmorom | [32 empty] | 23 | Slobozia | Ialomita | [7 empty] | 2 |  | 1 | 2
Phase_2 | CS | BX122 | BOLDESTI-SCAIENI_RTC | Road Ploiesti_Sacele(6) | BX122 Boldesti_Sacaieni_RTC | Muntenia | 45 01 55.3 | 26 01 58 | 45 01 55.3 | 26 01 58 | RTC Calea Unirii nr.52, Boldesti-Scaieni | Romtelecom/ | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-11-17 | N/A | N/A |  |  |  | 0 | TE | 38.8 |  | N/A | IMSAT | OK | FIBEC | 2000-10-20 | 2000-11-25 | YesV | 2001-02-06 | Doru | 2001-01-11 | 2001-02-07 |  |  |  | N/A | 2000-09-27 |  | 2000-10-03 | 2000-10-24 |  |  |  | 2000-12-18 | ICOM | DIEKAT | 2000-11-24 | 2000-12-15 | 2000-12-19 | 2001-01-09 | 2001-01-11 |  | Yes | Ion Soare | 2001-03-07 | 2001-03-07 | 2001-03-07 | 2001-06-29 | 2001-07-11 | K 739 494 | 195 | 0 | 37.4 | K 739 494 | 350 | 0 | 37.4 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 80 | 80 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 160 | N/A | Baneasa | FO | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | RBS | [7 empty] | 70/Outdoor |  |  | BSC21 | BSC BANEASA |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | RADU | OK | N/A |  | N/A | N/A | 30N01 Boldesti Scaieni-Baneasa |  | OK | Cristian CROITOR | Petrica BURGHIU | [32 empty] | 227 | Boldesti - Scaieni | Prahova | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | BX123 | MAGURELE_RTC | Road Ploiesti_Sacele(6) | BX123 Magurele_RTC | Muntenia | 45 06 00.7 | 26 02 08.4 | 45 06 00.7 | 26 02 08.4 | Oficiul postal Magurele | Oficiul postal Magurele/ | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-11-17 | N/A | N/A |  |  |  | 0 | TE | 33 |  | N/A | IMSAT | OK | FIBEC | 2000-10-20 | 2000-11-30 | YesV | 2001-02-16 | Doru | 2000-12-12 | 2001-03-02 |  |  |  | N/A | 2000-09-27 |  | 2000-10-03 | 2000-10-24 |  |  |  | 2000-12-15 | ICOM | DIEKAT | 2000-12-14 | 2000-12-15 | 2000-12-19 | 2001-01-09 | 2001-01-11 |  | Yes | Ion Soare | 2001-02-20 | 2001-02-20 | 2001-02-20 | 2001-04-10 | 2001-04-23 | K 739 494 | 163 | 0 | 31 | K 739 494 | 343 | 0 | 31 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 39 | 39 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 78 | N/A | Baneasa | FO | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | RBS |  | 2001-06-21 | [5 empty] | 30/Outdoor |  | 1 | BSC21 | BSC BANEASA | N/A | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | RADU | OK | N/A |  | N/A | N/A | 30N01 Magurele-Baneasa |  | OK | Cristian CROITOR | Cosmorom | [32 empty] | 261 | Magurele | Prahova | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | BX124 | VALENII DE MUNTE | Road Ploiesti_Sacele(6) | BX123 Magurele_RTC | Muntenia | 45 11 58.9 | 26 01 46.4 | 45 11 55.4 | 26 01 50.4 | Str. Cizmari nr.30A, Valenii de Munte | Macovei Eliza, str. Cismari nr.30A, Valenii de Munte/Macovei Eliza, str. Cismari nr.30A, Valenii de Munte | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-12-11 | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | IMSAT | OK | FIBEC | 2000-11-15 | 2001-02-05 | YesV | 2001-03-20 | Doru | 2001-02-12 | 2001-03-29 |  |  |  |  | 2000-09-27 |  | 2000-11-13 | 2001-02-28 |  |  |  | 2001-02-16 | ICOM | TRY | 2001-02-06 | 2001-02-06 | 2001-02-19 | 2001-02-22 | 2001-02-23 |  | Yes | Alexandru Toma | 2001-03-08 | 2001-03-08 | 2001-03-08 | 2001-05-31 | 2001-06-19 | K 739 494 | 0 | 0 | 48.3 | K 739 494 | 175 | 0 | 48.3 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Baneasa | MW | 177 | 1.2 | 44 | 57 | 15/84 |  |  | 2U-3 |  |  |  | RBS | [9 empty] | 1 | BX123 | MAGURELE_RTC | 358 | 0.6c | 25/1.2 | 35.5 | 15/89 | [6 empty] | 28* | TRYLON | 2001-02-16 | 621 | 2001-02-19 | 2001-02-20 | 2001-02-23 | IVAN | OK | 2001-03-08 |  | 2001-03-21 | 2001-04-06 | 30N01 Magurele-Baneasa |  | OK | Theo RADOI | Cosmorom | [32 empty] | 400 | Valenii de Munte | Prahova | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BX125 | POIANA MARE_DRTV | Road Ploiesti_Sacele(6) | BX123 Magurele_RTC | Muntenia | 45 19 58.4 | 25 56 14.6 | 45 19 58.4 | 25 56 14.6 | DRTv Poiana Mare | DRTV/Dl. Popescu Constantin - Cheia, 092/ 300 577; D-na Protopescu, DRTv Bucuresti | MAXITE | M | 1 | 2 | 2PBC | [6 empty] | 2000-11-17 | N/A | N/A |  |  |  | 0 | TE | 80 |  | N/A | IMSAT | OK | COMARK | 2000-11-08 | 2000-11-30 | YesV | 2001-06-09 | Doru | 2001-01-11 | 2001-06-14 |  |  |  | N/A | 2000-09-27 |  | 2000-10-03 | 2000-10-17 |  |  |  | 2000-12-15 | ICOM | DIEKAT | 2000-12-14 | 2000-12-15 | 2000-12-19 | 2001-01-08 | 2001-01-09 |  | Yes | Ion Soare | 2001-05-10 | 2001-05-10 | 2001-05-10 | 2001-06-29 | 2001-07-11 | AAU | 20 | 0 | 38 | AAU | 120 | 0 | 38 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 45 | 45 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 90 | ML 15 E 1+0 | Baneasa | MW | 154 | 1.2 | 40/1.2 | 52 | 15/89 |  |  | 4U-1 |  |  |  | TMR 9000 | [9 empty] | 1 | BX124 | VALENII DE MUNTE | 333 | 1.2 | 44 | 57 | 15/84 | [6 empty] | 28* | TRYLON | 2001-02-16 | 644 | 2001-02-19 | 2001-02-20 | 2001-02-23 | DINCA | OK | 2001-05-11 |  | 2001-05-21 | 2001-05-25 | 30N01 Magurele-Baneasa |  | OK | Cristian CROITOR | Cosmorom | [32 empty] | 1127 | Poiana Mare | Prahova | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | BX126 | CHEIA_DRTV | Road Ploiesti_Sacele(6) | BX123 Magurele_RTC | Muntenia | 45 27 23.6 | 25 56 48.7 | 45 27 23.6 | 25 56 48.7 | Statia DRTv Cheia | DRTv/Ovidiu Angelescu - 044/ 297 017 | MAXITE | M | 1 | 2 | 2PBC | [6 empty] | 2000-11-17 | N/A | N/A |  |  |  | 0 | TE | 66.25 | Turn Telerom | N/A | IMSAT | OK | COMARK | 2000-11-01 | 2000-11-29 | YesV | 2000-12-06 | Doru | 2001-01-11 | 2000-12-14 |  |  |  | N/A | 2000-09-05 |  | 2000-10-03 | 2000-11-10 |  |  |  | 2000-11-30 | ICOM | TRY | 2000-11-30 | 2000-11-30 | 2000-11-30 | 2000-11-28 | 2000-12-04 |  | Yes | Ion Soare | 2001-05-10 | 2001-05-11 | 2001-05-11 | 2001-05-31 | 2001-06-19 | AAU | 180 | 0 | 58.5 | AAU | 320 | 0 | 58.5 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 87 | 87 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 174 | ML 15 E 1+0 | Baneasa | MW | 183 | 1.2 | 61.5/1.2 | 130 | 15/84 |  |  | 4U-1+2U-3 | [13 empty] | 1 | BX125 | POIANA MARE_DRTV | 3 | 1.2 | 40/1.2 | 52 | 15/89 | [6 empty] | 8* | DIEKAT | 2000-12-15 | 480 | 2000-12-15 | 2001-01-30 | 2001-04-02 | IVAN | OK | 2001-05-10 | PENDING |  |  | 30N01 Magurele-Baneasa |  | OK | Cristian CROITOR | CATALINA CIOCAN | [32 empty] | 892 | Cheia | Prahova | [7 empty] | 2 |  |  | 2
Phase_2 | CS | BX127 | BRATOCEA_DRTV | Road Ploiesti_Sacele(6) | BX123 Magurele_RTC | Muntenia | 45 29 31.8 | 25 53 32.9 | 45 29 31.8 | 25 53 32.9 | DRTv Bratocea | DRTv/ | MAXITE | M | 1 | 2 | 2PBC | [7 empty] | N/A | N/A |  |  |  | 10.2 | B | 12.7 | 12m existing pylon | N/A | IMSAT | OK | COMARK | 2000-11-08 | 2000-11-30 | YesV | 2000-12-06 | Doru | 2001-01-11 | 2000-12-14 |  |  |  | N/A | 2000-09-27 |  | 2000-10-03 | 2000-10-20 |  |  |  | 2000-12-18 | ICOM | DIEKAT | 2000-12-14 | 2000-12-15 | 2000-12-19 | 2001-01-09 | 2001-01-11 |  | Yes | Ion Soare | 2001-05-11 | 2001-05-11 | 2001-05-11 |  |  | AAU | 120 | 0 | 19.7 | AAU | 300 | 0 | 19.7 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 16 | 16 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 30 | ML 23 E 1+0 | Baneasa | MW | 133 | 0.6 | 17.7/1.2 | 29 | 23/58 |  |  | 4U-1+2U-3 | [13 empty] | 1 | BX126 | CHEIA_DRTV | 313 | 0.6 | 61.5/0.6 | 130 | 23/56 | [6 empty] | 8* | DIEKAT | 2000-12-15 | 479 | 2000-12-18 | 2001-01-30 | 2001-04-02 | DINCA | OK | 2001-05-11 | PENDING |  |  | 30N01 Magurele-Baneasa |  | OK | Cristian CROITOR | Petrica BURGHIU | [32 empty] | 1388 | Bratocea | Prahova | [7 empty] | 2 |  |  | 2
Phase_3 | CS | BX128 | TULCEA_DRTV | Road Tulcea-Braila(2) | YX829 Mahmudia_RTC | Dobrogea | 45 09 40.3 | 28 47 08.4 | 45 09 40.3 | 28 47 08.4 |  | DRTV TULCEA 040/515018 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-11-17 | N/A | N/A |  |  |  | 0 | TE | 76 |  | N/A | PROTELCO | OK | CRIS-CORI | 2000-10-27 | 2000-11-22 | YesV | 2001-05-31 | Bogdan |  | 2001-01-08 | 2001-04-05 |  |  | N/A | 2000-10-03 |  | 2000-10-03 | 2000-10-20 | Old Obs: |  |  |  |  | TRYLON | 2000-11-23 |  | 2000-11-24 | 2000-12-19 | 2000-12-22 |  | Yes |  | CW YX829 |  |  |  |  | K 739 494 | 0 | 0 | 27 | K 739 494 | 80 | 0 | 27 | K 739 494 | 220 | 0 | 27 |  |  |  |  | N/A | 35 | 35 | 7/8" | 35 | 35 | 7/8" | 35 | 35 | 7/8" |  |  |  | 210 | ML 38 E 1+0* | Galati | MW | 44 | 0.3 | 40/0.3 | 50 | 38/18 |  | 4x2/8 | 4U-1 |  |  |  | N/A | [10 empty] | YX829 | MAHMUDIA_RTC | 224 | 0.3 | 18.5 | 45 | [7 empty] | 17 | TRYLON | 2000-11-23 | 400 | 2000-11-23 | [5 empty] | BX128-BX130 s-a desfiintat,se vor muta echipamentele pe BX128-YX829 | [5 empty] | Cosmorom | Cosmorom | [42 empty] | 2 |  |  | 3
Phase_3 | CS | BX130 | BLOC-PELICAN | Tulcea(5+1) | YX829 Mahmudia_RTC | Dobrogea | 45 10 45.2 | 28 47 20.4 | 45 10 45.2 | 28 47 20.4 | Str. Isaccea, nr.57,sc.B Tulcea | Asociatie de proprietari/Ancuta M.-040/524.607 (sc.C, ap.11) | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-11-17 | N/A | N/A |  |  |  | 28.4 | B | 32.35 | C3m+C3m | Room | PROTELCO | OK | CRIS-CORI | 2000-11-02 | 2000-11-22 | YesV | 2001-07-06 | Bogdan |  | 2001-06-12 |  |  |  | 2000-10-03 | 2000-10-20 |  | 2000-10-20 | 2000-11-03 | [5 empty] | TRYLON | 2000-11-23 |  | 2000-11-24 | 2000-12-19 | 2000-12-22 |  | Yes |  | CW BX833 |  |  |  |  | K 739 494 | 70 | 0 | 33 | K 739 494 | 140 | 0 | 33 | K 739 494 | 270 | 0 | 33 |  |  |  |  | N/A | 10 | 10 | 7/8" | 23 | 23 | 7/8" | 10 | 10 | 7/8" |  |  |  | 86 | ML 38 E 1+0* | Galati | MW | 188 | 0.3 | 32.5/0.3 | 23 | 38/14 |  | 4x2/8 | 2U-3 |  |  |  | Indoor Comteck | [10 empty] | BX833 | TABEREI | 138 | 0.3 | 30.7 | 8 | [7 empty] | 17 | TRYLON | 2000-11-23 | 400 | 2000-11-23 | [11 empty] | Cosmorom | Petrica BURGHIU | [33 empty] | Tulcea | Tulcea | [7 empty] | 2 |  |  | 3
Phase_2 | CS | BX131 | MACIN_RTC | Road Tulcea-Braila(6) | BX131 Macin_RTC | Dobrogea | 45 14 42.4 | 28 07 53.2 | 45 14 42.4 | 28 07 53.2 | Romtelecom - Macin | Romtelecom/ | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-11-17 | N/A | N/A |  |  |  | 0 | TE | 50 |  | Room | PROTELCO | OK | DUAL | 2000-10-23 | 2000-11-11 | YesV | 2000-11-17 | Dragos | 2001-01-09 | 2000-11-22 |  |  |  | N/A | 2000-09-05 |  | 2000-09-27 | 2000-10-17 |  |  |  | 2000-11-10 | ICOM | IMSAT | 2000-11-10 | 2000-11-10 | 2000-11-13 | 2000-11-15 | 2000-11-20 |  | Yes |  | 2Mb/s |  |  |  |  | K 739 494 | 10 | 0 | 45 | K 739 494 | 130 | 0 | 45 | K 739 494 | 290 | 0 | 45 |  |  |  |  | N/A | 70 | 70 | 1 1/4" | 70 | 70 | 1 1/4" | 70 | 70 | 1 1/4" |  |  |  | 540 | N/A | Galati | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | [15 empty] | BSC22 | BSC GALATI |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A |  |  | 2001-04-30 | Cosmorom | Cosmorom | [32 empty] | 20 | Macin | Tulcea | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | BX132 | BABADAG_RTC | Road Tulcea-Constanta(7) | BX132 Babadag_RTC | Dobrogea | 44 53 38.7 | 28 43 25.1 | 44 53 38.7 | 28 43 25.1 | Romtelecom - Babadag | Romtelecom/ | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-10-20 | N/A | N/A |  |  |  | 0 | TE | 50 |  | Room | PROTELCO | OK | ORION | 2000-10-20 | 2000-11-14 | YesV | 2000-11-30 | Dragos | 2000-12-08 | 2000-12-07 |  |  |  | N/A | 2000-09-05 |  | 2000-09-27 | 2000-10-25 |  |  |  | 2000-11-15 | ICOM | IMSAT | 2000-11-15 | 2000-11-15 | 2000-11-16 | 2000-11-21 | 2000-11-22 | IVAN | Yes | Valentin C-tinescu | 2001-06-20 | 2001-06-20 | 2001-06-20 |  |  | K 739 494 | 0 | 0 | 33.5 | K 739 494 | 120 | 0 | 33.5 | K 739 494 | 210 | 0 | 33.5 |  |  |  |  | N/A | 62 | 62 | 1 1/4" | 62 | 62 | 1 1/4" | 62 | 62 | 1 1/4" |  |  |  | 372 | N/A | Constanta | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | [5 empty] | 30132 | [6 empty] | 36/8p outdoor | 36/8p outdoor |  | BSC13 | BSC CONSTANTA |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | 30N01 Babadag-Constanta |  | 2001-05-28 | Cosmorom | Petrica BURGHIU | [32 empty] | 31 | Babadag | Tulcea | [7 empty] | Site Near=Insertion Point
Phase_3 | CS | BX133 | SAMOVA | Road Tulcea-Braila(2) | YX829 Mahmudia_RTC | Dobrogea | 45 11 12.6 | 28 39 46.5 | 45 11 12.6 | 28 39 46.5 | Com. Samova | Luca Marcel | 2101 | M | C+ | 2 | 2101 |  | N/A | N/A | N/A | N/A | N/A | 2000-11-17 | N/A | N/A |  |  |  | 0 | TN | 50 |  | N/A | PROTELCO | OK | DUAL | 2000-10-16 | 2001-01-25 | YesV | 2001-02-13 | Marin |  | 2001-06-06 | 2001-04-05 |  |  |  | 2001-05-16 | [9 empty] | 2001-02-02 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 110 | 0 | 48 | K 739 494 | 270 | 0 | 48 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0* | Galati | MW | 107 | 1.2 | 40/1.2 | 60 | [7 empty] | N/A | [10 empty] | BX128 | TULCEA_DRTV | 287 | 0.3 | 40/0.3 | 50 | [23 empty] | Cosmorom | Cosmorom | [33 empty] | Samova | Tulcea | [7 empty] | 2 |  |  | 2
Phase_2 | CS | BX134 | NICULITEL | Road Tulcea-Braila(6) | BX065 Braila_RTC3 | Moldova | 45 11 36.1 | 28 32 41.1 | 45 11 36.1 | 28 32 41.1 | Com. Sarica Niculitel, Teren scoala | Teren scoala/ | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-11-17 | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | PROTELCO | OK | DUAL | 2000-10-16 | 2001-01-30 | YesV | 2001-02-13 | Marin | 2001-06-06 | 2001-02-26 |  |  |  |  | 2000-09-05 |  | 2000-10-06 | 2000-10-24 |  |  |  |  | ICOM |  | 2001-02-02 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 110 | 0 | 48 | K 739 494 | 290 | 0 | 48 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Galati | MW | 315 | 1.2 | 40/1.2 | 50 | [7 empty] | RBS | [10 empty] | BX135 | ISACCEA TURN | 138 |  | 48/1.2 | 60 | [22 empty] | 2001-02-02 | Cosmorom | Cosmorom | [32 empty] | 59 | Sarica Niculitel | Tulcea | [7 empty] | 2 |  |  | 2
Phase_2 | CS | BX135 | ISACCEA TURN | Road Tulcea-Braila(6) | BX065 Braila_RTC3 | Moldova | 45 15 32 | 28 27 50 | 45 15 34 | 28 27 52 | Str. Avram Iancu, nr.42 | Str. Avram Iancu, nr.42/Ailincai Valentin, str. Avram Iancu nr.42, Isaccea | MAXITE | M | 1 | 2 | 2PBC | [12 empty] | 0 | TN | 50 |  | N/A/TMR9000 | DIEKAT | OK | ORION | 2001-05-15 | 2001-06-18 | YesV | 2001-07-04 | Bogdan | 2001-07-06 | 2001-06-12 |  |  |  |  | 2001-04-18 |  | N/A | 2001-07-18 | [6 empty] | 2001-07-13 |  |  |  |  | GATA-MAXITE | Yes |  | RBS 2101 BX136 |  |  |  |  | AAU | 160 | 0 | 50 | AAU | 320 | 0 | 50 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | YES | 60 | 60 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Galati | MW | 284 |  | 40/1.2 | 50 | [18 empty] | BX136 | RACHELU | 104 | [25 empty] | 2001-02-02 | SORIN UNTARU | Cosmorom | [32 empty] | 48.36 | Isaccea | Tulcea | [7 empty] | 2 |  |  | 2
Phase_2 | CS | BX136 | RACHELU | Road Tulcea-Braila(6) | BX065 Braila_RTC3 | Moldova | 45 17 06 | 28 19 21.20 | 45 17 10.5 | 28 19 25.7 | Intravilan com.Luncavita, sat Rachelu | Nichifor Constantin - com. Luncavita, sat Rachelu/Nichifor Constantin - com. Luncavita, sat Rachelu | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-11-17 | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | PROTELCO | OK | CRIS-CORI | 2000-10-16 | 2001-02-15 | YesV | Respins | Bogdan | [6 empty] | 2000-09-05 |  | 2000-10-06 | 2000-10-20 | [6 empty] | 2001-02-16 | 2001-02-16 |  |  |  | GATA-2101 |  |  | RBS 2101 |  |  |  |  | K 739 494 | 100 | 0 | 48 | K 739 494 | 280 | 0 | 48 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Galati | MW | 293 | 1.2 | 40/1.2 | 60 | [7 empty] | RBS | [10 empty] | BX137 | VACARENI_DRTV | 113 | 1.2 | 46/1.2 | 60 | [22 empty] | 2001-02-02 | Cosmorom | Cosmorom | [32 empty] | 54 | Rachelu | Tulcea | [7 empty] | 2 |  |  | 2
Phase_2 | CS | BX137 | VACARENI_DRTV | Road Tulcea-Braila(6) | BX065 Braila_RTC3 | Moldova | 45 19 41.1 | 28 10 38.3 | 45 19 41.1 | 28 10 38.3 | Statia DRTv Vacareni | DRTv Bucuresti/ | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-12-11 | N/A | N/A |  |  |  | 0 | TE | 200 |  | N/A | ORION | OK | ORION | 2000-11-07 | 2000-11-30 | YesV | 2000-12-19 | Dragos | 2000-11-28 | 2001-02-07 |  |  |  | N/A | 2000-09-05 |  | 2000-10-30 | 2000-11-17 |  |  |  | 2000-12-15 | ICOM | DIEKAT | 2000-12-12 | 2000-12-15 | 2000-12-19 | 2001-03-11 | 2001-03-12 |  | Yes | Alexandru Toma | 2001-03-23 | 2001-03-23 | 2001-03-23 |  |  | K 739 494 | 20 | 0 | 60 | K 739 494 | 160 | 0 | 60 | K 739 494 | 330 | 0 | 60 |  |  |  |  | N/A | 75 | 75 | 1 1/4" | 75 | 75 | 1 1/4" | 75 | 75 | 1 1/4" |  |  |  | 450 | ML 15 E 1+1 | Galati | MW | 255 | 1.2 | 46/1.2 | 60 | 15/89 |  | 4x2/8 |  |  |  |  | RBS | [9 empty] | 1 | BX065 | BRAILA_RTC3 | 75 | 1.2 | 32 | 32 | 15/84 | [6 empty] | 8* | DIEKAT | 2000-12-15 | 481/562 | 2000-12-15 | 2001-02-22 | 2001-03-08 | RADU | OK | 2001-03-23 | PENDING | [5 empty] | Cosmorom | Cosmorom | [32 empty] | 148 | Vacareni | Tulcea | [6 empty] | 1 | 2 |  | 1 | 2
Phase_3 | CS | BX138 | SANTIERUL SANAB | Braila | BX063 Independentei_RTC | Moldova | 45 14 56.2 | 27 57 39 |  |  |  |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [17 empty] | ROMPSAR | OK | @ | 2001-09-01 | 2001-09-30 |  |  | Bogdan |  |  | 2001-07-10 | [8 empty] | 2001-07-10 | [10 empty] | Yes | [36 empty] | ML 38 E 1+0* | Galati | MW | [22 empty] | BX063 | INDEPENDENTEI_RTC | [27 empty] | Theo RADOI | Theo RADOI
Phase_2 | CS | BX139 | PLOIESTI_5 | Ploiesti(6) | BX140 Ploiesti Sud_RTC | Muntenia | 44 56 17.3 | 26 00 18.3 | 44 56 17.3 | 26 00 18.3 | Str. Ghe. Grigore Cantacuzino nr.1, bl.1C | Asociatie de locatari/Str. Ghe. Grigore Cantacuzino nr.1, bl.1C, ap.1 - 044/ 117 968 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-12-11 | Yes | N/A |  |  |  | 26.5 | B | 30.5 | T6m+T6m | N/A | SETRACO | OK | SETRACO | 2000-11-09 | 2000-12-20 | YesV | 2001-03-02 | Mugur |  | 2001-03-06 |  |  |  |  | 2000-09-29 |  | 2000-10-30 | 2000-11-13 |  |  |  | 2000-12-28 | ICOM | DIEKAT | 2000-12-20 | 2001-01-10 | 2001-01-11 | 2001-01-29 | 2001-02-05 |  | Yes | Theo Radoi | 2001-02-09 | 2001-02-09 | 2001-02-09 | 2001-03-15 | 2001-04-10 | K 739 494 | 40 | 0 | 33.5 | K 739 494 | 160 | 0 | 33.5 | K 739 494 | 280 | 0 | 33.5 |  |  |  |  | N/A | 20 | 20 | 7/8" | 20 | 20 | 7/8" | 20 | 20 | 7/8" |  |  |  | 120 | ML 38 E 1+0 | Baneasa | MW | 103 | 0.3 | 32/0.3 | 20 | 38/18 |  |  | 2U-3 |  |  |  | RBS | [9 empty] | 1 | BX140 | PLOIESTI SUD_RTC | 283 | 0.3 | 20/0.3 | 33 | 38/14 | [6 empty] | 15* | DIEKAT | 2001-01-08 | 506 | 2001-01-31 | 2001-02-01 | 2001-02-02 | DINCA | OK | 2001-02-09 |  | 2001-07-12 |  | 30N05 Ploiesti Sud-Baneasa |  | 2001-01-30 | Camil DUMITRESCU | Cosmorom | [32 empty] | 166 | Ploiesti | Prahova | [7 empty] | 2 |  |  | 2
Phase_2 | CS | BX140 | PLOIESTI SUD_RTC | Ploiesti(6) | BX140 Ploiesti Sud_RTC | Muntenia | 44 56 00.9 | 26 01 54.8 | 44 56 00.9 | 26 01 54.8 | Str. Democratiei nr.1 - Terasa cladirii RTc Sud | Romtelecom/ | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-12-11 | Yes | N/A |  |  |  | 17 | B | 17 | T6m+T6m | N/A | SETRACO | OK | SETRACO | 2000-11-07 | 2000-12-21 | YesV | 2001-01-26 | Mugur | 2001-01-11 | 2001-03-06 |  |  |  | N/A | 2000-09-29 |  | 2000-10-30 | 2000-12-14 |  |  |  | 2000-12-28 | ICOM | DIEKAT | 2000-12-27 | 2001-01-10 | 2001-01-11 | 2001-01-29 | 2001-02-02 |  | Yes | Theo Radoi | 2001-02-06 | 2001-02-06 | 2001-02-06 | 2001-04-24 | 2001-05-03 | K 739 494 | 100 | 0 | 21 | K 739 494 | 200 | 0 | 20 | K 739 494 | 320 | 0 | 20 |  |  |  |  | N/A | 50 | 50 | 7/8" | 40 | 40 | 7/8" | 45 | 45 | 7/8" |  |  |  | 270 | N/A | Baneasa | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | 2U-3 |  |  |  | RBS |  | 2001-06-21 | [5 empty] | 40/Outdoor |  | 1 | BSC21 | BSC BANEASA | N/A | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | DINCA | OK | N/A |  | N/A | N/A | 30N05 Ploiesti Sud-Baneasa |  | 2001-01-30 | Camil DUMITRESCU | Cosmorom | [32 empty] | 159 | Ploiesti | Prahova | [7 empty] | Site Near=Insertion Point
Phase_3 | CS | BX141 | UNIRII | Galati | BX080 Central_RTC | Moldova | 45 27 06.5 | 28 02 11.5 |  |  |  |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [17 empty] | PERFECT |  | @ | 2001-09-01 | 2001-09-30 |  |  | Bogdan |  |  | 2001-07-10 | [8 empty] | 2001-07-10 | [47 empty] | ML 38 E 1+0* | Galati | MW | [22 empty] | BX083 | DEPOZIT_RTC | [27 empty] | Theo RADOI | Theo RADOI
Phase_3 | CS | BX142 | DUNAREA | Galati | BX080 Central_RTC | Moldova | 45 24 47.5 | 28 47.5 |  |  |  |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [17 empty] | PERFECT |  | @ | 2001-09-01 | 2001-09-30 |  |  | Bogdan |  |  | 2001-07-10 | [8 empty] | 2001-07-10 | [47 empty] | ML 38 E 1+0* | Galati | MW | [22 empty] | BX072 | OTELARILOR | [27 empty] | Theo RADOI | Theo RADOI
Phase_3 | CS | BX143 | TURN CONEL | Galati | BX080 Central_RTC | Moldova | 45 26 18 | 28 02 19 |  |  |  |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [17 empty] | PERFECT |  | @ | 2001-09-01 | 2001-09-30 |  |  | Bogdan |  |  | 2001-07-10 | [8 empty] | 2001-07-10 | [47 empty] | ML 38 E 1+0* | Galati | MW | [22 empty] | BX080 | CENTRAL_RTC | [27 empty] | Theo RADOI | Theo RADOI
Phase_2 | CS | BX144 | POGOANELE_RTC | Buzau area(9) | BX144 Pogoanele_RTC | Moldova | 44 54 58.6 | 26 59 29.8 | 44 54 58.6 | 26 59 29.8 | Oficiul Romtelecom, str. Nicolae Balcescu | Romtelecom/DTc Buzau-Dir. Costea Nicolae | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | N/A | N/A |  |  |  | 0 | TE | 50 |  | N/A | DIEKAT | OK | APOLLO | 2000-12-13 | 2001-01-15 | YesV | 2001-06-01 | Eugen | 2001-02-02 | 2001-06-06 |  |  |  | N/A | 2000-11-23 |  | 2000-11-30 | 2000-12-14 |  |  |  | 2001-02-01 | ICOM | DIEKAT | 2001-01-26 | 2001-01-26 | 2001-02-05 | 2001-02-26 | 2001-03-12 |  | Yes | Ion Soare | 2001-03-28 | 2001-03-28 | 2001-03-28 |  |  | K 739 494 | 120 | 0 | 30 | K 739 494 | 220 | 0 | 30 | K 739 494 | 340 | 0 | 30 |  |  |  |  | N/A | 40 | 40 | 7/8" | 40 | 40 | 7/8" | 40 | 40 | 7/8'' |  |  |  | 240 | N/A | Galati | FO | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | RBS | [7 empty] | 45/Outdoor |  |  | BSC22 | BSC GALATI |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | RADU | OK | N/A |  | N/A | N/A |  |  | 2001-03-20 | Petrica BURGHIU | Cosmorom | [32 empty] | 67 | Pogoanele | Buzau | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | BX145 | GOLDEANU SILISTEA_RTC | Buzau area(9) | BX144 Pogoanele_RTC | Moldova | 44 49 48.9 | 26 48 01.7 | 44 49 48.1 | 26 48 01.7 | Goldeanu Silistea | Primaria Goldeanu Silistea/DTc Buzau-Dir. Costea Nicolae | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | N/A | N/A |  |  |  | 0 | TE | 50 |  | N/A | DIEKAT | OK | APOLLO | 2001-01-19 | 2001-01-31 | YesV | 2001-03-27 | Eugen | 2001-03-23 | 2001-03-29 |  |  |  | 2000-11-27 | 2001-11-23 |  | 2001-01-09 | 2001-01-19 |  |  |  | 2001-02-01 | ICOM | DIEKAT | 2001-02-01 | 2001-02-01 | 2001-02-05 | 2001-02-26 | 2001-03-13 |  | Yes | Bogdan Bogodai | 2001-04-18 | 2001-04-18 | 2001-04-18 |  |  | K 739 494 | 70 | 0 | 30 | K 739 494 | 200 | 0 | 30 | K 739 494 | 300 | 0 | 30 |  |  |  |  | N/A | 45 | 45 | 7/8" | 42 | 42 | 7/8" | 42 | 42 | 7/8" |  |  |  | 258 | N/A | Galati | FO | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | RBS | [7 empty] | 50/Outdoor |  |  | BX144 | POGOANELE_RTC |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | RADU | OK | N/A |  | N/A | N/A |  |  | 2001-03-20 | Petrica BURGHIU | Cosmorom | [32 empty] | 72 | Goldeanu Silistea | Buzau | [7 empty] | Site Near=Insertion Point
Phase_3 | CS | BX150 | SCANTEIA | Road Slobozia-Braila(3) | BX152 Insuratei | Dobrogea | 44 44 00.8 | 27 27 53.5 | 44 44 00.8 | 27 27 53.5 | Sediul Romtelecom , loc. Scanteia | Romtelecom | MAXITE | M | 1 | 2 | 2PBC | [12 empty] | 0 | TE/6mp | 50 |  | N/A | DIEKAT | OK | ORION | 2001-05-16 | 2001-05-28 | YesV | 2001-06-05 | Bogdan |  | 2001-06-14 | 2001-03-12 | 2001-06-25 |  |  | 2001-06-25 |  | 2001-04-18 | 2001-05-07 | [6 empty] | 2001-05-30 |  |  |  |  | GATA-MAXITE |  |  | MAXITE |  |  |  |  | AAU | 30 | 0 | 49 | AAU | 210 | 0 | 49 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | 60 | 60 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Galati | MW | [12 empty] | XC30152 | [6 empty] | 25/Outdoor |  |  | BX152 | INSURATEI | [24 empty] | 30N01 Insuratei-Galati |  | 2001-06-15 | Petrica BURGHIU | Florin RIZESCU | [32 empty] | 34 | Scanteia | Ialomita | [7 empty] | Site Near=Insertion Point
Phase_3 | CS | BX152 | INSURATEI | Road Slobozia-Braila(3) | BX152 Insuratei | Dobrogea | 44 54 51.4 | 27 36 16.6 | 44 54 51 | 27 36 16 | Sediul Romtelecom, Sos. Brailei, nr. 29 | Romtelecom | 2202 | M | C+C+C+ | 1/1/1 | 2202 | [12 empty] | 4 | TE | 80.93 |  | Room/Rack19" | DIEKAT | OK | ORION | 2001-05-16 | 2001-06-24 | YesV | Respins | Bogdan |  |  | 2001-03-12 |  |  |  | 2001-06-25 |  | 2001-05-14 | 2001-06-01 | [6 empty] | 2001-05-30 | [7 empty] | CW NOT READY |  |  |  |  | K 739 494 | 40 | 0 | 60 | K 739 494 | 220 | 0 | 60 | K 739 494 | 320 | 0 | 60 |  |  |  |  | N/A | 70 | 70 | 1 1/4" | 70 | 70 | 1 1/4" | 70 | 70 | 1 1/4" |  |  |  | 420 | N/A | Galati | FO | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | Indoor Comteck | XC30152 | [6 empty] | 25/Outdoor |  |  | BSC11 | DRUMUL TABEREI | N/A | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 30N01 Insuratei-Galati |  | 2001-06-15 | Petrica BURGHIU | Florin RIZESCU | [32 empty] | 28 | Insuratei | Braila | [7 empty] | Site Near=Insertion Point
Phase_3 | CS | BX153 | VIZIRU | Road Slobozia-Braila(3) | BX152 Insuratei | Dobrogea | 45 02 35 | 45 02 35 | 45 02 35 | 45 02 35 | Comuna Viziru | Primaria Viziru, jud. Braila/Primar Stanciu I Stanciu | 2102 | M | C+C+C+ | 1/1/1 | N/A | [12 empty] | 0 | TN | 50/12mp |  | N/A | DIEKAT | OK | ORION | 2001-05-16 | 2001-05-28 | YesV | 2001-06-05 | Bogdan |  | 2001-06-14 | 2001-03-12 |  |  |  | 2001-06-25 |  | 2001-04-17 | 2001-05-07 |  |  |  | 2001-06-21 | ICOM | ORION | 2001-05-30 | 2001-05-30 | 2001-06-20 | 2001-06-20 | 2001-06-20 |  |  |  | RBS NOT STARTED |  |  |  |  | K 739 494 | 40 | 0 | 49 | K 739 494 | 210 | 0 | 49 | K 739 494 | 310 | 0 | 49 |  |  |  |  | N/A | 60 | 60 | 1 1/4" | 60 | 60 | 1 1/4" | 60 | 60 | 1 1/4" | N/A | N/A | N/A | 360 | ML 15 E 1+0 | Galati | MW | 219 | 1.2 | 42 | 50 | [7 empty] | N/A | XC30152 | [9 empty] | BX152 | INSURATEI | 39 | 1.2 | 50 | 60 | [20 empty] | 30N01 Insuratei-Galati |  | 2001-06-15 | Petrica BURGHIU | Florin RIZESCU | [32 empty] | 18.55 | Viziru | Braila | [7 empty] | 3 |  |  | 3
Phase_3 | CS | BX154 | BENTU | Road Braila-Buzau(5) | BX160 Faurei_RTC | Dobrogea | 45 03 45 | 26 58 26 | 45 03 45 | 26 58 26 | Sat Bentu, com. Galbinasi |  | MAXITE | M | 1 | 2 | 2PBC | [12 empty] | 0 | TN/6mp | 50 |  | N/A/TMR9000 | DIEKAT | OK | DIEKAT | 2001-05-17 | 2001-06-15 | YesV | 2001-07-03 | Bogdan |  | 2001-06-12 | 2001-03-12 |  |  | OK |  |  | 2001-04-11 | 2001-05-16 | [6 empty] | 2001-07-11 |  |  |  |  | GATA-MAXITE |  |  | MAXITE |  |  |  |  | AAU | 110 | 0 | 49 | AAU | 290 | 0 | 49 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | 60 | 60 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Galati | MW | 100 | 1.2 | 42/1.2 | 50 | [8 empty] | XC30160 | [9 empty] | BX155 | CA ROSETTI | 280 | 1.2 | 42/1.2 | 50 | [20 empty] | 30N01 Faurei-Galati |  | 2001-06-15 | Petrica BURGHIU | Florin RIZESCU | [32 empty] | 65 | Bentu | Buzau | [7 empty] | 3 |  |  | 3
Phase_3 | CS | BX155 | CA ROSETTI | Road Braila-Buzau(5) | BX160 Faurei_RTC | Dobrogea | 45 02 35 | 27 09 29 | 45 02 35 | 27 09 29 | Com. CA Rosetti | Nastase D Stela - com. CA Rosetti | 2101 | M | C+ | 2 | 2101 | [12 empty] | 0 | TN/6mp | 50 |  | N/A | DIEKAT | OK | DIEKAT | 2001-04-15 | 2001-06-15 | YesV | 2001-07-03 | Bogdan |  | 2001-06-12 | 2001-03-12 | [5 empty] | 2001-04-11 | 2001-05-16 | [6 empty] | 2001-07-11 |  |  |  |  | GATA-2101 |  |  | RBS 2101 |  |  |  |  | K 739 494 | 100 | 0 | 49 | K 739 494 | 270 | 0 | 49 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Galati | MW | 63 | 1.2 | 42/1.2 | 50 | [7 empty] | N/A | XC30160 | [9 empty] | BX160 | FAUREI_RTC | 243 | 0.6 | 32 | 35 | [20 empty] | 30N01 Faurei-Galati |  | 2001-06-15 | Petrica BURGHIU | Florin RIZESCU | [32 empty] | 50 | CA Rosetti | Buzau | [7 empty] | 3 |  |  | 3
Phase_3 | CS | BX157 | IANCA COS | Road Braila-Buzau(5) | BX160 Faurei_RTC | Dobrogea | 45 08 17.4 | 27 29 50 |  |  |  |  | MAXITE | M | 1 | 2 | 2PBC | [27 empty] | 2001-03-12 | [21 empty] | MAXITE | [34 empty] | ML 15 E 1+0* | Galati | MW | 251 | [11 empty] | XC30160 | [9 empty] | BX160 | FAUREI_RTC | 71 | 1.2 | 32 | 35 | [20 empty] | 30N01 Faurei-Galati |  | 2001-06-15 | Petrica BURGHIU | Florin RIZESCU | [42 empty] | 3 |  |  | 3
Phase_3 | CS | BX158 | SILISTRARU | Road Braila-Buzau(5) | BX152 Insuratei | Dobrogea | 45 09 41 | 27 46 41 | 45 09 41 | 27 46 41 | Sat Silistraru, com. Traian | Motoc Ioana - sat Silistraru, com. Traian | MAXITE | M | 1 | 2 | 2PBC | [12 empty] | 0 | TN/6mp | 50 |  | N/A/TMR9000 | DIEKAT | OK | DIEKAT | 2001-05-30 | 2001-06-27 | YesV | 2001-07-03 | Bogdan |  | 2001-06-12 | 2001-03-12 |  |  |  | 2001-06-25 |  | 2001-04-11 | 2001-05-16 | [6 empty] | 2001-07-11 |  |  |  |  | GATA-MAXITE |  |  | MAXITE |  |  |  |  | AAU | 70 | 0 | 49 | AAU | 210 | 0 | 49 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | 60 | 60 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Galati | MW | 199 | 1.2 | 42/1.2 | 50 | [8 empty] | XC30152 | [9 empty] | BX153 | VIZIRU | 19 | 1.2 | 42 | 50 | [20 empty] | 30N01 Insuratei-Galati |  | 2001-06-15 | Petrica BURGHIU | Florin RIZESCU | [32 empty] | 13 | Silistraru | Braila | [7 empty] | 3 |  |  | 3
Phase_3 | CS | BX160 | FAUREI_RTC | Road Braila-Buzau(5) | BX160 Faurei_RTC | Dobrogea | 45 05 04.7 | 27 16 24.5 | 44 05 05 | 27 16 23 | Str. Pacii 1-5 | Romtelecom | 2202 | M/E | C+C+C+ | 2/2/2 | 2202 | [12 empty] | 3.3 | TN | 40/6mp |  | Room/Rack19" | DIEKAT | OK | DIEKAT | 2001-05-16 | 2001-08-10 | in exec |  | Bogdan |  |  | 2001-03-12 | [5 empty] | 2001-05-09 | 2001-06-01 | [14 empty] | CW NOT READY |  |  |  |  | K 739 494 | 65 | 0 | 39 | K 739 494 | 210 | 0 | 39 | K 739 494 | 320 | 0 | 39 |  |  |  |  | N/A | 40 | 40 | 7/8" | 40 | 40 | 7/8" | 40 | 40 | 7/8" |  |  |  | 360 | N/A | Galati | FO | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | Indoor Comteck | XC30160 | [6 empty] | 30/indoor |  |  | BSC22 | BSC GALATI |  | N/A |  |  | N/A | [10 empty] | N/A | N/A | N/A |  |  | N/A |  |  |  | 30N01 Faurei-Galati |  | 2001-06-15 | Petrica BURGHIU | Florin RIZESCU | [32 empty] | 33 | Faurei | Braila | [7 empty] | Site Near=Insertion Point
Phase_3 | CS | BX165 | CATALOI | Road Tulcea-Constanta(9) | BX132 Babadag_RTC | Dobrogea | 45 06 16 | 28 44 53 | 45 06 11.8 | 28 44 58.8 | Siloz intersectie DN E87 cu DN 22A, la iesire. | CS Cereal Com, jud. Tulcea/Dir. Gen. Doros Florian, Dir. Ec. Barsan Elena | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | YES |  |  |  |  | 47 | S | 47 | C5m | N/A | DIEKAT | OK | DIRDATES | 2001-05-16 | 2001-05-31 | YesV |  | Doru |  |  | 2001-01-15 |  |  | 2001-02-15 | OK |  | 2001-03-15 | 2001-04-18 | [6 empty] | 2001-06-04 |  |  |  |  | NO-CIPRIAN |  |  | CW BX167 |  |  |  |  | K 739 494 | 10 | 0 | 51 | K 739 494 | 170 | 0 | 50.5 | K 739 494 | 260 | 0 | 50.5 |  |  |  |  | N/A | 12 | 12 | 7/8" | 12 | 12 | 7/8" | 12 | 12 | 7/8" |  |  |  | 72 | ML 15 E 1+0 | Constanta | MW | 189 | 1.2 | 49.5/1.2 | 12 | [7 empty] | N/A | [10 empty] | BX166 | PECO KOGALNICEANU | 9 | 1.2 | 48/1.2 | 60 | [20 empty] | new02 Babadag-Constanta |  | 2001-05-28 | SORIN UNTARU | CATALINA CIOCAN | [32 empty] | 57 | Com. Cataloi | Tulcea | [7 empty] | 3 |  |  | 3
Phase_3 | CS | BX166 | PECO KOGALNICEANU | Road Tulcea-Constanta(9) | BX132 Babadag_RTC | Dobrogea | 45 01 46 | 28 43 53 | 45 01 50.7 | 28 43 58.9 | Com. Mihail Kogalniceanu, jud. Tulcea, in incinta SC AGROMEC M. Kogalniceanu | SC AGROMEG Mihail Kogalniceanu/Ciuraru Mihai-Director | MAXITE | M | 1 | 2 | 2PBC | [12 empty] | 0 | TN | 50/6mp |  | N/A/TMR9000 | DIEKAT | OK | DIRDATES | 2001-05-16 | 2001-06-22 | YesV |  | Doru |  |  | 2001-01-15 |  |  | 2001-02-09 | OK |  | 2001-02-27 | 2001-03-20 |  |  | 1111 | 2001-07-16 | ICOM | ELECTROTRADE | 2001-07-11 | 2001-07-16 | 2001-07-17 |  |  | GATA-MAXITE |  |  | MAXITE |  |  |  |  | AAU | 0 | 0 | 50 | AAU | 200 | 0 | 50 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | 60 | 60 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Constanta | MW | 181 | 1.2 | 48/1.2 | 60 | [18 empty] | BX167 | INTERSECTIE SARICHIOI | 1 | 1.2 | 47 | 60 | [20 empty] | 30N01 Babadag-Constanta |  |  | SORIN UNTARU | CATALINA CIOCAN | [32 empty] | 18 | Mihail Kogalniceanu | Tulcea | [7 empty] | 3 |  |  | 3
Phase_3 | CS | BX167 | INTERSECTIE SARICHIOI | Road Tulcea-Constanta(9) | BX132 Babadag_RTC | Dobrogea | 44 56 20 | 28 43 30 | 44 54 55.9 | 28 43 40.5 | Extravilan Comuna Babadag parcela T80, A946-neproductiv | Primaria Babadag/Gemanaru Nicolai-primar, tel. 040/561012 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [12 empty] | 0 | TN | 50/6mp |  | N/A | DIEKAT | OK | DIRDATES | 2001-07-09 | 2001-08-10 | in exec |  | Doru |  |  | 2001-01-15 |  |  | 2001-02-15 | OK |  | 2001-03-28 | 2001-05-07 | [14 empty] | CW NOT STARTED |  |  |  |  | K 739 494 | 0 | 0 | 49 | K 739 494 | 180 | 0 | 49 | K 739 494 | 290 | 0 | 49 |  |  |  |  | N/A | 60 | 60 | 1 1/4" | 60 | 60 | 1 1/4" | 60 | 60 | 1 1/4" |  |  |  | 360 | ML 23 E 1+0 | Constanta | MW | 188 | 0.6 | 47 | 60 | [7 empty] | N/A | [10 empty] | BX132 | BABADAG_RTC | 8 | [23 empty] | 30N01 Babadag-Constanta |  | 2001-05-28 | SORIN UNTARU | CATALINA CIOCAN | [32 empty] | 56 | Babadag | Tulcea | [7 empty] | 3 |  | 1 | 3
Phase_3 | CS | BX168 | PADURE BABADAG | Road Tulcea-Constanta(9) | BX004 Navodari_CTA | Dobrogea | 44 48 32 | 28 41 15 | 44 48 31.2 | 28 41 16.2 | Extravilan Comuna Baia | Primaria Baia, Comuna Baia, str. Heraclea nr. 6/Ianus Nicolae, com. Baia, str. Maracleea, nr.6, jud. Tulcea si PascaleaN. -Vice-primar | MAXITE | M | 1 | 2 | 2PBC | [7 empty] | N/A | N/A |  |  |  | 0 | TN | 50/6mp |  | N/A/TMR9000 | DIEKAT | OK | DIEKAT | 2001-05-16 | 2001-07-15 | in exec |  | Doru |  |  | 2001-01-15 |  |  | 2001-02-09 | OK |  | 2001-02-27 | 2001-03-20 | [14 empty] | MAXITE |  |  |  |  | AAU | 0 | 0 | 50 | AAU | 180 | 0 | 50 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | 60 | 60 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Constanta | MW | 182 | 1.2 | 48 | 60 | [18 empty] | BX169 | SILOZ BAIA | 2 | 1.2 | 54.5 | 10 | [20 empty] | new02 Navodari-Constanta |  | 2001-08-01 | SORIN UNTARU | CATALINA CIOCAN | [32 empty] | 88 | Com. Baia | Tulcea | [7 empty] | 3 |  |  | 3
Phase_3 | CS | BX169 | SILOZ BAIA | Road Tulcea-Constanta(9) | BX004 Navodari_CTA | Dobrogea | 44 44 21 | 28 41 2 | 44 44 12.4 | 28 41 07.5 | Siloz Baia, Comuna Baia | SC Comcereal SA Tulcea, str. Mircea Voda nr.4/Ing. Alexandru Costache, tel. 092/834573 sau 040/561454 | MAXITE | M | 1 | 2 | 2PBC | [7 empty] | N/A | N/A |  |  |  | 52 | S | 52 | T5m+T5m | TMR9000 | DIEKAT | OK | DIEKAT | 2001-05-16 | 2001-05-31 | YesV | 2001-07-05 | Doru |  | 2001-06-12 | 2001-01-15 |  |  | 2001-02-09 | OK |  | 2001-04-18 | 2001-05-25 | [6 empty] | 2001-06-04 |  |  |  |  | GATA-MAXITE |  |  | MAXITE |  |  |  |  | AAU | 0 | 0 | 56 | AAU | 180 | 0 | 56 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | 10 | 10 | 1/2" | 10 | 10 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A | 40 | ML 15 E 1+0 | Constanta | MW | 201 | 1.2 | 54.5 | 12 | [18 empty] | BX170 | MIHAI VITEAZU | 21 | 1.2 | 48 | 60 | [20 empty] | new02 Navodari-Constanta |  | 2001-08-01 | SORIN UNTARU | CATALINA CIOCAN | [32 empty] | 17 | Com. Baia | Tulcea | [7 empty] | 3 |  |  | 3
Phase_3 | CS | BX170 | MIHAI VITEAZU | Road Tulcea-Constanta(9) | BX004 Navodari_CTA | Dobrogea | 44 37 37 | 28 37 27 | 44 37 34.9 | 28 37 33.3 | Extravilan Comuna Mihai Viteazu | Primaria Comuna Mihai Viteazu/Dl. Patru-secretar, tel. 094/510135 | MAXITE | M | 1 | 2 | 2PBC | [7 empty] | N/A | N/A |  |  |  | 0 | TN/6mp | 50 |  | TMR9000 | DIEKAT | OK | DIEKAT | 2001-06-20 | 2001-07-18 | in exec |  | Doru |  |  | 2001-01-15 |  |  | 2001-02-09 | OK |  | 2001-04-18 | 2001-05-25 | [14 empty] | MAXITE |  |  |  |  | AAU | 30 | 0 | 50 | AAU | 180 | 0 | 50 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | 60 | 60 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Constanta | MW | 201 | 1.2 | 48 | 60 | [18 empty] | BX171 | INTERSECTIE COGEALAC | 21 | 1.2 | 48 | 60 | [20 empty] | new02 Navodari-Constanta |  | 2001-08-01 | SORIN UNTARU | CATALINA CIOCAN | [32 empty] | 179 | Com. Mihai Viteazu | Constanta | [7 empty] | 3 |  |  | 3
Phase_3 | CS | BX171 | INTERSECTIE COGEALAC | Road Tulcea-Constanta(9) | BX004 Navodari_CTA | Dobrogea | 44 32 11 | 28 34 28 | 44 31 42.5 | 28 34 43.5 | SC VITICOLA Cogealac, Ferma3, comuna Cogealac | SC VITICOLA Cogealan, comuna Cogealan, jud. Constanta | 2102 | M | C+C+C+ | 2/2/2 | N/A | [12 empty] | 0 | TN | 50/6mp |  | N/A | DIEKAT | OK | DIEKAT | 2001-06-20 | 2001-07-18 | in exec |  | Doru |  |  | 2001-01-15 |  |  | 2001-02-09 | OK |  | 2001-05-07 | 2001-06-14 | [14 empty] | CW NOT STARTED |  |  |  |  | K 739 494 | 30 | 0 | 50 | K 739 494 | 190 | 0 | 50 | K 739 494 | 340 | 0 | 50 |  |  |  |  | N/A | 60 | 60 | 1 1/4" | 60 | 60 | 1 1/4" | 60 | 60 | 1 1/4" |  |  |  | 360 | ML 15 E 1+0 | Constanta | MW | 193 | 1.2 | 48 | 60 | [7 empty] | N/A | [10 empty] | BX172 | PIATRA | 14 | 1.2 | 48 | 60 | [20 empty] | new02 Navodari-Constanta |  | 2001-08-01 | SORIN UNTARU | CATALINA CIOCAN | [32 empty] | 130 | Com. Cigealac | Constanta | [7 empty] | 3 |  |  | 3
Phase_3 | CS | BX172 | PIATRA | Road Tulcea-Constanta(9) | BX004 Navodari_CTA | Dobrogea | 44 23 56 | 28 31 40 | 44 24 00.9 | 28 31 39.7 | Parcela NP153, zona Cariera Sitorman | Primaria Comunei Mihail Kogalniceanu, jud. Constanta, tel. 094305165 | MAXITE | M | 1 | 2 | 2PBC | [7 empty] | N/A | N/A |  |  |  | 0 | TN/6mp | 50 |  | N/A/TMR9000 | DIEKAT | OK | DIEKAT | 2001-06-20 | 2001-07-18 | in exec |  | Doru |  |  | 2001-01-15 |  |  | 2001-02-09 | OK |  | OK | 2001-05-07 | [14 empty] | MAXITE |  |  |  |  | AAU | 20 | 0 | 50 | AAU | 180 | 0 | 50 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | 60 | 60 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Constanta | MW | 141 | 1.2 | 48 | 60 | [18 empty] | BX004 | NAVODARI CTA | 321 | 0.6 | 30 | 35 | [20 empty] | new02 Navodari-Constanta |  | 2001-08-01 | SORIN UNTARU | CATALINA CIOCAN | [32 empty] | 79 | Mihail Kogalniceanu | Constanta | [6 empty] | 1 | 3 |  | 1 | 3
Phase_3 | CS | BX173 | NALBANT | Road Harsova-Tulcea(6) | ? | Dobrogea | 45 04 13 | 28 39 28 |  |  |  |  | MAXITE | M | 1 | 2 | 2PBC | [12 empty] | 0 | TN | 50 | [12 empty] | 2001-01-15 | [21 empty] | MAXITE | [35 empty] | Constanta | ? | [22 empty] | No | [28 empty] | SORIN UNTARU | CATALINA CIOCAN | [42 empty] | Site Near=Insertion Point
Phase_3 | CS | BX174 | NICOLAE BALCESCU | Road Harsova-Tulcea(6) | ? | Dobrogea | 45 00 09 | 28 35 46 |  |  |  |  | MAXITE | M | 1 | 2 | 2PBC | [12 empty] | 0 | TN | 50 | [12 empty] | 2001-01-15 | [21 empty] | MAXITE | [35 empty] | Constanta | ? | [22 empty] | No | [28 empty] | SORIN UNTARU | CATALINA CIOCAN | [42 empty] | Site Near=Insertion Point
Phase_3 | CS | BX175 | CIUCUROVA | Road Harsova-Tulcea(6) | ? | Dobrogea | 44 55 25 | 28 29 08 |  |  |  |  | MAXITE | M | 1 | 2 | 2PBC | [12 empty] | 0 | TN | 50 | [12 empty] | 2001-01-15 | [21 empty] | MAXITE | [35 empty] | Constanta | ? | [22 empty] | No | [28 empty] | SORIN UNTARU | CATALINA CIOCAN | [42 empty] | Site Near=Insertion Point
Phase_3 | CS | BX176 | TOPOLOG_DRTV | Road Harsova-Tulcea(6) | ? | Dobrogea | 44 51 33 | 28 25 07 |  |  |  |  | MAXITE | M | 1 | 2 | 2PBC | [13 empty] | TE | [13 empty] | 2001-01-15 | [21 empty] | MAXITE | [35 empty] | Constanta | ? | [22 empty] | No | [28 empty] | SORIN UNTARU | CATALINA CIOCAN | [42 empty] | Site Near=Insertion Point
Phase_3 | CS | BX177 | RAHMAN | Road Harsova-Tulcea(6) | ? | Dobrogea | 44 49 27 | 28 16 08 |  |  |  |  | MAXITE | M | 1 | 2 | 2PBC | [12 empty] | 0 | TN | 50 | [12 empty] | 2001-01-15 | [21 empty] | MAXITE | [35 empty] | Constanta | ? | [22 empty] | No | [28 empty] | SORIN UNTARU | CATALINA CIOCAN | [42 empty] | Site Near=Insertion Point
Phase_3 | CS | BX178 | SARAIU | Road Harsova-Tulcea(6) | ? | Dobrogea | 44 43 38 | 28 09 46 |  |  |  |  | MAXITE | M | 1 | 2 | 2PBC | [12 empty] | 0 | TN | 50 | [12 empty] | 2001-01-15 | [21 empty] | MAXITE | [35 empty] | Constanta | ? | [22 empty] | No | [28 empty] | SORIN UNTARU | CATALINA CIOCAN | [42 empty] | Site Near=Insertion Point
Phase_3 | CS | BX180 | VALEA CALUGAREASCA_RTC | Road Ploiesti-Mizil(3) | BX122 Boldesti_Sacaieni_RTC | Muntenia | 44 57 45 | 26 08 49 | 44 57 45 | 26 08 49 | Sos. Ploiesti-Buzau DN1B, Valea Calugareasca | Romtelecom,d-ul Pintoiu, tel. 092/720174 | MAXITE | M | 1 | 2 | 2PBC | [7 empty] | N/A | N/A |  |  |  | 10.6 | B | 10.6 | 15m new pylonet | Room/Rack19" | SETRACO | OK | SETRACO | 2001-05-16 | 2001-05-30 | YesV | 2001-07-03 | Doru |  | 2001-06-12 | 2001-01-29 |  |  | N/A |  |  | 2001-02-20 | 2001-04-17 | [6 empty] | 2001-06-04 |  |  |  |  | GATA-MAXITE |  |  | RBS NOT STARTED |  |  |  |  | AAU | 100 | 0 | 24.5 | AAU | 270 | 0 | 24.5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | 16 | 16 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 32 | N/A | Baneasa | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | [12 empty] | 28/outdoor |  |  | BX122 | BOLDESTI SCAIENI_RTC |  | N/A |  |  | N/A | [10 empty] | N/A | N/A | N/A |  |  | N/A |  |  |  | 30N01 Valea Calugareasca-Boldesti Scaieni |  | 2001-06-19 | Petrica BURGHIU | [34 empty] | Valea Calugareasca | Prahova | [7 empty] | Site Near=Insertion Point
Phase_3 | CS | BX181 | ARIONESTI_DRTV | Road Ploiesti-Mizil(3) | BX122 Boldesti_Sacaieni_RTC | Muntenia | 44 59 15 | 26 11 52 | 44 59 15 | 26 11 52 | DRTV Arionesti | DRTv/Sef Statie ing. Simion Petre - 044/236 715 | MAXITE | M | 1 | 2 | 2PBC | [12 empty] | 5 | B | 13.75 | 9m existing pylonet | Room/Rack19" | SETRACO | OK | SETRACO | 2001-05-17 | 2001-06-05 | YesV | Respins | Doru |  |  | 2001-01-29 |  |  | N/A |  |  | 2001-04-10 | 2001-03-01 | [6 empty] | 2001-06-05 |  |  |  |  | GATA-MAXITE |  |  | RBS NOT STARTED |  |  |  |  | AAU | 60 | 0 | 23.4 | AAU | 120 | 0 | 23.4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | 45 | 45 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 90 | ML 15 E 1+0 | Baneasa | MW | 86 | 1.2 | 19.35 | 56 | [18 empty] | BX182 | MIZIL_RTC | 267 | 1.2 | 27 | 57 | [20 empty] | 30N01 Mizil-Valea Calugareasca |  | 2001-06-19 | Petrica BURGHIU | [34 empty] | Valea Calugareasca | Prahova | [7 empty] | 3 |  |  | 3
Phase_3 | CS | BX182 | MIZIL_RTC | Road Ploiesti-Mizil(3) | BX122 Boldesti_Sacaieni_RTC | Muntenia | 45 00 00.8 | 26 26 40 | 45 00 00.8 | 26 26 40 | Str. Blajului, nr. 5 | Romtelecom, Sef centru D-ul Zaharescu, tel. 092/843817, 044/253031 | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [12 empty] | 0 | TE | 32 |  | Room/Rack19" | SETRACO | OK | SETRACO | 2001-05-11 | 2001-05-25 | YesV | 2001-06-13 | Doru |  | 2001-06-26 | 2001-01-29 |  |  | N/A |  |  | 2001-02-20 | 2001-04-09 |  |  | 1902-10-31 | 2001-06-06 | ICOM | INTERACTIVE | 2001-06-04 |  | 2001-06-07 | 2001-06-07 | 2001-06-10 | RADU |  | Alexandru Toma | 2001-06-20 | 2001-06-20 | 2001-06-20 |  |  | K 739 494 | 60 | 0 | 27 | K 739 494 | 250 | 0 | 28 | K 739 494 | 330 | 0 | 28 |  |  |  |  | N/A | 57 | 57 | 1 1/4" | 68 | 68 | 1 1/4" | 68 | 68 | 1 1/4" |  |  |  | 344 | N/A | Baneasa | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | [5 empty] | 30182 | [6 empty] | 48/Indoor |  |  | BX180 | VALEA CALUGAREASCA_RTC | N/A | N/A |  |  | N/A | [10 empty] | N/A | N/A | N/A | RADU |  | N/A |  |  |  | 30N01 Mizil-Valea Calugareasca |  | 2001-06-19 | Petrica BURGHIU | [34 empty] | Mizil | Prahova | [7 empty] | Site Near=Insertion Point
Phase_3 | CS | BX183 | NAVODARI_2 | Road Tulcea-Constanta(9) | BX004 Navodari_CTA | Dobrogea | 44 19 3.8 | 28 36 33 | 44 19 12 | 28 36 58 | Navodari, str. Albinelor, nr.21, bl.A9, sc. A sau sc. B | Manole Marian, str. Albinelor, nr. 21, bl.A9, ap.33, et.1, Navodari | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | YES |  |  |  |  | 23.2 | B | 27.72 | C3.5m+C3.5m | N/A | DIEKAT | OK | VECTOR | 2001-04-23 | 2001-04-30 | YesV | 2001-05-17 | Doru |  | 2001-05-23 | 2001-01-30 |  |  | 2001-02-20 | OK |  | OK | 2001-04-10 |  |  | 1902-08-03 | 2001-05-02 | ICOM | ELECTOTRADE | 2001-05-02 |  | 2001-05-03 | 2001-05-03 | 2001-05-04 | PAUN |  | Alexandru Toma | 2001-05-30 | 2001-05-30 | 2001-05-30 | 2001-06-05 | 2001-06-19 | K 739 494 | 120 | 0 | 30.2 | K 739 494 | 250 | 0 | 30.2 | K 739 494 | 350 | 0 | 30.2 |  |  |  |  | N/A | 13 | 13 | 7/8" | 22 | 22 | 7/8" | 22 | 22 | 7/8" |  |  |  | 132 | ML 38 E 1+0* | Constanta | MW | 31 | 0.3 | 29.2 | 21 | 38/18 | [16 empty] | 1 | BX004 | NAVODARI CTA | 211 | 0.3 | 30 | 35 | 38/14 | [6 empty] | 62* | ELECTOTRADE |  | 876 | 2001-05-03 | 2001-05-03 | 2001-05-04 | PAUN | 2001-05-23 | 2001-05-30 |  |  | 2001-06-18 | 30N01 Navodari-Constanta |  | OK | Petrica BURGHIU | [33 empty] | 36 | Navodari | Constanta | [7 empty] | 3 |  |  | 3
Phase_3 | CS | BX184 | HOTEL COMANDOR | Constanta(3) | BX003 Mamaia_CTA | Dobrogea | 44 15 36 | 28 37 8.8 | 44 16 07 | 28 37 18 | B-dul Mamaia, Hotel Comandor | Adrian Petre- administrator, tel. 092/666848 | 2102 | M | C+C+ | 2/2 | N/A | [7 empty] | YES |  |  |  |  | 27.4 | B | 27.4 | T6m+C4.5m | N/A | DIEKAT | OK | ORION | 2001-05-16 | 2001-06-25 | YesV | 2001-07-05 | Doru |  | 2001-06-12 | 2001-01-30 |  |  | 2001-02-20 | OK |  | OK | 2001-04-09 |  |  | 1094 | 2001-07-09 | ICOM | INTERACTIVE | 2001-07-09 | 2001-07-10 | 2001-07-10 | 2001-07-11 | 2001-07-13 |  |  |  | CW NOT READY |  |  |  |  | K 739 494 | 0 | 0 | 33 | K 739 494 | 170 | 0 | 31.4 | N/A | N/A | N/A | N/A |  |  |  |  | N/A | 17 | 17 | 7/8" | 16 | 16 | 7/8" | N/A | N/A | N/A |  |  |  | 66 | ML 23 E 1+0* | Constanta | MW | 167 | 0.6 | 29.4/0.6 | 15 | 23/58 | N/A | 4x2/8 | 2U-3 |  |  |  | RBS | XC30003 | [8 empty] | 1 | BX003 | MAMAIA CTA | 348 | 0.6 |  |  | 23/56 | [6 empty] | 79* | INTERACTIVE | 2001-07-09 | 1072 |  | 2001-07-11 | 2001-07-13 | PAUN | [5 empty] | 30N01 Mamaia-Constanta |  | OK | Petrica BURGHIU | [34 empty] | Mamaia | Constanta | [7 empty] | 3 |  |  | missing
Phase_3 | CS | BX185 | NEPTUN MIORITA | Road Constanta-Vama Veche(5) | BX051 Neptun_RTC | Dobrogea | 43 52 21 | 28 35 53 | 43 52 34 | 28 35 28 | Hotel Miorita | SC Neptun SA - Str. Plopilor nr.1, Neptun/Filip Dumitru - dir., Dumitru Ion - dir ec. | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | YES |  |  |  |  | 18.3 | B | 21 | T6m | N/A | DIEKAT | OK | COMARK | 2001-04-05 | 2001-04-24 | YesV | 2001-05-17 | Doru |  | 2001-05-23 | 2001-01-30 |  |  | 2001-02-20 | OK |  | 2001-04-09 | 2001-04-25 |  |  | 1902-07-24 | 2001-04-25 | ICOM | DIRDATES | 2001-04-25 |  | 2001-04-25 | 2001-04-27 | 2001-05-11 | PAUN |  | Alexandru Toma | 2001-05-29 | 2001-05-29 | 2001-05-29 | 2001-06-05 | 2001-06-19 | K 739 494 | 20 | 0 | 26.5 | K 739 494 | 140 | 0 | 26.5 | K 739 494 | 220 | 0 | 26.5 |  |  |  |  | N/A | 16 | 16 | 7/8" | 16 | 16 | 7/8" | 16 | 16 | 7/8" |  |  |  | 96 | ML 38 E 1+0* | Constanta | MW | 30 | 0.3 | 24.5 | 15 | 38/18 |  |  | 2U-3 |  |  |  | N/A | [9 empty] | 1 | BX056 | OLIMP | 210 | 0.3 | 49 | 20 | 38/14 | [6 empty] | 61* | DIRDATES |  | 864 | 2001-04-27 | 2001-04-27 | 2001-05-02 | PAUN | 2001-05-24 | 2001-05-29 |  |  | 2001-06-18 | 30N02 Neptun-Constanta |  | OK | Denis CIUCU | Florin RIZESCU | [32 empty] | 44 | Neptun | Constanta | [7 empty] | 3 |  |  | 3
Phase_3 | CS | BX186 | JUPITER CAPITOL | Road Constanta-Vama Veche(5) | BX051 Neptun_RTC | Dobrogea | 43 51 16 | 28 36 27 | 43 51 32 | 28 36 49 | Hotel Capitol, Jupiter | Dan Cotleanu, Teodora Cotleanu tel. 094/528922 | 2102 | M | C+C+ | 2/2 | N/A | [7 empty] | YES |  |  |  |  | 39 | B | 42.3 | C5m+C8m |  | DIEKAT | OK | COMARK | 2001-04-05 | 2001-04-24 | YesV | 2001-05-17 | Doru |  | 2001-05-23 | 2001-01-30 |  |  | 2001-02-20 | OK |  | 2001-03-21 | 2001-04-10 |  |  | 1902-07-25 | 2001-04-25 | ICOM | DIRDATES | 2001-04-25 |  | 2001-04-25 | 2001-04-27 | 2001-05-01 | PAUN |  | Alexandru Toma | 2001-05-29 | 2001-05-29 | 2001-05-29 | 2001-06-05 | 2001-06-19 | K 739 494 | 200 | 0 | 46 | K 739 494 | 300 | 0 | 46.3 | N/A | N/A | N/A | N/A |  |  |  |  | N/A | 13 | 13 | 7/8" | 26 | 26 | 7/8" | N/A | N/A | N/A |  |  |  | 78 | ML 38 E 1+0* | Constanta | MW | 326 | 0.3 | 44/0.6 | 25 | 38/14 |  |  | 2U-3 |  |  |  | N/A | [9 empty] | 1 | BX051 | NEPTUN_RTC | 146 | 0.3 | 14 | 30 | 38/18 | [6 empty] | 61* | DIRDATES |  | 865 | 2001-04-27 | 2001-04-27 | 2001-05-02 | PAUN | 2001-05-24 | 2001-05-29 |  |  | 2001-06-18 | 30N01 Neptun-Constanta |  | 2001-05-22 | Petrica BURGHIU | [33 empty] | 26 | Jupiter | Constanta | [7 empty] | 3 |  |  | 3
Phase_3 | CS | BX187 | SATURN CLEOPATRA | Road Constanta-Vama Veche(5) | BX051 Neptun_RTC | Dobrogea | 43 49 36 | 28 35 19 | 43 49 70 | 28 35 39 | Saturn, hotel Cleopatra | Bucovala Nicolae-patron, tel. 041/751704 | 2102 | M | C+C+ | 2/2 | N/A | [7 empty] | YES |  |  |  |  | 17.9 | B | 17.9 | C3.5m+C3.5m | N/A | DIEKAT | OK | COMARK | 2001-04-05 | 2001-04-24 | YesV | 2001-05-17 | Doru |  | 2001-05-23 | 2001-01-30 |  |  | 2001-02-20 | OK |  | 2001-03-22 | 2001-04-25 |  |  | 1902-07-26 | 2001-04-25 | ICOM | DIRDATES | 2001-04-25 |  | 2001-04-25 | 2001-04-27 | 2001-05-01 | PAUN |  | Alexandru Toma | 2001-05-29 | 2001-05-29 | 2001-05-29 | 2001-06-05 | 2001-06-19 | K 739 494 | 0 | 0 | 24.4 | K 739 494 | 170 | 0 | 24.4 | N/A | N/A | N/A | N/A |  |  |  |  | N/A | 15 | 15 | 7/8" | 17 | 17 | 7/8" | N/A | N/A | N/A |  |  |  | 64 | ML 23 E 1+0* | Constanta | MW | 25 | 0.6 | 23.4/0.3 | 14 | 23/56 |  | 4x2/8 | 2U-3 |  |  |  | N/A | [9 empty] | 1 | BX186 | JUPITER CAPITOL | 205 | 0.6 | 44/0.6 | 12 | 23/58 | [6 empty] | 61* | DIRDATES |  | 866 | 2001-04-27 | 2001-04-27 | 2001-05-02 | PAUN | 2001-05-24 | 2001-05-29 |  |  | 2001-06-18 | 30N01 Neptun-Constanta |  | 2001-05-22 | Petrica BURGHIU | [33 empty] | 27 | Saturn | Constanta | [7 empty] | 3 |  |  | 3
Phase_3 | CS | BX188 | VAMA VECHE | Road Constanta-Vama Veche(5) | BX052 Mangalia_RTC | Dobrogea | 43 44 45 | 28 34 08 |  |  |  |  | 2102 | M | C+C+ | 2/2 | N/A | [7 empty] | YES |  |  |  |  | 0 | TN | 30 |  |  | DIEKAT | OK | DIEKAT | 2001-08-01 | 2001-08-30 |  |  | Doru |  |  | 2001-01-30 | 2001-06-22 |  |  | OK | [17 empty] | RBS 2101 |  |  |  |  | K 739 494 | 0 | 0 | 30 | K 739 494 | 200 | 0 | 30 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | [13 empty] | ML 15 E 1+0 | Constanta | MW | 7 | [21 empty] | ZX052 | MANGALIA_RTC | [24 empty] | new03 Mangalia-Constanta |  |  | Dragos BICIU | Leonard BANU | [42 empty] | 3 |  |  | missing
Phase_3 | CS | BX189 | METRO CONSTANTA | Constanta(3) | BX002 Tomis Nord | Dobrogea | 44 12 1 | 28 36 51 | 44 12 09 | 28 36 58 | Str. Aleea Murelor, nr. 14, Bl. BC2, sc. A | Asociatia de locatari ai bl. BC2, nr. 203-ConstantaHopirtean Emil-administrator, Etem Icherem si Petror Anastase | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | YES |  |  |  |  | 32.0 | B | 32.0 | C3.5m+T3m | N/A | DIEKAT | OK | VECTOR | 2001-08-01 | 2001-08-20 |  |  | Doru |  |  | 2001-01-30 |  |  | 2001-02-20 | OK |  | 2001-03-21 | 2001-04-10 | [14 empty] | CW NOT STARTED |  |  |  |  | K 739 494 | 0 | 0 | 38.4 | K 739 494 | 110 | 0 | 38.4 | K 739 494 | 250 | 0 | 34 |  |  |  |  | N/A | 18 | 18 | 7/8" | 18 | 18 | 7/8" | 17 | 17 | 7/8" |  |  |  | 106 | ML 38 E 1+0* | Constanta | MW | 47 |  | 37.4 | 17 | [7 empty] | N/A | [10 empty] | BX014 | DOBRILA | [24 empty] | 30N04 Tomis Nord-Constanta |  | OK | Petrica BURGHIU | [33 empty] | 26 | Constanta | Constanta | [7 empty] | 3 |  |  | missing
Phase_3 | CS | BX190 | CONSTANTA OVIDIU | Constanta(3) | BX001 Constanta_CTA | Dobrogea | 44 10 31 | 28 39 22.4 |  |  | Constanta str. Revolutiei nr. 16, Bl. L10, sc.1 |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | YES | [5 empty] | B |  |  |  | DIEKAT |  | @ | 2001-08-01 | 2001-09-10 |  |  | Doru |  |  | 2001-01-30 | 2001-06-14 |  |  | OK | [17 empty] | CTR | [34 empty] | ML 38 E 1+0 | Constanta | MW | 309 | [21 empty] | BX001 | PERLA | [24 empty] | new03 RTC-Constanta-conectare locala |  |  | Petrica BURGHIU | Leonard BANU | [42 empty] | 3 |  |  | missing
Phase_3 | CS | BX191 | 2 MAI | Road Constanta-Vama Veche(5) | BX052 Mangalia_RTC | Dobrogea | 43 47 00 | 28 34 40.8 |  |  |  |  | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [7 empty] | YES | [9 empty] | DIEKAT | OK | DIEKAT | 2001-08-01 | 2001-08-30 |  |  | Doru |  |  | 2001-04-25 | [21 empty] | CW NOT STARTED | [34 empty] | ML 23 E 1+0 | Constanta | MW | 189 | [21 empty] | BX188 | VAMA VECHE | 9 | [23 empty] | new03 Mangalia-Constanta |  |  | Petrica BURGHIU | Leonard BANU | [42 empty] | 3 |  |  | 3
Phase_3 | CS | BX192 | HOTEL RIVIERA | Constanta(3) | BX003 Mamaia_CTA | Dobrogea | 44 14 40.5 | 28 37 16.5 | 44 14 42 | 28 37 18 | Hotel Riviera | SC Mamaia SA | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | YES |  |  |  |  | 45.5 | B | 46 | C3m+C3m+C3m |  | DIEKAT | OK | VECTOR | 2001-08-01 | 2001-08-20 |  |  | Doru |  |  | 2001-04-25 |  |  | 2001-05-14 |  |  | 2001-06-01 | 2001-06-13 | [14 empty] | CW NOT STARTED |  |  |  |  | K 739 494 | 160 | 0 | 46 | K 739 494 | 270 | 0 | 48 | K 739 494 | 320 | 0 | 46 |  |  |  |  | N/A | 20 | 20 | 7/8" | 45 | 45 | 1 1/4" | 15 | 15 | 7/8" |  |  |  | 160 | ML 38 E 1+0 | Constanta | MW | 160 | 0.3 | 47 | 20 | [7 empty] | N/A | XC30003 | [9 empty] | BX003 | MAMAIA CTA | [24 empty] | 30N01 Mamaia-Constanta |  | OK | Petrica BURGHIU | Leonard BANU | [32 empty] | 50 | Mamaia | Constanta | [7 empty] | 3 |  |  | missing
Phase_3 | CS | BX201 | VESTULUI | Ploiesti(5) | BX059 Ploiesti_1 | Muntenia | 44 56 53 | 25 59 46.9 | 44 56 53 | 25 59 46.9 | Sos Vestului, bl. 1 | Asociatia de locatari bl. 1 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [12 empty] | 27 | B | 27 |  | N/A | ISAF | OK | @ | 2001-08-01 | 2001-08-20 |  |  | Doru |  |  | 2001-05-30 |  |  | OK | 2001-05-30 |  | 2001-07-04 | [15 empty] | CTR |  |  |  |  | K 739 494 | 40 | 0 | 32 | K 739 494 | 160 | 0 | 32 | K 739 494 | 280 | 0 | 32 | N/A | N/A | N/A | N/A | N/A | 22 | 22 | 7/8" | 22 | 22 | 7/8" | 14 | 14 | 7/8" | N/A | N/A | N/A | 72 |  | Baneasa | MW | 106 | 0.3 | 33.5 | 24 | [18 empty] | BX059 | PLOIESTI_1 | 286 | [26 empty] | SORIN UNTARU | SORIN UNTARU | [33 empty] | Ploiesti | Prahova | [7 empty] | missing |  |  | missing
Phase_3 | CS | BX202 | REPUBLICII | Ploiesti(5) | BX140 Ploiesti Sud_RTC | Muntenia | 44 56 44.9 | 26 00 44.3 |  |  |  |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [17 empty] | ISAF | OK | EL-MONT | 2001-08-01 | 2001-08-20 |  |  | Doru |  |  | 2001-05-30 |  |  |  | 2001-05-30 | [17 empty] | CTR | [35 empty] | Baneasa | MW | [22 empty] | BX139 | PLOIESTI_5 | [24 empty] | new |  |  | SORIN UNTARU | SORIN UNTARU | [42 empty] | missing |  |  | missing
Phase_3 | CS | BX203 | EROILOR | Ploiesti(5) | BX140 Ploiesti Sud_RTC | Muntenia | 44 55 50.5 | 26 00 28.1 |  |  |  |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [17 empty] | ISAF |  | @ | 2001-08-15 | 2001-08-30 |  |  | Doru |  |  | 2001-05-30 |  |  |  | 2001-05-30 | [17 empty] | CTR | [35 empty] | Baneasa | MW | [22 empty] | BX139 | PLOIESTI_5 | [24 empty] | new |  |  | SORIN UNTARU | SORIN UNTARU | [42 empty] | missing |  |  | missing
Phase_3 | CS | BX204 | GIOCONDA | Ploiesti(5) | BX059 Ploiesti_1 | Muntenia | 44 55 36.1 | 26 01 41.8 |  |  |  |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [17 empty] | ISAF |  | @ | 2001-08-15 | 2001-08-30 |  |  | Doru |  |  | 2001-05-30 |  |  |  | 2001-05-30 | [17 empty] | CTR | [35 empty] | Baneasa | MW | [22 empty] | BX059 | PLOIESTI_1 | [27 empty] | SORIN UNTARU | SORIN UNTARU | [42 empty] | missing |  |  | missing
Phase_3 | CS | BX205 | DOJA | Ploiesti(5) | BX059 Ploiesti_1 | Muntenia | 44 56 44.2 | 26 02 00.5 |  |  | Str Gheorghe Doja, Nr 148, Bl A, Sc 1 |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [17 empty] | ISAF |  | @ | 2001-08-15 | 2001-08-30 |  |  | Doru |  |  | 2001-05-30 |  |  |  | 2001-05-30 | [17 empty] | CTR | [35 empty] | Baneasa | MW | [22 empty] | BX204 | GIOCONDA | [27 empty] | SORIN UNTARU | SORIN UNTARU | [42 empty] | missing |  |  | missing
Phase_3 | CS | BX224 | TULUCESTI | Road Galati-Husi | BX080 Central_RTC | Moldova | 45 34 49.8 | 28 02 14.2 |  |  |  |  | MAXITE | M | 1 | 2 | 2PBC | [17 empty] | ORION |  | @ | 2001-08-15 | 2001-09-20 |  |  | Bogdan |  |  | 2001-07-10 | [8 empty] | 2001-07-10 | [47 empty] | ML 15 E 1+0* | Galati | MW | [22 empty] | BX086 | MIHAI BRAVU
Phase_3 | CS | BX226 | FOLTESTI | Road Galati-Husi | YX226 Foltesti_RTC | Moldova | 45 43 54.2 | 28 03 09.1 |  |  |  |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [17 empty] | ORION |  | @ | 2001-08-15 | 2001-09-20 |  |  | Bogdan |  |  | 2001-07-10 |  |  |  | 2001-07-11 |  |  |  |  | 2001-07-10 | [47 empty] | ML 38 E 1+1 | Galati | MW | [22 empty] | YX226 | FOLTESTI_RTC | [61 empty] | 130
Phase_3 | CS | BX227 | BRANESTI | Road Galati-Husi | YX226 Foltesti_RTC | Moldova | 45 48 52.2 | 28 05 01.9 |  |  |  |  | 2101 | M | C+ | 2 | 2101 | [17 empty] | ORION |  | @ | 2001-08-15 | 2001-09-20 |  |  | Bogdan |  |  | 2001-07-10 |  |  |  | 2001-07-11 |  |  |  |  | 2001-07-10 | [47 empty] | ML 15 E 1+0 | Galati | MW | [22 empty] | BX226 | FOLTESTI | [61 empty] | 80
Phase_3 | CS | BX228 | OANCEA | Road Galati-Husi | YX226 Foltesti_RTC | Moldova | 45 54 32.2 | 28 06 30.2 |  |  |  |  | 2101 | M | C+ | 2 | 2101 | [17 empty] | ORION |  | @ | 2001-08-15 | 2001-09-20 |  |  | Bogdan |  |  | 2001-07-10 |  |  |  | 2001-07-11 |  |  |  |  | 2001-07-10 | [47 empty] | ML 15 E 1+0 | Galati | MW | [22 empty] | BX227 | BRANESTI | [61 empty] | 80
Phase_3 | CS | BX229 | CAVARDINESTI | Road Galati-Husi | YX226 Foltesti_RTC | Moldova | 46 03 12.6 | 28 01 09.2 |  |  |  |  | MAXITE | M | 1 | 2 | 2PBC | [17 empty] | ORION |  | @ | 2001-08-15 | 2001-09-20 |  |  | Bogdan |  |  | 2001-07-10 |  |  |  | 2001-07-11 |  |  |  |  | 2001-07-10 | [47 empty] | ML 15 E 1+0 | Galati | MW | [22 empty] | BX228 | OANCEA | [61 empty] | 190
Phase_1 | CS | BX501 | ROMANESTI(OPTIMIZARE) | Road Buc-Bra | BX523 Ploiesti Vest_CTA | Muntenia | 26 04'28,4"E | 44 51'20,5"N | 44 51 10.7 | 26 04 31.9 | Comuna Romanesti |  | 2202 | M | C+C+C+ | 2/2/2 | 2202 | Warehouse | MAXITE | M | No | 2 | 2PBC | OK | N/A | N/A | Phase_1 |  |  | N/A | TN | 32 | New 32m tower | SHELTER | SVF | OK | SVF | OK | OK | YesV | OK | DRAGOS | 2000-01-07 | 1999-12-22 |  |  | 2001-06-29 | 1999-11-18 | 1999-12-22 |  | 1999-12-22 | 1999-12-21 |  |  |  | 2001-07-09 | ICOM | ICOM | 2001-07-09 | 2001-07-10 | 2001-07-10 | 2001-07-11 | 2001-07-12 | PAUN | Yes | Mircea Mihut | 2001-07-12 | 2001-07-12 | 2001-07-12 |  |  | K 739 494 | 70 | 0 | 30 | K 739 494 | 170 | 0 | 30 | K 739 494 | 330 | 0 | 30 | N/A | N/A | N/A | N/A | N/A | 35 | 35 | 7/8" | 35 | 35 | 7/8" | 35 | 35 | 7/8" | N/A | N/A | N/A | 140 | ML 23 E 1+0 | Baneasa | MW | 303 | 0.6 |  |  | 23/58 |  | 4X2/8 | 4u-1 |  |  |  | Indoor Comteck | [10 empty] | BX502 | PETROBRAZI | 123 | 0.6 |  |  | 23/56 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-05-24 |  |  | 2000-05-31 | 30N01 Ploiesti Vest-Dr.Taberei |  | OK | DAN | DAN | [21 empty] | 2000-01-31 |  | 2001-07-09 | YRO | SVF | 2000-02-08 | Cristian Croitor | 2000-03-23 | 2000-03-23 | 2000-03-27 | OK | 115 | Romanesti | Prahova | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BX502 | PETROBRAZI | Road Buc-Bra | BX523 Ploiesti Vest_CTA | Muntenia | 44 52 54.6 | 26 00 52.9 | 44 53 04.0 | 26 00 42.5 | SC REMMERO SA Ploiesti, Centrala Termoelectrica Petrobrazi, cladirea administrativa, Ploiesti, Prahova | SC Petrobrazi, dir. Tehnic Daniel Soare/Dna. Tudoran-Director Administrativ, 044.121620; fax. 044112616 | 2101 | M | C+ | 2 | 2101 | [6 empty] | OK |  | 2000-06-27 |  |  |  | 25 | B | 15 | New 15m mast | OUTDOOR | SVF | OK | SVF | OK | OK | YesV | OK | DRAGOS | 1999-12-21 | OK |  |  |  | OK | 1999-11-04 |  | 1999-11-04 | 2000-02-21 |  |  |  | N/A | YRO | SVF | OK | OK | OK | OK | OK |  | Yes | Cristian Croitor | 2000-02-26 | 2000-03-23 | 2000-03-23 | 2000-03-27 | OK | K 739 494 | 100 | 0 | 33.2 | K 739 494 | 340 | 0 | 33.2 | N/A | N/A | N/A | N/A |  |  |  |  | K 63 55 8 | 12 | 12 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 24 | ML 23 E 1+0 | Baneasa | MW | 336 | 0.6 |  |  | 23/56 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [10 empty] | BX503 | PLOIESTI VEST | 156 | 0.6 |  |  | 23/58 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-05-10 |  |  | 2000-05-31 | 30N01 Ploiesti Vest-Dr.Taberei |  | OK | MIHAI C. | MIHAI C. | [32 empty] | 141 | Ploiesti | Prahova | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BX503 | PLOIESTI VEST | Road Buc-Bra | BX523 Ploiesti Vest_CTA | Muntenia | 25 59'37,8"E | 44 55'35,1"N | 44 55 50.8 | 25 59 06.6 | Strada Erou Nicolae Arhip no 13, bl. 65 | Private/Vlad Ion, Strada Erou Nicolae Arhip no 10, bl. 65 apt 33 | 2202 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | B | 30 | C3m+C3m+C3m+C4m | ROOM | TRANSDATA | OK | TRANSDATA | OK | OK | YesV | OK | DORU | 2000-01-24 | OK |  |  |  | 1999-11-16 | OK |  | OK | 2000-02-21 |  |  |  | N/A | YRO | SVF | 2000-02-01 | OK | 2000-02-04 | 2000-02-04 | 2000-02-05 |  | Yes | Cristian Croitor | 2000-02-25 | 2000-03-23 | 2000-03-23 | 2000-03-27 | OK | K 739 494 | 60 | 0 | 37 | K 739 494 | 160 | 0 | 37 | K 739 494 | 330 | 0 | 37 |  |  |  |  | N/A | 25 | 25 | 7/8" | 20 | 20 | 7/8" | 20 | 20 | 7/8" |  |  |  | 130 | ML 38 E 1+1 | Baneasa | MW | 60 | 0.3 |  |  | 38/18 | YES | 34+2 | 4U-1 |  |  |  | Indoor Comteck | [10 empty] | BX523 | PLOIESTI VEST CTA | 240 | 0.3 |  |  | 38/14 | [6 empty] | 2/ N/A | RADCOM | 2000-09-15 | OK | OK | OK | OK | OK | OK | 2000-05-10 |  |  | 2001-01-08 | 30N01 Ploiesti Vest-Dr.Taberei |  | OK | DAN | DAN | [32 empty] | 163 | Ploiesti | Prahova | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BX504 | BUDA(OPTIMIZARE) | Road Buc-Bra | BX523 Ploiesti Vest_CTA | Muntenia | 44 54 45.6 | 26 02 39.1 | 44 59 11.5 | 25 55 16.7 | Movila Vulpii |  | 2202 | M | C+C+C+ | 2/2/2 | 2202 | Warehouse | MAXITE | M | No | 2 | 2PBC | OK |  | N/A | Phase_1 |  |  | N/A | TN | 30 | New 30m tower | SHELTER | SVF | OK | SVF | OK | OK | YesV | OK | DRAGOS | 2000-01-07 | 1999-12-22 |  |  | 2001-06-29 | 1999-11-18 | 1999-12-22 |  | 1999-12-22 | 1999-12-21 |  |  |  | 2001-07-09 | ICOM | ICOM | 2001-07-09 | 2001-07-09 | 2001-07-10 | 2001-07-10 | 2001-07-12 | RADU |  | Mircea Mihut | 2001-07-13 | 2001-07-13 | 2001-07-13 |  |  | K 739 494 | 30 | 0 | 28 | K 739 494 | 135 | 0 | 28 | K 739 494 | 300 | 0 | 28 | N/A | N/A | N/A | N/A | N/A | 35 | 35 | 7/8" | 35 | 35 | 7/8" | 35 | 35 | 7/8" | N/A | N/A | N/A | 140 | ML 23 E 1+0 | Baneasa | MW | 140 | 0.6 |  |  | 23/56 |  | 4x2/8 | 2U-3 |  |  |  | Indoor Comteck | [10 empty] | BX503 | PLOIESTI VEST | 320 | 0.6 |  |  | 23/58 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-05-08 |  |  | 2000-05-31 | 30N02 Ploiesti Vest-Baneasa |  | OK | MIHAI C. | MIHAI C. | [22 empty] | N/A | 2001-07-09 | YRO | SVF | 2000-02-08 | Cristian Croitor | 2000-03-23 | 2000-03-23 | 2000-03-27 | OK | 215 | Movila Vulpii | Prahova | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BX505 | BAICOI_RTC(OPTIMIZARE) | Road Buc-Bra | BX523 Ploiesti Vest_CTA | Muntenia | 25 52'02,3"E | 45 01'58,7"N | 45 01 58.2 | 25 49 12.6 | Romtelecom Baicoi | Romtelecom/ | 2102 | M | C+C+C+ | 2/2/2 | 2202 | Warehouse | 2101 | M | C+ | 2 | 2101 | OK | N/A | N/A | Phase_1 | N/A | N/A | N/A | TE | 34 | T34m | Room | TRANSDATA | OK | TRANSDATA | OK | OK | YesV | OK | DORU | 2000-01-13 | 1999-12-28 |  |  | 2001-06-22 | OK | 1999-12-02 |  | 1999-12-02 | 1999-12-13 | [8 empty] | _ |  |  |  | Yes | [6 empty] | K 739 494 | 130 | 0 | 32 | K 739 494 | 240 | 0 | 32 | K 739 494 | 330 | 0 | 32 | N/A | N/A | N/A | N/A | K 63 55 8 | 36 | 36 | 7/8" | 36 | 36 | 7/8" | 36 | 36 | 7/8" | N/A | N/A | N/A | 216 | ML 15 E 1+0 | Baneasa | MW | 122 | 0.6 |  |  | 15/89 |  | 4X2/8 | 2U-3 |  |  |  | RBS | [10 empty] | BX504 | BUDA | 302 | 0.6 |  |  | 15/84 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-05-12 |  |  | 2000-05-31 | 30N02 Ploiesti Vest-Dr.Taberei |  | OK | DAN | DAN | [21 empty] | 2000-02-01 | N/A | N/A | YRO | SVF | 2000-02-04 | C.Croitor | 2000-03-22 | 2000-03-22 | 2000-03-27 | OK | 299 | Baicoi | Prahova | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BX506 | BANESTI | Road Buc-Bra | BX523 Ploiesti Vest_CTA | Muntenia | 25 47'04,0"E | 45 04'22,2"N | 45 05 40.3 | 25 45 53.4 | Statia de betoane Banesti | Private/ | MAXITE | M | No | 2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | TN | 30 | New 30m tower | SHELTER | SVF | OK | SVF | OK | 2000-02-10 | YesV | OK | DRAGOS | 2000-02-10 | 2000-01-26 |  |  |  | 1999-11-18 | OK |  | OK | 2000-01-14 |  |  |  | N/A | YRO | SVF | OK | OK | 2000-02-03 | 2000-02-03 | 2000-02-04 |  | Yes | Cristian Croitor | 2000-02-26 | 2000-02-22 | 2000-03-18 | 2000-03-21 | OK | AAU | 150 | 0 | 28.5 | AAU | 320 | 0 | 38.5 | N/A | N/A | N/A | N/A |  |  |  |  | MAXITE | 45 | 45 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 90 | ML 23 E 1+0 | Baneasa | MW | 147 | 0.6 |  |  | 23/56 |  | 4x2/8 | 2U-3 |  |  |  | Indoor Comteck | [10 empty] | BX505 | BAICOI_RTC | 327 | 0.6 |  |  | 23/58 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-05-12 |  |  | 2000-05-31 | 30N02 Ploiesti Vest-Dr.Taberei |  | OK | DAN | DAN | [32 empty] | 364 | Banesti | Prahova | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BX507 | CAMPINA_RTC(OPTIMIZARE) | Road Buc-Bra | BX507 Campina_RTC | Muntenia | 25 43'58,0"E | 45 06'48,7"N | 45 07 30.1 | 25 43 58.3 | Bdul. Carol I, nr. 31, Romtelecom Campina | Romtelecom/ | 2202 | M | C+C+C+ | 2/2/2 | N/A | FEEDER | N/A | N/A | N/A | N/A | N/A | OK | N/A | N/A | 2000-11-17 | N/A | N/A |  | B |  |  | ROOM | FIBEC | OK | FIBEC | OK | OK | YesV | OK | DORU | 2000-01-19 | 2000-01-18 |  |  |  | OK | OK |  | OK | OK |  |  | N/A | N/A | YRO | N/A | 2000-11-08 | 2000-11-08 | 2000-11-09 | 2000-11-10 | 2000-11-12 |  | Yes | Cristian Croitor | 2000-11-13 | 2000-11-15 | 2000-11-16 | 2000-11-18 | 2001-06-16 | K 739 494 | 60 | 4 | 31.4 | K 739 494 | 180 | 0 | 31.4 | K 739 494 | 300 | 4 | 31.4 |  |  |  |  | N/A | 30 | 30 | 7/8" | 30 | 30 | 7/8" | 30 | 30 | 7/8" | N/A | N/A | N/A | 180 | N/A | Dr. Taberei | FO | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | [9 empty] | BSC11 | DRUMUL TABEREI |  | N/A |  |  | N/A | [6 empty] | OK | OK | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 30N01 Campina-Dr.Taberei |  | OK | DAN | DAN | [23 empty] | N/A | YRO | SVF | 2000-02-15 |  | 2000-02-18 | 2000-03-27 | 2000-03-27 | OK | 387 | Campina | Prahova | [7 empty] | Site Near=Insertion Point
Phase_1 | CS | BX509 | BREAZA(OPTIMIZARE) | Road Buc-Bra | BX524 Comarnic_RTC | Muntenia | 25 40'59,8"E | 45 10'42,7"N | 45 10 32.0 | 25 40 55.0 | Strada Erou Caporal Miron Caproiu no. 12, Breaza, Jud. Prahova | Bucur Mircea/Bucur Mircea, aceeasi adresa | 2202 | M | C+C+C+ | 2/2/2 | 2202 | Warehouse | MAXITE | M | No | 2 | N/A | OK | N/A | N/A | Phase_1 | N/A | N/A | N/A | TN | 35 | New 35 m tower | SHELTER | VECTOR | OK | VECTOR | OK | OK | YesV | OK | DORU | 2000-01-12 | 1999-12-28 |  |  | 2001-06-22 | 1999-11-18 | OK |  | OK | OK |  |  |  | 2001-06-26 | ICOM | SVF | 2001-06-27 | 2001-06-26 | 2001-06-27 | 2001-06-28 | 2001-06-29 | IVAN | Yes | Ion Soare | 2001-06-29 | 2001-06-29 | 2001-06-29 | 2001-07-05 | 2001-07-11 | K 739 494 | 160 | 0 | 31 | K 739 494 | 250 | 0 | 31 | K 739 494 | 340 | 0 | 31 | N/A | N/A | N/A | N/A | N/A | 45 | 45 | 7/8" | 45 | 45 | 7/8" | 45 | 45 | 7/8" | N/A | N/A | N/A | 270 | ML 23 E 1+0 | Dr. Taberei | MW | 329 | 0.6 |  | 45 | 23/56 |  | 4x2/8 | 2U-3 |  |  |  | Indoor Comteck | [10 empty] | BX510 | COMARNIC | 149 | 0.6 |  | 45 | 23/58 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-05-11 |  |  | 2000-05-31 | 30N01 Comarnic-Dr.taberei |  | OK | DAN | DAN | [22 empty] | N/A | N/A | YRO | SVF | 2000-02-13 | C.Croitor | 2000-03-22 | 2000-03-22 | 2000-03-27 | OK | 465 | Breaza | Prahova | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BX510 | COMARNIC | Road Buc-Bra | BX524 Comarnic_RTC | Muntenia | 25 38'05,0"E | 45 13'55,9"N | 45 14 32.4 | 25 37 31.9 | Strada Ghiosesti no 260, Comarnic Prahova | Ion OTOC/Ion OTOC, Strada Ghiosesti no. 260, Comarnic, Prahova | MAXITE | M | No | 2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | TN | 35 | New 35 m tower | SHELTER | FIBEC | OK | FIBEC | OK | OK | YesV | OK | DORU | 2000-01-19 | 2000-01-18 |  |  |  | 1999-11-17 | OK |  | OK | 1999-12-10 |  |  |  | N/A | YRO | SVF | OK | OK | 2000-02-04 | 2000-02-04 | 2000-02-13 |  | Yes | Cristian Croitor | 2000-02-18 | 2000-03-21 | 2000-03-21 | 2000-03-27 | OK | AAU | 145 | 0 | 31 | AAU | 355 | 0 | 31 | N/A | N/A | N/A | N/A |  |  |  |  | MAXITE | 45 | 45 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 90 | ML 38 E 1+0 | Dr. Taberei | MW | 283 | 0.3 |  | 45 | 38/18 |  | 4x2/8 | 4U-1 |  |  |  | Indoor Comteck | [9 empty] | 1 | BX524 | COMARNIC_RTC | 103 | 0.3 |  | 55 | 38/14 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-10-03 |  |  | 2000-10-03 | 30N01 Comarnic-Dr.taberei |  | OK | DAN | DAN | [32 empty] | 556 | Comarnic | Prahova | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BX511 | POSADA | Road Buc-Bra | BX524 Comarnic_RTC | Muntenia | 25 36'55,6"E | 45 17'25,4"N | 45 17 10.4 | 25 37 06.7 | Strada Posada no. 13, Comarnic (DN1, Km 133) jud. Prahova. | Private/Traba Cornel, 044198827; 094.351.120 | 2101 | M | C+ | 2 | 2101 | [6 empty] | OK |  | N/A |  |  |  | N/A | TN | 40 | New 40m tower. | OUTDOOR | ISAF | OK | ISAF | OK | OK | YesV | OK | AUREL | 2000-03-03 | OK |  |  |  | 1999-11-24 | OK |  | OK | 2000-01-20 |  |  |  | N/A | YRO | ISAF | 2000-02-11 | OK | OK | OK | 2000-03-03 |  | Yes | Cristian Croitor | 2000-03-23 | 2000-03-23 | 2000-03-25 | 2000-03-27 | OK | K 739 494 | 170 | 0 | 35 | K 739 494 | 305 | 0 | 35 | N/A | N/A | N/A | N/A |  |  |  |  | K 63 55 8 | 45 | 45 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 90 | ML 23 E 1+0 | Dr. Taberei | MW | 173 | 0.6 |  | 55 | 23/56 |  | 4x2/8 | 2U-3 |  |  |  | Indoor Comteck | [10 empty] | BX510 | COMARNIC | 353 | 0.6 |  | 45 | 23/58 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-05-11 |  |  | 2000-05-31 | 30N01 Comarnic-Dr.taberei |  | OK | DAN | DAN | [32 empty] | 754 | Comarnic | Prahova | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BX513 | SINAIA_1400 | Road Buc-Bra | BX521 Sinaia_CTA | Muntenia | 45 21 30.3 | 25 31 04.7 | 45 21 19.8 | 25 31 03.5 | DRTV Sinaia Cota 1500 | DRTV/Ivanciu Iuliu - 044312728 | 2202 | M | C+C+C+ | 1/1/1 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | TE | N/A | montant | ROOM | ISAF | OK | ISAF | OK | 1999-12-13 | YesV | OK |  | OK | OK |  |  |  | OK | 1999-10-06 |  | 1999-10-06 | 1999-11-09 |  |  |  | N/A | YRO | YRO | 1999-11-13 | OK | 1999-12-14 | OK | 1999-12-17 |  | Yes | Cristian Croitor | 2000-02-28 | 2000-02-23 | 2000-03-17 | 2000-03-21 | OK | K 739 494 | 0 | 10 | 15 | K 739 494 | 0 | 0 | 15 | K 739 494 | 0 | 10 | 15 |  |  |  |  | No | 30 | 30 | 7/8" | N/A | 32 | 7/8" | 30 | 30 | 7/8" |  |  |  | 0 | ML 23 E 1+0 | Dr. Taberei | MW | 102 | 0.6 |  | 40 | 23/56 |  | 4x2/8 | 2U-3 |  |  | n/a | Indoor Comteck | [9 empty] | 1 | BX521 | SINAIA POSTA | 282 | 0.6 |  | 20 | 23/58 | [6 empty] | N/A | N/A | OK | OK | OK | OK | OK | OK | OK | 2000-10-01 |  |  | 2000-10-25 | 30N01 Sinaia-Dr.Taberei |  | N/A | COSMIN | COSMIN | [32 empty] | 1457 | Sinaia | Prahova | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BX514 | SINAIA PISCUL CAINELUI | Road Buc-Bra | BX521 Sinaia_CTA | Muntenia | 45 20 95 | 25 33 553 | 45 20 46.9 | 25 33 21.9 | DRTV Piscul Cainelui - Sinaia | DRTV/SEVERIN 092624577; Alexandrescu (cabanier) - 044315492 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | 2000-06-27 |  |  |  | N/A | TE |  | montanti | OUTDOOR | ISAF | OK | ISAF | OK | OK | YesV | OK |  | 2000-01-10 | 1999-12-28 |  |  |  | OK | OK |  | OK | OK |  |  |  | N/A | YRO | ISAF | 2000-02-04 | OK | 2000-02-29 | OK | 2000-03-03 |  | Yes | Cristian Croitor | 2000-03-06 | 2000-02-08 | 2000-03-18 | 2000-03-21 | OK | K 739 494 | 190 | 6 | 12.5 | K 739 494 | 270 | 4 | 15 | K 739 494 | 350 | 6 | 15 |  |  |  |  | N0 | 25 | 25 | 7/8" | 25 | 25 | 7/8" | 25 | 25 | 7/8" |  |  |  | 150 | ML 15 E 1+0 | Dr. Taberei | MW | 288 | 0.6 |  |  | 23/58 |  | 4x2/8 |  |  |  |  | Indoor Comteck | [10 empty] | BX513 | SINAIA_1400 | 108 | 0.6 |  |  | 23/56 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-05-09 |  |  | 2000-05-31 | 30N01 Sinaia-Dr.Taberei |  | N/A | COSMIN | COSMIN | [32 empty] | 945 | Sinaia | Prahova | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BX515 | BUSTENI _RTC | Road Buc-Bra | BX515 Busteni_RTC | Muntenia | 25 32' 07" E | 45 24' 52.2" N | 45 24 56.9 | 25 32 11.4 | Busteni, Str. Libertatii, nr. 89 | Romtelecom/ | MAXITE | M | No | 2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | TN | 35 | P35m | N/A | FIBEC | OK | FIBEC | OK | OK | YesV | OK |  | 2000-01-19 | 2000-01-18 |  |  |  | OK | OK |  | OK | 1999-12-10 |  |  |  | 00:0009 | ETR | Electotrade | OK | OK | OK | OK | 2000-02-05 |  | Yes | Cristian Croitor | 2000-02-20 | 2000-03-30 | 2000-03-30 | 2000-04-10 | OK | AAU | 50 | 0 | 31 | AAU | 175 | 0 | 31 | N/A | N/A | N/A | N/A |  |  |  |  | MAXITE | 45 | 45 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 90 | N/A | Dr. Taberei | FO | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | Indoor Comteck | N/A | [9 empty] | BSC11 | DRUMUL TABEREI |  | N/A |  |  | N/A | [6 empty] | OK | OK | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 30N01 Busteni-Dr.Taberei |  | OK | DAN | DAN | [32 empty] | 925 | Busteni | Prahova | [7 empty] | Site Near=Insertion Point
Phase_1 | CS | BX517 | AZUGA | Road Buc-Bra | BX525 Azuga_RTC | Transilvania | 25 33' 20" E | 45 26' 40.4" N | 45 26 45.3 | 25 33 10.6 | Teren apartinand Primaria Azuga langa gara, in spatele cosurilor. | Primaria Azuga/Moraru, 044326720; 044326728 | 2101 | M | C+C+C+ | 4 | 2102 | [6 empty] | OK |  | N/A |  |  |  | N/A | TN | 40 | New 40m tower | OUTDOOR | IMSAT | OK | IMSAT | OK | OK | YesV | OK | AUREL | 2000-05-08 | OK |  |  |  | OK | OK |  | OK | 2000-05-08 |  |  |  | NA | YRO | YRO | 2000-05-08 | OK | 2000-05-09 | 2000-05-09 | 2000-05-10 |  | Yes | Alexandru Bucur | 25-Mai-00 | 2000-05-25 | 2000-05-25 | 2000-05-26 | OK | K 739 494 | 40 | 0 | 38 | K 739 494 | 170 | 0 | 38 | N/A | N/A | N/A | N/A |  |  |  |  | K 63 55 8 | 45 | 45 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 90 | ML 38 E 1+0 | Dr. Taberei | MW | 96 | 0.3 |  |  | 38/18 |  | 4x2/8 | 2U-3 |  |  |  | Indoor Comteck | [9 empty] | 1 | BX525 | AZUGA_RTC | 276 | 0.3 |  |  | 38/14 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-10-03 |  |  | 2000-10-03 | 30N01 Azuga-Dr.Taberei |  | N/A | DAN | DAN | [32 empty] | 954 | Azuga | Prahova | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BX518 | URSOAIA | Road Buc-Bra | BV001 Brasov_CTA | Transilvania | 25 33'42,2"E | 45 28'12,0"N | 45 28 05.7 | 25 33 41.3 | Zona Malului Ursului, Predeal, jud. Brasov(DN1 intre Predeal si Azuga) | Romsilva Ploiesti Directia Silvica/Puscasu Gheorghe, 092650667 | 2101 | M | C+ | 2 | 2101 | [6 empty] | OK |  | N/A |  |  |  | N/A | TN | 40 | New 40m tower | OUTDOOR | IMSAT | OK | IMSAT | OK | OK | YesV | OK | AUREL | 2000-07-04 | 2000-06-29 |  |  |  | OK | OK |  | OK | 2000-07-03 |  |  |  | NA | YRO | YRO | 2000-07-04 | OK | 2000-07-05 | 2000-07-06 | 2000-07-10 |  | Yes | Burghiu Petrica | 2000-07-12 | 2000-07-12 | 2000-07-12 | 2000-08-02 | ok | K 739 494 | 10 | 0 | 45 | K 739 494 | 145 | 0 | 45 | N/A | N/A | N/A | N/A |  |  |  |  | K 63 55 8 | 55 | 55 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 110 |  | Brasov | MW | 3 | 0.6 |  | 50 | 15/84 |  | 4x2/8 | 2U-3 |  |  |  | Indoor Comteck | [9 empty] | 1 | BV505 | POSTAVARU | 183 | 0.6 |  |  | 15/89 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-07-04 |  |  | 2000-08-09 | 30N04 conectare locala |  | OK | SORIN UNTARU | [33 empty] | 968 | Malul Ursului | Prahova | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BX519 | PREDEAL_RTC | Road Buc-Bra | BV001 Brasov_CTA | Transilvania | 25 34' 30.6" E | 45 30' 29.8" N | 45 30 27.9 | 25 34 30.4 | Posta Predeal, Str. Panduri nr. 8, Predeal | Romtelecom/Arsene, 068456033; 068455875 | MAXITE | M | No | 2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | TN | 15 | P12m | ROOM | IMSAT | OK | IMSAT | OK | OK | YesV | OK | AUREL | 2000-01-31 | 2000-01-30 |  |  |  | 1999-11-30 | OK |  | OK | 2000-01-27 |  |  |  | 00:0009 | ETR | Electotrade | OK | OK | OK | OK | 2000-02-05 |  | Yes | Cristian Croitor | 2000-02-23 | 2000-03-30 | 2000-03-30 | 2000-04-10 | OK | AAU | 10 | 7 | 25 | AAU | 180 | 4 | 25 | N/A | N/A | N/A | N/A |  |  |  |  | MAXITE | 40 | 40 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 80 |  | Brasov | MW | 323.6 | 0.6 |  |  | 23/56 |  | 4x2/8 | 4U-1 |  |  |  | Indoor Comteck | [9 empty] | 1 | BV505 | POSTAVARU | 176 | 0.6 |  |  | 23/58 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-10-03 |  |  | 2000-10-03 | 30N04 conectare locala |  | OK | DAN | DAN | [32 empty] | 767 | Predeal | Brasov | [7 empty] | 1 |  |  | 1
Phase_3 | CS | BX520 | BAICOI_RTC_ORAS | Road Buc-Bra | BX523 Ploiesti Vest_CTA | Muntenia | 45 02 05.5 | 25 52 36.6 |  |  |  |  | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [17 empty] | SVF |  | @ | 2001-08-15 | 2001-08-30 |  |  | Doru |  |  | 2001-06-27 |  |  |  | 2001-07-16 |  |  |  |  | 2001-06-27 | [48 empty] | Baneasa | MW | [12 empty] | XC30523/4 | [9 empty] | BX504 | BAICOI_RTC | [24 empty] | 30N07 Ploiesti Vest-Baneasa |  | OK
Phase_1 | TM | BX521 | SINAIA POSTA | Road Buc-Bra | BX521 Sinaia_CTA | Muntenia | 45 21 35.3 | 25 31 01.6 | 45 21 01.4 | 25 33 00.0 | Bdul. Carol 1, nr. 33 | Romtelecom/Director centru :TECU - 094838809 | N/A | N/A | N/A | N/A | N/A | [8 empty] | N/A |  |  |  | N/A | B |  |  | ROOM | ISAF | OK | ISAF | OK | 1999-12-17 | YesV | OK | AUREL | OK | 1999-12-16 |  |  |  | N/A | OK |  | OK | OK |  |  |  | N/A | YRO | ISAF | N/A | N/A | N/A | N/A | N/A |  | Yes | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 0 | N/A | Dr. Taberei | FO | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | TMR 9202 | 30521 | Phase_1 | [7 empty] | 1 | BSC11 | DRUMUL TABEREI | N/A | N/A |  |  | N/A | [6 empty] | OK | OK | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 30N01 Sinaia-Dr.Taberei |  | N/A | COSMIN | COSMIN | [32 empty] | 920 | Sinaia | Prahova | [7 empty] | Site Near=Insertion Point
Phase_1 | TM | BX523 | PLOIESTI VEST CTA | Road Buc-Bra | BX523 Ploiesti Vest_CTA | Muntenia | 44 56 08.6 | 25 59 32.9 | 44 56 08.6 | 25 59 32.9 | Centrala Telefonica Ploiesti Vest, Strada Cosminelor no 8. | Romtelecom/Director Tehnic Romtelecom PRAHOVA - Ciobanas. | N/A | N/A | N/A | N/A | N/A | [8 empty] | N/A |  |  |  | N/A | B | 12 | T4m | ROOM | TRANSDATA | OK | TRANSDATA | OK | OK | YesV | OK | DORU | OK | OK |  |  |  | OK | OK |  | OK | 1999-12-09 |  |  |  | N/A | YRO | YRO | N/A | N/A | N/A | N/A | N/A |  | Yes | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 0 | N/A | Baneasa | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | 4U-1 |  |  |  | TMR 9202 | 30523 | 2000-04-19 | [8 empty] | BSC21 | BSC BANEASA | N/A | N/A |  |  | N/A | [6 empty] | OK | OK | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A |  | N/A | DAN | DAN | [32 empty] | 163 | Ploiesti | Prahova | [7 empty] | Site Near=Insertion Point
Phase_1 | TM | BX524 | COMARNIC_RTC | Road Buc-Bra | BX524 Comarnic_RTC | Muntenia | 45 14 30.8 | 25 38 02.5 | 45 14 30.8 | 25 38 02.5 | Oficiul Comercial Romtelecom Comarnic | Romtelecom/Director Tehnic Romtelecom PRAHOVA - Ciobanas. | N/A | N/A | N/A | N/A | N/A | [8 empty] | N/A |  |  |  | N/A | B | 8 | C3m | ROOM | FIBEC | OK | FIBEC | OK | OK | YesV | OK | DRAGOS | OK | 2000-01-18 |  |  |  | N/A | OK |  | OK | 2000-01-17 |  |  |  | N/A | YRO | YRO | N/A | N/A | N/A | N/A | N/A |  | Yes | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 0 | N/A | Dr. Taberei | FO | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | Indoor Comteck | 30524 | 2000-04-19 | [7 empty] | 1 | BSC11 | DRUMUL TABEREI | N/A | N/A |  |  | N/A | [6 empty] | OK | OK | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A |  | OK | DAN | DAN | [32 empty] | 536 | Comarnic | Prahova | [7 empty] | Site Near=Insertion Point
Phase_1 | TM | BX525 | AZUGA_RTC | Road Buc-Bra | BX525 Azuga_RTC | Transilvania | 45 26 40.6 | 25 33 20.1 | 45 26 40.6 | 25 33 20.1 | Oficiul Comercial Romtelecom Comarnic | Romtelecom/Director Tehnic Romtelecom PRAHOVA - Ciobanas. | N/A | N/A | N/A | N/A | N/A | [8 empty] | N/A |  |  |  | N/A | B | 12 | Suport MW 1m | ROOM | IMSAT | OK | IMSAT | OK | 2000-02-14 | YesV | OK | AUREL | OK | 2000-02-10 |  |  |  | OK | 2000-02-08 |  | 2000-02-08 | OK |  |  |  | 00:0009 | ETR | N/A | N/A | N/A | N/A | N/A | N/A |  | Yes | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 0 | N/A | Dr. Taberei | FO | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | TMR 9202 | 30525 | 2000-04-19 | [7 empty] | 1 | BSC11 | DRUMUL TABEREI | N/A | N/A |  |  | N/A | [6 empty] | OK | OK | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A |  | N/A | DAN | DAN | [32 empty] | 950 | Azuga | Prahova | [7 empty] | Site Near=Insertion Point
Phase_1 | CS | BX601 | LILIECI | Road Buc-Fet-Con | BX604 Urziceni | Dobrogea | 44 33'10,8"N | 26 22'31,3"E | 44 33 06.7 | 26 22 34.6 | Stan Ion, Comuna Lilieci, Jud. Ialomita | /Stan Ion, Comuna Lilieci, Jud Ialomita | MAXITE | M | No | 2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | TN | 50 | New 50m tower | SHELTER | SVF | OK | SVF | OK | OK | YesV | OK | DRAGOS | 2000-03-01 | 2000-01-21 |  |  |  | 1999-11-19 | OK |  | OK | 2000-01-14 |  |  |  | 00:0009 | ETR | Electotrade | OK | OK | 2000-02-07 | 2000-02-07 | 2000-02-12 |  | Yes | Theo Radoi | 2000-03-14 | 2000-03-24 | 2000-03-24 | 2000-03-29 | OK | AAU | 40 | 5 | 48 | AAU | 0 | 5 | 48 | N/A | N/A | N/A | N/A |  |  |  |  | MAXITE | 55 | 55 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 110 | ML 15 E 1+0 | Dr. Taberei | MW | 42 | 0.6 |  |  | 15/89 |  | 4x2/8 | 2U-3 |  |  |  | Indoor Comteck | [10 empty] | BX602 | MOVILITA | 222 | 0.6 |  |  | 15/84 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-06-07 |  |  | 2000-09-05 | 30N01 Urziceni-Dr.Taberei |  | N/A | Craiu | Craiu | [32 empty] | 75 | Lilieci | Ialomita | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BX602 | MOVILITA | Road Buc-Slo-Con | BX604 Urziceni | Dobrogea | 44 37'37,2"N | 26 28'06,5"E | 44 37 57.8 | 26 27 56.1 | Comuna Movilita, Jud. Ialomita | /Iancu Vasilica, Movilita, Jud Ialomita | MAXITE | M | No | 2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | TN | 50 | New 50m tower | SHELTER | SVF | OK | SVF | OK | OK | YesV | OK | DRAGOS | 2000-03-01 | 2000-01-28 |  |  |  | 1999-11-19 | OK |  | OK | 2000-01-27 |  |  |  | 00:0009 | ETR | Electotrade | OK | OK | 2000-02-07 | 2000-02-07 | 2000-02-12 |  | Yes | Theo Radoi | 2000-03-24 | 2000-03-24 | 2000-03-24 | 2000-03-29 | OK | AAU | 60 | 5 | 48 | AAU | 0 | 5 | 48 | N/A | N/A | N/A | N/A |  |  |  |  | MAXITE | 55 | 55 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 110 | ML 23 E 1+0 | Dr. Taberei | MW | 51 | 0.6 |  |  | 23/56 |  | 4x2/8 |  |  |  |  | Indoor Comteck | [9 empty] | 1 | BX603 | COSERENI | 231 | 0.6 |  |  | 23/58 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-10-03 |  |  | 2000-10-03 | 30N01 Urziceni-Dr.Taberei |  | N/A | CRAIU | CRAIU | [32 empty] | 54 | Movilita | Ialomita | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BX603 | COSERENI | Road Buc-Slo-Con | BX604 Urziceni | Dobrogea | 44 40'06,5"N | 26 32'33,5"E | 44 40 41.0 | 26 34 08.2 | Cosereni, Jud. Ialomita | Private - dl. Bors Ion/ | 2101 | M | C+ | 2 | 2101 | [6 empty] | OK |  | N/A |  |  |  | N/A | TN | 50 | New 50m tower | OUTDOOR | SVF | OK | SVF | OK | OK | YesV | OK | DRAGOS | 2000-03-03 | OK |  |  |  | 2000-02-02 | OK |  | OK | 2000-02-07 |  |  |  | 00:0009 | ETR | Electotrade | OK | OK | OK | OK | OK |  | Yes | Theo Radoi | 2000-03-23 | 2000-03-23 | 2000-03-23 | 2000-03-24 | OK | K 739 494 | 60 | 5 | 48 | K 739 494 | 230 | 5 | 48 | N/A | N/A | N/A | N/A |  |  |  |  | K 63 55 8 | 71 | 71 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 142 | ML 23 E 1+0 | Dr. Taberei | MW | 59 | 0.6 | 48 |  | 23/58 |  | 4x2/8 | [14 empty] | 1 | BX604 | URZICENI | 239 | 0.6 | 48 |  | 23/56 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-06-08 |  |  | 2000-06-13 | 30N01 Urziceni-Dr.Taberei |  | N/A | SORIN UNTARU | SORIN UNTARU | [32 empty] | 72 | Cosereni | Ialomita | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BX604 | URZICENI | Road Buc-Slo-Con | BX604 Urziceni | Dobrogea | 44 42'53,9"N | 26 38'44,9"E | 44 42 57.1 | 26 38 46.1 | ROMTELECOM URZICENI | Romtelecom/ | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | 2000-06-27 |  |  |  | N/A | TE |  |  | OUTDOOR | ORION | OK | ORION | OK | OK | YesV | OK | MUGUREL | 2000-01-07 | 1999-11-25 |  |  |  | OK | OK |  | OK | 1999-11-24 |  |  |  | 00:0009 | ETR | Electotrade | OK | OK | OK | OK | 2000-02-05 |  | Yes | Theo Radoi | 2000-02-20 | 2000-03-23 | 2000-03-23 | 2000-03-24 | OK | K 739 494 | 0 | 5 | 49 | K 739 494 | 110 | 5 | 49 | K 739 494 | 240 | 5 | 49 | [5 empty] | 65 | 65 | 1 1/4" | 65 | 65 | 11/4" | 65 | 65 | 11/4" |  |  |  | 390 | N/A | Dr. Taberei | FO | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | RBS | 30604 | Phase_1 | [7 empty] | 1 | BSC11 | DRUMUL TABEREI |  | N/A |  |  | N/A | [6 empty] | OK | OK | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 30N01 Urziceni-Dr.Taberei |  | N/A | CRAIU | CRAIU | [32 empty] | 54 | Urziceni | Ialomita | [7 empty] | Site Near=Insertion Point
Phase_1 | CS | BX605 | ION ROATA | Road Buc-Slo-Con | BX604 Urziceni | Dobrogea | 44 40'12,4"N | 26 45'37,7"E | 44 40 07.0 | 26 45 47.5 | Ion Roata, judetul Ialomita | Private/Ilie Ionel - 092398163 | MAXITE | M | No | 2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | TN | 50 | New 50m tower | SHELTER | ORION | OK | ORION | OK | OK | YesV | OK | MUGUREL | 2000-02-21 | 1999-12-22 |  |  |  | 1999-11-15 | OK |  | OK | 1999-12-21 |  |  |  | 00:0009 | ETR | Electotrade | OK | OK | 2000-02-07 | 2000-02-10 | 2000-02-12 |  | Yes | Theo Radoi | 2000-03-23 | 2000-03-23 | 2000-03-23 | 2000-03-24 | OK | AAU | 110 | 5 | 50 | AAU | 285 | 5 | 50 | N/A | N/A | N/A | N/A |  |  |  |  | MAXITE | 70 | 70 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 140 | ML 15 E 1+0 | Dr. Taberei | MW | 299 | 0.6 |  |  | 15/89 |  | 4x2/8 | 2U-3 |  |  |  | Indoor Comteck | [9 empty] | 1 | BX604 | URZICENI | 119 | 0.6 |  |  | 15/84 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-06-07 |  |  | 2000-06-07 | 30N02 Urziceni-Dr.Taberei |  | N/A | MIHAI C. | MIHAI C. | [32 empty] | 49 | Ion Roata | Ialomita | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BX606 | BALACIU | Road Buc-Slo-Con | BX604 Urziceni | Dobrogea | 44 38'11,7"N | 26 52'54,6"E | 44 38 07.6 | 26 53 20.6 | Oficiul Comercial Romtelecom Balaciu | Romtelecom/Stoica Sorin, 092.873.213 | 2101 | M | C+ | 2 | 2101 | [6 empty] | OK |  | N/A |  |  |  | N/A | TE | 30 | Existing 30m tower | OUTDOOR | ORION | OK | ORION | OK | OK | YesV | OK | MUGUREL | 2000-02-21 | OK |  |  |  | 2000-02-02 | 2000-01-19 |  | 2000-01-19 | 2000-02-07 |  |  |  | 00:0009 | ETR | Electotrade | OK | OK | OK | OK | 2000-03-02 |  | Yes | Theo Radoi | 2000-03-22 | 2000-03-22 | 2000-03-22 | 2000-03-24 | OK | K 739 494 | 120 | 2 | 27 | K 739 494 | 290 | 2 | 27 | N/A | N/A | N/A | N/A |  |  |  |  | K 63 55 8 | 40 | 40 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 80 | ML 15 E 1+0 | Dr. Taberei | MW | 290 | 0.6 | 26 |  | 15/84 |  | 4x2/8 |  |  |  |  | RBS | [10 empty] | BX605 | ION ROATA | 110 | 0.6 | 48 |  | 15/89 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-06-07 |  |  | 2000-06-07 | 30N02 Urziceni-Dr.Taberei |  | N/A | DAN | DAN | [32 empty] | 40 | Balaciu | Ialomita | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BX607 | CAZANESTI(OPTIMIZARE) | Road Buc-Slo-Con | BX604 Urziceni | Dobrogea | 44 37'05,7"N | 27 00'49,8"E | 44 37 05.0 | 27 00 48 | Comuna Cazanesti | Romtelecom/ | 2202 | M | C+C+C+ | 2/2/2 | 2202 | TM206_CUBULCUT_RTC | 2101 | M | C+ | 2 | Yes | 2001-04-26 | N/A | N/A | Phase_1 | N/A | N/A | N/A | TN | 50 | New 50m tower | SHELTER |  | OK |  |  |  | YesV |  |  |  |  | 1999-12-22 |  | 2001-05-16 | 1999-11-15 | OK |  | OK | 1999-12-21 |  |  |  | 2001-05-22 | ICOM | VECTOR | 2001-05-23 | 2001-05-23 | 2001-05-25 | 2001-05-26 | 2001-06-03 | VLAD | Yes | Mircea Mihut | 2001-06-04 | 2001-06-04 | 2001-06-04 |  |  | K 739 494 | 120 | 0 | 48 | K 739 494 | 210 | 0 | 48 | K 739 494 | 295 | 0 | 48 | N/A | N/A | N/A | N/A | N/A | 56 | 56 | 1 1/4" | 56 | 56 | 1 1/4" | 56 | 56 | 1 1/4" | N/A | N/A | N/A | 336 | ML 15 E 1+0 | Dr. Taberei | MW | 281 | 0.6 | 48 |  | 15/89 |  | 4x2/8 | [14 empty] | 1 | BX606 | BALACIU | 101 | 0.6 | 26 |  | 15/84 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-06-08 |  |  | 2000-06-13 | 30N02 Urziceni-Dr.Taberei |  | N/A | MIHAI C. | [23 empty] | 00:0009 | N/A | ETR | RAD | 2000-02-12 |  | OK | 2000-03-22 | 2000-03-24 | OK | 35 | Cazanesti | Ialomita | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BX608 | ANDRASESTI | Road Buc-Slo-Con | BX604 Urziceni | Dobrogea | 44 34'39,2"N | 27 08'17,3"E | 44 34 36.2 | 27 08 19.8 | Andrasesti, Jud. Ialomita | /State Zainea | MAXITE | M | No | 2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | TN | 50 | New 50m tower | SHELTER | ORION | OK | ORION | OK | OK | YesV | OK | MUGUREL | 2000-02-21 | 1999-12-22 |  |  |  | 1999-11-15 | OK |  | OK | OK |  |  |  | 00:0008 | ETR | N/A | OK | OK | 2000-02-03 | OK | OK |  | Yes | Theo Radoi | 2000-03-22 | 2000-03-22 | 2000-03-22 | 2000-03-24 | OK | AAU | 95 | 5 | 48 | AAU | 275 | 5 | 48 | N/A | N/A | N/A | N/A |  |  |  |  | MAXITE | 70 | 70 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 140 | ML 15 E 1+0 | Dr. Taberei | MW | 294 | 0.6 |  |  | 15/84 |  | 4x2/8 | 2U-3 |  |  |  | Indoor Comteck | [9 empty] | 1 | BX607 | CAZANESTI(OPTIMIZARE) | 114 | 0.6 |  |  | 15/89 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-06-07 |  |  | 2000-06-07 | 30N02 Urziceni-Dr.Taberei |  | N/A | MIHAI C. | MIHAI C. | [32 empty] | 36 | Andrasesti | Ialomita | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BX609 | PERIETI | Road Buc-Slo-Con | BX615 Slobozia_RTC | Dobrogea | 44 34'13,7"N | 27 15'14,0"E | 44 34 07.2 | 27 15 06.1 | Comuna Perieti, jud. Ialomita | /Tvetanschi Gheorghe | MAXITE | M | No | 2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | TN | 50 | New 50m tower | SHELTER | ORION | OK | ORION | OK | OK | YesV | OK | MUGUREL | 2000-01-22 | 2000-01-06 |  |  |  | 1999-11-15 | OK |  | OK | 2000-01-04 |  |  |  | 00:0009 | ETR | Electotrade | OK | OK | 2000-02-09 | OK | 2000-02-15 |  | Yes | Theo Radoi | 2000-03-28 | 2000-03-28 | 2000-03-28 | 2000-04-06 | OK | AAU | 95 | 5 | 48 | AAU | 275 | 5 | 48 | N/A | N/A | N/A | N/A |  |  |  |  | MAXITE | 70 | 70 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 140 | ML 15 E 1+0 | Dr. Taberei | MW | 92 | 1.2 |  |  | 15/89 | [6 empty] | Indoor Comteck | [9 empty] | 1 | BX610 | SLOBOZIA | 272 | 0.6 |  |  | 15/84 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-05-05 |  | 2001-03-02 |  | 30N01 Slobozia-Dr.Taberei |  | OK | MIHAI C. | MIHAI C. | [32 empty] | 28 | Perieti | Ialomita | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BX610 | BX610 | Road Buc-Slo-Con | BX615 Slobozia_RTC | Dobrogea | 44 33 53.8 | 27 21 28.2 | 44 33 53.8 | 27 21 28.2 | Bulevardul Unirii bl. U12, Sc.A | Private/MUNTEANU HONORIU, 043214407; Bdul. Unirii, bl. U12, sc. B, et. VII, ap. 75 | 2202 | M/E | C+C+C+ | 2/2/2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | B | 36 | 6m + 4m | ROOM | ORION | OK | ORION | OK | 1999-11-08 | YesV | OK | MUGUREL | 1999-11-08 | 1999-11-02 |  |  |  | 1999-10-06 | OK |  | OK | 2000-01-31 |  |  |  | 99:0003 | ETR | N/A | 1999-11-30 | OK | OK | OK | 1999-12-17 |  | Yes | Cristian Croitor | 2000-03-09 | 2000-05-02 | 2000-05-02 | 2000-05-03 | OK | K 739 494 | 70 | 2 | 38.5 | K 739 494 | 155 | 0 | 39.5 | K 739 494 | 275 | 3 | 39.5 |  |  |  |  | N/A | 20 | 20 | 7/8" | 20 | 20 | 7/8" | 25 | 25 | 7/8 " |  |  |  | 130 | N/A | Dr. Taberei | CABLU | Cablu | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | Indoor Comteck | 30610 | Phase_1 |  | 31610 | [5 empty] | 1 | BX615 | SLOBOZIA RTC | CABLU | N/A |  |  | N/A | [6 empty] | OK | OK | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 30N01 Slobozia-Dr.Taberei |  | OK | MIHAI C. | MIHAI C. | [32 empty] | 24 | Slobozia | Ialomita | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BX611 | BUCU | Road Buc-Slo-Con | BX615 Slobozia_RTC | Dobrogea | 44 37'36,6"N | 27 29'47,0"E | 44 36 34.3 | 27 29 26.1 | Comuna Bucu, Siloz comcereal pe dreapta (sens de mers Buc-Cta) | Private/Nespecificat - portar non stop | 2101 | M | C+ | 2 | 2101 | [6 empty] | OK |  | 2000-06-27 |  |  |  | 65 | SILO | 65 | 4m + 4m | OUTDOOR | ORION | OK | ORION | OK | 1999-10-29 | YesV | OK | MUGUREL | 1999-10-29 | 1999-11-02 |  |  |  | 1999-10-08 | OK |  | OK | OK |  |  |  | 00:0008 | ETR | N/A | OK | OK | 2000-02-01 | 2000-02-02 | 2000-02-09 |  | Yes | Theo Radoi | 2000-03-28 | 2000-03-28 | 2000-03-28 | 2000-04-19 | OK | K 739 494 | 90 | 8 | 66.5 | K 739 494 | 235 | 8 | 66.5 | N/A | N/A | N/A | N/A |  |  |  |  | K 63 55 8 | 10 | 10 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 20 | ML 15 E 1+0 | Dr. Taberei | MW | 244 | 0.6 |  |  | 15/89 |  | 4x2/8 | 4U-1 |  |  |  | Indoor Comteck | [9 empty] | 1 | BX610 | SLOBOZIA | 64 | 0.6 |  |  | 15/84 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-06-09 |  |  | 2000-09-05 | 30N02 Slobozia-Dr. Taberei |  | OK | DAN | DAN | [32 empty] | 31 | Bucu | Ialomita | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BX612 | TANDAREI | Road Buc-Slo-Con | BX615 Slobozia_RTC | Dobrogea | 44 37'50,5"N | 27 36'22,9"E | 44 38 04.1 | 27 36 34.7 | Sos. Bucuresti-Constanta nr. 1 | /Rublea George, 043215720, fax. 043211868 | 2101 | M | C+ | 2 | 2101 | [6 empty] | OK |  | N/A |  |  |  | N/A | TN | 50 | New 50m tower | OUTDOOR | SERACOM | OK | SERACOM | OK | 2000-03-06 | YesV | OK | DRAGOS | OK | OK |  |  |  | 1999-11-11 | OK |  | OK | 2000-01-24 |  |  |  | 00:0009 | ETR | Electotrade | OK | OK | OK | OK | 2000-03-10 |  | Yes | Theo Radoi | 2000-03-29 | 2000-03-29 | 2000-03-29 | 2000-04-06 | OK | K 739 494 | 75 | 5 | 48 | K 739 494 | 0 | 5 | 48 | N/A | N/A | N/A | N/A |  |  |  |  | K 63 55 8 | 55 | 55 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 110 | ML 23 E 1+0 | Dr. Taberei | MW | 255 | 1.2 |  |  | 23/56 |  | 4x2/8 |  |  |  |  | RBS | [10 empty] | BX611 | BUCU | 75 | 1.2 |  |  | 23/58 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-06-09 |  | 2000-08-23 | 2000-09-05 | 30N02 Slobozia-Dr. Taberei |  | OK | SORIN UNTARU | SORIN UNTARU | [32 empty] | 19 | Tandarei | Ialomita | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BX613 | MIHAIL KOGALNICEANU 1(OPTIMIZARE) | Road Buc-Slo-Con | BX615 Slobozia_RTC | Dobrogea | 44 39'34,7"N | 27 43'40,1"E | 44 39 27.3 | 27 43 21.9 | DN2A LANGA U.M. 01445 TANDAREI | Private/MUNTEANU HONORIU, 043214407; Bdul. Unirii, bl. U12, sc. B, et. VII, ap. 75 | MAXITE | M | 1 | 2 | N/A | Warehouse | 2101 | M | C+ | 2 | Yes |  | N/A | N/A | Phase_1 | N/A | N/A | N/A | TN | 50 | New 50m tower | SHELTER |  | OK |  |  |  | YesV |  |  |  |  | OK |  | 2001-06-14 | 1999-11-13 | OK |  | OK | 2000-01-06 |  |  |  | 2001-05-22 | ICOM | SVF | 2001-06-13 | 2001-06-13 | 2001-06-14 | 2001-06-17 | 2001-06-21 | IVAN | Yes | Valentin C-tinescu | 2001-06-22 | 2001-06-22 | 2001-06-22 |  |  | AAU | 60 | 5 | 48 | AAU | 240 | 5 | 48 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | MAXITE | 51 | 51 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 110 | ML 23 E 1+0 | Dr. Taberei | MW | 251 | 1.2 |  |  | 23/58 |  | 4x2/8 | [15 empty] | BX612 | TANDAREI | 71 | 1.2 |  |  | 23/56 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-06-09 |  |  | 2000-09-05 | 30N02 Slobozia-Dr. Taberei |  | OK | SORIN UNTARU | SORIN UNTARU | [21 empty] | 2000-02-26 | N/A | 00:0009 | ETR | RAD | 2000-03-02 |  | OK | 2000-03-29 | 2000-04-06 | OK | 12 | Mihail Kogalniceanu | Ialomita | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BX614 | GIURGENI | Road Buc-Slo-Con | BX615 Slobozia_RTC | Dobrogea | 44 42'47,1"N | 27 50'59,1"E | 44 43 20.3 | 27 51 08.9 | Teren Agricol IAS Giurgeni. | IAS Giurgeni/Dinu Valeriu, Primar Giurgeni, 043/277010 | 2101 | M | C+ | 2 | 2101 | [6 empty] | OK |  | N/A |  |  |  | N/A | TN | 50 | New 50m tower | OUTDOOR | DIEKAT | OK | DIEKAT | OK | 2000-03-06 | YesV | OK | AUREL | 2000-03-06 | OK |  |  |  | 1999-12-14 | 2000-01-13 |  | 2000-01-13 | OK |  |  |  | 00:0009 | ETR | Electotrade | OK | OK | OK | OK | 2000-03-10 |  | Yes | Theo Radoi | 2000-03-29 | 2000-03-29 | 2000-03-29 | 2000-04-06 | OK | K 739 494 | 25 | 5 | 48.5 | K 739 494 | 230 | 5 | 48.5 | N/A | N/A | N/A | N/A |  |  |  |  | K 63 55 8 | 55 | 55 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 110 | ML 15 E 1+0 | Dr. Taberei | MW | 238 | 0.6 |  |  | 15/84 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [10 empty] | BX613 | MIHAIL KOGALNICEANU 1(OPTIMIZARE) | 238 | 0.6 |  |  | 15/89 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-06-09 |  |  | 2000-09-05 | 30N02 Slobozia-Dr. Taberei |  | OK | DAN | DAN | [32 empty] | 7 | Giurgeni | Ialomita | [7 empty] | 1 |  |  | 1
Phase_1 | TM | BX615 | SLOBOZIA RTC | Road Buc-Slo-Con | BX615 Slobozia_RTC | Dobrogea | 44 33 53.8 | 27 21 30.0 | 44 33 53.8 | 27 21 30.0 | Romtelecom Slobozia, B-dul Unirii | RTC/ | N/A | N/A | N/A | N/A | N/A | [8 empty] | N/A |  |  |  | N/A | B | 15 | Not necessary | ROOM | ORION | OK | ORION | OK | OK | YesV | OK | MUGUREL | OK | OK |  |  |  | OK | OK |  | OK | OK |  |  |  | OK | ETR | N/A | N/A | N/A | N/A | N/A | N/A |  | Yes | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 0 | N/A | Dr. Taberei | FO | CABLU | N/A | N/A | N/A | N/A |  | N/A | [15 empty] | BSC11 | DRUMUL TABEREI | N/A | N/A | N/A | N/A | N/A | [6 empty] | OK | OK | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A |  | OK | SORIN UNTARU | SORIN UNTARU | [32 empty] | 24 | Slobozia | Ialomita | [7 empty] | Site Near=Insertion Point
Phase_1 | CS | BX651 | HARSOVA | Road Buc-Slo-Con | YX616 Mihail Kogalniceanu_RTC | Dobrogea | 44 41'21,7"N | 27 55'49,4"E | 44 41 21.7 | 27 55 49.4 | DRTV Harsova | DRTV/ | 2202 | M | C+C+C+ | 2/2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | TE | 80 | Exusting DRTV 80m tower | ROOM | ORION | OK | ORION | OK | OK | YesV | OK | MUGUREL | 1999-12-23 | 1999-12-22 |  |  |  | OK | OK |  | OK | OK |  |  |  | 00:0008 | ETR | N/A | 2000-01-28 | OK | OK | OK | 2000-02-05 |  | Yes | Theo Radoi | 2000-03-22 | 2000-03-22 | 2000-03-22 | 2000-03-24 | OK | K 739 494 | 105 | 7 | 50 | K 739 494 | 305 | 7 | 50 | N/A | N/A | N/A | N/A |  |  |  |  | N/A | 80 | 80 | 1 1/4" | 80 | 80 | 1 1/4" | 80 | 80 | 1 1/4" |  |  |  | 480 | ML 15 E 1+0 | Constanta | MW | 109 | 0.6 |  |  | 15/89 |  | 4x2/8 | 2U-3 |  |  |  | Indoor Comteck | [9 empty] | 1 | BX652 | HORIA | 289 | 0.6 |  |  | 15/84 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-10-03 |  |  | 2000-10-03 | 30N02 Kogalniceanu-Constanta |  | OK | DAN | DAN | [32 empty] | 56 | Harsova | Constanta | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BX652 | HORIA | Road Buc-Slo-Con | YX616 Mihail Kogalniceanu_RTC | Dobrogea | 44 39'05,3"N | 28 04'38,3"E | 44 39 11.8 | 28 04 09.8 | Teren langa drumul spre miorita | Lacusta Constantin, Strada Concordiei no 6, Harsova, 041/870565/Lacusta Constantin, Strada Concordiei no 6, Harsova, 041/870565 | MAXITE | M | 1 | 2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | TN | 50 | New 50m tower | SHELTER | DIEKAT | OK | DIEKAT | OK | OK | YesV | OK | AUREL | 2000-02-17 | 2000-02-07 |  |  |  | 1999-12-14 | 2000-01-07 |  | 2000-01-07 | 2000-01-25 |  |  |  | 00:0009 | ETR | Electotrade | OK | OK | 2000-02-09 | OK | 2000-02-12 |  | Yes | Theo Radoi | 2000-03-21 | 2000-03-21 | 2000-03-21 | 2000-03-24 | OK | AAU | 145 | 5 | 49 | AAU | 295 | 5 | 49 | N/A | N/A | N/A | N/A |  |  |  |  | MAXITE | 65 | 65 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 130 | ML 15 E 1+0 | Constanta | MW | 137 | 0.6 |  |  | 15/84 |  | 4x2/8 | 2U-3 |  |  |  | Indoor Comteck | [9 empty] | 1 | BX653 | STUPINA | 317 | 0.6 |  |  | 15/89 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-10-03 |  |  | 2000-10-03 | 30N02 Kogalniceanu-Constanta |  | OK | DAN | DAN | [32 empty] | 100 | Horia | Constanta | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BX653 | STUPINA | Road Buc-Slo-Con | YX616 Mihail Kogalniceanu_RTC | Dobrogea | 44 34'05,9"N | 28 10'57,0"E | 44 34 20.0 | 28 10 17.8 | Teren agricol la intrarea in Stupina | Nastase Maria, Stupina, CT/Nastase Maria, Stupina, CT | MAXITE | M | 1 | 2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | TN | 50 | New 50m tower | SHELTER | DIEKAT | OK | DIEKAT | OK | OK | YesV | OK | AUREL | 2000-02-17 | 2000-02-07 |  |  |  | 1999-12-14 | 2000-01-07 |  | 2000-01-07 | 2000-01-25 |  |  |  | 00:0009 | ETR | Electotrade | OK | OK | 2000-02-09 | OK | 2000-02-12 |  | Yes | Theo Radoi | 2000-03-21 | 2000-03-21 | 2000-03-21 | 2000-03-24 | OK | AAU | 140 | 5 | 49 | AAU | 310 | 5 | 49 | N/A | N/A | N/A | N/A |  |  |  |  | MAXITE | 65 | 65 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 130 | ML 23 E 1+0 | Constanta | MW | 139 | 0.6 |  |  | 23/56 |  | 4x2/8 |  |  |  |  | Indoor Comteck | [9 empty] | 1 | BX654 | CRUCEA | 319 | 0.6 |  |  | 23/58 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-10-03 |  |  | 2000-10-03 | 30N02 Kogalniceanu-Constanta |  | OK | DAN | DAN | [32 empty] | 118 | Stupina | Constanta | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BX654 | CRUCEA | Road Buc-Slo-Con | YX616 Mihail Kogalniceanu_RTC | Dobrogea | 44 30'50,7"N | 28 14'51,1"E | 44 31 01.5 | 28 14 36.3 | In incinta IAS CRUCIDAVA, Crucea, CT | IAS CRUCIDAVA/Tilicea Septimiu, Crucea, CT, 041870198 | MAXITE | M | 1 | 2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | TN | 50 | New 50m tower | SHELTER | DIEKAT | OK | DIEKAT | OK | OK | YesV | OK | AUREL | 2000-02-17 | OK |  |  |  | 1999-12-14 | 2000-01-07 |  | 2000-01-07 | 2000-01-25 |  |  |  | 00:0009 | ETR | Electotrade | OK | OK | 2000-02-09 | OK | 2000-02-12 |  | Yes | Theo Radoi | 2000-03-21 | 2000-03-21 | 2000-03-21 | 2000-03-24 | OK | AAU | 140 | 5 | 49 | AAU | 320 | 5 | 49 | N/A | N/A | N/A | N/A |  |  |  |  | MAXITE | 65 | 65 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 130 | ML 23 E 1+0 | Constanta | MW | 152 | 0.6 |  |  | 23/58 |  | 4x2/8 | 2U-3 |  |  |  | Indoor Comteck | [9 empty] | 1 | BX655 | DOROBANTU | 332 | 0.6 |  |  | 23/56 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-10-03 |  |  | 2000-10-03 | 30N02 Kogalniceanu-Constanta |  | OK | DAN | DAN | [32 empty] | 100 | Crucea | Constanta | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BX655 | DOROBANTU | Road Buc-Slo-Con | YX616 Mihail Kogalniceanu_RTC | Dobrogea | 44 26'12,1"N | 28 18'09,2"E | 44 26 21.0 | 28 18 01.0 | Teren agricol comuna Dorobantu, borna km 167+3 |  | MAXITE | M | 1 | 2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | TN | 50 | New 50m tower | SHELTER | DIEKAT | OK | DIEKAT | OK | OK | YesV | OK | AUREL | 2000-02-17 | 2000-02-07 |  |  |  | 1999-12-14 | 1999-12-20 |  | 1999-12-20 | 2000-01-25 |  |  |  | 00:0009 | ETR | Electotrade | OK | OK | 2000-02-09 | OK | 2000-02-12 |  | Yes | Theo Radoi | 2000-03-21 | 2000-03-21 | 2000-03-21 | 2000-03-24 | OK | AAU | 140 | 5 | 48 | AAU | 320 | 5 | 48 | N/A | N/A | N/A | N/A |  |  |  |  | MAXITE | 65 | 65 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 130 | ML 15 E 1+1 | Constanta | MW | 124 | 0.6 |  |  | 15/84 | YES | 4X2/8 | 4U-1 |  |  |  | Indoor Comteck | [9 empty] | 1 | BX656 | MIHAIL KOGALNICEANU 2(OPTIMIZARE) | 304 | 0.6 |  |  | 15/89 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-10-03 |  |  | 2000-10-03 | 30N02 Kogalniceanu-Constanta |  | OK | MIHAI C. | MIHAI C. | [32 empty] | 112 | Dorobantu | Constanta | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BX656 | MIHAIL KOGALNICEANU 2(OPTIMIZARE) | Road Buc-Slo-Con | YX616 Mihail Kogalniceanu_RTC | Dobrogea | 44 22'27,2"N | 28 25'43,1"E | 44 22'27,2"N | 28 25'43,1"E | E60, borna km 180+5 | Private/MUNTEANU HONORIU, 043214407; Bdul. Unirii, bl. U12, sc. B, et. VII, ap. 75 | 2102 | M | C+C+C+ | 2/2/2 | N/A | CR144_DIOSTI | 2101 | M | C+ | 2 | Yes | 2001-04-26 | N/A | N/A | Phase_1 | N/A | N/A | N/A | TN | 50 | New 50m tower | OUTDOOR |  | OK |  |  |  | YesV |  |  |  |  | 2000-02-07 | 2001-05-16 | 2001-06-08 | 1999-11-23 | 1999-12-20 |  | 1999-12-20 | 2000-01-25 |  |  |  | 2001-05-22 | ICOM | VECTOR | 2001-05-23 | 2001-05-23 | 2001-05-25 | 2001-06-16 | 2001-06-20 | IVAN | Yes | Valentin C-tinescu | 2001-06-20 | 2001-06-20 | 2001-06-20 | 2001-06-29 | 2001-07-11 | K 739 494 | 15 | 0 | 48 | K 739 494 | 130 | 0 | 48 | K 739 494 | 290 | 0 | 48 | N/A | N/A | N/A | N/A | N/A | 60 | 60 | 1 1/4" | 60 | 60 | 1 1/4" | 60 | 60 | 1 1/4" | N/A | N/A | N/A | 360 | ML 23 E 1+1 | Constanta | MW | 111 | 0.6 |  |  | 23/56 | YES |  | N/A |  |  | N/A | RBS | [9 empty] | 1 | YX616 | MIHAIL KOGALNICEANU_RTC | 291 | 0.6 |  |  | 23/58 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-10-03 |  |  | 2000-10-03 | 30N01 Kogalniceanu-Constanta |  | OK | MIHAI C. | [23 empty] | 00:0009 | N/A | ETR | RAD | 2000-02-18 | OK | OK | 2000-03-21 | 2000-04-06 | OK | 105 | Mihail Kogalniceanu | Constanta | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BX657 | LUMINA | Road Buc-Slo-Con | YX616 Mihail Kogalniceanu_RTC | Dobrogea | 44 18'04,6"N | 28 31'50,4"E | 44 17 54 | 28 31 47 | Comuna Lumina |  | 2101 | M | C+ | 2 | 2101 | [6 empty] | OK |  | N/A |  |  |  | N/A | TN | 50 | New 50m tower | OUTDOOR | DIEKAT | OK | DIEKAT | OK | OK | YesV | OK | AUREL | 2000-03-01 | OK |  |  |  | 2000-01-04 | OK |  | OK | OK |  |  |  | 00:0009 | ETR | Electotrade | OK | OK | OK | 2000-03-06 | 2000-03-05 |  | Yes | Theo Radoi | 2000-03-29 | 2000-03-29 | 2000-03-29 | 2000-04-06 | OK | K 739 494 | 150 | 5 | 48.5 | K 739 494 | 330 | 5 | 48.5 | N/A | N/A | N/A | N/A |  |  |  |  | K 63 55 8 | 55 | 55 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 110 | ML 15 E 1+0 | Constanta | MW | 314 | 0.6 |  |  | 15/84 |  | 4X2/8 | 2U-3 |  |  |  | RBS | [10 empty] | BX656 | MIHAIL KOGALNICEANU 2(OPTIMIZARE) | 134 | 0.6 |  |  | 15/89 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-10-12 |  |  | 2000-10-12 | 30N01 Kogalniceanu-Constanta |  | OK | MIHAI C. | MIHAI C. | [32 empty] | 89 | Lumina | Constanta | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BX658 | PALAZU MARE | Road Buc-Slo-Con | BX002 Tomis Nord | Dobrogea | 44 14'07,9"N | 28 34'51,6"E | 44 14'07,9"N | 28 34'51,6"E | Comuna Palazu Mare |  | 2101 | M | C+ | 2 | 2101 | [6 empty] | OK |  | N/A |  |  |  | N/A | TN | 50 | New 50m tower | OUTDOOR | DIEKAT | OK | DIEKAT | OK | OK | YesV | OK | AUREL | 2000-03-01 | OK |  |  |  | 2000-01-04 | OK |  | OK | OK |  |  |  | 00:0009 | ETR | Electotrade | OK | OK | 2000-03-07 | 2000-03-07 | 2000-03-10 |  | Yes | Theo Radoi | 2000-03-29 | 2000-03-29 | 2000-03-29 | 2000-04-27 | OK | K 739 494 | 140 | 5 | 48.5 | K 739 494 | 310 | 5 | 48.5 | N/A | N/A | N/A | N/A |  |  |  |  | K 63 55 8 | 55 | 55 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 110 |  | Constanta | MW | 110 | 0.6 |  |  | 23/58 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [9 empty] | 1 | BX015 | PERLA | 292 | 0.6 |  |  | 23/56 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-10-11 |  |  | 2000-12-08 | De mutat pe 30N01 de pe 30N04 Tomis Nord-Constanta+DXX |  | OK | MIHAI C. | MIHAI C. | [32 empty] | 22 | Palazu Mare | Constanta | [7 empty] | 1 |  |  | missing
Phase_1 | CS | BX701 | FUNDULEA | Road Buc-Fet-Con | BU009 Baneasa_RTC | Muntenia | 44 27'09,6"N | 26 28'30,8"E | 44 27 57.9 | 26 31 00.1 | Romtelecom Fundulea, Bd. 22 Decembrie 111 | Romtelecom/Doina POPA, Diriginta Oficiu. 042/642239; Dl. Chiru Florin : 642 228( are cheia din RTC!) | MAXITE | M | No | 2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | TE | 28 | Existing 28m tower | ROOM | DUAL | OK | DUAL | OK | OK | YesV | OK | MUGUREL | 2000-01-07 | OK |  |  |  | OK | OK |  | OK | 2000-02-08 |  |  |  | N/A | YRO | HAR | 2000-02-04 | OK | OK | OK | 2000-02-13 |  | Yes | Theo Radoi | 2000-02-26 | 2000-04-25 | 2000-04-25 | 2000-04-26 | OK | AAU | 90 | 2 | 26 | AAU | 275 | 2 | 26 | N/A | N/A | N/A | N/A |  |  |  |  | MAXITE | 45 | 45 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 90 |  | Baneasa | MW | 268 | 0.6 |  |  | 15/84 |  | 4x2/8 |  |  |  |  | Indoor Comteck | [10 empty] | BU702 | BRANESTI | 88 | 0.6 |  |  | 15/89 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-05-15 |  |  | 2000-05-18 | 30N02 Baneasa-Dr.Taberei |  | OK | SORIN UNTARU | SORIN UNTARU | [32 empty] | 66 | Fundulea | Calarasi | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BX703 | STEFANESTI | Road Buc-Fet-Con | BU009 Baneasa_RTC | Muntenia | 44 26'45,2"N | 26 43'16,3"E | 44 30 30.2 | 26 43 34.6 | Ferma Stefanesti | Private/ | MAXITE | M | No | 2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | TN | 50 | New 50m tower | SHELTER | DUAL | OK | DUAL | OK | 2000-02-09 | YesV | OK | MUGUREL | 2000-02-09 | 2000-02-08 |  |  |  | 1999-11-30 | OK |  | OK | 2000-01-25 |  |  |  | N/A | YRO | SVF | 2000-02-11 | OK | 2000-02-15 | 2000-02-15 | 2000-02-20 |  | Yes | Cristian Croitor | 2000-02-26 | 2000-05-02 | 2000-05-02 | 2000-05-03 | OK | AAU | 115 | 5 | 48 | AAU | 270 | 5 | 48 | N/A | N/A | N/A | N/A |  |  |  |  | MAXITE | 65 | 65 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 130 | ML 15 E 1+0 | Baneasa | MW | 74 | 1.2 |  |  | 15/89 |  | 4X2/8 | 2U-3 |  |  |  | Indoor Comteck | [10 empty] | BX701 | FUNDULEA | 254 | 0.6 |  |  | 15/84 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-05-10 |  |  | 2000-05-10 | 30N02 Baneasa-Dr.Taberei |  | OK | SORIN UNTARU | SORIN UNTARU | [32 empty] | 54 | Stefanesti | Calarasi | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BX704 | LEHLIU GARA | Road Buc-Fet-Con | BX615 Slobozia_RTC | Dobrogea | 44 26'16,6"N | 26 51'39,0"E | 44 26 28.8 | 26 51 05.9 | Romtelecom Lehliu | Romtelecom Tr. Dig./042304216, 042640300 | MAXITE | M | No | 2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | TE | 30 | Existing 30m tower | ROOM | DUAL | OK | DUAL | OK | OK | YesV | OK | MUGUREL | 2000-01-07 | OK |  |  |  | OK | 1999-12-02 |  | 1999-12-02 | 2000-01-04 |  |  |  | N/A | YRO | HAR | 2000-02-04 | OK | 2000-02-04 | OK | 2000-02-24 |  | Yes | Cristian Croitor | 2000-03-27 | 2000-04-22 | 2000-04-22 | 2000-04-24 | OK | AAU | 95 | 2 | 28 | AAU | 320 | 2 | 28 | N/A | N/A | N/A | N/A |  |  |  |  | MAXITE | 65 | 65 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 130 |  | Dr. Taberei | MW | 92 | 0.6 |  |  | 15/84 |  | 4X2/8 | 2U-3 |  |  |  | Indoor Comteck |  |  |  | XC31610 | [5 empty] | 1 | BX705 | DOR MARUNT | 272 | 0.6 |  |  | 15/89 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-06-06 |  | 2000-10-18 | 2000-10-25 | 30N03 Slobozia-Dr.Taberei |  | OK | SORIN UNTARU | SORIN UNTARU | [32 empty] | 52 | Lehliu Gara | Calarasi | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BX705 | DOR MARUNT | Road Buc-Fet-Con | BX615 Slobozia_RTC | Dobrogea | 44 26'05,6"N | 26 59'48,7"E | 44 26 12.3 | 26 57 55.9 | FNC Lehliu - Dor Marunt (siloz cereale) | Private/Dir. General, Magla Stefan; 092.423.288 | 2101 | M | C+ | 2 | 2101 | [6 empty] | OK |  | 2000-06-27 |  |  |  | 35 | SILO | 34 | T4m+T4m | OUTDOOR | DUAL | OK | DUAL | OK | OK | YesV | OK | MUGUREL | 2000-01-21 | OK |  |  |  | 1999-11-26 | 1999-12-08 |  | 1999-12-08 | 2000-01-04 |  |  |  | N/A | YRO | HAR | 2000-02-04 | OK | 2000-02-04 | OK | 2000-02-24 |  | Yes | Cristian Croitor | 2000-03-23 | 2000-04-22 | 2000-04-22 | 2000-04-24 | OK | K 739 494 | 95 | 2 | 36 | K 739 494 | 270 | 2 | 36 | N/A | N/A | N/A | N/A |  |  |  |  | K 63 55 8 | 40 | 40 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 80 |  | Dr. Taberei | MW | 84 | 0.6 |  |  | 15/89 |  | 4x2/8 | 2U-3 |  |  |  | RBS |  |  |  | XC31610 | [5 empty] | 1 | BX706 | DRAGOS VODA | 264 | 0.6 |  |  | 15/84 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-06-08 |  |  |  | 30N03 Slobozia-Dr.Taberei |  | OK | SORIN UNTARU | SORIN UNTARU | [32 empty] | 50 | Dor Marunt | Calarasi | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BX706 | DRAGOS VODA | Road Buc-Fet-Con | BX615 Slobozia_RTC | Dobrogea | 44 26'45,0"N | 27 08'10,0"E | 44 26 45.0 | 27 08 10.0 | DRTV DRAGOS VODA | DRTV/ | 2202 | M | C+C+C+ | 2/2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | TE | 75 | Existing 75m tower | ROOM | IMSAT | OK | IMSAT | OK | OK | YesV | OK | AUREL | 2000-01-14 | OK |  |  |  | OK | OK |  | OK | 1999-11-08 |  |  |  | 00:0008 | ETR | N/A | 2000-01-28 | OK | OK | OK | 2000-02-05 |  | Yes | Cristian Croitor | 2000-03-23 | 2000-04-22 | 2000-04-22 | 2000-04-24 | OK | K 739 494 | 105 | 5 | 50 | K 739 494 | 255 | 5 | 50 | N/A | N/A | N/A | N/A |  |  |  |  | N/A | 65 | 65 | 1 1/4" | 65 | 65 | 1 1/4" | N/A | N/A | N/A |  |  |  | 260 |  | Dr. Taberei | MW | 100 | 0.6 | 50 |  | 15/84 |  | 4x2/8 |  |  |  |  | Indoor Comteck |  |  |  | XC31610 | [5 empty] | 1 | BX707 | IVANESTI GARA | 280 | 0.6 | 48 |  | 15/89 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-06-08 |  |  | 2000-06-13 | 30N03 Slobozia-Dr.Taberei |  | OK | SORIN UNTARU | SORIN UNTARU | [32 empty] | 47 | Dragos Voda | Calarasi | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BX707 | IVANESTI GARA | Road Buc-Fet-Con | BX615 Slobozia_RTC | Dobrogea | 44 25'42,7"N | 27 17'07,5"E | 44 25 37.4 | 27 16 26.3 | Ferma 11 Ivanesti, jud. Calarasi | SCA IVANESTI; 042.311.656; 042 312 335/Preda Constantin - Director tehnic, 092.249.891 | 2101 | M | C+ | 2 | 2101 | [6 empty] | OK |  | N/A |  |  |  | N/A | TN | 50 | New 50m tower | OUTDOOR | IMSAT | OK | IMSAT | OK | 2000-03-15 | YesV | OK | AUREL | 2000-03-17 | OK |  |  |  | 1999-11-30 | OK |  | OK | 2000-02-28 |  |  |  | 00:0009 | ETR | Electotrade | OK | OK | 2000-03-14 | 2000-03-20 | 2000-03-21 |  | Yes | Cristian Croitor | 2000-03-23 | 2000-04-22 | 2000-04-22 | 2000-04-24 | OK | K 739 494 | 90 | 5 | 48 | K 739 494 | 270 | 5 | 48 | N/A | N/A | N/A | N/A |  |  |  |  | K 63 55 8 | 55 | 55 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 110 |  | Dr. Taberei | MW | 23 | 1.2 |  |  | 15/89 |  | 4x2/8 | [8 empty] | XC31610 | [5 empty] | 1 | BX610 | SLOBOZIA | 203 | 0.6 |  |  | 15/84 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-10-03 |  |  | 2000-10-03 | 30N03 Slobozia-Dr.Taberei |  | OK | SORIN UNTARU | SORIN UNTARU | [32 empty] | 45 | Ivanesti Gara | Calarasi | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BX708 | DRAGALINA(OPTIMIZARE) | Road Buc-Fet-Con | BX615 Slobozia_RTC | Dobrogea | 44 25'34,9"N | 27 25'38,0"E | 44 25 33.5 | 27 23 23.3 | Islaz primaria Dragalina | Private/MUNTEANU HONORIU, 043214407; Bdul. Unirii, bl. U12, sc. B, et. VII, ap. 75 | 2102 | M | C+C+C+ | 2/2/2 | N/A | CR181_CAPU_DEALULUI | 2101 | M | No | 2 | Yes | 2001-05-04 | N/A | N/A | Phase_1 | N/A | N/A | N/A | TN | 50 | New 50m tower | OUTDOOR |  | OK |  |  |  | YesV |  |  |  |  | OK |  |  | 2000-01-19 | OK |  | OK | 2000-02-28 |  |  |  | 2001-05-22 | ICOM | VECTOR | 2001-05-23 | 2001-05-23 | 2001-05-25 | 2001-06-12 | 2001-06-13 | VLAD | Yes | Mircea Mihut | 2001-06-08 | 2001-06-08 | 2001-06-08 | 2001-06-15 | 2001-07-11 | K 739 494 | 90 | 1 | 49 | K 739 494 | 190 | 1 | 49 | K 739 494 | 350 | 1 | 49 | N/A | N/A | N/A | N/A | N/A | 61 | 61 | 1 1/4" | 61 | 61 | 1 1/4" | 61 | 61 | 1 1/4" | N/A | N/A | N/A | 366 |  | Dr. Taberei | MW | 270 | 0.6 | 48 |  | 15/84 |  | 4X2/8 | 2U-3 |  |  |  | RBS | [10 empty] | BX707 | IVANESTI GARA | 90 | 0.6 | 48 |  | 15/89 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-06-08 |  |  | 2000-06-13 | 30N01 Slobozia-Dr.Taberei |  | OK | SORIN UNTARU | SORIN UNTARU | [22 empty] | 00:0009 | N/A | ETR | RAD | OK | OK | 2000-03-23 | 2000-03-31 | 2000-04-07 | OK | 39 | Dragalina | Calarasi | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BX709 | PERISORU | Road Buc-Fet-Con | YX751 Cernavoda_RTC | Dobrogea | 44 25'19,6"N | 27 33'56,7"E | 44 25 19.63 | 27 33 56.67 | Siloz DN3A, Borna 59, km 21, Bucuresti-Fetesti | Cerealcom, jud. Calarasi/Dir. Gen. Popa, 092.512.835; 042.316.075 | 2101 | M | C+ | 2 | 2101 | [6 empty] | OK |  | 2000-06-27 |  |  |  | 60 | SILO | 60 | T4m +T4m | OUTDOOR | TEHNOROB | OK | TEHNOROB | OK | OK | YesV | OK | MARIUS | 2000-03-01 | 2000-02-08 |  |  |  | 1999-11-26 | OK |  | OK | 2000-01-24 |  |  |  | 00:0009 | ETR | Electotrade | OK | OK | 2000-02-09 | OK | 2000-02-12 |  | Yes | Theo Radoi | 2000-03-31 | 2000-03-31 | 2000-03-31 | 2000-04-06 | OK | K 739 494 | 90 | 2 | 65 | K 739 494 | 270 | 2 | 65 | N/A | N/A | N/A | N/A |  |  |  |  | K 63 55 8 | 10 | 10 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 20 | ML 23 E 1+0 | Constanta | MW | 91 | 0.6 |  |  | 23/58 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [9 empty] | 1 | BX710 | GARA BARAGANU | 271 | 0.6 |  |  | 23/56 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-10-03 |  |  | 2000-10-03 | 30N02 Cernovoda-Constanta+DXX |  | OK | SORIN UNTARU | SORIN UNTARU | [32 empty] | 41 | Perisoru | Calarasi | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BX710 | GARA BARAGANU | Road Buc-Fet-Con | YX751 Cernavoda_RTC | Dobrogea | 44 25'12,5"N | 27 42'12,3"E | 44 25 12.95 | 27 41 18.16 | Siloz DN 3A, Borna 52, Km14, Bucurest-Fetesti | S.C. Cerealcom S.A., Jud. Ialomita, Slobozia/Dir. Gen Miclici Ioan, 043.214.467; 043.231.633 | 2101 | M | C+ | 2 | 2101 | [6 empty] | OK |  | 2000-06-27 |  |  |  | 60 | SILO | 60 | T4m +T4m | OUTDOOR | TEHNOROB | OK | TEHNOROB | OK | OK | YesV | OK | MARIUS | 2000-03-01 | 2000-02-08 |  |  |  | 1999-11-26 | OK |  | OK | 2000-01-24 |  |  |  | 00:0009 | ETR | Electotrade | OK | OK | 2000-02-09 | OK | 2000-02-12 |  | Yes | Theo Radoi | 2000-03-31 | 2000-03-31 | 2000-03-31 | 2000-04-06 | OK | K 739 494 | 90 | 2 | 65 | K 739 494 | 270 | 2 | 65 | N/A | N/A | N/A | N/A |  |  |  |  | K 63 55 8 | 10 | 10 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 20 | ML 15 E 1+0 | Constanta | MW | 93 | 0.6 |  |  | 15/84 |  | 4x2/8 |  |  |  |  | RBS | [9 empty] | 1 | BX801 | FETESTI | 273 | 0.6 |  |  | 15/89 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-10-24 |  |  | 2000-10-24 | 30N02 Cernovoda-Constanta+DXX |  | OK | SORIN UNTARU | SORIN UNTARU | [32 empty] | 55 | Gara Baraganu | Ialomita | [7 empty] | 1 |  |  | 1
Phase_3 | CS | BX711 | VALU LUI TRAIAN | Constanta | BX006 Bratianu_CTA | Dobrogea | 44 09 53 | 28 28 25 | [94 empty] | Constanta | MW | [22 empty] | BX754 | BASARABI | [24 empty] | new03 Bratianu-Constanta |  | 2001-07-21
Phase_1 | CS | BX751 | CERNAVODA | Road Buc-Fet-Con | YX751 Cernavoda_RTC | Dobrogea | 44 20'09,3"N | 28 01'32,4"E | 44 21 02.77 | 28 02 27.01 | Pilon Administratia Canalului | Societ. Nationala CAN Agigea;738300/Sef. S.Tc. Alexandru Muntoiu | 2102 | M | C+C+ | 2/2 | N/A | [6 empty] | OK |  | 2000-06-27 |  |  |  | N/A | TE | 82 | Existing 82m tower | OUTDOOR | EL-MONT | OK | EL-MONT | OK | 2000-02-01 | YesV | OK | DRAGOS | 2000-02-01 | OK |  |  |  | 1999-11-19 | OK |  | OK | 1999-12-16 |  |  |  | 00:0008 | ETR | N/A | 2000-01-11 | OK | OK | OK | OK |  | Yes | Theo Radoi | 2000-02-26 | 2000-03-16 | 2000-03-16 | 2000-03-23 | OK | K 739 494 | 160 | 5 | 40 | K 739 494 | 275 | 5 | 40 | N/A | N/A | N/A | N/A |  |  |  |  | N/A | 50 | 50 | 1 1/4" | 50 | 50 | 1 1/4" | N/A | N/A | N/A |  |  |  | 200 | ML 38 E 1+1 | Constanta | MW | 193 | 0.3 |  |  | 38/14 | YES | 4X2/8 | 4U-1 |  |  | N/A | RBS | XC30711 | [8 empty] | 1 | YX751 | CERNAVODA_RTC | 13 | 0.3 |  |  | 38/18 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-10-03 |  |  | 2000-10-03 | 30N01 Cernovoda-Constanta+DXX |  | OK | SORIN UNTARU | SORIN UNTARU | [32 empty] | 97 | Cernavoda | Constanta | [7 empty] | 1 |  |  | missing
Phase_1 | CS | BX752 | FACLIA | Road Buc-Fet-Con | YX751 Cernavoda_RTC | Dobrogea | 44 16'24,8"N | 28 07'02,4"E | 44 16 27.0 | 28 05 07.3 | IAS Cernavoda, Statie de pompare | SC Vrifucer SA Cernavoda, CT/Nicolae DINU, Director General, 092/352011 | 2101 | M | C+ | 2 | 2101 | [6 empty] | OK |  | N/A |  |  |  | N/A | TN | 40 | New 40m tower | OUTDOOR | DUAL | OK | DUAL | OK | OK | YesV | OK | MUGUREL | 2000-02-17 | OK |  |  |  | 1999-11-30 | OK |  | OK | 2000-02-08 |  |  |  | 00:0009 | ETR | Electotrade | OK | OK | OK | OK | 2000-03-02 |  | Yes | Theo Radoi | 2000-03-31 | 2000-03-31 | 2000-03-31 | 2000-04-06 | OK | K 739 494 | 95 | 2 | 38 | K 739 494 | 340 | 2 | 38 | N/A | N/A | N/A | N/A |  |  |  |  | K 63 55 8 | 45 | 45 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 90 | ML 23 E 1+0 | Constanta | MW | 338 | 0.6 |  |  | 23/58 |  | 4x2/8 | 2U-3 |  |  |  | Indoor Comteck | XC30711 | [8 empty] | 1 | BX751 | CERNAVODA | 158 | 0.6 |  |  | 23/56 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-10-03 |  |  | 2000-10-03 | 30N01 Cernovoda-Constanta+DXX |  | OK | SORIN UNTARU | SORIN UNTARU | [32 empty] | 8 | Faclia | Constanta | [7 empty] | 1 |  |  | missing
Phase_1 | CS | BX753 | MEDGIDIA | Road Buc-Fet-Con | YX751 Cernavoda_RTC | Dobrogea | 44 14'25,8"N | 28 15'41,0"E | 44 14 25.8 | 28 15 41.0 | DRTV Medgidia | DRTV/ | 2102 | M | C+C+ | 2/2 | N/A | [6 empty] | OK |  | 2000-06-27 |  |  |  | N/A | TE | 80.5 | Existing 80m tower | OUTDOOR | IMSAT | OK | IMSAT | OK | 1999-12-17 | YesV | OK | AUREL | 2000-01-14 | OK |  |  |  | OK | OK |  | OK | 1999-11-24 |  |  |  | 00:0009 | ETR | Electotrade | OK | OK | OK | OK | 2000-02-05 |  | Yes | Theo Radoi | 2000-02-26 | 2000-03-16 | 2000-03-16 | 2000-04-06 | OK | K 739 494 | 115 | 5 | 65 | K 739 494 | 270 | 5 | 65 | N/A | N/A | N/A | N/A |  |  |  |  | N/A | 80 | 80 | 1 1/4" | 80 | 80 | 1 1/4" | N/A | N/A | N/A |  |  |  | 320 | ML 15 E 1+0 | Constanta | MW | 285 | 1.2 |  |  | 15/89 |  | 4x2/8 | 2U-3 |  |  |  | RBS | XC30711 | [8 empty] | 1 | BX752 | FACLIA | 105 | 1.2 |  |  | 15/84 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-10-03 |  |  | 2000-10-03 | 30N01 Cernovoda-Constanta+DXX |  | OK | SORIN UNTARU | SORIN UNTARU | [32 empty] | 75 | Medgidia | Constanta | [7 empty] | 1 |  |  | 1
Phase_1 | CS | BX754 | BASARABI(OPTIMIZARE) | Road Buc-Fet-Con | BX006 Bratianu_CTA | Dobrogea | 44 12'56,2"N | 28 23'20,5"E | 44 10 36.29 | 28 23 06.3 | Pilon Administratie Canal | Societ. Nationala CAN Agigea;738300/Sef. S.Tc. Alexandru Muntoiu | 2202 | M | C+C+C+ | 2/2/2 | N/A | Warehouse | MAXITE | M | No | 2 | N/A | OK |  | N/A | Phase_1 |  |  | N/A | TE | 84 | Existing 84m tower | SHELTER | SETRACO | OK | SETRACO | OK | 2000-02-02 | YesV | OK | AUREL | 2000-02-02 | OK |  |  | 2001-07-12 | 1999-11-16 | OK |  | OK | 2000-01-21 |  |  |  | 2001-07-17 | ICOM | [7 empty] | Yes | [6 empty] | K 739 707 | 80 | 2 | 65 | K 739 707 | 215 | 0 | 70 | K 739 494 | 350 | 1 | 70 | N/A | N/A | N/A | N/A | N/A | 70 | 70 | 1 1/4" | 75 | 75 | 1 1/4" | 75 | 75 | 1 1/4" | N/A | N/A | N/A | 440 |  | Constanta | MW | 92 | 1.2 |  |  | 15/84 |  | 4x2/8 | 2U-3 |  |  |  | Indoor Comteck | [9 empty] | 1 | BX022 | STEFAN-STANCA | 273 | 1.2 | 1.2 |  | 15/89 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-10-03 |  |  | 2000-10-03 | Se muta de pe 30N01 pe new03 Bratianu-Constanta | Optimizare (vezi harta de transmisiuni) | 2001-07-21 | SORIN UNTARU | SORIN UNTARU | [22 empty] | N/A | 00:0009 | ETR | Electotrade | 2000-02-12 | Cristian Croitor | 2000-04-19 | 2000-04-19 | 2000-04-24 | OK | 11 | Basarabi | Constanta | [7 empty] | 1 |  |  | missing
Phase_1 | CS | BX801 | FETESTI | Road Buc-Fet-Con | YX751 Cernavoda_RTC | Dobrogea | 44 24'52,0"N | 27 50'06,6"E | 44 24 51.73 | 27 49 18.38 | Romtelecom Fetesti | Romtelecom/ | 2202 | M | C+C+C+ | 2/2 | N/A | [6 empty] | OK |  | N/A |  |  |  | N/A | TE | 80 | Existing 80m tower | ROOM | IMSAT | OK | IMSAT | OK | OK | YesV | OK | AUREL | 1999-12-21 | OK |  |  |  | OK | 1999-10-12 |  | 1999-10-12 | 1999-11-11 |  |  |  | N/A | ETR | N/A | 2000-01-11 | OK | OK | OK | OK |  | Yes | Theo Radoi | 2000-02-26 | 2000-03-16 | 2000-03-16 | 2000-03-23 | OK | K 739 494 | 140 | 5 | 70 | K 739 494 | 270 | 5 | 70 | N/A | N/A | N/A | N/A |  |  |  |  | N/A | 80 | 80 | 1 1/4" | 80 | 80 | 1 1/4" | N/A | N/A | N/A |  |  |  | 320 | ML 15 E 1+0 | Constanta | MW | 112 | 1.2 |  |  | 15/89 |  | 4x2/8 | 4U-1 |  |  |  | Indoor Comteck | [9 empty] | 1 | BX751 | CERNAVODA | 292 | 1.2 |  |  | 15/84 | [6 empty] | OK | OK | OK | OK | OK | OK | OK | OK | OK | 2000-10-03 |  |  | 2000-10-03 | 30N02 Cernovoda-Constanta+DXX |  | OK | SORIN UNTARU | SORIN UNTARU | [32 empty] | 60 | Fetesti | Ialomita | [7 empty] | 1 |  |  | missing
Phase_2 | CS | BX802 | JEGALIA_RTC | Road Buc-Constanta(4) | BX116 Calarasi_RTC | Moldova | 44 17 06 | 27 37 23 | 44 17 06 | 27 37 23 | Romtelecom, Jegalia | Romtelecom/ | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  | 0 | TE | 32 |  | N/A | DIEKAT | OK | APOLLO | 2001-01-12 | 2001-01-30 | YesV | 2001-04-23 | Doru | 2001-02-05 | 2001-05-03 |  |  |  | N/A | 2000-12-07 |  | 2000-12-14 | 2001-01-10 | [6 empty] | 2001-02-01 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 55 | 0 | 30 | K 739 494 | 220 | 0 | 30 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 40 | 40 | 7/8'' | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 80 | N/A | Baneasa | RR | RR | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | RBS | XC30116 | [6 empty] | 15/outdoor |  |  | BX116 | CALARASI_RTC | RR | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 30N01 Calarasi-Baneasa |  | 2001-03-01 | Eugen-CW | Cosmorom | [32 empty] | 20 | Jegalia | Calarasi | [7 empty] | 2 |  |  | 2
Phase_2 | CS | BX803 | BORCEA_RTC | Road Buc-Constanta(4) | BX116 Calarasi_RTC | Moldova | 44 19 52 | 27 44 50 | 44 19 52 | 27 44 50 | Romtelecom, Borcea | Romtelecom/ | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  | 0 | TE | 36 |  | N/A | DIEKAT | OK | APOLLO | 2001-01-12 | 2001-01-30 | YesV | 2001-04-23 | Doru | 2001-02-05 | 2001-05-03 |  |  |  | N/A | 2000-12-07 |  | 2000-12-11 | 2001-01-10 | [6 empty] | 2001-02-01 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 50 | 0 | 35 | K 739 494 | 250 | 0 | 35 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 40 | 40 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 80 | N/A | Baneasa | RR | RR | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | RBS | XC30116 | [6 empty] | 25/Outdoor |  |  | BX802 | JEGALIA_RTC | RR | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 30N01Calarasi-Baneasa |  | 2001-03-01 | Marian-CW | Petrica BURGHIU | [32 empty] | 18 | Borcea | Calarasi | [7 empty] | 2 |  |  | 2
Phase_2 | CS | BX805 | AMARA_RTC | Road Buc-Constanta(4) | BX615 Slobozia_RTC | Muntenia | 44 36 51 | 27 18 52 | 44 36 51 | 27 18 52 | Romtelecom, Amara | Romtelecom/ | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  | 0 | TE | 30 |  | N/A | DIEKAT | OK | PROFIL | 2001-01-19 | 2001-01-26 | YesV | 2001-02-01 | Doru | 2001-05-07 | 2001-03-06 |  |  |  | N/A | 2000-12-07 |  | 2000-12-12 | 2001-01-19 | [6 empty] | 2001-01-30 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 150 | 0 | 26 | K 739 494 | 340 | 0 | 29 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 35 | 35 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 70 | N/A | Dr. Taberei | RR | RR | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | RBS |  |  |  | XC31610 |  |  |  | 35/outdoor |  |  | BX610 | SLOBOZIA |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | RR+30N03 Slobozia-Dr.Taberei |  | OK | Eugen-CW | #N/A | [32 empty] | 31 | Amara | Ialomita | [7 empty] | 2 |  |  | missing
Phase_2 | CS | BX806 | FACAENI_RTC | Ialomita area(2) | YX751 Cernavoda_RTC | Muntenia | 44 33 28 | 27 53 31 | 44 33 28 | 27 53 31 | Romtelecom, Facaeni | Romtelecom/ | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  | 0 | TE | 30 |  | N/A | DIEKAT | OK | PROFIL | 2001-02-23 | 2001-03-15 | YesV | 2001-04-23 | Doru | 2001-04-17 | 2001-05-03 |  |  |  | N/A | 2000-12-07 |  | 2000-12-11 | 2001-02-26 | [6 empty] | 2001-03-19 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 190 | 0 | 29 | K 739 494 | 330 | 0 | 29 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 35 | 35 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 70 | ML 15 E 1+0 | Constanta | MW | 199 |  | 29 | 35 | [7 empty] | RBS | XC30711 | [9 empty] | BX801 | FETESTI | [24 empty] | 30N01 Cernovoda-Constanta+DXX | Se va integra pe 30N01 folosindu-se MXU |  | Eugen-CW | Cosmorom | [32 empty] | 36 | Facaeni | Ialomita | [7 empty] | 2 |  |  | missing
Phase_2 | CS | BX807 | COZIENI_RTC | Buzau area(9) | BX812 Parscov_RTC | Moldova | 45 19 35 | 26 29 27 | 45 19 35 | 26 29 27 | Romtelecom, Cozieni | Romtelecom/DTc Buzau-Dir. Costea Nicolae | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  | 0 | TE | 50 |  | N/A | DIEKAT | OK | DIEKAT | 2001-01-12 | 2001-01-20 | YesV | 2001-02-06 | Marin | 2001-01-23 | 2001-02-07 |  |  |  | N/A | 2001-11-23 |  | 2000-12-18 | 2001-01-09 | [6 empty] | 2001-01-26 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 120 | 0 | 46 | k 739 494 | 330 | 0 | 46 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 52 | 52 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 104 | N/A | Galati | HDSL | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | RBS | [10 empty] | BX812 | PARSCOV_RTC |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A |  |  |  | Marian-CW | COSMOROM | [32 empty] | 295 | Cozieni | Buzau | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | BX809 | VIPERESTI_RTC | Buzau area(9) | BX809 Viperesti_RTC | Moldova | 45 13 36 | 26 27 25 | 45 13 36 | 26 27 25 | Romtelecom, Viperesti | Romtelecom/DTc Buzau-Dir. Costea Nicolae | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  | 0 | TE | 30 |  | N/A | DIEKAT | OK | DIEKAT | 2000-12-21 | 2001-01-20 | YesV | 2001-02-06 | Marin | 2001-01-23 | 2001-02-07 |  |  |  | N/A | 2000-12-07 |  | 2000-12-14 | 2001-01-09 | [6 empty] | 2001-01-26 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 60 | 0 | 27 | K 739 494 | 290 | 0 | 27 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 35 | 35 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 70 | N/A | Galati | HDSL | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | RBS | [10 empty] | ? | N/A |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A |  |  |  | Marian-CW | Cosmorom | [32 empty] | 235 | Viperesti | Buzau | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | BX812 | PARSCOV_RTC | Buzau area(9) | BX812 Parscov_RTC | Moldova | 45 17 10 | 26 33 06 | 45 17 10 | 26 33 06 | Romtelecom, Parscov | Romtelecom/DTc Buzau-Dir. Costea Nicolae | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  | 0 | TE | 30 |  | N/A | DIEKAT | OK | DIEKAT | 2000-12-21 | 2001-01-20 | YesV | 2001-02-06 | Marin | 2001-01-23 | 2001-02-07 |  |  |  | N/A | 2000-12-07 |  | 2000-12-15 | 2001-01-09 | [6 empty] | 2001-01-30 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 80 | 0 | 27 | K 739 494 | 240 | 0 | 27 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 27 | 27 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 54 | N/A | Galati | FO | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | RBS | [7 empty] | 30/outdoor |  |  | ? | N/A |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A |  |  |  | Marian-CW | Cosmorom | [32 empty] | 118 | Parscov | Buzau | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | BX814 | SARATA MONTEORU_RTC | Buzau area(9) | BX814 Sarata Monteoru_RTC | Moldova | 45 17 10 | 26 33 06 | 45 08.48.2 | 26 38 31.7 | Romtelecom, Sarata Monteoru | Romtelecom/DTc Buzau-Dir. Costea Nicolae | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  | 0 | TE | 30 |  | N/A | DIEKAT | OK | CRIS-CORI | 2001-01-12 | 2001-02-14 | YesV | 2001-04-23 | Bogdan | 2001-03-14 | 2001-05-03 |  |  |  | N/A | 2000-12-07 |  | 2000-12-14 | 2001-01-09 | [6 empty] | 2001-02-16 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 130 | 0 | 27 | K 739 494 | 220 | 0 | 27 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 30 | 30 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 60 | N/A | Galati | HDSL | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | RBS | [10 empty] | ? | N/A |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A |  |  |  | Eugen-CW | Cosmorom | [32 empty] | 118 | Sarata Monteoru | Buzau | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | BX818 | SAHATENI_RTC | Buzau area(9) | BX819 Ulmeni_RTC | Moldova | 45 02 04 | 26 31 06 | 45 02 04 | 26 31 06 | Romtelecom, Sahateni | Romtelecom/DTc Buzau-Dir. Costea Nicolae/ Dl. Zaharia | MAXITE | M | 1 | 2 | 2PBC | [7 empty] | N/A | N/A |  |  |  | 0 | TE | 30 |  | N/A | DIEKAT | OK | CRIS-CORI | 2001-01-12 | 2001-02-14 | YesV | 2001-04-23 | Bogdan | 2001-03-14 | 2001-05-03 |  |  |  | N/A | 2000-12-07 |  | 2000-12-15 | 2001-01-09 |  |  |  | 2001-02-16 | ICOM | SVF | 2001-02-16 | 2001-02-16 | 2001-02-19 | 2001-03-06 | 2001-03-12 |  | Yes | Bogdan Bogodai | 2001-04-23 | 2001-04-23 | 2001-04-23 |  |  | AAU | 60 | 0 | 27 | AAU | 240 | 0 | 27 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 35 | 35 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 70 | N/A | Galati | FO | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | [10 empty] | BX819 | ULMENI_RTC |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | RADU | OK | N/A |  | N/A | N/A |  |  | 2001-03-20 | Marian-CW | Cosmorom | [32 empty] | 127 | Sahateni | Buzau | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | BX819 | ULMENI_RTC | Buzau area(9) | BX819 Ulmeni_RTC | Moldova | 45 04 45 | 26 30 20 | 45 04 45 | 26 30 20 | Romtelecom, Ulmeni | Romtelecom/DTc Buzau-Dir. Costea Nicolae | MAXITE | M | 1 | 2 | 2PBC | [7 empty] | N/A | N/A |  |  |  | 0 | TE | 30 |  | N/A | DIEKAT | OK | COMENS | 2001-01-12 | 2001-02-12 | YesV | 2001-03-19 | Marin | 2001-03-08 | 2001-03-21 |  |  |  | N/A | 2000-12-07 |  | 2000-12-15 | 2001-01-09 |  |  |  | 2001-02-14 | ICOM | Interactive | 2001-02-14 | 2001-02-14 | 2001-02-15 | 2001-02-20 | 2001-02-21 |  | Yes | Bogdan Bogodai | 2001-04-23 | 2001-04-23 | 2001-04-23 |  |  | AAU | 60 | 0 | 27 | AAU | 250 | 0 | 27 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 35 | 35 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 70 | N/A | Galati | FO | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | [7 empty] | 30/Outdoor |  |  | BSC22 | BSC GALATI |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | RADU | OK | N/A |  | N/A | N/A |  |  | 2001-03-20 | Marian-CW | Cosmorom | [32 empty] | 228 | Ulmeni | Buzau | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | BX824 | BALTA ALBA_RTC | Buzau area(9) | BX088 Buzau_RTC | Moldova | 45 18 16 | 27 17 08 | 45 18 16 | 27 17 08 | Romtelecom, Com. Balta Alba | Romtelecom/DTc Buzau-Dir. Costea Nicolae | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  | 0 | TE | 35 |  | N/A | DIEKAT | OK | COMENS | 2000-12-21 | 2001-02-12 | YesV | 2001-03-06 | Marin | 2001-02-21 | 2001-03-13 |  |  |  | N/A | 2000-12-07 |  | 2000-12-12 | 2001-01-09 | [6 empty] | 2001-02-14 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 100 | 0 | 32 | K 739 494 | 290 | 0 | 32 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 40 | 40 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 90 | N/A | Galati | FO | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | RBS | [7 empty] | 60/Outdoor |  |  | BX088 | BUZAU_RTC |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A |  |  |  | Marian-CW | Petrica BURGHIU | [32 empty] | 40 | Balta Alba | Buzau | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | BX826 | ISACCEA BLOC | Road Tulcea-Braila(6) | BX065 Braila_RTC3 | Moldova | 45 16 26 | 28 27 28 | 45 16 26 | 28 27 28 | Str. Crinului nr.6, bl.85, sc.D | Str. Crinului nr.6, bl.85, sc.D/Asociatia de propietari nr.1Marin Mihai, tel. 040/540010 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [12 empty] | 14 | B | 14 | T4m+T4m | N/A | DIEKAT | OK | ORION | 2001-05-15 | 2001-06-18 | YesV | 2001-07-04 | Bogdan |  | 2001-06-12 |  |  |  |  | 2001-04-18 |  | 2001-05-09 | 2001-06-04 | [6 empty] | 2001-07-11 | [7 empty] | RBS 2101 BX136 |  |  |  |  | K 739 494 | 0 | 0 | 17 | K 739 494 | 140 | 0 | 17 | K 739 494 | 260 | 0 | 17 |  |  |  |  | N/A | 10 | 10 | 7/8" | 10 | 10 | 7/8" | 10 | 10 | 7/8' |  |  |  | 60 | ML 38 E 1+0 | Galati | MW | 163 | 0.3 | 16 | 10 | [7 empty] | RBS | [10 empty] | BX135 | ISACCEA TURN | 343 |  | 40/0.3 | 50 | [23 empty] | SORIN UNTARU | Cosmorom | [33 empty] | Isaccea | Tulcea | [7 empty] | 2 |  |  | 2
Phase_3 | CS | BX827 | GARII | Tulcea(5+1) | YX829 Mahmudia_RTC | Dobrogea | 45 10 46.4 | 28 48 06.3 | 43 44 51.8 | 24 52 12.6 | Str. Garii, nr2, bl.1, sc.A | Asociatia de propietarilor 2001 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [12 empty] | 37 | B | 37 | T4.5m+T4.5m | N/A | SVF | OK | CRIS-CORI | 2001-07-12 | 2001-07-25 | in exec |  | Bogdan |  |  | 2001-05-16 | 2001-06-22 |  | N/A | 2001-05-16 |  | OK | 2001-07-09 | [19 empty] | K 739 494 | 80 | 0 | 40.7 | K 739 494 | 180 | 0 | 40.6 | K 739 494 | 270 | 0 | 40.7 | N/A | N/A | N/A | N/A | N/A | 17 | 17 | 7/8" | 17 | 17 | 7/8" | 17 | 17 | 7/8" | N/A | N/A | N/A | 102 |  | Galati | MW | 131 | 0.3 | 40.7 | 17 | [18 empty] | YX829 | MAHMUDIA_RTC | 311 | acest link nu este proiectat la data venirii DDE | [25 empty] | Petrica BURGHIU | Tiberiu LICA | [33 empty] | Tulcea | Tulcea | [7 empty] | missing |  |  | 3
Phase_3 | CS | BX831 | 11 IUNIE | Braila(1) | BX063 Independentei_RTC | Dobrogea | 45 16 24.5 | 27 58 26.2 | 45 16 18.5 | 27 58 33.8 | str. Calea Galati, nr.8, bl.11 iunie,sc.2 | Asociatia de locataribl. 11 Iunie, sc.2 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | YES |  |  |  |  | 26.05 | B | 26.05 | new pylonet 6m | N/A | SVF | OK | CRIS-CORI | 2001-07-12 | 2001-07-25 | in exec |  | Bogdan | [5 empty] | 2001-05-07 |  |  |  | 2001-06-08 | [14 empty] | CW NOT STARTED |  |  |  |  | K 739 494 | 60 | 2 | 32 | K 739 494 | 180 | 2 | 32 | K 739 494 | 330 | 2 | 32 |  |  |  |  | N/A | 11 | 11 | 7/8" | 11 | 11 | 7/8" | 11 | 11 | 7/8" |  |  |  | 66 | ML 23 E 1+0 | Galati | MW | 310 | 0.3 | 29 | 8 | [18 empty] | BX063 | INDEPENDENTEI_RTC | [27 empty] | SORIN UNTARU | CATALINA CIOCAN | [33 empty] | Braila | Braila | [7 empty] | 3 |  |  | missing
Phase_3 | CS | BX832 | NEPTUN | Tulcea(5+1) | YX829 Mahmudia_RTC | Dobrogea | 45 09 56.6 | 28 48 14.2 | 45 09 56.6 | 28 48 14.2 | Str. Neptun, bl. R3, sc.C | Asociatia de locatari, nr.9 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | YES |  |  |  |  | 15.20 | B | 15.20 | new pylonet-9m | N/A | SVF | OK | VEGA | 2001-07-12 | 2001-07-25 | in exec |  | Bogdan |  |  | 2001-05-16 |  |  | 2001-05-08 | 2001-05-16 |  | 2001-06-12 | 2001-06-14 | [14 empty] | CTR |  |  |  |  | K 739 494 | 30 | 0 | 23 | K 739 494 | 250 | 0 | 23 | K 739 494 | 320 | 0 | 23 |  |  |  |  | N/A | 15 | 15 | 7/8" | 15 | 15 | 7/8" | 15 | 15 | 7/8" |  |  |  | 90 |  | Galati | MW | 332 | 0.3 | 19 | 12 | [7 empty] | N/A | [10 empty] | BX835 | VICTORIEI | 152 | 0.3 | 23 | 17 | [23 empty] | Petrica BURGHIU | Tiberiu LICA | [33 empty] | Tulcea | Tulcea | [7 empty] | 3 |  |  | 3
Phase_3 | CS | BX833 | TABEREI | Tulcea(5+1) | YX829 Mahmudia_RTC | Dobrogea | 45 11 16.7 | 28 46 40.3 | 45 11 16.7 | 28 46 40.3 | Str. Taberei, nr.38, bl.C3, sc.B | Asociatia de locatari,adm. Gheorghe Voicu, tel. 093/944068 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | YES |  |  |  |  | 29.3 | B | 29.3 | S5m+S5m | N/A | SVF | OK | VEGA | 2001-07-12 | 2001-07-25 | in exec |  | Bogdan |  |  | 2001-05-16 |  |  |  | 2001-05-16 |  | 2001-06-12 | 2001-06-14 | [14 empty] | CTR |  |  |  |  | K 739 494 | 70 | 0 | 32.4 | K 739 494 | 155 | 0 | 32.3 | K 739 494 | 220 | 0 | 32.4 |  |  |  |  | N/A | 12 | 12 | 7/8" | 9 | 9 | 7/8" | 9 | 9 | 7/8" |  |  |  | 60 |  | Galati | MW | 116 | 0.3 | 30.8 | 11 | [7 empty] | N/A | [10 empty] | BX827 | GARII | 296 | 0.3 | 39.6 | 17 | [23 empty] | Petrica BURGHIU | Tiberiu LICA | [33 empty] | Tulcea | Tulcea | [7 empty] | 3 |  |  | missing
Phase_3 | CS | BX835 | VICTORIEI | Tulcea(5+1) | YX829 Mahmudia_RTC | Dobrogea | 45 10 38.9 | 28 47 42.8 | 45 10 38.2 | 28 47 42.3 | Str. Victoriei, bl.14, sc.B | Asociatia de Locatari nr.44 Tulcea | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | YES |  |  |  |  | 19.85 | B | 19.85 | new pilonet-9m | N/A | SVF | OK | CRIS-CORI | 2001-07-12 | 2001-07-25 | in exec |  | Bogdan |  |  | 2001-05-16 |  |  | OK | 2001-05-16 |  | 2001-05-25 | 2001-06-14 | [14 empty] | CW NOT STARTED |  |  |  |  | K 739 494 | 60 | 0 | 28 | K 739 494 | 180 | 0 | 28 | K 739 494 | 300 | 0 | 28 |  |  |  |  | N/A | 20 | 20 | 7/8" | 20 | 20 | 7/8" | 20 | 20 | 7/8" |  |  |  | 120 | ML 38 E 1+0 | Galati | MW | 97 | 0.3 | 23 | 17 | [7 empty] | N/A | [10 empty] | YX829 | MAHMUDIA_RTC | 276 | 0.3 | 18 | 45 | [23 empty] | Petrica BURGHIU | Tiberiu LICA | [33 empty] | Tulcea | Tulcea | [7 empty] | 3 |  |  | 3
Phase_3 | CS | BX838 | PACII | Tulcea(5+1) | YX829 Mahmudia_RTC | Dobrogea | 45 10 21.6 | 28 48 20.8 |  |  |  |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [17 empty] | SVF* | [6 empty] | Bogdan* |  |  | 2001-06-22 |  |  |  | 2001-05-16 | [53 empty] | Galati | MW | [22 empty] | BX827 | GARII | 158 | 0.3 | 38.8 | 17 | [23 empty] | Petrica BURGHIU | Tiberiu LICA | [42 empty] | missing |  |  | missing
Phase_2 | CS | CJ001 | SEBES_RTC | Road Sebes-Miercurea Sibiului(2) | CJ001 Sebes_RTC | Transilvania | 45 57 15.93 | 23 34 34.7 | 45 57 15.93 | 23 34 34.7 | Romtelecom Sebes |  | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-08-09 | N/A | N/A |  |  |  | 6 | B | 6 | Pilon 6m existent | Room | SVF | OK | SETRACO | 2000-06-25 | 2000-07-14 | YesV | 2000-07-25 | Mugur | 2000-08-04 | 2000-09-04 |  |  |  | N/A | 2000-05-10 |  | 2000-05-23 | 2000-06-12 |  |  |  | 2000-08-21 | YRO | DIEKAT | 2000-08-21 | 2000-08-21 | 2000-08-22 | 2000-08-23 | 2000-08-31 |  | Yes | Constantin Mihai | 2000-12-15 | 2000-12-15 | 2000-12-15 | 2001-06-19 | 2001-07-11 | K 739 494 | 117 | 0 | 35 | K 739 494 | 205 | 0 | 35 | K 739 494 | 335 | 0 | 35 |  |  |  |  | N/A | 40 | 40 | 7/8" | 40 | 40 | 7/8" | 39 | 39 | 7/8" |  |  |  | 238 | N/A | Cluj | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | 2U-3 |  |  |  |  | 60001 | [8 empty] | 1 | BSC41 | BSC CLUJ | N/A | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PITURCESCU | OK | N/A |  | N/A | N/A | 30N01 Sebes-Cluj |  | 2000-12-15 | Cristian CROITOR | Cosmorom | [32 empty] | 250 | Sebes | Alba | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | CJ003 | CUT | Road Sebes-Miercurea Sibiului(2) | CJ001 Sebes_RTC | Transilvania | 45 55 06.35 | 23 39 48.92 | 45 55 02.7 | 23 40 14.1 | Com. Clinic, sat Deal |  | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-09-19 | N/A | N/A |  |  |  |  | TN | 50 | 50m new tower | N/A | SVF | OK | SETRACO | 2000-06-20 | 2000-08-04 | YesV | 2000-08-08 | Mugur | 2000-10-06 | 2000-08-14 |  |  |  | OK | 2000-05-12 |  | 2000-05-25 | 2000-06-22 |  |  |  | 2000-10-20 | ICOM | SVF | 2000-08-23 | 23/08/00 | 2000-10-24 | 2000-11-02 | 2000-11-03 |  | Yes | Alexandru Toma | 2001-02-22 | 2001-02-22 | 2001-02-22 | 2001-03-20 | 2001-04-10 | K 739 494 | 70 | 0 | 49 | K 739 494 | 270 | 0 | 49 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 71 | 71 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 142 | ML 23 E 1+0 | Cluj | MW | 289 | 1.2 | 47.5 | 70 | 23/58 |  |  | 4U-1 |  |  |  | RBS | [7 empty] | N/A/N/A |  | 1 | CJ001 | SEBES_RTC | 119 | 0.6 | 33.5 | 35 | 23/56 | [6 empty] | 9/2 | SVF/DIEKAT | 20.10.00-21.08.00 | 233/142 | 10/24/00-8/21/00 | 2000-10-25 | 2000-11-03 | DINCA | OK | 2001-02-22 |  | 2001-02-27 | 2001-03-02 | 30N01 Sebes-Cluj |  | 2000-12-15 | Cristian CROITOR | Cosmorom | [32 empty] | 322 | Com. Clinic | Alba | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CJ026 | TG. MURES_RTC | Targu Mures(8) | CJ026 Tg. Mures_RTC | Transilvania | 46 32 25.6 | 24 33 30.8 | 46 32 25.6 | 24 33 30.8 | Str. Piata Victoriei nr.14 |  | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-07-25 | N/A | N/A |  |  |  | 30 | B | 40 | Existed tower 10m | Room | ISAF | OK | ROMPSAR | 2000-06-12 | 2000-06-30 | YesV | 2000-07-13 | Dragos | 2000-07-24 | 2000-07-26 |  |  |  | N/A | 2000-05-05 |  | OK | 2000-06-06 |  |  |  | NA | YRO | NA | 2000-07-25 | 2000-07-25 | 2000-07-26 | 2000-07-30 | 2000-08-02 |  | Yes | Ionut Grigorescu | 2000-10-30 | 2000-10-25 | 2000-10-25 | 2000-11-09 | 2000-11-22 | K 739 494 | 0 | 0 | 52 | K 739 494 | 120 | 0 | 52 | K 739 494 | 240 | 0 | 45 |  |  |  |  | N/A | 50 | 50 | 7/8" | 50 | 50 | 7/8" | 45 | 45 | 7/8" |  |  |  | 290 | N/A | Tg. Mures | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | 4U-1(TMR9202) |  |  |  | TMR 9202 | [9 empty] | 1 | BSC14 | BSC TG. MURES |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | IVAN | OK | N/A |  | N/A | N/A |  |  | OK | Bogdan CRAIU | Cosmorom | [32 empty] | 311 | Tg. Mures | Mures | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | CJ027 | PANDURILOR | Targu Mures(8) | CJ026 Tg. Mures_RTC | Transilvania | 46 31 59.68 | 24 34 55.51 | 46 31 59.4 | 24 34 49.8 | B-dul Pandurilor Bl. 92 | Asociatia de proprietari/Adm. Gliga Mihai, b-dul Pandurilor nr.92, et.4, ap.13, tel.065-143.072 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-10-20 | Yes | N/A |  |  |  | 25 | B | 31.5 | C4m+C4.5m | N/A | ISAF | OK | ROMPSAR | 2000-10-20 | 2000-11-13 | YesV | 2000-11-15 | Dragos | 2001-02-21 | 2000-11-22 |  |  |  |  | 2000-07-10 |  | 2000-10-04 | 2000-10-25 |  |  |  | 2000-11-10 | ICOM | Interactive | 2000-11-10 | 2000-11-10 | 2000-11-13 | 2000-11-14 | 2000-11-15 |  | Yes | Bogdan Bogodai | 2000-10-30 | 2000-11-28 | 2000-11-28 | 2000-12-05 | 2001-02-08 | K 739 494 | 5 | 0 | 32.5 | K 739 494 | 125 | 0 | 32.5 | K 739 494 | 240 | 0 | 32.5 |  |  |  |  | N/A | 15 | 15 | 7/8" | 11 | 11 | 7/8" | 22 | 22 | 7/8" |  |  |  | 96 | ML 38 E 1+0 | Tg. Mures | MW | 296 | 0.3 | 34.1/0.3 | 25 | 38/13 |  |  | 2U-3 |  |  |  | RBS | [10 empty] | CJ026 | TG. MURES_RTC | 113 | 0.3 | 52.4 | 57 | 38/17 | [6 empty] | 12 | INTERACTIVE | 2000-11-17 | 378 | 2000-11-20 | 2000-11-20 | 2000-11-23 | RADU | OK | 2000-11-28 |  | 2000-12-13 | 2001-01-10 |  |  | OK | Bogdan CRAIU | Cosmorom | [32 empty] | 352 | Tg. Mures | Mures | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CJ028 | GHEORGHE DOJA | Targu Mures(8) | CJ026 Tg. Mures_RTC | Transilvania | 46 31 23.02 | 24 32 04.32 | 46 31 23 | 24 32 04.3 | B-dul Ghe. Doja nr.181 Sc.B |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-07-25 | 2000-07-26 | MIC |  |  |  | 33 | B | 36.3 | C4.5m+C4.5m+C4.5m | N/A | ISAF | OK | ROMPSAR | 2000-06-12 | 2000-06-30 | YesV | 2000-07-13 | Dragos | 2000-07-24 | 2000-07-26 |  |  |  | 2000-05-19 | 2000-05-05 |  | 2000-05-19 | 2000-06-15 |  |  |  | NA | YRO | NA | 2000-07-25 | 2000-07-25 | 2000-07-26 | 2000-07-27 | 2000-07-29 |  | Yes | Ionut Grigorescu | 2000-10-30 | 2000-10-26 | 2000-10-26 | 2000-11-20 | 2000-11-29 | K 739 494 | 5 | 0 | 38 | K 739 494 | 125 | 0 | 38 | K 739 494 | 240 | 0 | 38 |  |  |  |  | N/A | 18 | 18 | 7/8" | 12 | 12 | 7/8" | 22 | 22 | 7/8" |  |  |  | 104 | ML 38 E 1+0 | Tg. Mures | MW | 61 | 0.3 | 38 | 10 | 38/13 |  |  | 2U-3 |  |  |  | RBS | [9 empty] | 1 | CJ029 | DAMBU PIETROS | 241 | 0.3 | 40 | 19 | 38/17 | [6 empty] | N/A | YRO | N/A | 78/80 | 2000-07-25 | 2000-07-27 | 2000-07-29 | IVAN | OK | 2000-10-26 |  | 2000-11-20 | 2001-01-08 |  |  | OK | Bogdan CRAIU | Cosmorom | [32 empty] | 312 | Tg. Mures | Mures | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CJ029 | DAMBU PIETROS | Targu Mures(8) | CJ026 Tg. Mures_RTC | Transilvania | 46 31 52.39 | 24 33 22.18 | 46 31 52.4 | 24 33 22.2 | Bd. 1848 nr.44 Bl.C67 |  | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-07-25 | N/A | N/A |  |  |  | 33 | B | 36.5 | C3.5m+C3.5m | Room | ISAF | OK | ROMPSAR | 2000-06-12 | 2000-06-30 | YesV | 2001-04-20 | Marin | 2000-07-24 | 2001-04-25 |  |  |  | 2000-05-19 | 2000-05-05 |  | 2000-05-19 | 2000-06-06 |  |  |  | NA | YRO | NA | 2000-07-25 | 2000-07-25 | 2000-07-26 | 2000-07-27 | 2000-07-28 |  | Yes | Ionut Grigorescu | 2000-10-30 | 2000-10-25 | 2000-10-25 | 2000-11-09 | 2000-11-22 | K 739 494 | 5 | 0 | 38 | K 739 494 | 125 | 0 | 38.5 | K 739 494 | 245 | 0 | 38 |  |  |  |  | N/A | 17 | 17 | 7/8" | 31 | 31 | 7/8" | 16 | 16 | 7/8" |  |  |  | 128 | ML 38 E 1+0 | Tg. Mures | MW | 10 | 0.3 | 40 | 20 | 38/17 |  |  | 4U-1 | [13 empty] | 1 | CJ026 | TG. MURES_RTC | 190 | 0.3 | 52.6/0.3 | 57 | 38/13 | [6 empty] | N/A | YRO | N/A | 80/79 | 2000-07-25 | 2000-07-27 | 2000-07-29 | IVAN | OK | 2000-10-25 |  | 2000-11-09 | 2000-11-20 |  |  | OK | Bogdan CRAIU | Cosmorom | [32 empty] | 331 | Tg. Mures | Mures | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CJ030 | CORNISEI | Targu Mures(8) | CJ026 Tg. Mures_RTC | Transilvania | 46 33 16.39 | 24 34 17.82 | 46 33 16.4 | 24 34 17.8 | Aleea Cornisei nr.32 | Asociatie de locatari/Beno Gyorgy - pres. Ap.39, 065/ 217 831 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-10-20 | Yes | N/A |  |  |  | 33.5 | B | 33.5 | C3.5m+C3.5m+C3.5m | N/A | ISAF | OK | ROMPSAR | 2000-10-09 | 2000-10-16 | YesV | 2000-11-14 | Dragos | 2000-11-10 | 2000-11-22 |  |  |  | 2000-05-19 | 2000-05-05 |  | 2000-05-19 | 2000-06-14 |  |  |  | 2000-10-20 | ICOM | SVF | 2000-10-06 | 2000-10-06 | 2000-10-24 | 2000-10-26 | 2000-10-30 |  | Yes | Durugy Iosif | 2000-12-15 | 2000-12-11 | 2000-12-11 | 2001-02-07 | 2001-02-16 | K 739 494 | 0 | 0 | 36 | K 739 494 | 120 | 0 | 36 | K 739 494 | 240 | 0 | 36 |  |  |  |  | N/A | 20 | 20 | 7/8" | 11 | 11 | 7/8" | 18 | 18 | 7/8" |  |  |  | 98 | ML 23 E 1+0 | Tg. Mures | MW | 122 | 0.6 | 36 | 20 | 23/56 |  |  | 4U-1 |  |  |  | RBS | [9 empty] | 1 | CJ032 | CORNESTI_ DRTV | 302 | 0.6 | 22 | 45 | 23/58 | [6 empty] | 9 | SVF | 2000-10-20 | 318 | 2000-10-16 | 2000-10-17 | 2000-10-20 | VLAD | OK | 2000-12-11 | PENDING |  |  |  |  | OK | Bogdan CRAIU | COSMOROM | [32 empty] | 317 | Tg. Mures | Mures | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CJ031 | AZOMURES | Targu Mures(8) | CJ026 Tg. Mures_RTC | Transilvania | 46 33 35.02 | 24 32 52.58 | 46 33 55 | 24 33 10.7 | Str. Plopilor nr.9, Tg. Mures | AZOMURES SA, Uzina de Materiale Fotosensibile - str. Plopilor nr.9/Dir. Gen. Doru Mihai Opriscan | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-10-20 | Yes | N/A |  |  |  | 54 | B | 57 | C3m+C3m | N/A | ISAF | OK | ROMPSAR | 2000-10-20 | 2000-11-13 | YesV | 2000-11-15 | Dragos | 2000-12-08 | 2000-11-22 |  |  |  | 2000-05-19 | 2000-05-05 |  | 2000-09-04 | 2000-09-21 |  |  |  | 2000-11-10 | ICOM | Interactive | 2000-11-10 | 2000-11-10 | 2000-11-13 | 2000-11-15 | 2000-11-16 |  | Yes | Durugy Iosif | 2000-12-15 | 2000-12-13 | 2000-12-13 | 2000-12-21 | 2001-01-08 | K 739 494 | 5 | 0 | 58 | K 739 494 | 125 | #N/A | 58 | K 739 494 | 245 | 0 | 58 |  |  |  |  | N/A | 20 | 20 | 7/8" | 22 | 22 | 7/8" | 20 | 20 | 7/8" |  |  |  | 124 | ML 38 E 1+0 | Tg. Mures | MW | 165 | 0.3 | 58/0.3 | 22 | 38/13 |  |  | 2U-3 |  |  |  | RBS | [9 empty] | 1 | CJ033 | PIATA TEATRULUI | 345 | 0.3 | 43.4/0.3 | 24 | 38/17 | [6 empty] | 12 | INTERACTIVE | 2000-11-17 | 376 | 2000-11-17 | 2000-11-20 | 2000-11-23 | RADU | OK | 2000-12-13 |  | 2000-12-18 | 2000-12-18 |  |  | OK | Bogdan CRAIU | #N/A | [32 empty] | 310 | Tg. Mures | Mures | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CJ032 | CORNESTI_ DRTV | Targu Mures(8) | CJ026 Tg. Mures_RTC | Transilvania | 46 32 54 | 24 35 09.82 | 46 32 54 | 24 35 09.8 | Platou Cornesti |  | 2202 | M | C+C+ | 2/2 | 2202 | [6 empty] | 2000-10-13 | N/A | N/A |  |  |  | 10 | TE | 13.3 | 16m existing tower | Room | ISAF | OK | ROMPSAR | 2000-09-27 | 2000-10-09 | YesV | 2000-10-20 | Dragos | 2000-11-10 | 2000-10-24 |  |  |  | 2000-05-19 | 2000-05-05 |  | 2000-05-19 | 2000-07-07 |  |  |  | 2000-10-20 | ICOM | SVF | 2000-10-09 | 2000-10-09 | 2000-10-24 | 2000-10-26 | 2000-10-30 |  | Yes | Durugy Iosif | 2000-12-15 | 2000-12-10 | 2000-12-10 |  |  | K 739 494 | 0 | 0 | 22 | K 739 494 | 240 | 0 | 22 | N/A | N/A | N/A | N/A |  |  |  |  | N/A | 30 | 30 | 7/8" | 30 | 30 | 7/8" | N/A | N/A | N/A |  |  |  | 120 | ML 38 E 1+0 | Tg. Mures | MW | 247 | 0.6 | 22 | 45 | 38/17 |  |  | 4U-1 | [14 empty] | CJ026 | TG. MURES_RTC | 67 | 0.6 | 44/0.3 | 50 | 38/13 | [6 empty] | 9 / N/A | SVF/YRO | 20.10.00-N/A | 305/79 | 13.10.00-25.07.00 | 2000-10-17 | 2000-10-20 | VLAD | OK | 2000-12-10 | PENDING |  |  |  |  | OK | Bogdan CRAIU | COSMOROM | [32 empty] | 450 | Tg. Mures | Mures | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CJ033 | PIATA TEATRULUI | Targu Mures(8) | CJ026 Tg. Mures_RTC | Transilvania | 46 32 49.3 | 24 33 41.8 | 46 32 44.4 | 24 33 37.8 | Str. Piata Teatrului nr.1, bl.U1 | Asociatie locatari/Boier Gheorghe - administrator, str. Piata Teatrului nr.1, bl.1, ap.29, tel.065-167.077 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-11-17 | Yes | N/A |  |  |  | 38 | B | 41.4 | S4m+S4m+S4m | N/A | ISAF | OK | PROFIL | 2000-10-30 | 2000-11-22 | YesV | 2000-11-28 | Dragos | 2000-11-23 | 2000-12-07 |  |  |  |  | 2000-07-10 |  | 2000-09-21 | 2000-10-25 |  |  |  | 2000-11-17 | ICOM | Interactive | 2000-11-17 | 2000-11-17 | 2000-11-21 | 2000-11-22 | 2000-11-22 |  | Yes | Durugy Iosif | 2000-12-15 | 2000-12-12 | 2000-12-12 | 2001-02-08 | 2001-02-16 | K 739 494 | 0 | 0 | 41.8 | K 739 494 | 120 | 0 | 41.8 | K 739 494 | 240 | 0 | 41.8 |  |  |  |  | N/A | 22 | 22 | 7/8" | 22 | 22 | 7/8" | 15 | 15 | 7/8" |  |  |  | 118 | ML 38 E 1+0 | Tg. Mures | MW | 194 | 0.3 | 43.4/0.3 | 24 | 38/17 |  |  | 2U-3 |  |  |  | RBS | [9 empty] | 1 | CJ026 | TG. MURES_RTC | 17 | 0.3 | 43.6/0.3 | 50 | 38/13 | [6 empty] | 12 | INTERACTIVE | 2000-11-17 | 377 | 2000-11-17 | 2000-11-20 | 2000-11-22 | RADU | OK | 2000-12-12 |  | 2000-12-18 | 2000-12-18 |  |  | OK | Bogdan CRAIU | Cosmorom | [32 empty] | 308 | Tg. Mures | Mures | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CJ034 | REGHIN_RTC | Reghin(3) | CJ034 Reghin_RTC | Transilvania | 46 47 01.7 | 24 42 07.3 | 46 47 02.3 | 24 42 08.4 | Str. Ion Creanga nr.3 | Romtelecom/ | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-07-12 | N/A | N/A |  |  |  | 18 | B | 18 | C4.5m+C4.5m | Room | ISAF | OK | ISAF | 2000-06-14 | 2000-06-26 | YesV | 2000-06-27 | Dragos | 2000-06-29 | 2000-06-29 |  |  |  | 2000-05-21 | 2000-05-06 |  | 2000-05-22 | 2000-06-26 |  |  |  | 2000-08-02 | YRO | ORION | 2000-07-03 | 2000-07-04 | 2000-08-03 | 2000-08-09 | 2000-08-13 |  | Yes | Ionut Grigorescu | 2000-10-30 | 2000-10-26 | 2000-10-26 | 2000-11-09 | 2000-11-22 | K 739 494 | 0 | 0 | 21 | K 739 494 | 120 | 0 | 21 | K 739 494 | 240 | 0 | 21 |  |  |  |  | N/A | 25 | 25 | 7/8" | 25 | 25 | 7/8" | 25 | 25 | 7/8" |  |  |  | 150 | N/A | Tg. Mures | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | 4U-1(TMR9202) |  |  |  | TMR 9202 | 60034 | 2001-05-07 | [7 empty] | 1 | BSC14 | BSC TG. MURES |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PAUN | OK | N/A |  | N/A | N/A | 30N01 |  | OK | Bogdan CRAIU | Cosmorom | [32 empty] | 398 | Reghin | Mures | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | CJ035 | LIBERTATII | Reghin(3) | CJ034 Reghin_RTC | Transilvania | 46 46 31.1 | 24 42 11.9 | 46 46 31 | 24 42 12.2 | Str. Libertatii Bl. 2 Sc.4 |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-07-25 | 2000-08-02 | N/A |  |  |  | 31 | B | 31 | C3.5m+C3.5m+C3.5m | N/A | ISAF | OK | ISAF | 2000-06-14 | 2000-06-26 | YesV | 2000-06-27 | Dragos | 2000-06-29 | 2000-11-22 |  |  |  | 2000-05-21 | 2000-05-06 |  | 2000-05-22 | 2000-06-15 |  |  |  | 2000-08-02 | YRO | ORION | 2000-07-04 | 2000-07-04 | 2000-08-03 | 2000-08-09 | 2000-08-11 |  | Yes | Ionut Grigorescu | 2000-10-30 | 2000-10-26 | 2000-10-26 | 2000-11-09 | 2000-11-22 | K 739 494 | 115 | 0 | 33 | K 739 494 | 235 | 0 | 33 | K 739 494 | 355 | 0 | 33 |  |  |  |  | N/A | 24 | 24 | 7/8" | 24 | 24 | 7/8" | 24 | 24 | 7/8" |  |  |  | 144 | ML 38 E 1+0 | Tg. Mures | MW | 355 | 0.3 | 33 |  | 38/17 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [9 empty] | 1 | CJ034 | REGHIN_RTC | 175 | 0.3 | 21.2 | 23 | 38/13 | [6 empty] | 1 | ORION | 2000-08-02 | 117 | 2000-08-11 | 2000-08-09 | 2000-08-11 | PAUN | OK | 2000-10-26 |  | 2000-11-09 | 2000-11-20 | 30N01 |  | OK | Bogdan CRAIU | Cosmorom | [32 empty] | 386 | Reghin | Mures | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CJ036 | TURN_RGA | Reghin(3) | CJ034 Reghin_RTC | Transilvania | 46 46 36 | 24 40 35 | 46 46 54.3 | 24 40 45.6 | Extravilan localitatea Reghin, Turn Regia Generala a apelor |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-09-19 | N/A | N/A |  |  |  | 0 | TE | 50 | 50m new tower | N/A | ISAF | OK | ISAF | 2000-07-15 | 2000-07-31 | YesV | 2000-08-01 | Dragos | 2000-11-27 | 2000-08-09 |  |  |  | 2000-05-21 | 2000-05-06 |  | 2000-05-22 | 2000-06-15 |  |  |  | 2000-09-08 | YRO | DIEKAT | 2000-08-23 | 23-08-01 | 2000-09-09 | 2000-09-09 | 2000-09-13 |  | Yes | Bogdan Bogodai | 2000-10-30 | 2000-11-12 | 2000-11-12 | 2000-12-21 | 2001-01-08 | K 739 494 | 115 | 0 | 51.5 | K 739 494 | 235 | 0 | 51.5 | K 739 494 | 330 | 0 | 51.5 |  |  |  |  | N/A | 76 | 76 | 1 1/4" | 76 | 76 | 1 1/4" | 76 | 76 | 1 1/4" |  |  |  | 456 | ML 38 E 1+1 | Tg. Mures | MW | 82 | 0.6 | 55 | 80 | 38/17 | YES | 4x2/8 | 2U-3 | 4U-1 |  |  | RBS | XC60034 | [9 empty] | CJ034 | REGHIN_RTC | 262 | 0.3 | 21.2 | 30 | 38/13 | [6 empty] | 4 / 63* | DIEKAT | 8.09.00 /4.05.01 | 885 | 2001-05-04 | 2000-09-09 | 2000-09-13 | DINCA | OK | 2000-11-12 |  | 2000-11-29 | 2000-11-29 | 30N02 |  | OK | Bogdan CRAIU | Cosmorom | [32 empty] | 473 | Reghin | Mures | [5 empty] | 1 | 1 | 2 | 1 | 1 | 2
Phase_2 | CS | CJ037 | GARII | Bistrita(2+1) | CJ078 Bistrita_RTC | Transilvania | 47 07 58.5 | 24 29 14 | 47 07 58.5 | 24 29 14 | Str. Garii nr.30 Sc.A si B |  | 2202 | M/E | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-08-08 | N/A | N/A |  |  |  | 42.5 | B | 42.6 | C3.5m+C3.5m | Room | ISAF | OK | EL-MONT | 2000-07-20 | 2000-07-27 | YesV | 2000-08-02 | Dragos | 2000-08-03 | 2000-08-09 |  |  |  | OK | 2000-05-15 |  | OK | 2000-06-14 |  |  |  | 2000-08-08 | YRO | ORION | 2000-08-08 | 2000-08-04 | 2000-08-09 | 2000-08-10 | 2000-08-14 |  | Yes | Alexandru Bucur | 2000-09-08 | 2000-09-08 | 2000-09-08 | 2000-12-08 | 2001-01-08 | K 739 494 | 55 | 0 | 45.6 | K 739 494 | 175 | 0 | 45.6 | K 739 494 | 295 | 0 | 45.6 |  |  |  |  | N/A | 54 | 54 | 1 1/4" | 17 | 17 | 7/8" | 17 | 17 | 7/8" |  |  |  | 0 | ML 38 E 1+0 | Tg. Mures | MW | 60.62 | 0.3 | 45.6 | 25 | 38/18 |  | 4x2/8 | 2U-3 | 4U-1 |  |  | Indoor Comteck | [9 empty] | 1 | CJ078 | BISTRITA_RTC | 240 | 0.3 | 9.1 | 50 | 38/14 | [6 empty] | 2 | ORION | 2000-08-08 | 112 | 2000-08-09 | 2000-08-10 | 2000-08-14 | PAUN | OK | 2000-09-08 |  | 2000-09-21 | 2000-09-25 |  |  | OK | Bogdan CRAIU | Cosmorom | [32 empty] | 349 | Bistrita | Bistrita Nasaud | [5 empty] | 1 | 1 | 2 | 1 | 1 | 2
Phase_2 | CS | CJ038 | CALEA MOLDOVEI | Bistrita(2+1) | CJ078 Bistrita_RTC | Transilvania | 47 08 28.8 | 24 30 21.9 | 47 08 29.4 | 24 30 21.1 | Calea Moldovei, bl.1, sc.B, Bistrita | Asociatie de locatari/Rebreanu I., presedinte bloc, Calea Moldovei, bl.1, sc.B, et.6, ap. , Bistrita, tel. 094-555.085 | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-09-04 | N/A | N/A |  |  |  | 36 | B | 36.4 | T3.5m+C3.5m | Room | ISAF | OK | EL-MONT | 2000-07-20 | 2000-07-27 | YesV | 2000-08-23 | Dragos | 2000-08-30 | 2000-08-30 |  |  |  | 2000-05-22 | 2000-05-15 |  | 2000-05-22 | 2000-07-24 |  |  |  | 2000-08-30 | YRO | ORION | 2000-08-30 | 2000-08-30 | 2000-08-30 | 2000-08-31 | 2000-09-04 |  | Yes | Burghiu Petrica | 2000-09-14 | 2000-09-15 | 2000-09-28 | 2000-12-08 | 2001-01-08 | K 739 494 | 50 | 0 | 37.8 | K 739 494 | 175 | 0 | 37.4 | K 739 494 | 295 | 0 | 37.4 |  |  |  |  | N/A | 27 | 27 | 7/8'' | 25 | 25 | 7/8'' | 25 | 25 | 7/8'' |  |  |  | 154 | ML 23 E 1+0 | Tg. Mures | MW | 236 | 0.6 | 39.65 | 22 | 23/56 |  | 4x2/8 | 2U-3 |  |  |  | N/A | [9 empty] | 1 | CJ037 | GARII | 56.8 | 0.6 | 45.6 | 17 | 23/58 | [6 empty] | 6 | ORION | 2000-08-31 | 163 | 2000-08-31 | 2000-08-31 | 2000-09-04 | PAUN | OK | 2000-09-28 |  | 2000-10-04 | 2000-12-06 |  |  | OK | Bogdan CRAIU | CATALINA CIOCAN | [32 empty] | 360 | Bistrita | Bistrita Nasaud | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CJ040 | TURN DEALUL GARII | Sighisoara(3+1) | CJ079 Sighisoara_RTC | Transilvania | 46 13 45.7 | 24 47 42.6 | 46 13 45.7 | 24 47 42.6 | Str. Dealul Garii, Turn Conel | Conel/ | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-10-20 | N/A | N/A |  |  |  | 0 | TE | 41.5 |  | N/A | ISAF | OK | DUAL | 2000-10-23 | 2000-11-08 | YesV | 2000-11-08 | Dragos | 2001-06-06 | 2001-02-07 |  |  |  | 2000-05-21 | 2000-05-15 |  | 2000-05-22 | 2001-01-04 |  |  |  | 2000-11-09 | ICOM | TRY | 2000-10-06 | 2000-10-06 | 2000-11-09 | 2000-11-09 | 2000-11-10 |  | Yes | Alexandru Toma | 2001-03-03 | 2001-03-02 | 2001-03-02 | 2001-04-24 | 2001-05-03 | K 739 494 | 120 | 0 | 29 | K 739 494 | 210 | 0 | 27 | K 739 494 | 330 | 0 | 29 |  |  |  |  | N/A | 37 | 37 | 7/8" | 35 | 35 | 7/8" | 37 | 37 | 7/8" |  |  |  | 218 | ML 38 E 1+0 | Tg. Mures | MW | 181 | 0.3 | 27/0.3 | 40 | 38/13 | YES | 4x2/8 | 4U-1 |  |  |  | RBS | [9 empty] | 1 | CJ079 | SIGHISOARA_RTC | 0 | 0.3 | /0.3 | 20 | 38/17 | [6 empty] | 15 | INTERACTIVE | 2000-10-04 | 387 | 2000-11-21 | 2001-01-10 | 2001-02-09 | IVAN | OK | 2001-03-02 |  | 2001-03-21 | 2001-04-06 |  |  | 2000-11-01 | Petrica BURGHIU | Cosmorom | [32 empty] | 435 | Sighisoara | Mures | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CJ041 | TELESON | Sighisoara(3+1) | CJ079 Sighisoara_RTC | Transilvania | 46 13 40 | 24 48 49.1 | 46 13 40.3 | 24 48 48.3 | Str. Mihai Viteazu nr.40 |  | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-08-08 | N/A | N/A |  |  |  | 33 | B | 36.6 | T4.5m+T3.5m | Room | ISAF | OK | DUAL | 2000-07-08 | 2000-07-17 | YesV | 2000-07-28 | Dragos | 2000-08-08 | 2000-08-03 |  |  |  | 2000-05-21 | 2000-05-15 |  | 2000-05-22 | 2000-06-15 |  |  |  | 2000-09-05 | YRO | TRY | 2000-08-14 | 2000-08-14 | 2000-09-05 | 2000-09-06 | 2000-09-08 |  | Yes | Ion Soare | 2001-03-03 | 2001-03-03 | 2001-03-03 | 2001-06-15 | 2001-07-11 | K 739 494 | 0 | 0 | 38.4 | K 739 494 | 60 | 0 | 38.4 | K 739 494 | 240 | 0 | 38.4 |  |  |  |  | N/A | 16 | 16 | 7/8" | 16 | 16 | 7/8" | 16 | 16 | 7/8" |  |  |  | 96 |  | Tg. Mures | MW | 276 | 0.3 | 37.8/0.3 | 30 | 38/18 |  | 4x2/8 | 2U-3 | [13 empty] | 1 | CJ040 | TURN DEALUL GARII | 97 | 0.3 | 27/0.3 | 45 | 38/14 | [6 empty] | 15 | INTERACTIVE | 2000-10-04 | 386 | 2000-11-21 | 2000-11-22 | 2000-11-24 | DINCA | OK | 2001-03-02 |  | 2001-03-21 | 2001-04-06 |  |  | 2000-11-01 | Bogdan CRAIU | Cosmorom | [32 empty] | 392 | Sighisoara | Mures | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CJ042 | ZUGRAVILOR | Sighisoara(3+1) | CJ079 Sighisoara_RTC | Transilvania | 46 12 50.6 | 24 47 02.9 | 46 12 57.4 | 24 47 49.8 | Str. Zugravilor (fost Axente Sever), Top parcela 8240/5/2 | Sandru Stefan - Str. Izvorului nr.45, Sighisoara/Sandru Stefan - Str. Izvorului nr.45, Sighisoara | 2102 | M | C+C+C+ | 2/2/2 | N/A | [12 empty] | 0 | TN | 30 |  | N/A | ISAF | OK | IMSAT | 2000-12-08 | 2001-03-12 | YesV | Respins | Marin | 2001-06-06 | [5 empty] | 2000-09-08 |  | 2000-10-27 | 2000-12-15 |  |  |  | 2001-03-15 | ICOM | Interactive | 2001-03-13 | 2001-03-13 | 2001-03-20 | 2001-03-20 | 2001-03-23 |  | Yes | Mircea Mihut | 2001-05-11 | 2001-05-11 | 2001-05-11 |  |  | K 739 494 | 90 | 0 | 30 | K 739 494 | 210 | 0 | 30 | K 739 494 | 330 | 0 | 30 |  |  |  |  | N/A | 40 | 40 | 7/8" | 40 | 40 | 7/8" | 40 | 40 | 7/8" |  |  |  | 240 | ML 38 E 1+0 | Tg. Mures | MW | 320 | 0.3 | 25/0.3 | 35 | 38/13 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [9 empty] | 1 | CJ079 | SIGHISOARA_RTC | 141 | 0.3 | 30 | 20 | 38/17 | [6 empty] | 43* | INTERACTIVE | 2001-03-15 | 719 | 2001-03-19 | 2001-03-20 | 2001-05-09 | IVAN | OK | 2001-05-11 |  | 2001-05-23 | 2001-05-25 |  |  | 2000-11-01 | Bogdan CRAIU | [33 empty] | 365 | Sighisoara | Mures | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CJ043 | ALBA IULIA_ RTC | Alba Iulia(5) | CJ043 Alba Iulia_RTC | Transilvania | 46 04 08 | 23 34 50 | 46 04 08 | 23 34 50 | Str. I.C.Bratianu nr.2, Alba Iulia, jud. Alba | RTC Alba Iulia/Roman Nicolae - sef serviciu comutatie, tel: 058/ 634 119, 094/ 695 159; Parjol - dir. Tehnic 058/621 933/ Fleresu (Fibra optica); Lischman (sef transmisiuni) | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-06-28 | N/A | N/A |  |  |  | 32 | B | 32 | Pilon 12m | Room | IMSAT | OK | IMSAT | 2000-05-30 | 2000-06-09 | YesV | 2000-06-13 | Relu | 2000-06-16 | 2000-06-19 |  |  |  | 2000-05-22 | 2000-05-10 |  | 2000-05-29 | 2000-06-29 |  |  |  | 2000-08-02 | YRO | ORION | 2000-07-21 | 2000-07-21 | 2000-08-03 | 2000-08-14 | 2000-08-16 |  | Yes | Theo Radoi | 2000-09-05 | 2000-09-08 | 2000-09-08 | 2000-09-18 | 2000-09-21 | K 739 494 | 0 | 0 | 39.5 | K 739 494 | 120 | #N/A | 39.5 | K 739 494 | 240 | 0 | 39.5 |  |  |  |  | N/A | 31 | 31 | 7/8" | 31 | 31 | 7/8" | 31 | 31 | 7/8" |  |  |  | 186 | N/A | Cluj | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | 4U-1(TMR9202) |  |  |  | TMR 9202 | 60043 | 2001-05-25 | [5 empty] | 75/8 pairs indoor |  | 1 | BSC41 | BSC CLUJ | N/A | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | DINCA | OK | N/A |  | N/A | N/A | 30N01 Alba Iulia-Cluj |  | OK | SORIN UNTARU | SORIN UNTARU | [32 empty] | 238 | Alba Iulia | Alba | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | CJ044 | AVANTULUI | Alba Iulia(5) | CJ043 Alba Iulia_RTC | Transilvania | 46 04 32.7 | 23 33 55.7 | 46 04 32.7 | 23 33 55.7 | Str. Avantului BL.AV2 | Asociatie de proprietari/Fam. Filip - str. Avantului nr.45 bl.AV2 sc.A ap.14 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-12-11 | Yes | N/A |  |  |  | 15 | B | 15 | C4m+C4m | N/A | IMSAT | OK | IMSAT | 2000-10-20 | 2000-11-03 | YesV | 2000-11-14 | Relu | 2000-11-21 | 2000-11-23 |  |  |  |  | 2000-08-20 |  | 2000-10-16 | 2000-11-20 |  |  |  | 2000-11-10 | ICOM | Interactive | 2000-11-10 | 2000-11-10 | 2000-11-13 | 2000-11-14 | 2000-11-18 |  | Yes | Ion Soare | 2001-05-18 | 2001-06-02 | 2001-06-02 | 2001-06-05 | 2001-06-19 | K 739 494 | 0 | 0 | 17 | K 739 494 | 120 | #N/A | 17.2 | K 739 494 | 240 | 0 | 16.5 |  |  |  |  | N/A | 14 | 14 | 7/8" | 14 | 14 | 7/8" | 18 | 18 | 7/8" |  |  |  | 92 | ML 38 E 1+0 | Cluj | MW | 54 | 0.3 | 15 | 14 | 38/17 |  |  | 2U-3 |  |  |  | RBS | [9 empty] | 1 | CJ045 | AMPOI_1 | 237 | 0.3 | 38.7/0.3 | 18 | 38/13 | [6 empty] | 15 | INTERACTIVE | 2000-10-04 | 393 | 2000-11-21 | 2000-11-22 | 2000-11-30 | IVAN | OK | 2001-06-02 |  |  |  | 30N02 Alba Iulia-Cluj |  | OK | Petrica BURGHIU | #N/A | [32 empty] | 266 | Alba Iulia | Alba | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CJ045 | AMPOI_1 | Alba Iulia(5) | CJ043 Alba Iulia_RTC | Transilvania | 46 05 14.45 | 23 35 19.08 | 46 05 14.45 | 23 35 19.08 | Str. Livezii nr.63 Bl.3 | Asociatie de locatari nr.19/Dl. Pop Ionel - presedinte asociatie locatari nr.19, Str. Livezii nr.63 Bl.3 Et.5 Ap.22, tel: 058/ 816 632 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-06-28 | N/A | N/A |  |  |  | 34 | B | 37 | C5m+C5m | N/A | IMSAT | OK | IMSAT | 2000-05-27 | 2000-06-07 | YesV | 2000-06-13 | Relu | 2000-06-16 | 2000-06-19 |  |  |  | 2000-05-22 | 2000-05-10 |  | 2000-06-05 | 2000-06-20 |  |  |  | 2000-08-02 | YRO | ORION | 2000-07-03 | 2000-07-03 | 2000-08-03 | 2000-08-14 | 2000-08-15 |  | Yes | Theo Radoi | 2000-09-05 | 2000-09-08 | 2000-09-08 | 2000-09-18 | 2000-10-04 | K 739 494 | 15 | 0 | 36.5 | K 739 494 | 220 | #N/A | 36.5 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 10 | 10 | 7/8" | 10 | 10 | 7/8" | N/A | N/A | N/A |  |  |  | 26 | ML 38 E 1+0 | Cluj | MW | 197 | 0.3 | 38.2 | 18 | 38/13 |  |  | 2U-3 |  |  |  | RBS | [9 empty] | 1 | CJ043 | ALBA IULIA_ RTC | 17 | 0.3 | 37.4 | 35 | 38/17 | [6 empty] | N/A | YRO | N/A | 91/92 | 2000-08-01 | 2000-08-02 | 2000-08-15 | DINCA | OK | 2000-09-08 |  | 2000-09-21 | 2000-10-04 | 30N01 Alba Iulia-Cluj |  | OK | SORIN UNTARU | SORIN UNTARU | [32 empty] | 240 | Alba Iulia | Alba | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CJ046 | CIMITIRUL REFORMAT | Turda(2) | CJ047 Turda_RTC | Transilvania | 46 33 58.71 | 23 47 37.91 | 46 34 00.5 | 23 47 37.6 | Cimitirul Turda Veche | /Nagy Aldbert - preot reformat, 064/ 311 174, str. Ratiu 44 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-08-09 | N/A | N/A |  |  |  | 0 | TN/9mp | 30 | 30m new tower | N/A/TMR9000 | IMSAT | OK | IMSAT | 2000-07-03 | 2000-07-21 | YesV | 2000-07-28 | Relu | 2000-11-02 | 2000-08-03 |  |  |  | 2000-05-30 | 2000-05-10 |  | 2000-06-27 | 2001-01-11 |  |  |  | 2000-09-27 | YRO | Interactive | 2000-08-25 | 25-08-00 | 2000-09-27 | 2000-10-05 | 2000-10-06 |  | Yes | Alexandru Toma | 2000-10-30 | 2000-11-04 | 2000-11-04 | 2000-11-20 | 2000-11-29 | K 739 494 | 310 | 0 | 28.5 | K 739 494 | 135 | 0 | 28.5 | K 739 494 | 210 | 0 | 28.5 |  |  |  |  | N/A | 39 | 39 | 7/8" | 39 | 39 | 7/8" | 39 | 39 | 7/8" |  |  |  | 234 | ML 23/38 E 1+1 | Cluj | MW | 298 | 0.6 | 30 | 38 | 23/58 | YES | 4x2/8 | 2U-3 | 4U-1 |  |  | TMR 9000 | 60046 | 2001-05-07 | [7 empty] | 1 | CJ047 | TURDA_RTC | 118 | 0.6 | 16 | 37 | 23/56 | [6 empty] | 7/57*BIS | INTERACTIVE/SVF | 27.09.00-20.04.01 | 232/852 | 28.09.00-18.04.01 | 2000-09-28 | 2000-10-06 | PITURCESCU | OK | 2000-11-06 | Dublare suplimentara:ACC:20.06.01 | 2000-11-20 | 2001-01-10 | 30N02 Turda-Cluj |  | OK | SORIN UNTARU | SORIN UNTARU | [32 empty] | 322 | Com. Turda veche | Cluj | [5 empty] | 1 | 1 | 2 | 1 | 1 | 2
Phase_2 | CS | CJ047 | TURDA_RTC | Turda(2) | CJ047 Turda_RTC | Transilvania | 46 34 10.59 | 23 47 09.75 | 46 34 10.59 | 23 47 09.75 | Str. 1 Decembrie 1918, nr.33-34 | RTC Turda/ | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-07-14 | N/A | N/A |  |  |  | 12 | B | 16 | C4m+C4m | Room | IMSAT | OK | IMSAT | 2000-06-05 | 2000-06-10 | YesV | 2000-06-13 | Relu | 2000-06-16 | 2000-06-19 |  |  |  | N/A | 2000-05-10 |  | 2000-05-29 | 2000-07-10 |  |  |  | 2000-08-02 | YRO | ORION | 2000-07-04 | 2000-07-04 | 2000-08-03 | 2000-08-11 | 2000-08-15 |  | Yes | Alexandru Bucur | 2000-09-05 | 2000-09-06 | 2000-09-06 | 2000-12-08 | 2001-01-08 | K 739 494 | 0 | 0 | 16.3 | K 739 494 | 120 | 0 | 16.3 | K 739 494 | 240 | 0 | 16.3 |  |  |  |  | N/A | 37 | 37 | 7/8" | 17 | 17 | 7/8" | 37 | 37 | 7/8" |  |  |  | 182 | N/A | Cluj | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | 4U-1 |  |  |  | Indoor Comteck | [9 empty] | 1 | BSC41 | BSC CLUJ | N/A | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PAUN | OK | N/A |  | N/A | N/A | 30N02 Turda-Cluj |  | OK | SORIN UNTARU | SORIN UNTARU | [32 empty] | 327 | Turda | Cluj | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | CJ048 | DEALUL ROZELOR | Dej(2) | CJ049 Dej_RTC | Transilvania | 47 08 16.37 | 23 53 24.91 | 47 08 16.37 | 23 53 24.91 | extravilan Dej, Dealul Rozelor | Teren Romtelecom/Romtelecom | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-08-16 | N/A | N/A |  |  |  | 0 | TN | 50 | Tower |  | IMSAT | OK | IMSAT | 2000-08-01 | 2000-08-31 | YesV | 2000-09-06 | Relu | 2000-12-08 | 2000-09-13 |  |  |  |  | 2000-05-13 |  | 2000-06-02 | 2001-01-11 |  |  |  | 2000-09-27 | YRO | Interactive | 2000-09-21 | 2000-09-21 | 2000-09-27 | 2000-09-28 | 2000-10-01 |  | Yes | Alexandru Toma | 2000-10-30 | 2000-11-04 | 2000-11-04 | 2000-12-06 | 2001-01-08 | K 739 494 | 165 | 0 | 48.5 | K 739 494 | 255 | 0 | 48.5 | K 739 494 | 345 | 0 | 48.5 |  |  |  |  | N/A | 60 | 60 | 1 1/4" | 60 | 60 | 1 1/4" | 60 | 60 | 1 1/4" |  |  |  | 360 | ML 23 E 1+1 | Cluj | MW | 290 | 0.6 | 47.6 | 60 | 23/56 |  |  | 2U-3 |  |  |  | RBS | [9 empty] | 1 | CJ049 | DEJ_RTC | 110 | 0.6 |  | 30 | 23/58 | [6 empty] | 7 | INTERACTIVE | 2000-09-27 | 234 | 2000-09-28 | 2001-01-30 | 2001-02-12 | PITURCESCU | OK | 2000-11-04 |  | 2000-11-20 | 2001-01-10 | 30N02 Dej-Cluj |  | OK | SORIN UNTARU | SORIN UNTARU | [32 empty] | 501 | Dej | Cluj | [5 empty] | 1 | 1 | 2 | 1 | 1 | 2
Phase_2 | CS | CJ049 | DEJ_RTC | Dej(2) | CJ049 Dej_RTC | Transilvania | 47 08 27.74 | 23 52 39.93 | 47 08 27.74 | 23 52 39.93 | Romtelecom Dej, Str. Avram Iancu nr.8 | /Pop Ioan - sef serviciu retea, tel. 095/ 601 620 | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-07-18 | N/A | N/A |  |  |  | 17 | B | 20 | T4.5m+T4.5m+T4.5m | Room | IMSAT | OK | IMSAT | 2000-06-05 | 2000-06-23 | YesV | 2000-06-29 | Relu | 2000-07-06 | 2000-07-04 |  |  |  | 2000-05-19 | 2000-05-13 |  | 2000-06-06 | 2000-06-26 |  |  |  | 2000-08-02 | YRO | ORION | 2000-07-12 | 2000-07-12 | 2000-08-03 | 2000-08-07 | 2000-08-09 |  | Yes | Alexandru Bucur | 2000-09-08 | 2000-09-08 | 2000-09-08 | 2000-10-04 | 2000-10-13 | K 739 494 | 40 | 0 | 21.5 | K 739 494 | 140 | 0 | 21.5 | K 739 494 | 260 | 0 | 21.5 |  |  |  |  | N/A | 44 | 44 | 7/8" | 16 | 16 | 7/8" | 51 | 51 | 1 1/4" |  |  |  | 222 | N/A | Cluj | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | 4U-1 |  |  |  | Indoor Comteck | 60049 | [8 empty] | 1 | BSC41 | BSC CLUJ | N/A | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PAUN | OK | N/A |  | N/A | N/A | 30N01 Dej-Cluj |  | OK | SORIN UNTARU | SORIN UNTARU | [32 empty] | 247 | Dej | Cluj | [7 empty] | Site Near=Insertion Point
Phase_2 | TM | CJ050 | ZALAU_RTC | Zalau(5+1) | CJ050 Zalau_RTC | Transilvania | 47 10 51.12 | 23 03 15.61 | 47 10 51.12 | 23 03 15.61 | Bd. Mihai Viteazu | Romtelecom/ | N/A | N/A | N/A | N/A | N/A | [7 empty] | N/A | N/A |  |  |  | N/A | B | 15 | T4m |  | IMSAT | OK | IMSAT | 2000-05-29 | 2000-06-14 | YesV | 2000-06-14 | Relu | 2000-06-16 | 2000-06-19 |  |  |  | N/A | 2000-05-26 |  | 2000-05-26 | 2000-07-10 |  |  |  | 2000-08-02 | YRO | ORION | N/A | N/A | 2000-08-03 | N/A | N/A |  | Yes | N/A | 2000-09-07 | 2000-09-08 | 2000-09-08 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A | Cluj | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | 2U-3 |  |  |  |  | 60050 | [9 empty] | BSC41 | BSC CLUJ | N/A | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | DINCA | OK | N/A |  | N/A | N/A | N/A |  | OK | SORIN UNTARU | N/A | [32 empty] | 277 | Zalau | Salaj | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | CJ051 | SARMIS | Zalau(5+1) | CJ050 Zalau_RTC | Transilvania | 47 10 54.53 | 23 03 21.37 | 47 10 54.3 | 23 03 21.3 | Bd. Mihai Viteazu nr.16 Bl.O1 | Asociatie de locatari, Dl. Varga - adm., tel: 060/ 61 965/Dl. Dobra, Ap.37, tel: 094/ 173 709 - Acces terasa | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-08-02 | 2000-08-02 | N/A |  |  |  | 33.5 | B | 37.2 | C1.6m+T4.5m+T3m | N/A | IMSAT | OK | IMSAT | 2000-06-20 | 2000-07-21 | YesV | 2000-07-28 | Relu | 2000-09-06 | 2000-08-03 |  |  |  | 2000-05-23 | 2000-05-05 |  | 2000-06-28 | 2000-07-06 |  |  |  | 2000-08-02 | YRO | ORION | 2000-08-02 | 2000-08-01 | 2000-08-03 | 2000-08-10 | 2000-08-13 |  | Yes | Alexandru Bucur | 2000-09-08 | 2000-09-09 | 2000-09-09 | 2000-09-21 | 2000-09-26 | K 739 494 | 115 | 0 | 37.7 | K 739 494 | 200 | 0 | 36.5 | K 739 494 | 340 | 0 | 37.7 |  |  |  |  | N/A | 22 | 22 | 7/8" | 7 | 7 | 7/8" | 33 | 33 | 7/8" |  |  |  | 174 | ML 38 E 1+1* | Cluj | MW | 229 | 0.3 | 35.5 | 15 | 38/18 |  |  | 4U-1 |  |  |  | RBS | [9 empty] | 1 | CJ050 | ZALAU_RTC | 49 | 0.3 | 17.5 | 25 | 38/14 | [6 empty] | 1 | ORION | 2000-08-02 | 99 | 2000-08-02 | 2000-08-10 | 2000-08-13 | DINCA | OK | 2000-09-09 |  | 2000-09-21 | 2000-09-25 | 30N01 Zalau_Cluj |  | OK | SORIN UNTARU | SORIN UNTARU | [32 empty] | 278 | Zalau | Salaj | [5 empty] | 1 | 1 | 2 | 1 | 1 | 2
Phase_2 | CS | CJ052 | DALIA | Zalau(5+1) | CJ050 Zalau_RTC | Transilvania | 47 11 31.17 | 23 03 38.93 | 47 11 27 | 23 03 41.8 | Bd. T. Vladimirescu nr.38 Bl. Dalia | Asociatie de locatari _ Brindea Floare - adm, Et.4 Ap.30, 060/ 612 850/Hategan Aurel - Et.10 Ap.62 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-08-16 | Yes | N/A |  |  |  | 27.3 | B | 35 | T4.5m+T4.5m+T4.5m | N/A | IMSAT | OK | IMSAT | 2000-06-20 | 2000-08-15 | YesV | 2000-08-23 | Relu | 2000-09-06 | 2000-08-30 |  |  |  | 2000-06-08 | 2000-05-05 |  | 2000-06-28 | 2000-07-06 |  |  |  | 2000-09-08 | YRO | DIEKAT | 2000-09-08 | 2000-09-08 | 2000-09-09 | 2000-09-09 | 2000-09-12 |  | Yes | Theo Radoi | 2000-10-09 | 2000-10-09 | 2000-10-09 | 2000-10-25 | 2000-11-09 | K 739 494 | 110 | 0 | 41.1 | K 739 494 | 230 | 0 | 41.1 | K 739 494 | 350 | 0 | 41.1 |  |  |  |  | N/A | 18 | 18 | 7/8" | 20 | 20 | 7/8" | 29 | 29 | 7/8" |  |  |  | 134 | ML 23 E 1+0 | Cluj | MW | 198 | 0.6 | 40.5 | 18 | 23/56 |  |  | 2U-3 |  |  |  | RBS | [9 empty] | 1 | CJ051 | SARMIS | 22 | 0.6 | 34.2 |  | 23/58 | [6 empty] | 4 | DIEKAT | 2000-09-08 | 183 | 2000-09-09 | 2000-09-09 | 2000-09-12 | DINCA | OK | 2000-10-28 |  | 2001-12-06 | 2001-01-10 | 30N01 Zalau_Cluj |  | OK | SORIN UNTARU | SORIN UNTARU | [32 empty] | 241 | Zalau | Salaj | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CJ053 | DEALUL NOIMAL | Zalau(5+1) | CJ050 Zalau_RTC | Transilvania | 47 12 28.72 | 23 03 40.65 | 47 12 28.2 | 23 03 42.9 | Dealul Noimal | Oprea iulian - Str. Maxim Gorki nr.20/Dan Ligia - sef administrativ | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-08-16 | N/A | N/A |  |  |  |  | TN | 30 | Tower | N/A | IMSAT | OK | IMSAT | 2000-08-20 | 2000-09-27 | YesV | 2000-10-10 | Relu | 2000-11-02 | 2000-10-13 |  |  |  | 2000-05-23 | 2000-05-05 |  | 2000-06-06 | 2000-08-11 |  |  |  | 2000-10-04 | YRO | Interactive | 2000-10-04 | 2000-10-04 | 2000-10-05 | 2000-10-09 | 2000-10-10 |  | Yes | Ion Soare | 2001-01-31 | 2001-01-31 | 2001-01-31 | 2001-03-15 | 2001-04-10 | K 739 494 | 340 | 0 | 28.5 | K 739 494 | 220 | 0 | 28.5 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 38 | 38 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 76 | ML 23 E 1+0 | Cluj | MW | 189 | 0.6 | 28 | 38 | 23/56 |  |  | 4U-1 |  |  |  | RBS | [10 empty] | CJ051 | SARMIS | 8 | 0.6 | 37.4 |  | 23/58 | [6 empty] | 8 | INTERACTIVE | 2000-10-04 | 263 | 2000-10-05 | 2000-10-09 | 2000-10-10 | PITURCESCU | OK | 2001-01-31 |  | 2001-02-21 | 2001-03-02 | 30N01 Zalau_Cluj |  | OK | SORIN UNTARU | SORIN UNTARU | [32 empty] | 320 | Zalau | Salaj | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CJ054 | BARITIU_RTC | Cluj(14) | CJ054 Baritiu_RTC | Transilvania | 46 46 24.2 | 23 35 16.7 | 46 46 24.2 | 23 35 16.7 | Romtelecom - Str. George Baritiu | /Roman Nicolae - sef serviciu comutatie, tel. 058/ 804 119, 094/ 695 159 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-07-18 | 2000-07-11 | SVF |  |  |  |  | B | 26 |  | N/A | IMSAT | OK | IMSAT | 2000-05-29 | 2000-06-07 | YesV | 2000-06-13 | Relu | 2000-06-16 | 2000-06-19 |  |  |  | 2000-05-19 | 2000-05-05 |  | 2000-05-29 | 2000-07-11 |  |  |  | NA | YRO | NA | 2000-07-11 | 2000-07-11 | 2000-07-12 | 2000-07-13 | 2000-07-21 |  | Yes | Alexandru Bucur | 2000-09-12 | 2000-09-12 | 2000-09-12 | 2000-10-18 | 2000-10-25 | K 739 494 | 0 | 0 | 34 | K 739 494 | 120 | 0 | 34 | K 739 494 | 240 | 0 | 36 |  |  |  |  | N/A | 27 | 27 | 7/8" | 27 | 27 | 7/8" | 27 | 27 | 7/8" |  |  |  | 162 | N/A | Cluj | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | 4U-1 |  |  |  | RBS | 60054 | [8 empty] | 1 | BSC41 | BSC CLUJ |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | DINCA | OK | N/A |  | N/A | N/A | 30N01 conectare locala |  | OK | SORIN UNTARU | SORIN UNTARU | [32 empty] | 318 | Cluj Napoca | Cluj | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | CJ055 | TAIETURA TURCULUI | Cluj(14) | CJ054 Baritiu_RTC | Transilvania | 46 46 34.5 | 23 33 49.9 | 46 46 36.34 | 23 33 56.4 | Str. Vantului | Hangan Mihaela Felicia - Rarau 12-14, tel: 064/ 420 344/ | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-08-16 | N/A | N/A |  |  |  | 0 | TN | 30 | 30m existing tower | N/A | IMSAT | OK | IMSAT | 2000-07-03 | 2000-08-20 | YesV | 2000-08-24 | Relu | 2000-10-24 | 2000-08-30 |  |  |  | 2000-05-30 | 2000-05-05 |  | 2000-07-03 | 2000-07-28 |  |  |  | 2000-09-27 | YRO | Interactive | 2000-09-20 | 2000-09-20 | 2000-09-27 | 2000-10-03 | 2000-10-04 |  | Yes | Alexandru Toma | 2000-10-30 | 2000-11-01 | 2000-11-01 | 2000-12-06 | 2001-01-08 | K 739 494 | 0 | 0 | 28.25 | K 739 494 | 120 | 0 | 28.25 | K 739 494 | 240 | 0 | 28.25 |  |  |  |  | N/A | 37 | 37 | 7/8" | 37 | 37 | 7/8" | 37 | 37 | 7/8" |  |  |  | 222 | ML 23 E 1+0 | Cluj | MW | 183 | 0.6 | 30.25 | 38 | 23/56 | YES | 4x2/8 | 4U-1 | 4U-1 |  |  | TMR 9000 | [9 empty] | 1 | CJ066 | MANASTUR_2 | 3 | 0.6 | 39.6 | 15 | 23/58 | [6 empty] | 7 | INTERACTIVE | 2000-09-27 | 224 | 2000-09-22 | 2000-09-28 | 2000-10-04 | PITURCESCU | OK | 2000-11-01 |  | 2000-11-20 | 2001-01-10 | 30N03 conectare locala |  | OK | SORIN UNTARU | SORIN UNTARU | [32 empty] | 402 | Cluj Napoca | Cluj | [5 empty] | 1 | 1 | 2 | 1 | 1 | 2
Phase_2 | CS | CJ056 | MANASTUR_1 | Cluj(14) | CJ054 Baritiu_RTC | Transilvania | 46 45 12.69 | 23 33 15.3 | 46 45 12.69 | 23 33 15.3 | Str. Bucegi nr.5 Bl. A3, Cartier Manastur Cluj | /Oltean iacob - adm., tel: 092/ 512 363 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-07-18 | 2000-07-11 | SVF |  |  |  | 31 | B | 34 | C3m+C3m+P3m | N/A | IMSAT | OK | IMSAT | 2000-06-12 | 2000-06-26 | YesV | 2000-06-26 | Relu | 2000-07-10 | 2000-07-04 |  |  |  | 2000-05-23 | 2000-05-05 |  | 2000-06-22 | 2000-07-11 |  |  |  | NA | YRO | NA | 2000-07-11 | 2000-07-11 | 2000-07-12 | 2000-07-13 | 2000-07-18 |  | Yes | Alexandru Bucur | 2000-09-12 | 2000-09-10 | 2000-09-10 | 2000-09-21 | 2000-09-26 | K 739 494 | 0 | 0 | 38.5 | K 739 494 | 120 | 0 | 38.5 | K 739 494 | 240 | 0 | 38.5 |  |  |  |  | N/A | 22 | 22 | 7/8" | 22 | 22 | 7/8" | 22 | 22 | 7/8" |  |  |  | 132 | ML 23 E 1+0 | Cluj | MW | 49 | 0.6 | 38 | 38 | 23/58 |  |  | 2U-3 |  |  |  | RBS | [10 empty] | CJ054 | BARITIU_RTC | 229 | 0.6 | 32 | 21 | 23/56 | [6 empty] | N/A | YRO | N/A | 54/49 | 2000-07-11 | 2000-07-13 | 2000-07-21 | DINCA | OK | 2000-09-12 |  | 2000-09-21 | 2000-09-25 | 30N01 conectare locala |  | OK | SORIN UNTARU | SORIN UNTARU | [32 empty] | 393 | Cluj Napoca | Cluj | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CJ057 | ZORILOR | Cluj(14) | CJ057 Zorilor_RTC | Transilvania | 46 45 20.20 | 23 34 36.56 | 46 45 20.2 | 23 34 36.56 | Str. Pasteur nr.58 Bl.5C Sc.1 | Admin. Locatari/Timis Maria - adm., tel: 094/ 877 249 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-08-02 | 2000-08-02 | N/A |  |  |  | 29.5 | B | 33 | T3m+T3m | N/A | IMSAT | OK | IMSAT | 2000-06-12 | 2000-06-26 | YesV | 2000-06-26 | Relu | 2000-07-25 | 2000-07-20 |  |  |  | 2000-05-23 | 2000-05-05 |  | 2000-06-22 | 2000-07-07 |  |  |  | 2000-08-02 | YRO | ORION | 2000-07-21 | 2000-07-21 | 2000-08-03 | 2000-08-04 | 2000-08-08 |  | Yes | Alexandru Bucur | 2000-09-06 | 2000-09-06 | 2000-09-06 | 2000-10-04 | 2000-10-13 | K 739 494 | 10 | 0 | 34.5 | K 739 494 | 110 | N/A | 34.5 | K 739 494 | 250 | 0 | 34.5 |  |  |  |  | N/A | 21 | 21 | 7/8" | 23 | 23 | 7/8" | 23 | 23 | 7/8" |  |  |  | 134 | N/A | Cluj | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | 4U-1 |  |  |  | RBS | 60057 | [6 empty] | 100/2p outdoor |  | 1 | BSC41 | BSC CLUJ | N/A | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PAUN | OK | N/A |  | N/A | N/A | 30N01 Zorilor-Cluj |  | OK | SORIN UNTARU | SORIN UNTARU | [32 empty] | 447 | Cluj Napoca | Cluj | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | CJ058 | CIPARIU | Cluj(14) | CJ054 Baritiu_RTC | Transilvania | 46 46 05.9 | 23 36 07.5 | 46 46 05.9 | 23 36 07.5 | Bd. N. Titulescu nr.11-15 | Asociatie de locatari - presedinte Pasca Gavril/Nmuresan Iosif - adm., Et. 9 Ap. 46, 064/ 14 40 23 | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-10-09 | N/A | N/A |  |  |  | 32 | B | 36 | C4m+C4m | Room | IMSAT | OK | IMSAT | 2000-09-20 | 2000-09-29 | YesV | 2000-10-26 | Relu | 2000-11-02 | 2000-10-31 |  |  |  | 2000-09-12 | 2000-09-08 |  | 2000-09-13 | 2000-09-29 |  |  |  | 2000-10-04 | YRO | Interactive | 2000-10-04 | 2000-10-04 | 2000-10-05 | 2000-10-09 | 2000-10-10 |  | Yes | Alexandru Toma | 2000-10-30 | 2000-10-27 | 2000-10-27 | 2000-11-20 | 2000-11-29 | K 739 494 | 0 | 0 | 36 | K 739 494 | 120 | 0 | 36 | K 739 494 | 240 | 0 | 36 |  |  |  |  | N/A | 10 | 10 | 7/8" | 26 | 26 | 7/8" | 26 | 26 | 7/8" |  |  |  | 124 | ML 38 E 1+0 | Cluj | MW | 114 | 0.6 | 36 | 26 | 38/14 |  |  | 4U-1 |  |  |  | N/A | [9 empty] | 1 | CJ059 | GHEORGHIENI_2 | 33 | 0.6 | 37 | 22 | 38/18 | [6 empty] | 8 | INTERACTIVE | 2000-10-04 | 264 | 2000-10-05 | 2000-10-04 | 2000-10-10 | DINCA | OK | 2000-10-27 |  | 2000-11-20 | 2001-01-10 | 30N02 conectare locala |  | OK | Denis CIUCU | CATALINA CIOCAN | [32 empty] | 325 | Cluj Napoca | Cluj | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CJ059 | GHEORGHIENI_2 | Cluj(14) | CJ054 Baritiu_RTC | Transilvania | 46 45 48.9 | 23 37 02.5 | 46 45 48.9 | 23 37 02.5 | Str. Albac nr.10 Bl.A5 Sc.1 | /Florea Vasile - administrator, tel: 064/ 156 471 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-07-11 | 2000-07-11 | SVF |  |  |  |  | B | 33 | C3m+C3m | N/A | IMSAT | OK | IMSAT | 2000-06-07 | 2000-06-19 | YesV | 2000-06-29 | Relu | 2000-07-10 | 2000-07-04 |  |  |  | 2000-05-19 | 2000-05-05 |  | 2000-05-29 | 2000-06-26 |  |  |  | NA | YRO | NA | 2000-07-11 | 2000-07-11 | 2000-08-02 | 2000-07-13 | 2000-07-18 |  | Yes | Alexandru Toma | 2000-10-30 | 2000-10-26 | 2000-10-26 | 2000-11-27 | 2000-11-29 | K 739 494 | 0 | 0 | 37.5 | K 739 494 | 90 | 0 | 37.5 | K 739 494 | 240 | 0 | 37.5 |  |  |  |  | N/A | 16 | 16 | 7/8" | 16 | 16 | 7/8" | 16 | 16 | 7/8" |  |  |  | 96 | ML 23 E 1+0 | Cluj | MW | 296 | 0.6 |  |  | 23/58 |  |  | 2U-3 |  |  |  | RBS | [9 empty] | 1 | CJ054 | BARITIU_RTC | 116 | 0.6 | 33 |  | 23/56 | [6 empty] | N/A | YRO/INTERACTIVE | N/A | 50/224 | 11.07.00-28.09.00 | 2000-07-13 | 2000-07-21 | DINCA | OK | 2000-10-26 |  | 2000-11-20 | 2001-01-10 | 30N02 conectare locala |  | OK | SORIN UNTARU | SORIN UNTARU | [32 empty] | 333 | Cluj Napoca | Cluj | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CJ060 | GHEORGHIENI_3 | Cluj(14) | CJ063 ICPIAF | Transilvania | 46 47 03.21 | 23 43 00.91 | 46 46 13.5 | 23 37 26.1 | Str. Herculane nr.9 | Asociatie de locatari - Morocoj Partenie adm., tel: 064/ 153 584, 092/ 879 211/Astalos Ioan | 2102 | M/E | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-07-11 | 2000-07-11 | SVF |  |  |  | 32 | B | 32 | C5m+C5m | N/A | IMSAT | OK | IMSAT | 2000-06-15 | 2000-06-26 | YesV | 2000-06-29 | Relu | 2000-07-10 | 2000-07-04 |  |  |  | 2000-05-23 | 2000-05-05 |  | 2000-06-06 | 2000-06-26 |  |  |  | NA | YRO | NA | 2000-07-11 | 2000-07-11 | 2000-08-02 | 2000-07-13 | 2000-07-19 |  | Yes | Alexandru Toma | 2000-10-30 | 2000-11-04 | 2000-11-04 | 2000-11-20 | 2001-01-08 | K 739 494 | 0 | 0 | 36.5 | K 739 494 | 120 | 0 | 36.5 | K 739 494 | 240 | 0 | 36.5 |  |  |  |  | N/A | 35 | 35 | 7/8" | 17 | 17 | 7/8" | 35 | 35 | 7/8" |  |  |  | 174 | ML 23 E 1+0 | Cluj | MW | 9 | 0.6 | 36 |  | 23/58 |  |  | 4U-1 |  |  |  | RBS | [9 empty] | 1 | CJ062 | MARASTI_2 | 188 | 0.6 |  |  | 23/56 | [6 empty] | N/A / 7 | YRO/INTERACTIVE | N/A-27.09.00 | 51/52/228 | 11.07.00-22.09.00 | 2000-07-13 | 2000-07-19 | DINCA | OK | 2000-11-04 |  | 2000-11-20 | 2001-01-10 | 30N02 ICPIAF-Cluj |  | OK | SORIN UNTARU | SORIN UNTARU | [32 empty] | 319 | Cluj Napoca | Cluj | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CJ061 | MARASTI_1 | Cluj(14) | CJ061 Marasti_1 | Transilvania | 46 46 53.6 | 23 36 47.2 | 46 46 40.3 | 23 36 43.7 | B-dul. 21 Decembrie nr.152 bl. 2a sc.1 | Asociatie de locatari/Bob Ioan - presedinte asociatie, 064/ 410 233 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-10-11 | Yes | N/A |  |  |  | 35.1 | B | 37.5 | C4m+C4m+C4m | N/A | IMSAT | OK | IMSAT | 2000-10-09 | 2000-10-18 | YesV | 2000-10-26 | Relu | 2000-10-27 | 2000-10-31 |  |  |  |  | 2000-08-11 |  | 2000-09-25 | 2000-10-12 |  |  |  | 2000-10-04 | YRO | Interactive | 2000-10-04 | 2000-10-04 | 2000-10-05 | 2000-10-12 | 2000-10-16 |  | Yes | Alexandru Toma | 2000-10-30 | 2000-11-01 | 2000-11-01 | 2000-11-20 | 2000-11-29 | K 739 494 | 0 | 0 | 39.5 | K 739 494 | 120 | 0 | 39.5 | K 739 494 | 240 | 0 | 39.5 |  |  |  |  | N/A | 27 | 27 | 7/8" | 18 | 18 | 7/8" | 20 | 20 | 7/8" |  |  |  | 152 | N/A | Cluj | FO | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | RBS | [7 empty] | 150/2p outdoor |  |  | BSC41 | BSC CLUJ |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | DINCA | OK | N/A |  | N/A | N/A | 30N01 Marasti-Cluj |  | OK | Denis CIUCU | Cosmorom | [32 empty] | 561 | Cluj Napoca | Cluj | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | CJ062 | MARASTI_2 | Cluj(14) | CJ063 ICPIAF | Transilvania | 46 46 52.83 | 23 37 34.42 | 46 46 52.83 | 23 37 34.42 | Str. Aurel Vlaicu 27 Sc.2-3 | /Drulea Ion - adm., Sc. 1 Et.2 Ap.8, tel: 094/ 695 304 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-07-11 | 2000-07-11 | SVF |  |  |  | 36.5 | B | 40 | T4m+T4m+T4m | N/A | IMSAT | OK | IMSAT | 2000-06-07 | 2000-06-07 | YesV | 2000-06-13 | Relu | 2000-07-10 | 2000-06-19 |  |  |  | 2000-05-23 | 2000-05-05 |  | 2000-05-26 | 2000-06-20 |  |  |  | NA | YRO | NA | 2000-07-11 | 2000-07-11 | 2000-08-02 | 2000-07-13 | 2000-07-16 |  | Yes | Alexandru Toma | 2000-10-30 | 2000-11-02 | 2000-11-02 | 2000-12-21 | 2001-01-08 | K 739 494 | 0 | 0 | 42.5 | K 739 494 | 110 | 0 | 42.5 | K 739 494 | 240 | 0 | 42.5 |  |  |  |  | N/A | 38 | 38 | 7/8" | 38 | 38 | 7/8" | 25 | 25 | 7/8" |  |  |  | 202 | ML 23 E 1+1 | Cluj | MW | 283 | 0.6 | 42.5 | 21 | 23/56 | YES | 4x2/8 | 4U-1 | 4U-1 |  |  | TMR 9000 | [9 empty] | 1 | CJ063 | ICPIAF | 103 | 0.6 | 44.2 | 16 | 23/58 | [6 empty] | 8 | INTERACTIVE | 2000-10-04 | 265/295 | 5.10.00-10.10.00 | 2000-07-13 | 2000-07-16 | DINCA | OK | 2000-11-02 |  | 2000-11-20 | 2001-01-10 | 30N02 ICPIAF-Cluj |  | OK | SORIN UNTARU | SORIN UNTARU | [32 empty] | 317 | Cluj Napoca | Cluj | [5 empty] | 1 | 1 | 2 | 1 | 1 | 2
Phase_2 | CS | CJ063 | ICPIAF | Cluj(14) | CJ063 ICPIAF | Transilvania | 46 47 15.61 | 23 35 15.98 | 46 47 15.61 | 23 35 15.98 | Str. Fabricii de Chibrituri nr.13-21 | ICPIAF/ | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-10-11 | Yes | N/A |  |  |  | 38 | B | 42 | C5m+C6m+C6m | N/A | IMSAT | OK | IMSAT | 2000-09-23 | 2000-09-29 | YesV | 2000-10-10 | Relu | 2000-11-22 | 2000-10-13 |  |  |  | N/A | 2000-06-21 |  | 2000-08-02 | 2000-10-18 |  |  |  | 2000-10-04 | YRO | Interactive | 2000-09-20 | 2000-09-20 | 2000-10-05 | 2000-10-11 | 2000-10-12 |  | Yes | Alexandru Toma | 2000-10-30 | 2000-10-25 | 2000-10-25 | 2000-11-27 | 2000-11-29 | K 739 494 | 0 | 0 | 43.5 | K 739 494 | 120 | 0 | 43 | K 739 494 | 240 | 0 | 43 |  |  |  |  | N/A | 35 | 35 | 7/8" | 17 | 17 | 7/8" | 23 | 23 | 7/8" |  |  |  | 150 | N/A | Cluj | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | 4U-1 |  |  |  | RBS | 60063 | 2001-05-07 | [5 empty] | 60/ |  | 1 | BSC41 | BSC CLUJ |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PITURCESCU | OK | N/A |  | N/A | N/A | 30N01 ICPIAF-Cluj |  | OK | SORIN UNTARU | SORIN UNTARU | [32 empty] | 313 | Cluj Napoca | Cluj | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | CJ064 | NAPOTEX | Cluj(14) | CJ063 ICPIAF | Transilvania | 46 47 03.21 | 23 43 00.91 | 46 46 51.8 | 23 41 09.4 | Str. Traian Vuia 208, Cluj Napoca | Nagy Cornelia - dir. General/ | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-06-28 | 2000-07-11 | SVF |  |  |  | 16.3 | B | 16.3 | T4m+T3m | N/A | IMSAT | OK | IMSAT | 2000-05-29 | 2000-06-09 | YesV | 2000-06-14 | Relu | 2000-06-16 | 2000-06-19 |  |  |  | 2000-05-23 | 2000-05-05 |  | 2000-05-26 | 2000-07-10 |  |  |  | NA | YRO | NA | 2000-07-05 | 2000-07-11 | 2000-08-02 | 2000-07-13 | 2000-07-16 |  | Yes | Alexandru Toma | 2000-10-30 | 2000-11-04 | 2000-11-04 | 2000-11-27 | 2000-11-29 | K 739 494 | 255 | 0 | 17.8 | K 739 494 | 50 | 0 | 17.8 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 21 | 21 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 80 | ML 23 E 1+1 | Cluj | MW | 270 | 0.6 | 17.8 | 20 | 23/58 | YES | 4x2/8 | 4U-1+2U-3 |  |  |  | RBS | [9 empty] | 1 | CJ062 | MARASTI_2 | 90 | 0.6 | 42.5 | 32 | 23/56 | [6 empty] | N/A / 7 | YRO/INTERACTIVE | N/A-27.09.00 | 53/229 | 11.07.00-22.09.00 | 2000-07-13 | 2000-07-16 | DINCA | OK | 2000-11-04 |  | 2000-11-20 | 2001-01-10 | 30N03 ICPIAF-Cluj |  | OK | SORIN UNTARU | SORIN UNTARU | [32 empty] | 316 | Cluj Napoca | Cluj | [5 empty] | 1 | 1 | 2 | 1 | 1 | 2
Phase_2 | CS | CJ065 | BUCURESTI | Cluj(14) | CJ063 ICPIAF | Transilvania | 46 46 54.8 | 23 36 22.3 | 46 46 51.9 | 23 36 18.9 | Str. Bucuresti, bloc Spray | Asociatie Locatari/Presedinte asociatie - Bl. Spray ap.36 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-08-16 | Yes | N/A |  |  |  | 36 | B | 37 | T3m+C2m+C2m | N/A | IMSAT | OK | IMSAT | 2000-08-18 | 2000-09-03 | YesV | 2000-09-06 | Relu | 2000-10-27 | 2000-09-13 |  |  |  |  | 2000-08-14 |  | 2000-08-14 | 2000-08-31 |  |  |  | 2000-09-27 | YRO | Interactive | 2000-09-20 | 2000-09-20 | 2000-09-27 | 2000-09-28 | 2000-10-01 |  | Yes | Alexandru Toma | 2000-10-30 | 2000-11-03 | 2000-11-03 | 2000-11-27 | 2000-11-29 | K 739 494 | 0 | 0 | 37.2 | K 739 494 | 120 | 0 | 37.2 | K 739 494 | 240 | 0 | 37.2 |  |  |  |  | N/A | 20 | 20 | 7/8" | 11 | 11 | 7/8" | 27 | 27 | 7/8" |  |  |  | 116 | ML 23 E 1+0 | Cluj | MW | 295 | 0.6 | 41.8 | 12 | 23/56 |  |  | 4U-1 |  |  |  | RBS | [9 empty] | 1 | CJ063 | ICPIAF | 115 | 0.6 | 44.2 | 21 | 23/58 | [6 empty] | 8 | INTERACTIVE | 2000-10-04 | 266 | 2000-10-05 | 2000-10-04 | 2000-10-06 | PITURCESCU | OK | 2000-11-03 |  | 2000-11-20 | 2001-01-10 | 30N01 ICPIAF-Cluj |  | OK | SORIN UNTARU | SORIN UNTARU | [32 empty] | 317 | Cluj Napoca | Cluj | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CJ066 | MANASTUR_2 | Cluj(14) | CJ054 Baritiu_RTC | Transilvania | 46 45 40.2 | 23 33 51.8 | 46 45 40 | 23 33 52.1 | Str. Manastur nr.70 bl. E5 sc.2 | Asociatie Locatari/Presedinte asociatie - Str. Manastur nr.70 bloc E5 sc.2 ap.53, 064/ 425 391 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-08-16 | Yes | N/A |  |  |  | 32 | B | 36 | T4m+T4.5m+T4m | N/A | IMSAT | OK | IMSAT | 2000-08-18 | 2000-08-31 | YesV | 2000-09-06 | Relu | 2000-10-27 | 2000-09-13 |  |  |  |  | 2000-08-02 |  | 2000-08-14 | 2000-09-20 |  |  |  | 2000-09-27 | YRO | Interactive | 2000-09-20 | 2000-09-20 | 2000-09-27 | 2000-10-03 | 2000-10-04 |  | Yes | Alexandru Toma | 2000-10-30 | 2000-11-01 | 2000-11-01 | 2000-11-20 | 2000-11-29 | K 739 494 | 0 | 0 | 37.7 | K 739 494 | 120 | 0 | 38.5 | K 739 494 | 225 | 0 | 38.5 |  |  |  |  | N/A | 14 | 14 | 7/8" | 13.5 | 13.5 | 7/8" | 23 | 23 | 7/8" |  |  |  | 101 | ML 23 E 1+0 | Cluj | MW | 53 | 0.6 | 40.4 | 15 | 23/58 | YES | 4x2/8 | 4U-1 |  |  |  | RBS | [9 empty] | 1 | CJ054 | BARITIU_RTC | 232 | 0.6 | 33 | 22 | 23/56 | [6 empty] | 7 | INTERACTIVE | 2000-09-27 | 225 | 2000-09-28 | 2000-09-28 | 2000-10-04 | PITURCESCU | OK | 2000-11-01 |  | 2000-11-20 | 2001-01-10 | 30N03 conectare locala |  | OK | Camil Dumitrescu | Cosmorom | [32 empty] | 350 | Cluj Napoca | Cluj | [5 empty] | 1 | 1 | 2 | 1 | 1 | 2
Phase_2 | CS | CJ067 | DONATH | Cluj(14) | CJ054 Baritiu_RTC | Transilvania | 44 45 54.9 | 23 32 34.2 | 44 45 54.9 | 23 32 34.2 | Str. Donath 200 bloc A2 | Asociatie Locatari/Presedinte asociatie - Str. Donath 200 bloc A2 ap.41, 064/ 18 83 03 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-08-16 | Yes | N/A |  |  |  | 34.5 | B | 38 | T4m+T34m | N/A | IMSAT | OK | IMSAT | 2000-08-18 | 2000-08-31 | YesV | 2000-09-06 | Relu | 2000-11-02 | 2000-09-13 |  |  |  |  | 2000-08-08 |  | 2000-08-08 | 2000-08-25 |  |  |  | 2000-09-27 | YRO | Interactive | 2000-09-20 | 2000-09-20 | 2000-09-27 | 2000-10-01 | 2000-10-03 |  | Yes | Alexandru Toma | 2000-10-30 | 2000-11-02 | 2000-11-02 | 2000-11-20 | 2000-11-29 | K 739 494 | 120 | 0 | 40.5 | K 739 494 | 240 | 0 | 40.5 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 18 | 18 | 7/8" | 18 | 18 | 7/8" | N/A | N/A | N/A |  |  |  | 60 | ML 23 E 1+0 | Cluj | MW | 55 | 0.6 | 40 | 17 | 23/58 |  |  | 2U-3 |  |  |  | RBS | [9 empty] | 1 | CJ055 | TAIETURA TURCULUI | 235 | 0.6 | 30.25 | 38 | 23/56 | [6 empty] | 7 | INTERACTIVE | 2000-09-27 | 223 | 2000-09-22 | 2000-09-28 | 2000-10-03 | PITURCESCU | OK | 2000-11-02 |  | 2000-11-20 | 2001-01-10 | 30N03 conectare locala |  | OK | Camil Dumitrescu | Cosmorom | [32 empty] | 353 | Cluj Napoca | Cluj | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CJ068 | BACIU | Road Cluj-Satu Mare(12) | CJ054 Baritiu_RTC | Transilvania | 46 47 43.1 | 23 31 39.6 | 46 47 42.8 | 23 31 39.7 | DN E 81 Cluj-Zalau, extravilan pe pamant arabil, parcela BURTUCA, sat Baciu, str. Viilor | Kovacs Elisabeta si Fodor Ana- Com. Baciu nr. 461/Kovaci Ghiury - Com. Baciu nr. 461 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-11-17 | N/A | N/A |  |  |  |  | TN | 40 |  | N/A | IMSAT | OK | IMSAT | 2000-10-20 | 2001-02-10 | YesV | 2001-05-29 | Marin | 2001-02-07 | 2001-05-31 |  |  |  |  | 2000-08-15 |  | 2000-10-06 | 2000-11-01 |  |  |  | 2001-03-26 | ICOM | SVF | 2000-10-16 | 2000-10-16 | 2001-03-27 | 2001-03-27 | 2001-04-02 |  | Yes | Bogdan Bogodai | 2001-04-29 | 2001-04-28 | 2001-04-28 | 2001-05-23 | 2001-05-31 | K 739 494 | 123 | 0 | 38.25 | K 739 494 | 280 | 0 | 38.25 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 53 | 53 | 7/8'' | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 106 | ML 23 E 1+1 | Cluj | MW | 125 | 0.6 | 37.25/0.6 | 50 | 23/58 | YES | 4x2/8 | 4U-1 |  |  |  | RBS | [9 empty] | 1 | CJ055 | TAIETURA TURCULUI | 297 | 0.6 | 30.25 | 38 | 23/56 | [6 empty] | 20* | SVF | 2001-01-24 | 546 | 2001-03-27 | 2001-03-27 | 2001-04-01 | VLAD | OK | 2001-04-28 |  | 2001-05-21 | 2001-05-25 | 30N04 conectare locala |  | OK | Denis CIUCU | Petrica BURGHIU | [32 empty] | 394 | Baciu | Cluj | [5 empty] | 1 | 1 | 2 | 1 | 1 | 2
Phase_2 | CS | CJ069 | VICTORIEI | Alba Iulia(5) | CJ043 Alba Iulia_RTC | Transilvania | 46 04 09.79 | 23 33 24.59 | 46 04 09.79 | 23 33 24.59 | Bd. Victoriei nr.21, bl. 3AB, sc. 2 | Asociatie de proprietari/ | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-10-11 | Yes | N/A |  |  |  | 32.73 | B | 34.9 | T4m+T4m+T4m | N/A | IMSAT | OK | IMSAT | 2000-09-20 | 2000-09-27 | YesV | 2000-10-11 | Relu | 2000-11-10 | 2000-10-13 |  |  |  | 2000-08-30 | 2000-07-22 |  | 2000-08-30 | 2000-09-19 |  |  |  | 2000-10-03 | YRO | ISAF | 2000-10-03 | 2000-10-03 | 2000-10-04 | 2000-10-11 | 2000-10-12 |  | Yes | Bogdan Bogodai | 2000-10-30 | 2000-11-11 | 2000-11-11 | 2000-11-27 | 2000-11-29 | K 739 494 | 30 | 0 | 35.05 | K 739 494 | 160 | 0 | 35.05 | K 739 494 | 270 | 0 | 35.05 |  |  |  |  | N/A | 16.5 | 16.5 | 7/8" | 15.25 | 15.25 | 7/8" | 20.5 | 20.5 | 7/8" |  |  |  | 105 | N/A | Cluj | FO | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | RBS | XC60043 | [6 empty] | 175/Outdoor |  |  | CJ043 | ALBA IULIA_ RTC |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | DINCA | OK | N/A |  | N/A | N/A | 30N01 Victoriei-Alba Iulia_RTC+30N01 Alba Iulia-Cluj |  | OK | Camil DUMITRESCU | Cosmorom | [32 empty] | 277 | Alba Iulia | Alba | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | CJ070 | PREFECTURA | Satu Mare(3+1) | CJ073 Satu Mare_RTC | Maramures | 47 47 21 | 22 52 23.2 | 47 47 19.4 | 22 52 23.2 | Str. 25 Octombrie | Prefectura - Str. 25 Octombrie/Dl. Puscas - 061/ 716 638 ,094796922 | 2202 | M/E | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-07-18 | N/A | N/A |  |  |  |  | B | 57 | C3m+C3m+C3m | Room | PROTELCO | OK | ESROM | 2000-06-27 | 2000-07-19 | YesV | 2000-07-27 | Doru | 2000-07-14 | 2000-08-03 |  |  |  | 2000-06-03 | 2000-05-20 |  | 2000-06-05 | 2000-06-22 |  |  |  | 2000-07-25 | YRO | MIC | 2000-07-18 | 2000-07-18 | 2000-07-26 | 2000-07-27 | 2000-07-29 |  | Yes | Ionut Grigorescu | 2000-08-22 | 2000-08-22 | 2000-08-22 | 2000-09-12 | 2000-09-21 | K 739 494 | 30 | 0 | 63.9 | K 739 494 | 150 | 0 | 60 | K 739 494 | 265 | 0 | 60 |  |  |  |  | N/A | 36 | 36 | 7/8" | 41 | 41 | 7/8" | 41 | 41 | 7/8" |  |  |  | 236 | ML 23/38 E 1+1 | Oradea | MW | 76 | 0.6 | 63.4 | 35 | 23/56 |  | 4x2/8 | 4U-1(TMR9202) | 4U-1 |  |  | TMR 9202 | [9 empty] | 1 | CJ073 | SATU MARE_RTC | 256 | 0.6 | 50.9 | 50 | 23/58 | CJ073 |  | 0.3 |  |  | 38/14 | 2/36* | U_ELECTRONICA/YRO | 26.07.00-3.05.01 | 65/698 | 21.07.00-7.03.01 | 2000-07-27 | 2000-07-29 | PAUN | OK | 2000-08-22 | Link dublat in alta banda | 2000-09-12 | 2000-09-29 | 30N01 Satu Mare-Oradea |  | OK | George IFRIM | Cosmorom | [32 empty] | 121 | Satu Mare | Satu Mare | [5 empty] | 1 | 1 | 2 | 1 | 1 | 2
Phase_2 | CS | CJ071 | LUCIAN BLAGA | Satu Mare(3+1) | CJ073 Satu Mare_RTC | Maramures | 47 46 30 | 22 53 02 | 47 46 46.7 | 22 52 55.8 | Str. Lucian Blaga UU9 | Asociatia de proprietari UU11-UU13, str. Lucian Blaga/Bogza Emil - Str. Lucian Blaga UU9, 061/ 763 250 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-07-18 | 2000-07-24 | N/A |  |  |  | 27.5 | B | 27.5 | Suport colt 3m+Suport colt 3m | N/A | PROTELCO | OK | ESROM | 2000-06-25 | 2000-07-19 | YesV | 2000-07-27 | Doru | 2000-07-14 | 2000-08-03 |  |  |  | 2000-06-01 | 2000-05-20 |  | 2000-06-05 | 2000-06-20 |  |  |  | 2000-07-25 | YRO | MIC | 2000-07-19 | 2000-07-19 | 2000-07-26 | 2000-07-27 | 2000-07-28 |  | Yes | Ionut Grigorescu | 2000-08-28 | 2000-08-28 | 2000-08-28 | 2000-09-12 | 2000-09-26 | K 739 494 | 30 | 0 | 33 | K 739 494 | 150 | 0 | 33 | K 739 494 | 265 | 0 | 33 |  |  |  |  | N/A | 13 | 13 | 7/8" | 21 | 21 | 7/8" | 21 | 21 | 7/8" |  |  |  | 110 | ML 23 E 1+0 | Oradea | MW | 150 | 0.6 | 32.5 | 11.5 | 23/58 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [10 empty] | CJ070 | PREFECTURA | 145 | 0.6 | 59.5 | 40 | 23/56 | [6 empty] | 2 | MIC | 2000-07-26 | 66 | 2000-07-21 | 2000-07-27 | 2000-07-28 | PAUN | OK | 2000-08-28 |  | 2000-09-12 | 2000-09-29 | 30N02 Satu Mare-Oradea |  | OK | George IFRIM | Cosmorom | [32 empty] | 122 | Satu Mare | Satu Mare | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CJ072 | CRISAN | Satu Mare(3+1) | CJ073 Satu Mare_RTC | Maramures | 47 46 55 | 22 51 31 | 47 46 53.2 | 22 51 37.5 | Aleea Milcov nr.2 Bl.T4 | Asociatia de proprietari 241/Moldovan Liviu - Ap.12, 093/ 460 381 | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-07-18 | N/A | N/A |  |  |  | 31 | B | 31 | C+C | Room | PROTELCO | OK | ESROM | 2000-06-25 | 2000-07-19 | YesV | 2000-07-27 | Doru | 2000-07-14 | 2000-08-03 |  |  |  | 2000-06-05 | 2000-05-20 |  | 2000-06-05 | 2000-06-26 |  |  |  | 2000-07-25 | YRO | MIC | 2000-07-18 | 2000-07-18 | 2000-07-26 | 2000-07-27 | 2000-07-28 |  | Yes | Ionut Grigorescu | 2000-08-28 | 2000-08-28 | 2000-08-28 | 2000-09-12 | 2000-10-30 | K 739 494 | 30 | 0 | 35 | K 739 494 | 150 | 0 | 34.5 | K 739 494 | 265 | 0 | 35 |  |  |  |  | N/A | 19 | 19 | 7/8" | 8 | 8 | 7/8" | 13 | 13 | 7/8" |  |  |  | 80 | ML 23 E 1+0 | Oradea | MW | 53 | 0.6 | 34.5 | 18 | 23/58 |  | 4x2/8 | 2U-3 |  |  |  | N/A | [10 empty] | CJ070 | PREFECTURA | 233 | 0.6 | 59.5 | 40 | 23/56 | [6 empty] | 2 | MIC | 2000-07-26 | 67 | 2000-07-21 | 2000-07-27 | 2000-07-28 | PAUN | OK | 2000-08-28 |  | 2000-09-12 | 2000-09-29 | 30N01 Satu Mare-Oradea |  | OK | George IFRIM | Cosmorom | [32 empty] | 121 | Satu Mare | Satu Mare | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | TM | CJ073 | SATU MARE_RTC | Satu Mare(3+1) | CJ073 Satu Mare_RTC | Maramures | 47 47 25 | 22 52 57 | 47 47 25.4 | 22 52 57.4 | Str. Miorita nr.2 | Romtelecom - str. Miorita nr.2/Dl. Katona - Sef centrala, tel: 061/ 711 210 | N/A | N/A | N/A | N/A | N/A | [7 empty] | N/A | N/A |  |  |  | 0 | TE | 55 |  | Room | PROTELCO | OK | ESROM | 2000-06-14 | 2000-06-26 | YesV | 2000-06-29 | Doru | 2000-07-03 | 2000-07-04 |  |  |  | N/A | 2000-05-20 |  | 2000-05-26 | 2000-06-08 |  |  |  | 2000-07-25 | YRO | MIC | N/A | N/A | 2000-07-26 | N/A | N/A |  | Yes | N/A | 2000-08-22 | 2000-08-22 | 2000-08-22 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A | Oradea | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | 2U-3 | 2U-3 |  |  | N/A | 60073 | [8 empty] | 1 | BSC32 | BSC ORADEA | N/A | N/A |  |  | N/A | CJ070 |  | 0.3 |  |  | 38/18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PAUN | OK | N/A |  | N/A | N/A | N/A |  | OK | George IFRIM | Cosmorom | [32 empty] | 121 | Satu Mare | Satu Mare | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | CJ074 | CAREI_RTC | Road Oradea-Satu Mare(16+3) | CJ073 Satu Mare_RTC | Maramures | 47 40 58 | 22 28 15 | 47 40 58.6 | 22 28 16.5 | Str. Mihai Viteazu nr.4 | Romtelecom/Sef centrala | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-07-25 | N/A | N/A |  |  |  | 24 | TE | 40 | Existing 40m tower | Room | PROTELCO | OK | ESROM | 2000-06-24 | 2000-07-07 | YesV | 2000-07-12 | Doru | 2000-07-14 | 2000-07-20 |  |  |  | N/A | 2000-05-13 |  | 2000-05-26 | 2000-06-08 |  |  |  | 2000-08-21 | YRO | Interactive | 2000-08-17 | 2000-08-21 | 2000-08-22 | 2000-08-23 | 2000-08-31 |  | Yes | Theo Radoi | 2001-03-31 | 2001-03-31 | 2001-03-31 | 2001-04-17 | 2001-04-23 | K 739 494 | 60 | 0 | 38 | K 739 494 | 170 | 0 | 38 | K 739 494 | 280 | 0 | 38 |  |  |  |  | N/A | 44 | 44 | 1 1/4" | 44 | 44 | 1 1/4" | 44 | 44 | 1 1/4" |  |  |  | 264 | ML 15 E 1+1 | Oradea | MW | 89 | 0.6 | 40/0.6 | 50 | 15/84 | YES | 4x2/8 | 4U-1 |  |  |  | Indoor Comteck | [9 empty] | 1 | CJ082 | MOFTINU MIC | 269 | 0.6 | 37/1.2 | 55 | 15/89 | [6 empty] | 13 | MOBILCOM | 2000-11-23 | 291 | 2000-11-24 | 2000-11-25 | 2001-03-19 | PAUN | OK | 2000-03-31 |  | 2001-05-03 | 2001-05-11 | 30N03 Satu Mare-Oradea |  | 2001-02-16 | George IFRIM | CATALINA CIOCAN | [32 empty] | 139 | Carei | Satu Mare | [6 empty] | 1 | 2 |  | 1 | 2
Phase_2 | CS | CJ075 | NEGRESTI OAS_RTC | Road Satu Mare-Sighetul Marmatiei(2) | CJ075 Negresti Oas_RTC | Maramures | 47 52 25 | 23 25 42 | 47 52 25.1 | 23 25 38.9 | Str. Vraticel nr.1 | Romtelecom/Micu Grigore | MAXITE | M | 1 | 2 | 2PBC | [6 empty] | 2000-07-18 | N/A | N/A |  |  |  | 16 | TE | 40 | Existing 40m tower | Room | PROTELCO | OK | ESROM | 2000-06-24 | 2000-07-05 | YesV | 2000-07-11 | Doru | 2000-07-14 | 2000-07-20 |  |  |  | N/A | 2000-05-20 |  | 2000-06-05 | 2000-06-28 |  |  |  | 2000-08-21 | YRO | Interactive | 2000-08-16 | 2000-08-21 | 2000-08-22 | 2000-08-23 | 2000-08-31 |  | Yes | Alexandru Bucur | 2001-02-09 | 2001-02-09 | 2001-02-09 | 2001-02-19 | 2001-04-10 | AAU | 30 | 0 | 38.5 | AAU | 195 | 0 | 34 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 41 | 41 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 82 | N/A | Oradea | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | [7 empty] | 50/Indoor |  |  | BSC32 | BSC ORADEA | N/A | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | AUREL | OK | N/A |  | N/A | N/A | 30N01 Nefresti oas-Oradea |  | 2001-02-07 | George IFRIM | Cosmorom | [32 empty] | 240 | Negresti-Oas | Maramures | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | CJ076 | UNIRII_RTC | Baia Mare(10) | CJ076 Unirii_RTC | Maramures | 47 39 13 | 23 34 03 | 47 39 13 | 23 34 03.7 | Bd. Unirii nr.10A | Romtelecom/Dl. Lazar, Dl. Zoicas, tel: 062/ 224 200, 062/ 204 151 | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-07-18 | N/A | N/A |  |  |  | 20 | B | 35.6 | C3m+C3m | Room | PROTELCO | OK | ESROM | 2000-06-25 | 2000-07-07 | YesV | 2000-07-11 | Doru | 2000-07-14 | 2000-07-20 |  |  |  | N/A | 2000-05-20 |  | 2000-06-05 | 2000-06-22 |  |  |  | 2000-08-21 | YRO | Interactive | 2000-08-17 | 2000-08-21 | 2000-08-22 | 2000-08-23 | 2000-08-31 |  | Yes | Bogdan Bogodai | 2001-01-31 | 2001-01-10 | 2001-01-10 | 2001-01-16 | 2001-01-26 | K 739 494 | 60 | 0 | 37 | K 739 494 | 170 | 0 | 37 | K 739 494 | 300 | 0 | 37 |  |  |  |  | N/A | 41 | 41 | 7/8" | 36 | 36 | 7/8" | 36 | 36 | 7/8" |  |  |  | 226 | N/A | Cluj | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | 4U-1(TMR9202) | 4U-1 | 4U-1 |  | TMR 9202 | [7 empty] | 55/Outdoor |  | 1 | BSC41 | BSC CLUJ |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | AUREL | OK | N/A |  | N/A | N/A | 30N03 Baia Mare-Cluj |  | 2001-12-21 | George IFRIM | Cosmorom | [32 empty] | 215 | Baia Mare | Satu Mare | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | CJ077 | SIGHITELUL MARMATIEI_RTC | Road Satu Mare-Sighetul Marmatiei(2) | CJ077 Sighetul Marmatiei_RTC | Maramures | 47 55 44.4 | 23 53 39.1 | 47 55 44.4 | 23 53 39.1 | Str. Dragos Voda nr.2 | Romtelecom/Dl. Bit | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-07-25 | N/A | N/A |  |  |  | 5.2 | B | 16.2 | Existed pylon | Room | PROTELCO | OK | ESROM | 2000-06-24 | 2000-07-03 | YesV | 2000-07-11 | Doru | 2000-07-14 | 2000-07-20 |  |  |  | N/A | 2000-05-20 |  | 2000-06-01 | 2000-06-22 |  |  |  | 2000-08-21 | YRO | Interactive | 2000-07-18 | 2000-08-21 | 2000-08-22 | 2000-08-23 | 2000-08-31 |  | Yes | Alexandru Bucur | 2001-02-10 | 2001-02-10 | 2001-02-10 | 2001-03-02 | 2001-04-10 | K 739 494 | 45 | 0 | 28 | K 739 494 | 135 | 0 | 28 | K 739 494 | 270 | 0 | 35 |  |  |  |  | N/A | 27 | 27 | 7/8" | 27 | 27 | 7/8" | 27 | 27 | 7/8" |  |  |  | 162 | N/A | Oradea | FO | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | [7 empty] | 45/Indoor |  |  | BSC32 | BSC ORADEA | N/A | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | AUREL | OK | N/A |  | N/A | N/A | 30N01 Sighetul Marmatiei-Oradea |  | 2001-02-07 | George IFRIM | Cosmorom | [32 empty] | 269 | Sighetul Marmatiei | Maramures | [7 empty] | Site Near=Insertion Point
Phase_2 | TM | CJ078 | BISTRITA_RTC | Bistrita(2+1) | CJ078 Bistrita_RTC | Transilvania | 47 08 14.4 | 24 29 55.4 | 47 08 14.4 | 24 29 55.4 | Romtelecom | Romtelecom/Biroul transmisiuni digitale - 063/ 213 344 | N/A | N/A | N/A | N/A | N/A | [7 empty] | N/A | N/A |  |  |  | N/A | B |  | 15m existing pylonet | N/A | ISAF | OK | EL-MONT | 2000-07-20 | 2000-07-27 | YesV | 2000-08-02 | Dragos | 2000-08-03 | 2000-08-09 |  |  |  | N/A | 2000-05-15 |  | 2000-06-07 | 2000-07-18 |  |  |  | 2000-08-08 | YRO | ORION | N/A | N/A | 2000-08-09 | N/A | N/A |  | Yes | N/A | 2000-09-14 | 2000-09-15 | 2000-09-15 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A | Tg. Mures | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | 2U-3 |  |  |  | N/A | 60078 | 2001-05-07 | [8 empty] | BSC32 | BSC ORADEA | N/A | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PAUN | OK | N/A |  | N/A | N/A |  |  | OK | Bogdan CRAIU | Petrica BURGHIU | [32 empty] | 360 | Bistrita | Bistrita Nasaud | [7 empty] | Site Near=Insertion Point
Phase_2 | TM | CJ079 | SIGHISOARA_RTC | Sighisoara(3+1) | CJ079 Sighisoara_RTC | Transilvania | 46 13 04 | 24 47 42 | 46 13 04 | 24 47 42 | Romtelecom - Sighisoara | RTC/ | N/A | N/A | N/A | N/A | N/A | [7 empty] | N/A | N/A |  |  |  | N/A | B |  |  | Room | ISAF | OK | DUAL | 2000-07-20 | 2000-08-11 | YesV | 2000-08-23 | Dragos | 2000-09-07 | 2000-08-30 |  |  |  | N/A | 2000-05-15 |  | 2000-06-07 | 2000-07-18 |  |  |  | 2000-11-21 | ICOM | Interactive | N/A | N/A | 2000-11-21 | N/A | N/A |  | Yes | N/A | 2001-03-03 | 2001-03-03 | 2001-03-03 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A | Tg. Mures | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | 4U-1 |  |  |  | Indoor Comteck | 70079 | 2001-05-07 | [7 empty] | 1 | BSC14 | BSC TG. MURES |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | IVAN | OK | N/A |  | N/A | N/A |  |  | 2000-11-01 | Bogdan CRAIU | Cosmorom | [32 empty] | 374 | Sighisoara | Mures | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | CJ081 | PISCOLT | Road Oradea-Satu Mare(16+3) | CJ073 Satu Mare_RTC | Maramures | 47 34 42 | 22 17 26 | 47 34 21.1 | 22 16 45.3 | Str. Libertatii nr.362 | Cons. Local Piscolt (tel prin comanda 22)/Dobos Iosif - primar, 094/ 537 309 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-10-19 | N/A | N/A |  |  |  | 0 | TN | 50 | Tower | N/A | PROTELCO | OK | ESROM | 2000-09-01 | 2000-10-15 | YesV | 2000-11-16 | Doru | 2001-01-17 | 2000-11-22 |  |  |  |  | 2000-07-07 |  | 2000-08-17 | 2000-08-31 |  |  |  | 2000-10-23 | ICOM | MOB | 2000-10-11 | 2000-10-11 | 2000-10-23 | 2000-10-30 | 2000-12-04 |  | Prov | Theo Radoi | 2001-04-12 | 2001-04-12 | 2001-04-12 | 2001-04-27 | 2001-05-31 | K 739 494 | 60 | 0 | 48 | K 739 494 | 230 | 0 | 48 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 65 | 65 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 130 | ML 15 E 1+0 | Oradea | MW | 64 | 0.6 | 47.5/1.2 | 65 | 15/84 |  | 4x2/8 | 4U-1 |  |  |  | RBS | [9 empty] | 1 | CJ106 | PETRESTI | 244 | 0.6 | 47.5/1.2 | 60 | 15/89 | [6 empty] | 13 | MOBILCOM | 2000-11-23 | 292 | 2000-11-25 | 2000-11-25 | 2001-03-19 | RADU | OK | 2001-04-12 |  | 2001-05-03 | 2001-05-11 | 30N03 Satu Mare-Oradea |  | 2001-02-16 | George IFRIM | Cosmorom | [32 empty] | 129 | Piscolt | Satu Mare | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CJ082 | MOFTINU MIC | Road Oradea-Satu Mare(16+3) | CJ073 Satu Mare_RTC | Maramures | 47 41 03 | 22 36 15 | 47 41 07.8 | 22 35 48.5 | MOFTINU MIC, DN 19, NR 229, |  | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-10-13 | N/A | N/A |  |  |  | 0 | TN | 40 | Tower | N/A | PROTELCO | OK | ESROM | 2000-08-15 | 2000-10-10 | YesV | 2000-10-19 | Doru | 2001-01-17 | 2000-10-24 |  |  |  |  | 2000-07-07 |  | 2000-08-18 | 2000-08-31 |  |  |  | 2000-10-20 | ICOM | MOB | 2000-10-11 | 2000-10-11 | 2000-10-23 | 2000-10-27 | 2000-10-30 |  | Yes | Theo Radoi | 2001-03-31 | 2001-03-31 | 2001-03-31 | 2001-04-17 | 2001-04-23 | K 739 494 | 55 | 0 | 38 | K 739 494 | 275 | 0 | 38 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 55 | 55 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 110 | ML 15 E 1+1 | Oradea | MW | 52 | 1.2 | 37/1.2 | 55 | 15/89 | YES | 4x2/8 | 4U-1 |  |  |  | RBS | [9 empty] | 1 | CJ083 | DOBA | 232 | 1.2 | 37.5/1.2 | 70 | 15/84 | [6 empty] | 9 | MOBILCOM | 2000-10-20 | 290/402 | 2000-10-14 | 2000-10-14 | 2001-03-19 | PAUN | OK | 2001-03-31 |  | 2001-05-10 | 2001-05-25 | 30N03 Satu Mare-Oradea |  | 2001-02-16 | George IFRIM | Cosmorom | [32 empty] | 119 | Moftinu Mic | Satu Mare | [5 empty] | 1 | 1 | 2 | 1 | 1 | 2
Phase_2 | CS | CJ083 | DOBA | Road Oradea-Satu Mare(16+3) | CJ073 Satu Mare_RTC | Maramures | 47 44 31 | 22 42 43 | 47 44 29.5 | 22 42 48.4 | Com. Doba (120m fata de posta) |  | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-10-13 | N/A | N/A |  |  |  | 0 | TN | 40 |  | N/A | PROTELCO | OK | ESROM | 2000-08-15 | 2000-10-10 | YesV | 2000-10-19 | Doru | 2001-01-17 | 2000-10-24 |  |  |  |  | 2000-08-05 |  | 2000-08-21 | 2000-09-07 |  |  |  | 2000-10-20 | ICOM | MOB | 2000-10-12 | 2000-10-12 | 2000-10-23 | 2000-10-27 | 2000-10-30 |  | Yes | Theo Radoi | 2001-03-30 | 2001-03-30 | 2001-03-30 | 2001-04-27 | 2001-05-31 | K 739 494 | 55 | 0 | 38 | K 739 494 | 235 | 0 | 38 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 70 | 70 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 140 | ML 15 E 1+1 | Oradea | MW | 66 | 0.6 | 38 |  | 15/84 | YES | 4x2/8 | 4U-1 |  |  |  | RBS | [9 empty] | 1 | CJ070 | PREFECTURA | 246 | 1.2 | 59 | 50 | 15/89 | [6 empty] | 13 | MOBILCOM | 2000-11-23 | 401/747 | 2000-10-14 | 2000-10-14 | 2001-03-19 | PAUN | OK | 2001-03-30 |  | 2001-05-03 | 2001-05-11 | 30N03 Satu Mare-Oradea |  | 2001-02-16 | George IFRIM | Cosmorom | [32 empty] | 121 | Doba | Satu Mare | [6 empty] | 1 | 2 |  | 1 | 2
Phase_2 | CS | CJ084 | LANCRAM | Road Cluj-Sebes(8+1) | CJ043 Alba Iulia_RTC | Transilvania | 46 00 54.2 | 23 32 01.8 | 46 00 53.7 | 23 32 02.4 | DN E85 Sebes-Cluj, borna372+500m, langa cantonul CFR, parcela CALEA MALAIULUI | Asociatia Lancram - 036/ 460 321, 092/ 693 140/Ing. Zbucea - 093/ 574 379 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-10-20 | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | DIEKAT |  | FIBEC | 2001-09-01 | 2001-09-30 | CROM |  | Doru | [6 empty] | 2000-07-15 |  | 2000-09-18 | 2000-10-12 | [14 empty] | CTR |  |  |  |  | K 739 494 | 30 | 0 | 49 | K 739 494 | 155 | 0 | 49 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 62 | 62 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 124 | ML 15 E 1+0 | Cluj | MW | 28 | 0.6 | 47/0.6 | 60 | [7 empty] | RBS | XC60043 | [9 empty] | CJ045 | AMPOI_1 | 208 | 0.6 | 48/0.6 | [21 empty] | 30N02 Alba Iulia-Cluj |  | OK | George IFRIM | Cosmorom | [32 empty] | 232 | Lancram | Cluj | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CJ085 | SINTIMBRU_RTC | Road Cluj-Sebes(8+1) | CJ085 Santimbru_RTC | Transilvania | 46 08 07 | 23 38 58 | 46 08 07 | 23 38 58 | Oficiu Romtelecom, Santimbru | Romtelecom/Romtelecom Sintimbru, jud. Alba | 2202 | M | C+C+ | 2/2 | 2202 | [6 empty] | 2000-10-11 | N/A | N/A |  |  |  | 0 | TE | 30 | Turn existent Romtelecom | Room | DIEKAT | OK | FIBEC | 2000-09-01 | 2000-09-08 | YesV | 2001-05-18 | Doru | 2001-03-23 | 2001-05-23 |  |  |  |  | 2000-08-08 |  | 2000-07-25 | 2000-08-23 |  |  |  | 2000-10-04 | YRO | Interactive | 2000-10-04 | 2000-10-04 | 2000-10-05 | 2000-10-11 | 2000-10-12 |  | Yes | Alexandru Toma | 2000-12-23 | 2000-12-23 | 2000-12-23 | 2001-03-02 | 2001-04-10 | K 739 494 | 20 | 0 | 28.5 | K 739 494 | 210 | 0 | 28.5 | N/A | N/A | N/A | N/A |  |  |  |  | N/A | 35 | 35 | 7/8" | 38 | 38 | 7/8" | N/A | N/A | N/A |  |  |  | 146 | N/A | Cluj | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | 4U-1 |  |  |  | Indoor Comteck | XC60085 | [6 empty] | 5/ |  |  | BSC41 | BSC CLUJ |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PITURCESCU | OK | N/A |  | N/A | N/A | 30N01 Santimbru-Cluj |  | 2000-12-22 | Bogdan CRAIU | Cosmorom | [32 empty] | 242 | Sintimbru | Alba | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | CJ086 | TEIUS | Road Cluj-Sebes(8+1) | CJ085 Santimbru_RTC | Transilvania | 46 12 24.8 | 23 40 23.1 | 46 13 52.7 | 23 41 35 | DN68a, loc. Cosevita, Castel de apa | SC DAMI PROD SRL, Teius - str. Octavian Goga nr.59, 058/ 851 158, 058/ 851 805/Halalai Danut - dir. ; ing. Sef Faur Sorin 095/254 694; dir. Tehnic Halalai Danut 095/ 634 564 | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  |  | B | 33 | T4.5m+T4.5m | N/A | SVF | OK | SVF | 2000-11-20 | 2000-12-13 | YesV | 2000-12-15 | Doru | 2001-03-23 | 2000-12-20 |  |  |  |  | 2000-11-03 |  | 2000-11-15 | 2000-11-30 |  |  |  | 2000-12-14 | ICOM | SVF | 2000-12-14 | 2000-12-15 | 2000-12-19 | 2001-01-12 | 2001-01-15 |  | Yes | Alexandru Bucur | 2001-02-07 | 2001-02-07 | 2001-02-07 |  |  | K 739 494 | 5 | 0 | 35.35 | K 739 494 | 205 | 0 | 35.35 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 63 | 63 | 1 1/4" | 52 | 52 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | 230 | ML 15 E 1+0 | Cluj | MW | 193 | 1.2 | 33.5 |  | 23/56 |  |  | 4U-1 |  |  |  | RBS | XC60085 | [8 empty] | 1 | CJ085 | SINTIMBRU_RTC | 13 | 1.2 | 22 |  | 23/58 | [6 empty] | 7* | SVF | 2000-12-14 | 460 | 2000-12-18 | 2001-01-12 | 2001-01-15 | PITURCESCU | OK | 2001-02-07 |  |  |  | 30N01 Santimbru-Cluj |  | 2000-12-22 | Petrica BURGHIU | Cosmorom | [32 empty] | 253 | Beldiur | Cluj | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CJ087 | AIUD_DRTv | Road Cluj-Sebes(8+1) | CJ085 Santimbru_RTC | Transilvania | 46 18 50.6 | 23 42 47.1 | 46 18 50.7 | 23 42 47.3 | DRTv - Aiud | DRTV - Aiud/DRTv | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | N/A | N/A |  |  |  | 0 | TE | 34 | 35m existing tower | N/A | SVF | OK | SVF | 2001-01-19 | 2001-01-31 | YesV | 2001-04-03 | Doru | 2001-02-07 | 2001-04-06 |  |  |  |  | 2000-11-20 |  | 2000-11-21 | 2001-01-23 |  |  |  | 2001-02-02 | ICOM | TRY | 2001-02-02 | 2001-02-02 | 2001-02-05 | 2001-02-08 | 2001-02-09 |  | Yes | Mihai Constantin | 2001-03-20 | 2001-03-20 | 2001-03-20 |  |  | K 739 494 | 10 | 0 | 25 | K 739 494 | 110 | 0 | 25 | K 739 494 | 220 | 0 | 25 |  |  |  |  | N/A | 33 | 33 | 7/8" | 33 | 33 | 7/8" | 33 | 33 | 7/8" |  |  |  | 198 | ML 15 E 1+0 | Cluj | MW | 195 | 1.2 | 25/1.2 | 33 | 15/89h |  |  | 2U-3 |  |  |  | RBS | XC60085 | [8 empty] | 1 | CJ086 | TEIUS | 14 | 1.2 | 33.5 | 62 | 15/84h | [6 empty] | 20* | INTERACTIVE |  | 610 | 2001-02-22 | 2001-02-22 | 2001-03-07 | RADU | OK | 2001-03-20 |  | 2001-04-11 | 2001-04-17 | 30N01 Santimbru-Cluj |  | 2000-12-22 | Petrica BURGHIU | #N/A | [32 empty] | 321 | Aiud | Alba | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CJ088 | INOC | Road Cluj-Sebes(8+1) | CJ092 Unirea_RTC | Transilvania | 46 23 03.8 | 23 47 01.3 | 46 23 04.7 | 23 47 03 | DN E85 Sebes-Cluj, sat Inoc, borna 422+700m | Primaria Inoc - 058/ 876 151/Matea Cristinel - primar, 058/ 876 151 | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | DIEKAT | OK | JACLYN | 2001-01-29 | 2001-03-02 | YesV | 2001-04-25 | Doru | 2001-05-07 | 2001-05-03 |  |  |  |  | 2000-07-15 |  | 2001-01-16 | 2001-02-26 | [6 empty] | 2001-03-08 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 55 | 0 | 49 | K 739 494 | 250 | 0 | 49 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 |  | Cluj | MW | 44 | 0.6 | 49/0.6 | 60 | [7 empty] | RBS | XC60092 | [9 empty] | CJ092 | UNIREA_RTC | 224 | 0.6 | 17/0.6 | 70 | [20 empty] | 30N01 Unirea-Cluj |  | 2001-03-26 | SORIN UNTARU | Cosmorom | [32 empty] | 262 | Inoc | Cluj | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CJ089 | DUMBRAVA | Road Cluj-Sebes(8+1) | CJ092 Unirea_RTC | Transilvania | 46 26 31 | 23 46 19 | 46 26 31 | 23 46 19 | DN E81 Sebes-Cluj borna 430+500m, com. Unirea, sat Dumbrava, tarlaua DUPA VII | Petrideanu Aurel - sat Dumbrava/D-na. Invatatoare Popa Victoria- 094/ 774 551 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-10-20 | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | DIEKAT | OK | JACLYN | 2000-10-16 | 2000-11-24 | YesV | 2000-12-14 | Doru |  | 2001-02-20 |  |  |  |  | 2000-09-15 |  | 2000-09-21 | 2000-10-12 |  |  |  | 2000-12-18 | ICOM | IMSAT | 2000-11-24 | 2000-12-15 | 2000-12-19 | 2001-01-22 | 2001-01-25 |  | Yes | Mircea Mihut | 2001-05-16 | 2001-05-14 | 2001-05-14 |  |  | K 739 494 | 15 | 0 | 49 | K 739 494 | 130 | 0 | 49 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 62 | 62 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 124 | ML 23 E 1+0 | Cluj | MW | 144 | 0.6 | 47/0.6 | 60 | 23/58 |  |  | 2U-3 |  |  |  | RBS | XC60092 | [8 empty] | 1 | CJ092 | UNIREA_RTC | 324 | 0.6 | 17/0.6 | 70 | 23/56 | [6 empty] | 43* | INTERACTIVE | 2001-03-15 | 720 | 2001-03-20 | 2001-03-20 | 2001-03-23 | DINCA | OK | 2001-06-14 |  | 2001-06-19 | 2001-07-10 | 30N01 Unirea-Cluj |  | 2001-03-26 | George IFRIM | Cosmorom | [32 empty] | 400 | Dumbrava | Cluj | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CJ090 | TURENI | Road Cluj-Sebes(8+1) | CJ047 Turda_RTC | Transilvania | 46 38 07 | 23 42 01.4 | 46 38 07 | 23 42 01.4 | Sat Tureni, sos. Turda-Cluj (E81), in dreptul Km 453+900, langa cantonul CFR, tarlaua ROJAS | Andreica Eugen - sat Tureni nr.354, 064/ 310 085/Andreica Eugen - sat Tureni nr.354, 064/ 310 085 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-11-17 | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | DIEKAT | OK | VECTOR | 2000-10-16 | 2000-12-12 | YesV | 2000-12-19 | Doru | 2001-01-19 | 2000-12-20 |  |  |  |  | 2000-07-15 |  | 2000-09-18 | 2000-10-17 |  |  |  | 2000-12-14 | ICOM | ORION | 2000-12-13 | 2000-12-15 | 2000-12-19 | 2000-12-21 | 2000-12-28 |  | Yes | Alexandru Toma | 2001-02-20 | 2001-02-21 | 2001-02-21 | 2001-03-25 | 2001-04-10 | K 739 494 | 140 | 0 | 49 | K 739 494 | 315 | 0 | 49 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 62 | 62 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 124 | ML 15 E 1+0 | Cluj | MW | 138 | 0.6 | 47/1.2 | 60 | 15/84 |  |  | 4U-1 |  |  |  | RBS | [9 empty] | 1 | CJ046 | CIMITIRUL REFORMAT | 318 | 0.6 | 30 | 45 | 15/89 | [6 empty] | 7* | ORION | 2000-12-14 | 476 | 2000-12-18 | 2001-02-01 | 2001-02-09 | PITURCESCU | OK | 2001-02-21 |  | 2001-02-27 | 2001-03-02 | 30N02 Turda-Cluj |  | OK | Bogdan CRAIU | Cosmorom | [32 empty] | 572 | Tureni | Cluj | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CJ091 | FELEACU | Road Cluj-Sebes(8+1) | CJ047 Turda_RTC | Transilvania | 46 42 46.6 | 23 36 22.7 | 46 42 49.3 | 23 36 23.7 | Com. Feleacu, str. Prundarie nr.87 | Bolboaca Rozalia - str. Republicii nr.87, Feleacu/Bolboaca Rozalia - str. Republicii nr.87, Feleacu | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | DIEKAT | OK | SVF | 2000-11-15 | 2000-12-21 | YesV | 2001-01-30 | Doru | 2001-02-26 | 2001-02-01 |  |  |  |  | 2000-11-01 |  | 2000-11-15 | 2000-12-06 |  |  |  | 2000-12-28 | ICOM | ORION | 2000-12-27 | 2001-01-08 | 2001-01-09 | 2001-02-09 | 2001-02-14 |  | Yes | Alexandru Toma | 2001-03-30 | 2001-03-30 | 2001-03-30 |  |  | K 739 494 | 155 | 0 | 49 | K 739 494 | 330 | 0 | 49 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 65 | 65 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 130 | ML 15 E 1+0 | Cluj | MW | 141 | 1.2 | 47 | 62 | 15/89 |  |  | 4U-1 |  |  |  | RBS | XC60046 | [8 empty] | 1 | CJ090 | TURENI | 321 | 1.2 | 47/1.2 | 60 | 15/84 | [6 empty] | 15* | ORION | 2001-01-08 | 502 | 2001-01-29 | 2001-02-01 | 2001-02-16 | VLAD | OK | 2001-03-30 |  | 2001-04-11 | 2001-04-20 | 30N01 Turda-Cluj |  | OK | Denis CIUCU | Cosmorom | [32 empty] | 722 | Feleacu | Cluj | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | TM | CJ092 | UNIREA_RTC | Road Cluj-Sebes(8+1) | CJ092 Unirea_RTC | Transilvania | 46 24 14 | 23 48 40.2 | 46 24 14 | 23 48 40.2 | Str. Avram Iancu nr.84 | Primaria comunei Unirea/Metea Cristinel-primar | N/A | N/A | N/A | N/A | N/A | [7 empty] | N/A | N/A |  |  |  | N/A | PN | 18 | 18m new pylonet | Room/TMR9202 | DIEKAT | OK | PROFIL | 2001-01-18 | 2001-03-10 | YesV | 2001-03-29 | Doru | 2001-03-15 | 2001-05-04 |  |  |  | 2001-01-15 | 2000-11-14 |  | 2000-11-23 | 2001-04-10 |  |  |  | 2001-03-15 | ICOM | Interactive | N/A | N/A | 2001-03-20 | N/A | N/A |  | Yes | N/A | 2001-05-16 | 2001-05-16 | 2001-05-16 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A | Cluj | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | 4U-1(TMR9202) |  |  |  | TMR 9202 | 60092 | 2001-05-07 | [5 empty] | 8/outdoor |  | 1 | BSC41 | BSC CLUJ |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | DINCA | OK | N/A |  | N/A | N/A | N/A |  | 2001-03-26 | SORIN UNTARU | Cosmorom | [32 empty] | 312 | Com. Unirea | Alba | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | CJ094 | GORNESTI | Road Bistrita-Tg.Mures(4+1) | CJ026 Tg. Mures_RTC | Transilvania | 46 39 50.3 | 24 39 16.1 | 46 39 42.6 | 24 39 33.9 | Str. Salcamilor, com. Gornesti | Primaria com. Gornesti/Primarul com. Gornesti | MAXITE | M | 1 | 2 | 2PBC | [7 empty] | N/A | N/A |  |  |  |  | TN | 50 |  | N/A/TMR9000 | PROTELCO | OK | CONDOR | 2001-03-19 | 2001-05-31 | YesV | Respins | Andrei | [6 empty] | 2000-08-15 |  | 2001-02-28 | 2001-03-22 |  |  | 1112 | 2001-07-16 | ICOM | ELECTROTRADE | 2001-06-04 | 2001-07-16 | 2001-07-17 |  |  | GATA-MAXITE | Yes |  | RBS 2101 |  |  |  |  | AAU | 210 | 0 | 48 | AAU | 360 | 0 | 48 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 120 | ML 15 E 1+0 | Tg. Mures | MW | 207 |  | 42 | 50 | [7 empty] | N/A | [9 empty] | 1 | CJ030 | CORNISEI | 27 | 0.6 | 34/0.6 | [24 empty] | SORIN UNTARU | Cosmorom | [32 empty] | 341 | Gornesti | Mures | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CJ095 | LUNCA | Road Bistrita-Tg.Mures(4+1) | CJ034 Reghin_RTC | Transilvania | 46 50 32.9 | 24 36 03.1 | 46 50 10.6 | 24 36 47.6 | Comuna Lunca | Primaria Lunca Tecii/Primaria Lunca Tecii | MAXITE | M | 1 | 2 | 2PBC | [13 empty] | TN | 50 |  | N/A/TMR9000 | PROTELCO | OK | ESROM | 2001-05-24 | 2001-06-29 | YesV | Respins | Andrei | [6 empty] | 2001-07-13 |  | 2001-05-09 | OK | [6 empty] | 2001-07-13 |  |  |  |  | GATA-MAXITE |  |  | RBS 2101 |  |  |  |  | AAU | 140 | 0 | 48 | AAU | 325 | 0 | 48 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 58 | 58 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 116 | ML 15 E 1+0 | Tg. Mures | MW | 128 | 1.2 | 47 | 59 | [8 empty] | XC60034 | [9 empty] | CJ036 | TURN_RGA | 317 | 0.6 | 50/0.6 | [21 empty] | 30N02 |  | OK | Petrica BURGHIU | Cosmorom | [32 empty] | 477 | Lunca | Mures | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CJ096 | TEACA | Road Bistrita-Tg.Mures(4+1) | YJ096 Teaca_RTC | Transilvania | 46 54 07.6 | 24 30 09.9 | 46 54 57.1 | 24 29 59.5 | Islaz comunal, com. Teaca | Primaria com. Teaca - 065/ 525 449 int1/Primar Vultur Teodor - 094/ 394 145 | 2101 | M | C+ | 2 | 2101 | [12 empty] | 0 | TN | 50 |  | N/A | PROTELCO | OK | ESROM | 2001-05-24 | 2001-06-22 | YesV | 2001-07-13 | Andrei | [6 empty] | 2001-03-01 |  | 2001-05-09 | 2001-06-01 | [6 empty] | 2001-07-11 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 140 | 0 | 48 | K 739 494 | 320 | 0 | 48 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 58 | 58 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 116 | ML 38 E 1+0 | Tg. Mures | MW | 144 | 0.3 | 42 | 52 | [7 empty] | RBS | [10 empty] | YJ096 | TEACA_RTC | 324 | [26 empty] | Petrica BURGHIU | Cosmorom | [32 empty] | 540 | Teaca | Bistrita-Nasaud | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CJ097 | DIPSA | Road Bistrita-Tg.Mures(4+1) | YJ096 Teaca_RTC | Transilvania | 46 58 27 | 24 25 28.1 | 46 58 37 | 24 25 11.8 | Com. Dipsa | Dosu Nicolae, comGAlati Bistritei nr. 72 | 2302 | M | 1 | 2 | 2PBC | [12 empty] | 0 | TN | 50 |  | N/A/TMR9000 | PROTELCO | OK | ESROM | 2001-05-24 | 2001-07-17 | Yes |  | Andrei | [5 empty] | N/A |  |  |  | 2001-07-18 | [14 empty] | RBS 2101 |  |  |  |  | AAU | 140 | 0 | 48 | AAU | 345 | 0 | 48 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | 58 | 58 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | ML 15 E 1+0 | Tg. Mures | MW | 138 |  | 42/0.6 | 52 | [7 empty] | RBS | [10 empty] | CJ096 | TEACA | 318 | 0.6 | 42 | 52 | [23 empty] | SORIN UNTARU | Cosmorom | [32 empty] | 450 | Dipsa | Bistrita-Nasaud | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CJ098 | CRISTUR SIEU | Road Dej-Bistrita(5) | CJ078 Bistrita_RTC | Transilvania | 47 07 49.5 | 24 18 02.5 | 47 07 49.5 | 24 18 02.5 | Sat Cristur Sieu, com. Sieu Sfantu | Cocis Vasile Raveca -Sat Cristur Sieu nr. 57, com. Sieu Sfantu/Cocis Vasile Raveca -Sat Cristur Sieu nr. 57, com. Sieu Sfantu | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-10-19 | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | PROTELCO | OK | SETRACO | 2000-09-11 | 2000-11-17 | YesV | 2000-11-29 | Andrei | 2001-02-07 | 2000-12-07 |  |  |  |  | 2000-08-15 |  | 2000-08-29 | 2001-01-12 |  |  |  | 2000-11-10 | ICOM | SVF | 2000-11-10 | 2000-11-10 | 2000-11-13 | 2000-11-16 | 2000-11-17 |  | Yes | Alexandru Toma | 2001-05-12 | 2001-05-11 | 2001-05-11 | 2001-06-06 | 2001-06-19 | K 739 494 | 140 | 0 | 48.3 | K 739 494 | 330 | 0 | 48 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Tg. Mures | MW | 128 | 1.2 | 48/1.2 | 60 | 15/89 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [9 empty] | 1 | CJ121 | CRAINIMAT | 308 | 1.2 | 48/1.2 | 60 | 15/84 | [6 empty] | 4* | TRYLON | 2000-12-11 | 448 | 2000-12-12 | 2000-12-12 | 2001-04-04 | PAUN | OK | 2001-05-11 |  | 2001-05-21 | 2001-05-25 |  |  | OK | Petrica BURGHIU | Cosmorom | [32 empty] | 289 | Cristur Sieu | Bistrita-Nasaud | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CJ099 | COCIU | Road Dej-Bistrita(5) | CJ078 Bistrita_RTC | Transilvania | 47 11 47.7 | 24 14 07.4 | 47 11 47.7 | 24 14 07.4 | Sat Cociu, com Sintereag - pasunea comunala | Primaria Sintereag/Primar Bob Ioan - 092/ 656 457 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-11-17 | N/A |  |  |  |  | 0 | TN | 50 |  | N/A | PROTELCO | OK | ESROM | 2000-10-25 | 2001-03-17 | YesV | 2001-03-27 | Andrei | 2001-04-17 | 2001-05-04 |  |  |  |  | 2000-08-15 |  | 2000-10-17 | 2000-10-30 |  |  |  | 2001-03-26 | ICOM | TRY | 2000-12-08 | 2000-12-08 | 2001-03-27 | 2001-03-28 | 2001-04-02 |  | Yes | Alexandru Toma | 2001-05-12 | 2001-05-11 | 2001-05-11 | 2001-05-23 | 2001-05-31 | K 739 494 | 120 | 0 | 48 | K 739 494 | 260 | 0 | 48 | K 739 494 | 340 | 0 | 48 |  |  |  |  | N/A | 60 | 60 | 1 1/4" | 60 | 60 | 1 1/4" | 60 | 60 | 1 1/4" |  |  |  | 360 | ML 15 E 1+0 | Tg. Mures | MW | 147 | 0.6 | 28/0.6 | 40 | 15/84 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [9 empty] | 1 | CJ098 | CRISTUR SIEU | 327 | 0.6 | 28/ | 40 | 15/89 | [6 empty] | 4* | TRYLON | 2000-12-11 | 447 | 2000-12-11 | 2000-12-13 | 2000-12-17 | VLAD | OK | 2001-05-11 |  | 2001-05-21 | 2001-05-25 |  |  | OK | Petrica BURGHIU | COSMOROM | [32 empty] | 277 | Cociu | Bistrita-Nasaud | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CJ100 | COLDAU | Road Dej-Bistrita(5) | CJ049 Dej_RTC | Transilvania | 47 10 50.9 | 24 08 55.3 | 47 10 50.9 | 24 08 55.3 | Sat Coldau, primaria Beclean | SIMON STEFAN str.SIEULUI nr.25 ap.19 jud.BISTRITA NASAUD/SIMON STEFAN | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-12-11 | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | PROTELCO | OK | IMSAT | 2000-11-15 | 2001-03-16 | YesV | 2001-03-27 | Andrei | 2001-04-06 | 2001-05-04 |  |  |  |  | 2000-08-15 |  | 2000-11-13 | 2000-11-27 | [6 empty] | 2001-03-21 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 170 | 0 | 48 | K 739 494 | 280 | 0 | 48 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Cluj | MW | 272 | 1.2 | 41.5/1.2 | 60 | [7 empty] | RBS | [10 empty] | CJ101 | RETEAG | 92 | 0.6 | 28/0.6 | 45 | [20 empty] | 30N02 Dej-Cluj |  | OK | Petrica BURGHIU | COSMOROM | [32 empty] | 282 | Coldau | Bistrita-Nasaud | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CJ101 | RETEAG | Road Dej-Bistrita(5) | CJ049 Dej_RTC | Transilvania | 47 11 00.8 | 24 01 01.3 | 47 11 00.8 | 24 01 01.3 | Ferma Fortuna, sat Reteag | Chira Ioan/Chira Ioan, sat Reteag, com. Petru Rares, tf: prin comanda 22, 094 224448 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-10-19 | N/A | N/A |  |  |  |  | TN | 50 | Tower | N/A | PROTELCO | OK | SETRACO | 2000-09-11 | 2000-11-24 | YesV | 2000-11-29 | Andrei | 2001-01-29 | 2000-12-07 |  |  |  |  | 2000-08-15 |  | 2000-08-23 | 2001-01-12 |  |  |  | 2000-12-14 | ICOM | ORION | 2000-11-27 | 2000-12-15 | 2000-12-19 | 2000-12-21 | 2000-12-28 |  | Yes | Bogdan Bogodai | 2001-04-30 | 2001-04-29 | 2001-04-29 | 2001-06-06 | 2001-06-19 | K 739 494 | 60 | 0 | 48 | K 739 494 | 280 | 0 | 48 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 65 | 65 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 130 | ML 15 E 1+0 | Cluj | MW | 242 | 1.2 | 28/1.2 | 45 | 15/89 |  |  | 2U-3 |  |  |  | RBS | [9 empty] | 1 | CJ048 | DEALUL ROZELOR | 62 | 1.2 | 30 | 60 | 15/84 | [6 empty] | 4* | TRYLON | 2000-12-11 | 422 | 2000-12-12 | 2000-12-13 | 2000-12-28 | IVAN | OK | 2001-04-29 |  | 2001-05-17 | 2001-05-25 | 30N02 Dej-Cluj |  | OK | Petrica BURGHIU | Cosmorom | [32 empty] | 242 | Reteag | Bistrita Nasaud | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CJ106 | PETRESTI | Road Oradea-Satu Mare(16+3) | CJ073 Satu Mare_RTC | Maramures | 47 36 13 | 22 22 20 | 47 36 06 | 22 22 30.8 | Ferma de vaci Petresti, Com. Petresti | Ferma de vaci Petresti/ | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-10-19 | N/A | N/A |  |  |  | 0 | TN | 50 |  | N/A | PROTELCO | OK | ESROM | 2000-10-01 | 2000-11-22 | YesV | 2001-04-25 | Doru | 2001-01-17 | 2001-05-03 |  |  |  |  | 2000-08-05 |  | 2000-09-14 | 2000-09-25 |  |  |  | 2000-11-08 | ICOM | MOB | 2000-10-31 | 2000-10-31 | 2000-11-24 | 2000-11-28 | 2000-11-30 |  | Yes | Theo Radoi | 2001-03-31 | 2001-03-31 | 2001-03-31 |  |  | K 739 494 | 40 | 0 | 48 | K 739 494 | 240 | 0 | 48 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+1 | Oradea | MW | 40 | 0.6 | 47.5/0.6 | 60 | 15/89 | YES | 4x2/8 | 4U-1 |  |  |  | RBS | [9 empty] | 1 | CJ074 | CAREI_RTC | 220 | 0.6 | 40/0.6 |  | 15/84 | [6 empty] | 13 | MOBILCOM | 2000-11-23 | 293 | 2000-11-25 | 2000-11-25 | 2000-11-30 | RADU | OK | 2001-03-31 |  | 2001-05-03 | 2001-05-11 | 30N03 Satu Mare-Oradea |  | 2001-02-16 | George IFRIM | Cosmorom | [32 empty] | 140 | Petresti | Satu Mare | [6 empty] | 1 | 2 |  | 1 | 2
Phase_2 | CS | CJ121 | CRAINIMAT | Road Dej-Bistrita(5) | CJ078 Bistrita_RTC | Transilvania | 47 04 07.4 | 24 24 58.8 | 47 04 09.2 | 24 25 56 | Crainimat | Florea Dochia - com. Sieu-Magherus, sat Crainimat/Florea Dochia - com. Sieu-Magherus, sat Crainimat | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-11-17 | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | PROTELCO | OK | ESROM | 2000-10-20 | 2000-12-11 | YesV | 2001-05-11 | Andrei |  | 2001-05-16 |  |  |  |  | 2000-07-15 |  | 2000-09-25 | 2001-01-12 |  |  |  | 2000-12-11 | ICOM | TRY | 2000-12-08 | 2000-12-08 | 2001-01-08 | 2001-01-27 | 2001-01-29 |  | Yes | Alexandru Toma | 2001-05-11 | 2001-05-11 | 2001-05-11 | 2001-05-23 | 2001-05-31 | K 739 494 | 10 | 0 | 48 | K 739 494 | 200 | 0 | 48 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Tg. Mures | MW | 37 | 0.6 | 37.5/0.6 | 50 | 15/84 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [9 empty] | 1 | CJ037 | GARII | 217 | 0.6 | 45/0.6 | 20 | 15/89 | [6 empty] | 4* | TRYLON | 2000-12-11 | 449 | 2000-12-12 | 2000-12-13 | 2000-12-17 | IVAN | OK | 2001-05-11 |  | 2001-05-15 | 2001-05-25 |  |  | OK | Denis CIUCU | Cosmorom | [32 empty] | 321 | Crainimat | Bistrita Nasaud | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CJ122 | GHERLA | Road Cluj-Dej(4) | CJ063 ICPIAF | Transilvania | 47 01 12.1 | 23 54 01.6 | 47 01 12.8 | 23 54 02.4 | Baza siloz Gherla | SC Comcereal SA, Cluj - Piata Avram Iancu nr.15, 064/ 195 557, 064/ 197 201/Dl. Dir. Gen. Marinca Gheorghe, sef statie Cosmovici Radu - 064/ 241 527 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-11-17 | Yes | N/A |  |  |  | 56 | S | 56 | T3m+T3m | N/A | PROTELCO | OK | IMSAT | 2000-11-01 | 2000-11-22 | YesV | 2000-11-29 | Andrei | 2000-11-27 | 2000-12-07 |  |  |  |  | 2000-07-15 |  | 2000-10-17 | 2000-10-30 |  |  |  | 2000-11-23 | ICOM | MOB | 2000-11-23 | 2000-11-23 | 2000-11-24 | 2000-11-25 | 2000-11-26 |  | Yes | Alexandru Toma | 2001-05-10 | 2001-05-10 | 2001-05-10 |  |  | K 739 494 | 150 | 0 | 57.5 | K 739 494 | 330 | 0 | 57.5 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 10 | 10 | 7/8" | 10 | 10 | 7/8" | N/A | N/A | N/A |  |  |  | 40 | ML 15 E 1+0 | Cluj | MW | 236 | 0.6 | 57/0.6 | 10 | 15/89 |  |  | 2U-3 |  |  |  | RBS | [9 empty] | 1 | CJ123 | ICLOD | 56 | 0.6 | 39.5/0.6 | 70 | 15/84 | [6 empty] | 13 | MOBILCOM | 2000-11-23 | 399 | 2000-11-24 | 2000-11-25 | 2000-11-26 | PITURCESCU | OK | 2001-05-10 |  | 2001-05-15 | 2001-05-25 | 30N03 ICPIAF-Cluj |  | OK | Denis CIUCU | Cosmorom | [32 empty] | 251 | Gherla | Cluj | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CJ123 | ICLOD | Road Cluj-Dej(4) | CJ063 ICPIAF | Transilvania | 46 58 48.7 | 23 48 49.4 | 46 58 46.4 | 23 48 48.8 | Iclod, str. Garii nr.8 | SC PRODFURAJ Iclod, 064/ 263 245, 064/ 263 240/Dir. Solomon Ludovic | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-11-17 | N/A | N/A |  |  |  | 0 | S | 35 | C3m+C3m | N/A | PROTELCO | OK | IMSAT | 2000-10-20 | 2000-11-13 | YesV | 2000-11-15 | Andrei | 2000-11-21 | 2000-11-22 |  |  |  |  | 2000-07-15 |  | 2000-09-25 | 2000-10-17 |  |  |  | 2000-11-10 | ICOM | SVF | 2000-11-10 | 2000-11-10 | 2000-11-13 | 2000-11-14 | 2000-11-15 |  | Yes | Alexandru Toma | 2001-05-10 | 2001-05-10 | 2001-05-10 | 2001-06-06 | 2001-07-11 | K 739 494 | 30 | 0 | 40 | K 739 494 | 210 | 0 | 40 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 70 | 70 | 1 1/4" | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | 260 | ML 15 E 1+0 | Cluj | MW | 195 | 0.6 | 39.5/0.6 | 60 | 15/84 |  |  | 2U-3 |  |  |  | RBS | [9 empty] | 1 | CJ124 | RASCRUCI | 15 | 0.6 | 30/0.6 | 40 | 15/89 | [6 empty] | 54* | SVF | 2001-04-04 | 779 | 2001-04-06 | 2001-04-04 | 2001-04-06 | IVAN | OK | 2001-05-09 |  | 2001-05-23 | 2001-05-25 | 30N03 ICPIAF-Cluj |  | OK | Denis CIUCU | Cosmorom | [32 empty] | 264 | Iclod | Cluj | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CJ124 | RASCRUCI | Road Cluj-Dej(4) | CJ063 ICPIAF | Transilvania | 46 53 44.8 | 23 47 00.6 | 46 54 02.7 | 23 46 45.6 | Com. Botilda, sat Rascruci | Ropotean Gheorghe - com. Botilda, sat rascruci, 064/ 262 681/Ropotean Gheorghe - com. Botilda, sat rascruci, 064/ 262 681 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-11-17 | N/A | N/A |  |  |  |  | TN | 40 |  | N/A | PROTELCO | OK | IMSAT | 2000-10-25 | 2001-02-05 | YesV | 2001-03-12 | Andrei | 2001-03-08 | 2001-03-14 |  |  |  |  | 2000-07-15 |  | 2000-10-17 | 2001-01-12 |  |  |  | 2001-04-04 | ICOM | SVF | 2001-02-13 | 2001-02-13 | 2001-04-05 | 2001-04-09 | 2001-04-11 |  | Yes | Alexandru Toma | 2001-05-09 | 2001-05-09 | 2001-05-09 | 2001-06-06 | 2001-06-19 | K 739 494 | 0 | 0 | 48 | K 739 494 | 200 | 0 | 48 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Cluj | MW | 190 | 0.6 | 30/0.6 | 40 | 15/89 |  |  | 2U-3 |  |  |  | RBS | [9 empty] | 1 | CJ125 | APAHIDA | 10 | 0.6 | 41.5 | 55 | 15/84 | [6 empty] | 54* | INTRACOM | 2001-04-04 | 780 | 2001-04-06 | 2001-04-06 | 2001-04-12 | PAUN | OK | 2001-05-09 |  | 2001-05-15 | 2001-05-25 | 30N03 ICPIAF-Cluj |  | OK | Denis CIUCU | Cosmorom | [32 empty] | 277 | Rascruci | Cluj | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CJ125 | APAHIDA | Road Cluj-Dej(4) | CJ063 ICPIAF | Transilvania | 46 49 05.7 | 23 45 39.4 | 46 49 05.7 | 23 45 39.4 | Sat Apahida, pasune "Sub Tibaie-Podas" | Primaria com. Apahida, str. Libertatii nr.98/Ionel Farcas - primar | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-12-11 | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | PROTELCO | OK | TEHNOROB | 2000-11-15 | 2001-01-30 | YesV | 2001-02-06 | Andrei |  | 2001-02-07 |  |  |  |  | 2000-07-15 |  | 2000-11-13 | 2000-11-27 |  |  |  | 2001-04-04 | ICOM | SVF | 2001-02-01 | 2001-02-01 | 2001-04-05 | 2001-04-09 | 2001-04-11 |  | Yes | Alexandru Toma | 2001-05-09 | 2001-05-09 | 2001-05-09 | 2001-05-23 | 2001-05-31 | K 739 494 | 230 | 0 | 48 | K 739 494 | 350 | #N/A | 48 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Cluj | MW | 234 | 0.6 | 41.5 | 55 | 15/84 |  |  | 2U-3 |  |  |  | RBS | [9 empty] | 1 | CJ064 | NAPOTEX | 54 | 0.6 | 17/0.6 | 20 | 15/89 | [6 empty] | 54* | SVF | 2001-04-04 | 590 | 2001-04-05 | 2001-04-06 | 2001-04-12 | DINCA | OK | 2001-05-09 |  | 2001-05-21 | 2001-05-25 | 30N03 ICPIAF-Cluj |  | OK | Denis CIUCU | CATALINA CIOCAN | [32 empty] | 316 | Apahida | Cluj | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CJ126 | LUNA DE SUS | Road Oradea-Cluj(13) | CJ057 Zorilor_RTC | Transilvania | 46 44 46.1 | 23 25 12.8 | 46 44 57.5 | 23 25 10 | Extravilan Luna de Sus | Iepure Marin - str. Principala nr.399, com. Floresti, sat Luna de Sus/ | MAXITE | M | 1 | 2 | 2PBC | [7 empty] | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | IMSAT | OK | SVF | 2001-02-06 | 2001-03-07 | YesV | 2001-03-21 | Andrei | 2001-04-06 | 2001-03-29 |  |  |  |  | 2000-11-05 |  | 2001-01-25 | 2001-02-12 |  |  |  | 2001-03-13 | ICOM | SVF | 2001-03-12 | 2001-03-13 | 2001-03-14 | 2001-03-15 | 2001-03-19 |  | Yes | Theo Radoi | 2001-04-22 | 2001-04-22 | 2001-04-22 | 2001-06-19 | 2001-07-11 | AAU | 95 | 0 | 48.3 | AAU | 290 | 0 | 48.3 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 120 | ML 15 E 1+0 | Cluj | MW | 85 | 1.2 | 47/1.2 | 60 | 15/89 |  |  | 2U-3 |  |  |  | TMR 9000 | [9 empty] | 1 | CJ057 | ZORILOR | 265 | 1.2 | 36 | 30 | 15/84 | [6 empty] | 41* | SVF | 2001-03-13 | 715 | 2001-03-14 | 2001-03-16 | 2001-03-19 | IVAN | OK | 2001-04-22 |  | 2001-05-03 | 2001-05-11 | 30N01 Zorilor-Cluj |  | OK | Petrica BURGHIU | Cosmorom | [32 empty] | 399 | Luna de Sus | Cluj | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CJ127 | CAPUSU MARE | Road Oradea-Cluj(13) | CJ057 Zorilor_RTC | Transilvania | 46 47 08.6 | 23 17 41 | 46 47 09 | 23 17 38.5 | Com. Capusu Mare, sat Capusa Mare | Sallai Martin - str. Manastur nr.4, bl.B3, sc.2 ap.88, Cluj Napoca/Sallai Martin - str. Manastur nr.4, bl.B3, sc.2 ap.88, Cluj Napoca | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-11-17 | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | IMSAT | OK | IMSAT | 2000-10-16 | 2000-11-30 | YesV | 2000-12-12 | Andrei | 2000-12-18 | 2000-12-13 |  |  |  |  | 2000-08-18 |  | 2000-09-20 | 2000-10-17 |  |  |  | 2000-12-15 | ICOM | IMSAT | 2000-12-14 | 2000-12-15 | 2000-12-22 | 2001-01-22 | 2001-01-25 |  | Yes | Theo Radoi | 2001-04-22 | 2001-04-22 | 2001-04-22 | 2001-05-09 | 2001-05-28 | K 739 494 | 115 | 0 | 48.25 | K 739 494 | 295 | 0 | 48.25 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Cluj | MW | 115 | 1.2 | 47.3/1.2 | 58 | 15/84 |  |  | 4U-1 |  |  |  | RBS | [9 empty] | 1 | CJ126 | LUNA DE SUS | 295 | 1.2 | 47/1.2 | 60 | 15/89 | [6 empty] | 41* | SVF | 2001-03-13 | 714 | 2001-03-14 | 2001-03-16 | 2001-03-19 | IVAN | OK | 2001-04-22 |  | 2001-05-03 | 2001-05-11 | 30N01 Zorilor-Cluj |  | OK | Bogdan CRAIU | CATALINA CIOCAN | [32 empty] | 469 | Capusu Mare | Cluj | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CJ128 | DUMBRAVA | Road Oradea-Cluj(13) | CJ057 Zorilor_RTC | Transilvania | 46 49 10 | 23 12 19.7 | 46 49 09.5 | 23 12 19.1 | Extravilan com. Dumbrava (langa site-uri Connex si Diolog) | Kallo Ioan - Com. Dumbrava nr.150, 095/ 805 966/Kallo Ioan - Com. Dumbrava nr.150, 095/ 805 966 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-11-17 | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | IMSAT | OK | IMSAT | 2000-10-16 | 2000-12-14 | YesV | 2001-02-01 | Andrei | 2001-02-05 | 2001-02-07 |  |  |  |  | 2000-08-18 |  | 2000-09-14 | 2000-10-17 |  |  |  | 2000-12-15 | ICOM | IMSAT | 2000-12-14 | 2000-12-15 | 2000-12-22 | 2001-01-22 | 2001-01-25 |  | Yes | Theo Radoi | 2001-04-22 | 2001-04-22 | 2001-04-22 | 2001-05-15 | 2001-05-28 | K 739 494 | 130 | 0 | 48.25 | K 739 494 | 287 | 0 | 48.25 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 23 E 1+0 | Cluj | MW | 119 | 1.2 | 50.25/0.6 | 60 | 23/58 |  |  | 4U-1 |  |  |  | RBS | [9 empty] | 1 | CJ127 | CAPUSU MARE | 299 | 1.2 | 47.3/1.2 | 58 | 23/56 | [6 empty] | 19* | CAMUSAT | 2001-01-25 | 532 | 2001-01-30 | 2001-01-30 | 2001-02-12 | IVAN | OK | 2001-04-22 |  | 2001-05-03 | 2001-05-11 | 30N01 Zorilor-Cluj |  | OK | Bogdan CRAIU | Cosmorom | [32 empty] | 695 | Dumbrava | Cluj | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CJ129 | SAULA | Road Oradea-Cluj(13) | CJ130 Huedin_RTC | Transilvania | 46 50 38.7 | 23 04 38.4 | 46 50 39.6 | 23 04 38.4 | Extravilan com. Izvorul Crisului, lotul Verescere | Societatea Agricola Speranta, com. Izvorul Crisului, sat saula/Peter Ferentz - 064/ 251 030 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-11-17 | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | IMSAT | OK | IMSAT | 2000-10-16 | 2000-11-30 | YesV | 2001-01-09 | Andrei | 2001-01-19 | 2001-01-10 |  |  |  |  | 2000-08-18 |  | 2000-09-14 | 2000-10-17 |  |  |  | 2000-12-15 | ICOM | IMSAT | 2000-12-14 | 2000-12-15 | 2000-12-22 | 2001-01-22 | 2001-01-25 |  | Yes | Alexandru Toma | 2001-02-23 | 2001-02-23 | 2001-02-23 | 2001-03-15 | 2001-04-10 | K 739 494 | 125 | 0 | 48.25 | K 739 494 | 287 | 0 | 48.25 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 23 E 1+0 | Cluj | MW | 302 | 0.6 | 47.3/1.2 | 58 | 23/58 |  |  | 4U-1 |  |  |  | RBS | [9 empty] | 1 | CJ130 | HUEDIN_RTC | 122 | 0.6 | 21.6/0.6 | 17 | 23/56 | [6 empty] | 8* | TRYLON | 2000-12-15 | 478 | 2000-01-30 | 2001-01-30 | 2001-02-06 | IVAN | OK | 2001-02-23 |  | 2001-02-27 | 2001-03-02 | 30N01 Huedin-Cluj |  | 2001-02-01 | Bogdan CRAIU | Cosmorom | [32 empty] | 612 | Saula | Cluj | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CJ130 | HUEDIN_RTC | Road Oradea-Cluj(13) | CJ130 Huedin_RTC | Transilvania | 46 51 52.6 | 23 01 48 | 46 51 52.6 | 23 01 48 | RTC Huedin | RTC/ | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-10-13 | Yes | N/A |  |  |  | 10.2 | B | 12m new pylonet |  | N/A | IMSAT | OK | DUAL | 2000-10-09 | 2000-10-16 | YesV | 2000-10-26 | Andrei | 2000-11-16 | 2000-10-31 |  |  |  | N/A | 2000-08-18 |  | 2000-09-08 | 2000-10-09 |  |  |  | 2000-10-20 | ICOM | MOB | 2000-10-16 | 2000-10-16 | 2000-10-23 | 2000-10-25 | 2000-10-30 |  | Yes | Alexandru Bucur | 2001-02-08 | 2001-02-08 | 2001-02-08 | 2001-02-27 | 2001-04-10 | K 739 494 | 198 | 0 | 20.7 | K 739 494 | 305 | 0 | 20.7 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 17 | 17 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 34 | N/A | Cluj | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | 4U-1 |  |  |  | RBS | 60131 | [6 empty] | ?/Outdoor |  | 1 | BSC41 | BSC CLUJ |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PAUN | OK | N/A |  | N/A | N/A | 30N01 Huedin-Cluj |  | 2001-02-01 | Petrica BURGHIU | Cosmorom | [32 empty] | 566 | Huedin | Salaj | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | CJ131 | BRAISORU | Road Oradea-Cluj(13) | CJ130 Huedin_RTC | Transilvania | 46 51 34.2 | 22 57 28 | 46 51 34.2 | 22 57 28 | Extravilan sat. Braisoru (langa site Dioalog) | Oficiul Parohial Ortodox/Mudure Gheorghe | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-11-17 | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | IMSAT | OK | DUAL | 2000-10-15 | 2000-12-22 | YesV | 2001-02-06 | Andrei | 2001-01-23 | 2001-02-07 |  |  |  |  | 2000-08-18 |  | 2000-09-14 | 2000-10-24 |  |  |  | 2000-12-28 | ICOM | IMSAT | 2000-12-27 | 2001-01-10 | 2001-01-11 | 2001-01-12 | 2001-01-25 |  | Yes | Alexandru Toma | 2001-02-24 | 2001-02-24 | 2001-02-24 |  |  | K 739 494 | 85 | 0 | 48.25 | K 739 494 | 299 | 0 | 48.25 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Cluj | MW | 84 | 0.6 | 47.3/0.6 | 58 | 15/89 |  |  | 4U-1 | 4U-1 |  |  | RBS | [9 empty] | 1 | CJ130 | HUEDIN_RTC | 264 | 0.6 | 21.6/0.6 | 17 | 15/84 | [6 empty] | 15* | TRYLON | 2001-01-08 | 505 | 2000-01-30 | 2001-02-22 | 2001-02-23 | IVAN | OK | 2001-02-24 |  | 2001-02-27 | 2001-03-02 | 30N01 Huedin-Cluj |  | 2001-02-01 | Bogdan CRAIU | Petrica BURGHIU | [32 empty] | 561 | com. Sancraiu | Cluj | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CJ132 | POIENI | Road Oradea-Cluj(13) | CJ130 Huedin_RTC | Transilvania | 46 54 16.4 | 22 51 18.4 | 46 54 18.4 | 22 51 20.7 | Extravilan com. Poieni, cariera Poieni (langa site Diolog) | Matis Ana-Maria, comuna Poieni, sat valea Draganului, nr. 105, jud. Cluj/Matis Ana-Maria, comuna Poieni, sat valea Draganului, nr. 105, jud. Cluj | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-11-17 | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | IMSAT | OK | DUAL | 2000-10-15 | 2000-12-22 | YesV | 2001-02-01 | Andrei | 2001-01-23 | 2001-02-01 |  |  |  |  | 2000-08-18 |  | 2000-09-15 | 2000-12-18 |  |  |  | 2000-12-28 | ICOM | TRY | 2000-12-27 | 2001-01-10 | 2001-01-11 | 2001-01-12 | 2001-01-12 |  | Yes | Mihai Constantin | 2001-03-20 | 2001-03-20 | 2001-03-20 | 2001-04-24 | 2001-05-03 | K 739 494 | 131 | 0 | 48.25 | K 739 494 | 320 | 0 | 48.25 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Cluj | MW | 122 | 0.6c | 47.3/1.2 | 58 | 15/84h |  |  | 4U-1 |  |  |  | RBS | [9 empty] | 1 | CJ131 | BRAISORU | 302 | 0.6c | 47.3/0.6 | 58 | 15/89h | [6 empty] | 15* | TRYLON | 2001-01-08 | 504 | 2000-01-29 | 2001-02-22 | 2001-02-24 | PITURCESCU | OK | 2001-03-20 |  | 2001-05-10 | 2001-05-25 | 30N01 Huedin-Cluj |  | 2001-02-01 | Bogdan CRAIU | Cosmorom | [32 empty] | 637 | Poieni | Cluj | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CJ133 | NEGRENI | Road Oradea-Cluj(13) | CJ130 Huedin_RTC | Transilvania | 46 58 16.9 | 22 46 20.2 | 46 58 16.9 | 22 46 20.2 | Extravilan com. Negreni (langa site Dialog) | Primaria Negreni/ | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-11-17 | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | IMSAT | OK | FIBEC | 2000-10-15 | 2001-02-16 | YesV | 2001-03-29 | Andrei | 2001-03-08 | 2001-05-04 |  |  |  |  | 2000-08-18 |  | 2000-09-15 | 2000-10-17 | [6 empty] | 2001-02-19 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 132 | 0 | 48.5 | K 739 494 | 228 | 0 | 48.5 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Cluj | MW | 140 | 1.2 | 48/1.2 | 60 | [7 empty] | RBS | [10 empty] | CJ132 | POIENI | 320 | 1.2 | 47.3/1.2 | 58 | [20 empty] | 30N01 Huedin-Cluj |  | 2001-02-01 | Bogdan CRAIU | Cosmorom | [32 empty] | 640 | Negreni | Cluj | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CJ134 | PLAIUL MAGURII_DRTV | Road Oradea-Cluj(13) | TM091 Alesd_RTC | Transilvania | 46 52 49.1 | 22 41 49.8 | 46 58 49.1 | 22 41 49.8 | DRTv Plaiul Magurii | DRTv/ | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-10-19 | N/A | N/A |  |  |  | 0 | TE | 70.5 | Tower+22.5m pylon | N/A | IMSAT | OK | @ | 2001-07-20 | 2001-08-15 | DL |  | Andrei | [5 empty] | N/A | 2000-08-18 |  | 2000-09-18 | 2000-09-18 | [14 empty] | CTR |  |  |  |  | K 739 494 | 210 | 0 | 67 | K 739 494 | 280 | 0 | 67 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 83 | 83 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 166 | ML 15 E 1+0 | Oradea | MW | 279 | 0.6 | 68.5/0.6 | 85 | [7 empty] | RBS | [10 empty] | TM114 | TOPA DE CRIS | 99 | 1.2 | 47/1.2 | 58 | [23 empty] | Bogdan CRAIU | Cosmorom | [32 empty] | 752 | Plaiul Magurii | Salaj | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CJ135 | NADASELU | Road Cluj-Satu Mare(12) | CJ054 Baritiu_RTC | Transilvania | 46 49 13.9 | 23 24 25.1 | 46 49 13.9 | 23 24 35 | DN E 81 Cluj-Zalau, sat Nadaselu, com. Girbau | Primaria Girbau - str. Principala nr.188/Viceprimar Kovacs, com. Girbau, 095/ 887 138 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-10-20 | N/A | N/A |  |  |  |  | TN | 30 |  | N/A | IMSAT | OK | IMSAT | 2000-10-16 | 2000-12-22 | YesV | 2001-01-10 | Marin | 2001-01-23 | 2001-03-02 |  |  |  |  | 2000-07-15 |  | 2000-10-09 | 2000-11-01 |  |  |  | 2000-12-28 | ICOM | TRY | 2000-12-27 | 2001-01-10 | 2001-01-11 | 2001-01-12 | 2001-01-12 |  | Yes | Bogdan Bogodai | 2001-04-29 | 2001-04-28 | 2001-04-28 | 2001-06-05 | 2001-06-19 | K 739 494 | 5 | 0 | 28.25 | K 739 494 | 115 | 0 | 28.25 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 42 | 42 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 84 | ML 15 E 1+0 | Cluj | MW | 107 | 0.6 | 29.5/1.2 | 40 | 15/84 |  |  | 4U-1 |  |  |  | RBS | [9 empty] | 1 | CJ068 | BACIU | 287 | 0.6 | 37/1.2 | 50 | 15/89 | [6 empty] | 47* | SVF | 2001-03-26 | 544 | 2001-03-27 | 2001-03-28 | 2001-04-12 | VLAD | OK | 2001-04-28 |  | 2001-05-21 | 2001-05-25 | 30N04 conectare locala |  | OK | Denis CIUCU | Cosmorom | [32 empty] | 526 | Nadaselu | Cluj | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CJ136 | MIHAIESTI | Road Cluj-Satu Mare(12) | CJ054 Baritiu_RTC | Transilvania | 46 54 31 | 23 25 34.5 | 46 54 31.5 | 23 25 31.9 | DN E 81 Drum Cluj-Zalau, sat Mihailesti, pasune | Primaria Sinpaul/Sumblea Ioan (primar) | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-11-17 | N/A | N/A |  |  |  |  | TN | 30 |  | N/A | DIEKAT | OK | TEHNOROB | 2000-10-15 | 2000-12-08 | YesV | 2001-02-01 | Dragos | 2001-02-23 | [5 empty] | 2000-08-15 |  | 2000-09-19 | 2000-10-25 |  |  |  | 2000-12-11 | ICOM | TRY | 2000-12-08 | 2000-12-13 | 2000-12-14 | 2000-12-15 | 2000-12-18 |  | Yes | Bogdan Bogodai | 2001-04-29 | 2001-04-28 | 2001-04-28 |  |  | K 739 494 | 210 | 0 | 29 | K 739 494 | 325 | 0 | 29 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 40 | 40 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 80 | ML 15 E 1+0 | Cluj | MW | 189 | 0.6c | 28/1.2 | 38 | 15/89h |  |  | 4U-1 |  |  |  | RBS | [9 empty] | 1 | CJ135 | NADASELU | 9 | 0.6c | 38.5/0.6 | 40 | 15/84h | [6 empty] | 19* | TRYLON | 2001-01-25 | 534 | 2001-02-22 | 2001-02-22 | 2001-02-25 | PITURCESCU | OK | 2001-04-28 |  | 2001-05-21 | 2001-05-25 | 30N04 conectare locala |  | OK | Denis CIUCU | Cosmorom | [32 empty] | 439 | Mihaiesti | Cluj | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CJ137 | TOPA MICA | Road Cluj-Satu Mare(12) | CJ054 Baritiu_RTC | Transilvania | 46 56 28.2 | 23 23 03.8 | 46 56 26.5 | 23 23 02.4 | DN E 81 Cluj-Zalau, sat Topa Mica | Primaria Sinpaul/Sumblea Ioan - primar | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-11-17 | N/A | N/A |  |  |  |  | TN | 30 |  | N/A | DIEKAT | OK | TEHNOROB | 2000-10-15 | 2000-11-23 | YesV | 2001-02-01 | Dragos | 2001-02-23 | 2001-02-01 |  |  |  |  | 2000-08-15 |  | 2000-09-19 | 2000-10-17 |  |  |  | 2000-11-27 | ICOM | DIEKAT | 2000-11-24 | 2000-11-24 | 2000-11-28 | 2000-11-29 | 2000-12-01 |  | Yes | Bogdan Bogodai | 2001-04-29 | 2001-04-28 | 2001-04-28 |  |  | K 739 494 | 140 | 0 | 29 | K 739 494 | 295 | 0 | 29 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 40 | 40 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 80 | ML 15 E 1+0 | Cluj | MW | 139 | 0.6c | 21/0.6 | 30 | 15/84h |  |  | 4U-1 |  |  |  | RBS | [9 empty] | 1 | CJ136 | MIHAIESTI | 318 | 0.6c | 20/0.6 | 30 | 15/89h | [6 empty] | 19* | TRYLON | 2001-01-25 | 533 | 2001-02-22 | 2001-02-22 | 2001-02-25 | PITURCESCU | OK | 2001-04-28 |  | 2001-05-10 | 2001-05-25 | 30N04 conectare locala |  | OK | Denis CIUCU | Cosmorom | [32 empty] | 483 | Topa Mica | Cluj | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CJ138 | SUTORU | Road Cluj-Satu Mare(12) | CJ054 Baritiu_RTC | Transilvania | 46 58 44.4 | 23 14 39.5 | 46 58 43.9 | 23 14 39.4 | DN E 81 Cluj-Zalau, sat Sutoru, com. Zimbor | Primaria Zimbor, com. Zimbor/Ciuca Aurel - primar, com. Zimbor | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-11-17 | N/A | N/A |  |  |  |  | TN | 30 |  | N/A | DIEKAT | OK | MULTISERV | 2000-10-18 | 2001-03-10 | YesV | 2001-04-04 | Marin | 2001-04-17 | 2001-04-06 |  |  |  |  | 2000-08-15 |  | 2000-09-27 | 2000-10-24 | [6 empty] | 2001-03-13 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 15 | 0 | 29 | K 739 494 | 105 | 0 | 29 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 40 | 40 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 80 | ML 15 E 1+0 | Cluj | MW | 112 | 1.2 | 21/1.2 | 35 | [7 empty] | RBS | [10 empty] | CJ137 | TOPA MICA | 292 | 1.2 | 21/1.2 | 30 | [20 empty] | 30N04 conectare locala |  | OK | Denis CIUCU | Cosmorom | [32 empty] | 383 | Sutor | Salaj | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CJ139 | SANMIHAI | Road Cluj-Satu Mare(12) | CJ050 Zalau_RTC | Transilvania | 47 02 21.7 | 23 15 25 | 47 02 22.9 | 23 15 21.5 | DN E 81 Drum Cluj-Zalau km 54+500, sat Sinmihaiul Almasului | Moldovan Ioan tel: 348 - Com. Sanmihaiu Almasului, nr.30/Moldovan Ioan tel: 348 - Com. Sanmihaiu Almasului nr.30 | MUTAT | M | C+ | 2 | 2101 | [6 empty] | 2000-11-17 | N/A | N/A |  |  |  |  | TN | 30 |  | N/A | DIEKAT | OK | PROFIL | 2000-10-15 | 2000-11-17 | YesV | 2000-11-30 | Dragos | 2001-01-19 | 2000-12-07 |  |  |  |  | 2000-08-15 |  | 2000-09-19 | 2000-10-24 |  |  |  | 2000-11-20 | ICOM | Interactive | 2000-11-20 | 2000-11-20 | 2000-11-21 | 2000-12-01 | 2000-12-04 |  | Yes |  | 2101 MOVED |  |  |  |  | K 739 494 | 180 | 0 | 30 | K 739 494 | 313 | 0 | 30 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 40 | 40 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 80 | ML 15 E 1+0 | Cluj | MW | 317 | 1.2 | 28/1.2 | 38 | [7 empty] | N/A | XC60050 | [9 empty] | CJ140 | ZALAU_DRTV | 137 | 0.6 | 30 | 40 | [20 empty] | new02 Zalau-Cluj |  |  | Denis CIUCU | Cosmorom | [32 empty] | 280 | Sanmihaiul Almasului | Salaj | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CJ140 | ZALAU_DRTV | Road Cluj-Satu Mare(12) | CJ050 Zalau_RTC | Transilvania | 47 09 10.1 | 23 06 05.6 | 47 09 10.1 | 23 06 05.6 | Statia DRTV Zalau | DRTV | 2101 | M | C+ | 2 | 2101 | [12 empty] | 0 | TE | 56+6m suprainaltare |  | N/A | DIEKAT | OK | DIEKAT | 2001-07-01 | 2001-07-17 | in exec |  | Marin | [8 empty] | 2001-06-08 | OK | [14 empty] | CTR |  |  |  |  | K 739 494 | 135 | 0 | 62 | K 739 494 | 315 | 0 | 62 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | 75 | 75 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 150 | ML 15 E 1+0 | Cluj | MW | 311 | 0.3 | 30 | 45 | [7 empty] | RBS | [10 empty] | CJ050 | ZALAU_RTC | 131 | [23 empty] | new02 Zalau-Cluj |  |  | Denis CIUCU | Cosmorom | [33 empty] | Zalau | Zalau | [7 empty] | 2 |  |  | missing
Phase_2 | CS | CJ141 | BOCSA | Road Cluj-Satu Mare(12) | CJ073 Satu Mare_RTC | Maramures | 47 18 0.8 | 22 56 05.3 | 47 18 0.8 | 22 56 05.3 | Comuna Bocsa | Primaria Comunei Bocsa , jud. Salaj/Primarul Ioan Samsudan | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  | 0 | TN | 50 |  | N/A | DIEKAT | OK | SVF | 2001-03-27 | 2001-05-06 | YesV | 2001-05-17 | Marin |  | 2001-05-23 |  |  |  |  | 2000-08-15 |  | 2000-11-29 | 2001-01-09 | [6 empty] | 2001-05-09 |  |  |  |  | GATA-2101 |  |  | RBS 2101 |  |  |  |  | K 739 494 | 155 | 0 | 49 | K 739 494 | 305 | 0 | 49 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 52 | 52 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 124 | ML 15 E 1+0 | Oradea | MW | 302 | 1.2 | 48 | 60 | [7 empty] | RBS | XC60050 | [9 empty] | CJ142 | BOBOTA | [26 empty] | HOLD (Switching Planning)-CJ140 Zalau_DRTv | Denis CIUCU | Petrica BURGHIU | [32 empty] | 220 | Bocsa | Salaj | [7 empty] | 2 |  |  | missing
Phase_2 | CS | CJ142 | BOBOTA | Road Cluj-Satu Mare(12) | CJ073 Satu Mare_RTC | Maramures | 47 22 45.5 | 22 46 25.4 | 47 22 41.9 | 22 45 00.7 | DN E 81 Zalau-Satu Mare, sat Bobota | Primaria Bobota-sat Bobota nr.1/Primar Macarie Gheorghe - sat bobota nr.214 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-12-11 | N/A | N/A |  |  |  | 0 | TN | 30 |  | N/A | DIEKAT | OK | ESROM | 2000-11-13 | 2001-03-17 | YesV | 2001-04-25 | Marin | 2001-04-17 | 2001-05-03 |  |  |  |  | 2000-08-27 |  | 2000-11-07 | 2000-11-27 | [6 empty] | 2001-03-21 |  |  |  |  | GATA-2101 | Prov |  | RBS 2101 |  |  |  |  | K 739 494 | 0 | 0 | 30 | K 739 494 | 130 | 0 | 30 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 40 | 40 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 80 | ML 15 E 1+0 | Oradea | MW | [11 empty] | RBS | XC60050 | [9 empty] | CJ143 | SUPURU DE JOS | [26 empty] | HOLD (Switching Planning)-CJ140 Zalau_DRTv | Denis CIUCU | Petrica BURGHIU | [32 empty] | 199 | Bobota | Satu Mare | [7 empty] | 2 |  |  | missing
Phase_2 | CS | CJ143 | SUPURU DE JOS | Road Cluj-Satu Mare(12) | CJ073 Satu Mare_RTC | Maramures | 47 27 54.2 | 22 46 54.9 | 47 27 54.2 | 22 46 53.8 | DN E 81 Cluj-Zalau, sat Supur | Buciumar Marcela/Buciumar Marcela | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-11-17 | N/A | N/A |  |  |  | 0 | TN | 30 |  | N/A | DIEKAT | OK | ESROM | 2000-10-15 | 2000-11-22 | YesV | 2000-12-14 | Dragos | 2001-04-17 | 2001-02-07 |  |  |  |  | 2000-08-15 |  | 2000-09-19 | 2000-10-17 |  |  |  | 2000-11-23 | ICOM | MOB | 2000-11-23 | 2000-11-23 | 2000-11-24 | 2000-11-27 | 2000-12-04 |  | Yes | Theo Radoi | 2001-04-12 | 2001-04-12 | 2001-04-12 | 2001-05-31 | 2001-06-19 | K 739 494 | 0 | 0 | 29 | K 739 494 | 190 | 0 | 29 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 40 | 40 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 80 | ML 15 E 1+0 | Oradea | MW | 29 | 0.6 | 28/1.2 | 38 | 15/89 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [9 empty] | 1 | CJ144 | BELTIUG | 209 | 0.6 | 40 | 50 | 15/84 | [6 empty] | 40* | MOBILCOM | 2001-03-09 | 701 | 2001-03-12 | 2001-03-12 | 2001-03-19 | PITURCESCU | OK | 2001-04-12 |  | 2001-05-03 | 2001-05-11 | 30N02 Satu Mare-Oradea |  | OK | Denis CIUCU | Cosmorom | [32 empty] | 172 | Supuru de Jos | Satu Mare | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CJ144 | BELTIUG | Road Cluj-Satu Mare(12) | CJ073 Satu Mare_RTC | Maramures | 47 33 16.1 | 22 51 07.7 | 47 33 16.1 | 22 51 07.7 | DN E 81 Zalau-Satu Mare, sat Beltiug | Primaria Beltiug/Bartor Gurzau Ioan - primar | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-12-11 | N/A | N/A |  |  |  | 0 | TN | 50 |  | N/A | DIEKAT | OK | DIEKAT | 2000-11-13 | 2000-12-18 | YesV | 2000-12-15 | Dragos | 2001-03-06 | 2000-12-20 |  |  |  |  | 2000-07-15 |  | 2000-11-07 | 2000-11-27 |  |  |  | 2000-12-18 | ICOM | SVF | 2000-12-18 | 2000-12-18 | 2000-12-19 | 2001-01-11 | 2001-01-14 |  | Yes | Theo Radoi | 2001-04-03 | 2001-04-02 | 2001-04-02 | 2001-05-23 | 2001-05-28 | K 739 494 | 25 | 0 | 49 | K 739 494 | 240 | 0 | 49 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 62 | 62 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 124 | ML 15 E 1+0 | Oradea | MW | 15 | 0.6 | 48 | 60 | 15/89 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [9 empty] | 1 | CJ145 | ARDUD_RTC | 195 | 0.6 | 35/0.6 | 41 | 15/84 | [6 empty] | 40* | MOBILCOM | 2001-03-09 | 702 | 2001-03-12 | 2001-03-12 | 2001-03-19 | PITURCESCU | OK | 2001-04-02 |  | 2001-05-03 | 2001-05-11 | 30N02 Satu Mare-Oradea |  | OK | Denis CIUCU | Petrica BURGHIU | [32 empty] | 144 | Beltiug | Satu Mare | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CJ145 | ARDUD_RTC | Road Cluj-Satu Mare(12) | CJ073 Satu Mare_RTC | Maramures | 47 38 23.6 | 22 53 15.7 | 47 38 23.6 | 22 53 15.7 | Str. Stefan cel Mare nr.43 | Romtelecom/Popovici Lucia - Dir. Oficiu Comercial Romtelecom Ardud, 061/ 771 140 | 2202 | M | C+C+ | 2/2 | 2202 | [6 empty] | 2000-10-20 | N/A | N/A |  |  |  | 0 | TE | 33 | 2.5m Suport antena | Room | DIEKAT | OK | DIEKAT | 2000-10-20 | 2000-11-10 | YesV | 2001-01-22 | Dragos | 2000-11-15 | 2001-01-23 |  |  |  | N/A | 2000-07-15 |  | 2000-09-06 | 2000-09-21 |  |  |  | 2000-11-07 | ICOM | DIEKAT | 2000-11-07 | 2000-11-07 | 2000-11-08 | 2000-11-09 | 2000-11-10 |  | Yes | Theo Radoi | 2001-04-03 | 2001-04-02 | 2001-04-02 |  |  | K 739 494 | 205 | 0 | 36 | K 739 494 | 345 | #N/A | 32 | N/A | N/A | N/A | N/A |  |  |  |  | N/A | 42 | 42 | 7/8" | 38 | 38 | 7/8" | N/A | N/A | N/A |  |  |  | 138 | ML 15 E 1+1 (PS) | Oradea | MW | 357 | 0.6 | 30/0.6 | 36 | 15/84 |  | 4x2/8 | 2U-3 |  |  |  | N/A | [9 empty] | 1 | CJ073 | SATU MARE_RTC | 177 | 0.6 | 50/1.2 | 50 | 15/89 | [6 empty] | 36* | MOBILCOM | 2001-03-05 | 688 | 2001-03-05 | 2001-03-12 | 2001-03-19 | IVAN | OK | 2001-04-02 |  | 2001-05-21 | 2001-05-25 | 30N02 Satu Mare-Oradea |  | OK | Denis CIUCU | #N/A | [32 empty] | 138 | Ardud | Satu Mare | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CJ150 | TRAIAN | Baia Mare(10) | CJ076 Unirii_RTC | Transilvania | 47 39 01.8 | 23 33 35.6 | 47 39 01.8 | 23 33 35.6 | Str. Republicii nr.20 sc.B | Asociatia de locatari nr. 298, Baia Mare/Ing. Popa Marius Cristian | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | Yes | N/A |  |  |  | 26.65 | B | 26.65 | C3m+C3m | N/A | PROTELCO | OK | ESROM | 2000-11-27 | 2001-02-23 | YesV | 2001-04-06 | Marin | 2001-03-14 | 2001-04-10 |  |  |  | 2000-11-03 | 2000-10-25 |  | 2000-11-17 | 2000-11-29 |  |  |  | 2001-02-16 | ICOM | DIRDATES | 2001-02-16 | 2001-02-16 | 2001-02-19 | 2001-02-24 | 2001-03-13 |  | Yes | Ion Soare | 2001-03-31 | 2001-03-31 | 2001-03-31 | 2001-04-19 | 2001-04-23 | K 739 494 | 0 | 0 | 32.2 | K 739 494 | 120 | 0 | 32.2 | K 739 494 | 240 | 0 | 32.2 |  |  |  |  | N/A | 22 | 22 | 7/8" | 21 | 21 | 7/8" | 22 | 22 | 7/8" |  |  |  | 130 |  | Cluj | MW | 59 | 0.3 | 31.5 | 21.3 | 38/18 |  |  | 2U-3 |  |  |  | RBS | [9 empty] | 1 | CJ076 | UNIRII_RTC | 239 | 0.3 | 38 | 50 | 38/14 | [6 empty] | 28* | DIRDATES | 2001-02-16 | 651 | 2001-02-19 | 2001-02-20 | 2001-03-12 | PAUN | OK | 2001-03-31 |  | 2001-05-10 | 2001-05-25 | 30N02 Baia Mare-Cluj |  | 2001-03-28 | Denis CIUCU | Cosmorom | [32 empty] | 200 | Baia Mare | Maramures | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CJ151 | VASILE ALECSANDRI | Baia Mare(10) | CJ076 Unirii_RTC | Transilvania | 47 38 46.6 | 23 34 40 | 47 38 42.7 | 23 34 37.9 | Str. Vasile Alecsandri, NR. 91C, bl. 91C | Asociatia de proprietari nr.249, Str. Vasile Alecsandri, nr.91C, bl.91C/Kadar Ladislau - 062/ 278 673, Solomon Maria | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | Yes | N/A |  |  |  | 29.9 | B | 29.9 | C3m+C3m | N/A | PROTELCO | OK | ESROM | 2000-12-05 | 2001-02-23 | YesV | 2001-03-07 | Marin | 2001-03-14 | 2001-03-14 |  |  |  |  | 2000-10-25 |  | 2000-11-16 | 2000-12-05 |  |  |  | 2001-02-16 | ICOM | DIRDATES | 2001-02-16 | 2001-02-16 | 2001-02-19 | 2001-02-23 | 2001-03-13 |  | Yes | Ion Soare | 2001-03-31 | 2001-03-31 | 2001-03-31 | 2001-06-19 | 2001-07-11 | K 739 494 | 0 | 0 | 32.2 | K 739 494 | 120 | 0 | 32.2 | K 739 494 | 240 | 0 | 32.2 |  |  |  |  | N/A | 17 | 17 | 7/8" | 27 | 27 | 7/8" | 34 | 34 | 7/8" |  |  |  | 176 |  | Cluj | MW | 294 | 0.6 | 31.5 | 16 | 38/14 |  |  | 2U-3 |  |  |  | RBS | [9 empty] | 1 | CJ150 | TRAIAN | 114 | 0.6 | 31.5 | 20.3 | 38/18 | [6 empty] | 28* | DIRDATES | 2001-02-16 | 652 | 2001-02-19 | 2001-02-20 | 2001-03-02 | PAUN | OK | 2001-03-31 |  | 2001-05-10 | 2001-05-25 | 30N02 Baia Mare-Cluj |  | 2001-03-28 | Denis CIUCU | Cosmorom | [32 empty] | 215 | Baia Mare | Maramures | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CJ152 | ALEEA ROTUNDA | Baia Mare(10) | CJ076 Unirii_RTC | Maramures | 47 39 11 | 23 32 44.8 | 47 39 15.3 | 23 32 48.3 | Aleea Rotunda nr.5, bl.5 | Asociatia de locatari nr.42/Nebelea Francisc - Aleea Rotunda bl. 5, et.7, ap.29 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | Yes | N/A |  |  |  | 31.8 | B | 31.8 | C3m+C3m+S2m | N/A | PROTELCO | OK | ESROM | 2000-11-27 | 2000-12-30 | YesV | 2001-03-07 | Marin | 2001-03-14 | 2001-03-14 |  |  |  |  | 2000-10-17 |  | 2000-11-17 | 2000-11-29 |  |  |  | 2001-02-02 | ICOM | TRY | 2001-02-02 | 2001-02-02 | 2001-02-05 | 2001-02-11 | 2001-02-12 |  | Yes | Ion Soare | 2001-04-01 | 2001-04-01 | 2001-04-01 | 2001-04-19 | 2001-04-23 | K 739 494 | 0 | 0 | 36.6 | K 739 494 | 120 | #N/A | 36.6 | K 739 494 | 240 | 0 | 36.6 |  |  |  |  | N/A | 15 | 15 | 7/8" | 12 | 12 | 7/8" | 12 | 12 | 7/8" |  |  |  | 78 |  | Cluj | MW | 93 | 0.3 | 36.2 | 15 | 38/18 | YES | 4x2/8 | 4U-1 |  |  |  | RBS | [9 empty] | 1 | CJ076 | UNIRII_RTC | 273 | 0.3 | 36/0.3 |  | 38/14 | [6 empty] | 18* | TRYLON | 2001-02-02 | 596 | 2001-02-05 | 2001-02-06 | 2001-02-12 | RADU | OK | 2001-04-01 |  | 2001-05-10 | 2001-05-25 | 30N03 Baia Mare-Cluj |  | 2001-03-28 | Denis CIUCU | #N/A | [32 empty] | 202 | Baia Mare | Maramures | [5 empty] | 1 | 1 | 2 | 1 | 1 | 2
Phase_2 | CS | CJ153 | ENERGIEI | Baia Mare(10) | CJ076 Unirii_RTC | Transilvania | 47 39 13.3 | 23 35 19.4 | 47 39 16.5 | 23 35 28.1 | Str. Trenului nr.23 A, Sediul SC AGECOM SA | SC AGECOM SA/Ing. Bala Alexandru - 062/ 215 236 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [13 empty] | B | 20 |  | N/A | PROTELCO | OK | ESROM | 2001-02-02 | 2001-03-08 | YesV | 2001-04-02 | Marin | 2001-03-14 | 2001-05-04 |  |  |  |  | 2000-10-17 |  | 2000-11-20 | 2000-12-13 |  |  |  | 2001-03-13 | ICOM | CAMUSAT | 2001-03-07 | 2001-03-07 | 2001-03-14 | 2001-03-19 | 2001-03-23 |  | Yes | Ion Soare | 2001-04-01 | 2001-04-01 | 2001-04-01 | 2001-06-21 | 2001-07-11 | K 739 494 | 0 | 0 | 18.7 | K 739 494 | 120 | 0 | 18.7 | K 739 494 | 240 | 0 | 18.7 |  |  |  |  | N/A | 25 | 25 | 7/8" | 25 | 25 | 7/8" | 25 | 25 | 7/8" |  |  |  | 150 | ML 38 E 1+0 | Cluj | MW | 266 | 0.3 | 18.3 | 24.5 | 38/17 |  |  | 4U-1 |  |  |  | RBS | [9 empty] | 1 | CJ076 | UNIRII_RTC | 86 | 0.3 | 38.3 | 55 | 38/13 | [6 empty] | 41* | CAMUSAT | 2001-03-13 | 711 | 2001-03-14 | 2001-03-15 | 2001-03-27 | PAUN | OK | 2001-04-01 |  | 2001-05-10 | 2001-05-25 | 30N04 Baia Mare-Cluj |  | 2001-03-28 | Denis CIUCU | Cosmorom | [32 empty] | 231 | Baia Mare | Maramures | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CJ154 | INDEPENDENTEI | Baia Mare(10) | CJ076 Unirii_RTC | Transilvania | 47 39 30.7 | 23 33 24.8 | 47 39 29 | 23 33 19.5 | Str. Independentei nr.16 | Asociatia de proprietari nr. 15/Horincar Vasile - str. Independentei nr.16, 062/ 429 461 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | Yes | N/A |  |  |  | 34.6 | B | 34.6 | C4.5m+C4.5m | N/A | PROTELCO | OK | ESROM | 2000-11-27 | 2000-12-30 | YesV | 2001-03-07 | Marin | 2001-03-14 | 2001-03-14 |  |  |  |  | 2000-10-25 |  | 2000-11-17 | 2001-01-30 |  |  |  | 2001-02-05 | ICOM | DIRDATES | 2001-02-02 | 2001-02-02 | 2001-02-05 | 2001-02-21 | 2001-03-13 |  | Yes | Ion Soare | 2001-03-30 | 2001-03-30 | 2001-03-30 | 2001-06-21 | 2001-07-11 | K 739 494 | 0 | 0 | 34.8 | K 739 494 | 120 | 0 | 36.3 | K 739 494 | 240 | 0 | 36.1 |  |  |  |  | N/A | 45 | 45 | 7/8'' | 12 | 12 | 7/8" | 12 | 12 | 7/8" |  |  |  | 168 |  | Cluj | MW | 118 | 0.3 | 35.6 | 12 | 38/18 |  |  | 4U-1 |  |  |  | RBS | [9 empty] | 1 | CJ076 | UNIRII_RTC | 298 | 0.3 |  | 50 | 38/14 | [6 empty] | 28* | DIRDATES | 2001-02-16 | 597 | 2001-02-19 | 2001-02-20 | 2001-03-12 | PAUN | OK | 2001-03-30 |  | 2001-05-10 | 2001-05-25 | 30N01 Baia Mare-Cluj |  | 2001-03-28 | Denis CIUCU | Cosmorom | [32 empty] | 218 | Baia Mare | Maramures | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CJ155 | GHEORGHE SINCAI | Baia Mare(10) | CJ076 Unirii_RTC | Transilvania | 47 39 27.2 | 23 34 33.7 | 47 39 27.2 | 23 34 33.7 | Str. Gheorghe Sincai, nr.31, sc.B | Asociatie de locatari/Matei Vasile - Baia Mare, str. Gheorghe Sincai nr.31, sc.B, ap.18 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-12-11 | Yes | N/A |  |  |  | 14.2 | B | 14.2 | T6m | N/A | PROTELCO | OK | ESROM | 2000-11-15 | 2001-02-14 | YesV | 2001-03-07 | Marin | 2001-03-14 | 2001-03-14 |  |  |  | 2000-11-03 | 2000-10-28 |  | 2000-11-13 | 2000-11-27 |  |  |  | 2001-02-16 | ICOM | DIRDATES | 2001-02-16 | 2001-02-16 | 2001-02-19 | 2001-02-23 | 2001-02-28 |  | Yes | Ion Soare | 2001-04-02 | 2001-04-02 | 2001-04-02 | 2001-06-21 | 2001-07-11 | K 739 494 | 0 | 0 | 18.5 | K 739 494 | 120 | 0 | 18.5 | K 739 494 | 240 | 0 | 18.5 |  |  |  |  | N/A | 18 | 18 | 7/8" | 18 | 18 | 7/8" | 18 | 18 | 7/8" |  |  |  | 108 | ML 38 E 1+0 | Cluj | MW | 107 | 0.3 | 17.5 | 17.5 | 38/14 |  |  | 2U-3 |  |  |  | RBS | [9 empty] | 1 | CJ153 | ENERGIEI | 287 | 0.6 | 18 | 24.5 | 38/18 | [6 empty] | 42* | CAMUSAT | 2001-03-13 | 717 | 2001-03-14 | 2001-03-15 | 2001-03-27 | PAUN | OK | 2001-04-02 |  | 2001-05-10 | 2001-05-25 | 30N04 Baia Mare-Cluj |  | 2001-03-28 | Denis CIUCU | Cosmorom | [32 empty] | 220 | Baia Mare | Maramures | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CJ156 | KAROLY | Baia Mare(10) | CJ076 Unirii_RTC | Transilvania | 47 39 40.6 | 23 34 01.1 | 47 39 38.5 | 23 34 10.7 | Str. Victoriei nr.54 | Asociatie de locatari/Rogojan Ioan - Ap. 8, et.1, responsabil bloc - 062/ 276 792 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | Yes | N/A |  |  |  | 16 | B | 16 |  |  | PROTELCO | OK | ESROM | 2000-12-13 | 2001-02-23 | YesV | 2001-03-07 | Marin | 2001-03-14 | 2001-03-14 |  |  |  |  | 2000-10-17 |  | 2000-11-29 | 2000-12-12 |  |  |  | 2001-02-16 | ICOM | DIRDATES | 2001-02-16 | 2001-02-16 | 2001-02-19 | 2001-02-26 | 2001-02-28 |  | Yes | Ion Soare | 2001-03-30 | 2001-03-30 | 2001-03-30 | 2001-06-21 | 2001-07-11 | K 739 494 | 0 | 0 | 18.7 | K 739 494 | 120 | 0 | 17.8 | K 739 494 | 240 | 0 | 17.8 |  |  |  |  | N/A | 25 | 25 | 7/8" | 24 | 24 | 7/8" | 24 | 24 | 7/8" |  |  |  | 146 |  | Cluj | MW | 254 | 0.6 | 18.3 | 25 | 38/14 |  |  | 2U-3 |  |  |  | RBS | [9 empty] | 1 | CJ154 | INDEPENDENTEI | 74 | 0.6 | 34.5 | 45 | 38/18 | [6 empty] | 28* | DIRDATES | 2001-02-16 | 650 | 2001-02-19 | 2001-02-20 | 2001-03-12 | PAUN | OK | 2001-03-30 |  | 2001-05-10 | 2001-05-25 | 30N01 Baia Mare-Cluj |  | 2001-03-28 | Denis CIUCU | Cosmorom | [32 empty] | 221 | Baia Mare | Maramures | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CJ157 | VASILE LUCACIU | Baia Mare(10) | CJ076 Unirii_RTC | Transilvania | 47 39 41.8 | 23 35 25.8 | 47 39 42.5 | 23 35 25.3 | Str. Dr. Vasile Lucaciu nr.65 | Asociatia de proprietari/Stefan Richter - 094/ 784 540 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-12-11 | YES |  |  |  |  | 15 | B | 15 | T4.5m | N/A | PROTELCO | OK | ESROM | 2000-11-27 | 2001-03-07 | YesV | 2001-03-23 | Marin | 2001-03-14 | 2001-03-29 |  |  |  |  | 2000-10-25 |  | 2000-11-16 | 2000-11-27 |  |  |  | 2001-03-13 | ICOM | CAMUSAT | 2001-03-07 | 2001-03-07 | 2001-03-14 | 2001-03-19 | 2001-03-23 |  | Yes | Ion Soare | 2001-04-02 | 2001-04-02 | 2001-04-02 | 2001-06-21 | 2001-07-11 | K 739 494 | 0 | 0 | 18.2 | K 739 494 | 120 | 0 | 18.2 | K 739 494 | 240 | 0 | 18 |  |  |  |  | N/A | 14 | 14 | 7/8" | 22 | 22 | 7/8" | 14 | 14 | 7/8" |  |  |  | 100 |  | Cluj | MW | 176 | 0.6 | 17.5 | 22 | 38/14 |  |  | 2U-3 |  |  |  | RBS | [9 empty] | 1 | CJ153 | ENERGIEI | 358 | 0.3 | 18.3 | 24.5 | 38/18 | [6 empty] | 41* | CAMUSAT | 2001-03-13 | 710 | 2001-03-15 | 2001-03-15 | 2001-03-27 | PAUN | OK | 2001-04-02 |  | 2001-05-10 | 2001-05-25 | 30N05 Baia Mare-Cluj |  | 2001-03-28 | Denis CIUCU | Cosmorom | [32 empty] | 230 | Baia Mare | Maramures | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CJ158 | SIGHET | Baia Mare(10) | CJ076 Unirii_RTC | Transilvania | 47 39 38.5 | 23 34 10.8 | 47 39 36.9 | 23 36 35.5 | Proprietate Madaras Mihai, com. Tautii de Sus | Madaras Mihai - Satul Nou de Sus, nr.76, Oras Baia Sprie/Madaras Mihai | 2102 | M | C+C+C+ | 2/2/2 | N/A | [12 empty] | 0 | TN | 50 |  | N/A | PROTELCO | OK | ORION | 2001-02-20 | 2001-03-18 | YesV | 2001-05-07 | Marin | 2001-03-23 | 2001-05-09 |  |  |  |  | 2000-10-25 |  | 2000-12-04 | 2000-12-18 |  |  |  | 2001-03-19 | ICOM | Interactive | 2001-03-19 | 2001-03-19 | 2001-03-20 | 2001-03-21 | 2001-03-26 |  | Yes | Theo Radoi | 2001-04-06 | 2001-04-06 | 2001-04-06 | 2001-06-05 | 2001-06-19 | K 739 494 | 20 | 0 | 48.5 | K 739 494 | 90 | 0 | 48.5 | K 739 494 | 240 | 0 | 48.5 |  |  |  |  | N/A | 59 | 59 | 1 1/4" | 59 | 59 | 1 1/4" | 59 | 59 | 1 1/4" |  |  |  | 354 | ML 23 E 1+0 | Cluj | MW | 257 | 0.6 | 47.5 | 58 | 23/58 |  |  | 2U-3 |  |  |  | RBS | [9 empty] | 1 | CJ076 | UNIRII_RTC | 77 | 0.6 | 37.8 | 50 | 23/56 | [6 empty] | 45* | INTERACTIVE | 2001-03-19 | 738 | 2001-03-20 | 2001-03-20 | 2001-03-27 | PAUN | OK | 2001-04-06 |  | 2001-05-10 | 2001-05-25 | 30N05 Baia Mare-Cluj |  | 2001-03-28 | Denis CIUCU | Cosmorom | [32 empty] | 222 | Tautii de Sus | Maramures | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CJ160 | HIDEAGA | Road Baia Mare-Dej-Jibou(12) | CJ076 Unirii_RTC | Transilvania | 47 35 32.6 | 23 25 30.6 | 47 35 32.8 | 23 25 29.6 | Com. Catcau | Berintan Ilona - Baia Mare, str. Forestierilor nr.79, 062/ 270 067/Berintan Ilona - Baia Mare, str. Forestierilor nr.79, 062/ 270 067 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-12-11 | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | PROTELCO | OK | ALMO | 2000-11-15 | 2001-03-10 | YesV | 2001-03-16 | Marin |  | 2001-03-21 |  |  |  |  | 2000-10-28 |  | 2000-11-13 | 2000-11-27 | [6 empty] | 2001-03-13 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 50 | 0 | 48 | K 739 494 | 170 | 0 | 48 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+1 | Cluj | MW | 53 |  | 47.5 | 59 | [7 empty] | RBS | [10 empty] | CJ152 | ALEEA ROTUNDA | 233 |  | 36.4 | 12 | [20 empty] | 30N03 Baia Mare-Cluj |  | 2001-03-28 | Denis CIUCU | Cosmorom | [32 empty] | 160 | Catcau | Cluj | [6 empty] | 1 | 2 |  | 1 | 2
Phase_2 | CS | CJ161 | SOMCUTA MARE | Road Baia Mare-Dej-Jibou(12) | CJ076 Unirii_RTC | Transilvania | 47 30 18.7 | 23 28 47.9 | 47 30 49 | 23 28 52.5 | Extravilan Smcuta Mare | Butean Aurel - Somcuta Mare, str. Nicolae Balcescu nr.49/Butean Aurel - Somcuta Mare, str. Nicolae Balcescu nr.49 | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | PROTELCO | OK | ALMO | 2000-11-15 | 2001-03-03 | YesV | 2001-03-16 | Marin | 2001-03-14 | 2001-03-21 |  |  |  |  | 2000-10-19 |  | 2000-11-09 | 2000-11-29 | [6 empty] | 2001-03-07 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 180 | 0 | 48 | K 739 494 | 315 | 0 | 48 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+1 | Cluj | MW | 334 |  | 47.5 | 59 | [7 empty] | RBS | [10 empty] | CJ160 | HIDEAGA | 154 |  | 47.5 | 59 | [20 empty] | new06 |  | No | Denis CIUCU | Cosmorom | [32 empty] | 263 | Somcuta Mare | Maramures | [6 empty] | 1 | 2 |  | 1 | 2
Phase_2 | CS | CJ162 | DURUSA | Road Baia Mare-Dej-Jibou(12) | CJ076 Unirii_RTC | Transilvania | 47 24 47 | 23 28 34.5 | 47 24 46.2 | 23 28 33.2 | Com. Valea Chiorului, sat Durusa | Pop Maria/Pop Maria | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | PROTELCO | OK | ALMO | 2000-11-15 | 2001-02-02 | YesV | 2001-03-06 | Marin | 2001-03-15 | 2001-03-14 |  |  |  |  | 2000-10-28 |  | 2000-11-09 | 2000-11-29 | [6 empty] | 2001-02-07 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 10 | 0 | 48 | K 739 494 | 115 | 0 | 48 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+1 | Cluj | MW | 2 |  | 47.2 | 59 | [7 empty] | RBS | [10 empty] | CJ161 | SOMCUTA MARE | 182 |  | 46.8 | 59 | [20 empty] | new07 |  | No | Denis CIUCU | Cosmorom | [32 empty] | 399 | Durusa | Maramures | [6 empty] | 1 | 2 |  | 1 | 2
Phase_2 | CS | CJ163 | MESTEACAN | Road Baia Mare-Dej-Jibou(12) | CJ076 Unirii_RTC | Transilvania | 47 23 22.8 | 23 31 02.1 | 47 23 22.8 | 23 31 02.1 | Sat Mesteacan | Vaida Ileana, comuna Valea Chiorului, sat Valea Chiorului, jud. Maramures/Vaida Maria, comuna Valea Chiorului, sat Mesteacan, jud. Maramures | 2102 | M | C+C+C+ | 2/2/2 | N/A | [12 empty] | 0 | TN | 50/6mp |  | N/A | PROTELCO | OK | CONDOR | 2001-03-19 | 2001-06-25 | Yes |  | Marin | [6 empty] | 2000-10-28 |  | 2001-03-14 | 2001-04-10 | [6 empty] | 2001-07-13 | [5 empty] | Yes |  | RBS 2101 CJ162 |  |  |  |  | K 739 494 | 133 | 0 | 47.5 | K 739 494 | 205 | 0 | 47.5 | K 739 494 | 333 | 0 | 47.5 |  |  |  |  | N/A | 58 | 58 | 1 1/4" | 58 | 58 | 1 1/4" | 58 | 58 | 1 1/4" |  |  |  | 348 | ML 23 E 1+0 | Cluj | MW | 309 | 0.6 | 49/0.6 | 60 | [7 empty] | RBS | [10 empty] | CJ162 | DURUSA | 130 |  | 47.6 | 59 | [20 empty] | new06 |  | No | Denis CIUCU | Cosmorom | [32 empty] | 457 | Mesteacan | Maramures | [6 empty] | 1 | 2 |  | 1 | 2
Phase_2 | TM | CJ165 | BARSAU MARE | Road Baia Mare-Dej-Jibou(12) | CJ049 Dej_RTC | Transilvania | 47 16 27.1 | 23 39 48.1 | 47 16 21.8 | 23 39 44.6 | Comuna Galgau, sat Barsau Mare | D-na Rodica Centea, comuna Galgau, sat Barsau Mare , jud. Salaj/D-na Rodica Centea, comuna Galgau, sat Barsau Mare , jud. Salaj | N/A | N/A | N/A | N/A | N/A | [12 empty] | 0 | TN | 30 |  |  | PROTELCO | OK | TEHNOROB | 2001-01-10 | 2001-03-15 | YesV | 2001-05-07 | Marin | 2001-04-17 | 2001-05-09 |  |  |  |  | 2000-10-28 |  | 2000-12-13 | 2001-01-22 | [6 empty] | N/A | N/A |  |  |  |  | Prov |  | RBS 2101 CJ166 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | ML 23 E 1+0 | Cluj | MW | 101 |  | 29.5 | 39.5 | [18 empty] | CJ166 | DOBROCINA | 281 |  | 47.5 | 59 | [20 empty] | N/A |  | OK | Denis CIUCU | Petrica BURGHIU | [32 empty] | 387 | Galgau | Salaj | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CJ166 | DOBROCINA | Road Baia Mare-Dej-Jibou(12) | CJ049 Dej_RTC | Transilvania | 47 14 53.6 | 23 44 26.1 | 47 15 59.5 | 23 42 34.4 | Extravilan Com. Galgau, sat Dobrocina | Dl. Condor Vasile - com. Galgau, sat Dobrocina, 060/ 647 289/Dl. Condor Vasile - com. Galgau, sat Dobrocina, 060/ 647 289 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-12-11 | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | PROTELCO | OK | TEHNOROB | 2000-11-15 | 2001-02-13 | YesV | 2001-03-28 | Marin | 2001-04-17 | 2001-05-04 |  |  |  |  | 2000-10-19 |  | 2000-11-09 | 2000-11-27 | [6 empty] | 2001-02-16 |  |  |  |  | GATA-2101 | Prov |  | RBS 2101 |  |  |  |  | K 739 494 | 130 | 0 | 48 | K 739 494 | 280 | 0 | 48 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Cluj | MW | 130 |  | 47 | 58.5 | [7 empty] | RBS | [10 empty] | CJ167 | CATCAU | 310 |  | 47.5 | 59 | [20 empty] | 30N01 Dej-Cluj |  | OK | Denis CIUCU | Cosmorom | [32 empty] | 249 | Dobrocina | Cluj | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CJ167 | CATCAU | Road Baia Mare-Dej-Jibou(12) | CJ049 Dej_RTC | Transilvania | 47 12 46 | 23 37 06 | 47 13 24.8 | 23 46 59.4 | Extravilan Com. Catcau | Stretea Andrei, sat Catcau nr.445/Stretea Andrei, sat Catcau nr.445 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-12-11 | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | PROTELCO | OK | SVF | 2000-11-15 | 2000-12-21 | YesV | 2001-03-19 | Marin | 2001-03-15 | 2001-03-21 |  |  |  |  | 2000-10-19 |  | 2000-11-13 | 2000-11-27 |  |  |  | 2000-12-28 | ICOM | SVF | 2000-12-27 | 2001-01-10 | 2001-01-11 | 2001-01-12 | 2001-01-22 |  | Yes | Mihai Constantin | 2001-03-27 | 2001-03-27 | 2001-03-27 | 2001-05-15 | 2001-05-25 | K 739 494 | 115 | 0 | 48 | K 739 494 | 310 | 0 | 48.5 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Cluj | MW | 140 | 1.2 | 47.5 | 59 | 15/89 |  |  | 4U-1 |  |  |  | RBS | [9 empty] | 1 | CJ048 | DEALUL ROZELOR | 320 | 1.2 | 48/1.2 | 60 | 15/84 | [6 empty] | 15* | SVF | 2001-01-08 | 503 | 2001-01-26 | 2001-01-30 | 2001-02-12 | VLAD | OK | 2001-03-27 |  | 2001-05-10 | 2001-05-25 | 30N01 Dej-Cluj |  | OK | Denis CIUCU | CATALINA CIOCAN | [32 empty] | 281 | Catcau | Cluj | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CJ169 | BABENI | Road Baia Mare-Dej-Jibou(12) | CJ076 Unirii_RTC | Transilvania | 47 17 08 | 23 24 00 | 47 18 39.1 | 23 23 56.2 | Extravilan com Babeni | Ciulean Victoria, Sat Babeni nr 349 , Jud Salaj/Ciulean Victoria, Sat Babeni nr 349 , Jud Salaj | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-12-11 | [6 empty] | TN | 50 |  | N/A | PROTELCO | OK | SVF | 2000-11-15 | 2001-01-30 | YesV | 2001-03-06 | Marin | 2001-07-06 | 2001-03-14 |  |  |  |  | 2000-10-28 |  | 2000-11-13 | 2000-11-27 |  |  |  |  | ICOM |  | 2001-02-02 |  |  |  |  | GATA-2101 | Prov |  | RBS 2101 |  |  |  |  | K 739 494 | 50 | 0 | 47 | K 739 494 | 250 | 0 | 47 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 59 | 59 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 108 | ML 15 E 1+0 | Cluj | MW | 46 |  | 49 | 60 | [7 empty] | RBS | [10 empty] | CJ163 | MESTEACAN | 226 | 1.2 | 49.5/1.2 | 60 | [20 empty] | new07 |  | No | Denis CIUCU | Petrica BURGHIU | [32 empty] | 283 | Com.Babeni | Salaj | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CJ170 | JIBOU_RTC | Road Baia Mare-Dej-Jibou(12) | CJ076 Unirii_RTC | Maramures | 47 15 37.7 | 23 15 24.1 | 47 15 37.7 | 23 15 24.1 | Str. 1 Mai nr.3 | Romtelecom/ | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [7 empty] | N/A | N/A |  |  |  | 12 | B | 12 | 9m new pylonet | N/A | PROTELCO | OK | SVF | 2000-12-13 | 2001-01-25 | YesV | 2001-03-06 | Marin | 2001-02-05 | 2001-03-14 |  |  |  | N/A | 2000-10-24 |  | 2000-11-17 | OK |  |  |  | 2001-02-01 | ICOM | SVF | 2001-02-01 | 2001-02-01 | 2001-02-06 | 2001-02-12 | 2001-02-13 |  | Yes |  | RBS 2101 CJ175 |  |  |  |  | K 739 494 | 0 | 0 | 18.5 | K 739 494 | 130 | 0 | 18.5 | K 739 494 | 230 | 0 | 18.5 |  |  |  |  | N/A | 24 | 24 | 7/8" | 24 | 24 | 7/8" | 24 | 24 | 7/8" |  |  |  | 144 | ML 23 E 1+0 | Cluj | MW | 128 |  | 18 | [8 empty] | N/A | [10 empty] | CJ175 | VAR | 308 |  | 49 | 60 | [20 empty] | new07 |  | No | Denis CIUCU | Cosmorom | [32 empty] | 204 | Jibou | Salaj | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CJ172 | OCNA SUGATAG | Ocna Sugatag(1+1) | CJ179 Ocna Sugatag_RTC | Transilvania | 47 47 23.1 | 23 56 23.9 | 47 47 23 | 23 56 19 | Str. Unirii nr.2 | SC SIND ROMANIA/Dir. Bobariu Viorel - SC SIND ROMANIA | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | N/A | N/A |  |  |  |  | B | 24.7 | Turn de apa+T4.5m+T4.5m | N/A | PROTELCO | OK | MMK | 2000-12-13 | 2001-01-20 | YesV | 2001-03-08 | Marin | 2001-02-21 | 2001-03-14 |  |  |  |  | 2000-10-28 |  | 2000-11-27 | 2000-12-15 |  |  |  | 2001-02-01 | ICOM | TRY | 2001-01-26 | 2001-01-26 | 2001-02-05 | 2001-02-16 | 2001-02-17 |  | Yes | Theo Radoi | 2001-04-06 | 2001-04-06 | 2001-04-06 | 2001-05-15 | 2001-05-25 | K 739 494 | 0 | 0 | 27 | K 739 494 | 100 | 0 | 27 | K 739 494 | 200 | 0 | 27 |  |  |  |  | N/A | 38 | 38 | 7/8" | 38 | 38 | 7/8" | 38 | 38 | 7/8" |  |  |  | 228 | ML 38 E 1+0 | Cluj | MW | 186 | 0.3 | 26 | 38 | 38/18 |  |  | 2U-3 |  |  |  | RBS | XC60179 | [8 empty] | 1 | CJ179 | OCNA SUGATAG_RTC | 6 | 0.3 | 13.5 | 30 | 38/14 | [6 empty] | 22* | TRYLON |  | 552 | 2001-02-02 | 2001-02-06 | 2001-02-17 | RADU | OK | 2001-04-06 |  | 2001-05-17 | 2001-05-25 | 30N01 Ocna Sugatag-Cluj |  | OK | Denis CIUCU | Cosmorom | [32 empty] | 480 | Ocna Sugatag | Maramures | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CJ173 | VISEU DE SUS_RTC | Viseu de Sus(1) | CJ179 Ocna Sugatag_RTC | Transilvania | 47 42 31.8 | 24 25 48 | 47 42 31.8 | 24 25 48 | Str. Republicii nr.6, Viseu de Sus | Romtelecom/ | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [12 empty] | 5 | B | 14.3 | 9m new pylonet | Room | PROTELCO | OK | MMK | 2000-12-13 | 2001-03-08 | YesV | 2001-04-04 | Marin | 2001-03-23 | 2001-04-06 |  |  |  | N/A | 2000-10-28 |  | 2000-11-15 | 2000-12-22 |  |  |  | 2001-03-15 | ICOM | Interactive | 2001-02-21 | 2001-02-21 | 2001-03-20 | 2001-03-21 | 2001-03-26 | RADU | Yes | Ion Soare | 2001-05-16 | 2001-05-16 | 2001-06-01 |  |  | K 739 494 | 0 | 0 | 22 | K 739 494 | 100 | 0 | 22 | K 739 494 | 200 | 0 | 22 |  |  |  |  | N/A | 25 | 25 | 7/8" | 25 | 25 | 7/8" | 25 | 25 | 7/8" |  |  |  | 150 | N/A | Cluj | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | [5 empty] | XC60179 | [6 empty] | 35/indoor |  |  | CJ179 | OCNA SUGATAG_RTC |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | RADU | OK | N/A |  | N/A | N/A | 30N01 Viseu-Ocna Sugatag+30N01 Ocna Sugatag-Cluj |  | 2001-04-10 | Denis CIUCU | Cosmorom | [32 empty] | 477 | Viseu de Sus | Maramures | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | CJ174 | BORSA_DRTV | Borsa(1+1) | CJ180 Borsa_RTC | Transilvania | 47 39 23.7 | 24 40 25.1 | 47 39 23.7 | 24 40 25.1 | Drtv Borsa | DRTv/ | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-12-11 | N/A | N/A |  |  |  | 0 | TE | 35 |  | N/A | PROTELCO | OK | MMK | 2000-12-04 | 2000-12-20 | YesV | Respins | Marin | 2001-01-09 |  |  |  |  | N/A | 2000-10-28 |  | 2000-11-13 | 2000-11-27 | [6 empty] | 2000-12-20 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 114 | 0 | 33 | K 739 494 | 272 | 0 | 33 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 40 | 40 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 80 | ML 38 E 1+0 | Cluj | MW | 267 |  | 25 | 30 | [7 empty] | RBS | [10 empty] | CJ180 | BORSA_RTC | 87 | 0.3 | 15/0.3 | 15 | [20 empty] | new01 |  |  | Denis CIUCU | Petrica BURGHIU | [32 empty] | 752 | Borsa | Maramures | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CJ175 | VAR | Road Baia Mare-Dej-Jibou(12) | CJ076 Unirii_RTC | Transilvania | 47 16 27.1 | 23 39 48.1 | 47 13 55.2 | 23 18 37.0 | Oras Jibou, Sat Var | Teglas Viorel, Oras Jibou, Sat Var, Nr.12-060/641 012/Teglas Viorel, Oras Jibou, Sat Var, Nr.12- 060/641 012 | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | PROTELCO | OK | ESROM | 2000-11-22 | 2001-04-08 | YesV | 2001-04-24 | Marin | 2001-04-17 | 2001-05-03 |  |  |  |  | 2000-10-28 |  | 2000-11-15 | 2000-11-29 | [6 empty] | 2001-04-11 |  |  |  |  | GATA-2101 | Prov |  | RBS 2101 |  |  |  |  | K 739 494 | 45 | 0 | 47 | K 739 494 | 300 | 0 | 47 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Cluj | MW | 37 |  | 49 | 60 | [7 empty] | RBS | [10 empty] | CJ169 | BABENI | 217 |  | 49 | 60 | [20 empty] | new07 |  | No | Denis CIUCU | Cosmorom | [32 empty] | 277 | Sat Var | Salaj | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CJ176 | ILEANDA | Road Baia Mare-Dej-Jibou(12) | CJ076 Unirii_RTC | Transilvania | 47 19 51.8 | 23 36 38.8 | 47 19 51.8 | 23 36 38.8 | Extravilan Com Ileanda | Bude C.Valentin, Baia Mare, Str. Iuliu Maniu, Nr.24, Jud.Mures/Bude C.Valentin, Baia Mare, Str. Iuliu Maniu, Nr.24, Jud.Mures | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-12-11 | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | PROTELCO | OK | SVF | 2000-11-15 | 2001-01-15 | YesV | 2001-02-06 | Marin | 2001-03-26 | 2001-02-07 |  |  |  |  | 2000-10-28 |  | 2000-11-13 | 2000-11-27 | [6 empty] | 2001-01-26 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 210 | 0 | 48 | K 739 494 | 295 | 0 | 48 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Cluj | MW | 313 |  | 47 | 60 | [7 empty] | RBS | [10 empty] | CJ163 | MESTEACAN | 133 | 1.2 | 49/1.2 | 60 | [20 empty] | new06 |  | No | Denis CIUCU | Cosmorom | [32 empty] | 272 | Com Ileanda | Salaj | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CJ177 | CHIZENI | Road Baia Mare-Dej-Jibou(12) | CJ049 Dej_RTC | Transilvania | 47 18 01.3 | 23 36 56.2 | 47 16 47.9 | 23 37 57 | Sat Chizeni, com. Galgau | Primaria com. Galgau nr.169/Dl. Emil Daniel - primar | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | PROTELCO | OK | TEHNOROB | 2000-11-15 | 2001-02-13 | YesV | 2001-03-28 | Marin | 2001-04-17 | 2001-05-04 |  |  |  |  | 2000-10-28 |  | 2000-11-09 | 2000-11-29 | [6 empty] | 2001-02-16 |  |  |  |  | GATA-2101 | Prov |  | RBS 2101 |  |  |  |  | K 739 494 | 105 | 0 | 48 | K 739 494 | 280 | 0 | 48 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 38 E 1+0 | Cluj | MW | 110 |  | 47 | 59 | [7 empty] | RBS | [10 empty] | CJ165 | BARSAU MARE | 290 |  | 29.5 | 39.5 | [20 empty] | 30N01 Dej-Cluj |  | OK | Denis CIUCU | CATALINA CIOCAN | [32 empty] | 239 | Chizeni | Salaj | [7 empty] | 2 |  |  | 2
Phase_2 | TM | CJ179 | OCNA SUGATAG_RTC | Ocna Sugatag(1+1) | CJ179 Ocna Sugatag_RTC | Transilvania | 47 46 56.9 | 23 56 14.8 | 47 46 56.9 | 23 56 14.8 | Str. Unirii nr.48 | Romtelecom/ | N/A | N/A | N/A | N/A | N/A | [7 empty] | N/A | N/A |  |  |  | N/A | B | 13 | C | Room | PROTELCO | OK | MMK | 2000-11-27 | 2000-12-15 | YesV | 2001-03-08 | Marin | 2001-01-09 | 2001-03-14 |  |  |  | N/A | 2000-10-28 |  | 2000-11-17 | 2000-11-30 |  |  |  | 2001-02-01 | ICOM | TRY | N/A | N/A | 2001-02-05 | N/A | N/A |  | Yes | N/A | 2001-04-06 | 2001-04-06 | 2001-04-06 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A | Cluj | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | 2U-3 |  |  |  |  | 70179 | 2001-05-29 | [5 empty] | 30/Outdoor |  | 1 | BSC41 | BSC CLUJ | N/A | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | RADU | OK | N/A |  | N/A | N/A | N/A |  | N/A | Denis CIUCU | Cosmorom | [32 empty] | 481 | Ocna Sugatag | Maramures | [7 empty] | Site Near=Insertion Point
Phase_2 | TM | CJ180 | BORSA_RTC | Borsa(1+1) | CJ179 Ocna Sugatag_RTC | Transilvania | 47 39 22.5 | 24 39 48 | 47 39 22.5 | 24 39 48 | Str. Decebal nr.2 | Romtelecom/ | N/A | N/A | N/A | N/A | N/A | [12 empty] | N/A | B | 10 | S | Room | PROTELCO | OK | MMK | 2000-12-04 | 2000-12-20 | YesV | 2001-06-08 | Marin | 2001-02-13 | 2001-06-14 |  |  |  | N/A | 2000-10-28 |  | 2000-11-27 | 2000-12-12 | [6 empty] | N/A | N/A |  |  |  |  | Yes |  | RBS 2101 CJ 174 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A | Cluj | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | [5 empty] | 70180 | [6 empty] | 25/Indoor |  |  | CJ173 | OCNA SUGATAG_RTC | N/A | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A |  | N/A | Denis CIUCU | Petrica BURGHIU | [32 empty] | 667 | Borsa | Maramures | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | CJ181 | UNGHENI | Road Tg. Mures-Turda(5+1) | CJ026 Tg. Mures_RTC | Transilvania | 46 28 39 | 24 27 28 | 46 28 39 | 24 27 28 | Incinta fermei ECO CERES srl Ungheni | ECOCERES SRL UNGHENI, str. Muresului nr.111/Haradau Nicolae-065/142479 , 065/169230 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [12 empty] | 0 | TN | 50 |  | N/A | TRANSDAT |  | JACLYN | 2001-06-15 | 2001-07-20 | CTR |  | Andrei | [6 empty] | 2000-11-22 |  | 2000-11-29 | 2001-01-15 | [14 empty] | CTR |  |  |  |  | K 739 494 | 40 | 0 | 48.45 | K 739 494 | 100 | 0 | 48.45 | K 739 494 | 250 | 0 | 48.45 |  |  |  |  | N/A | 60 | 60 | 1 1/4" | 60 | 60 | 1 1/4" | 60 | 60 | 1 1/4" |  |  |  | 360 | ML 15 E 1+0 | Tg. Mures | MW | 49 |  | 47.5 | 58 | [7 empty] | RBS | [10 empty] | CJ028 | GHEORGHE DOJA | 229 |  | 38 | 22 | [23 empty] | Cristian CROITOR | Cosmorom | [32 empty] | 295 | Ungheni | Mures | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CJ182 | OGRA | Road Tg. Mures-Turda(5+1) | CJ047 Turda_RTC | Transilvania | 46 26 42 | 24 18 57 | 46 26 42 | 24 18 54 | Orga (DN 15) | Toma Octavian, Ogra, nr.216/Toma Octavian, Ogra, nr.216 | MAXITE | M | 1 | 2 | 2PBC | [7 empty] | N/A | N/A |  |  |  |  | TN | 50 |  | N/A/TMR9000 | TRANSDAT | OK | JACLYN | 2000-12-13 | 2001-03-02 | YesV | 2001-04-25 | Andrei | 2001-05-07 | 2001-05-03 |  |  |  |  | 2000-11-22 |  | 2000-11-29 | 2001-02-20 |  |  |  | 2001-03-26 | ICOM | TRY | 2001-03-07 | 2001-03-07 | 2001-03-27 | 2001-04-02 | 2001-04-05 |  | Yes | Bogdan Bogodai | 2001-05-10 | 2001-05-10 | 2001-05-10 | 2001-06-22 | 2001-07-11 | AAU | 80 | 0 | 48.45 | AAU | 270 | 0 | 48.45 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 59 | 59 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 118 | ML 15 E 1+0 | Cluj | MW | 274 | 0.6 | 47.5 | 57.5 | 15/89 | [6 empty] | TMR 9000 | XC60046 | [8 empty] | 1 | CJ183 | IERNUT | 94 | 0.6 | 47.5/0.6 | 60 | 15/84 | [6 empty] | 57* | SVF | 2001-04-10 | 848 | 2001-04-18 | 2001-04-18 | 2001-04-23 | PAUN | OK | 2001-05-10 |  | 2001-05-23 | 2001-05-25 | 30N01 Turda-Cluj |  | 2001-04-20 | Cristi CROITOR | Cosmorom | [32 empty] | 280 | Orga | Mures | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CJ183 | IERNUT | Road Tg. Mures-Turda(5+1) | CJ047 Turda_RTC | Transilvania | 46 26 59 | 24 12 39 | 46 26 58.9 | 24 12 39.2 | Localitatea Iernut (DN 15) | Dl. Orza Mircea - Iernut, str. 1 Decembrie 1918, nr.4, ap.6, sc.A, et.1/Dl. Orza Mircea - Iernut, str. 1 Decembrie 1918, nr.4, ap.6, sc.A, et.1, Tel. 065/470385 | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | TRANSDAT | OK | AXA | 2001-02-01 | 2001-03-15 | YesV | 2001-03-30 | Andrei | 2001-05-07 | 2001-05-04 |  |  |  |  | 2000-11-22 |  | 2001-01-16 | 2001-01-30 |  |  |  | 2001-04-10 | ICOM | SVF | 2001-03-19 | 2001-04-10 | 2001-04-18 | 2001-04-19 | 2001-04-20 |  | Yes | Bogdan Bogodai | 2001-05-10 | 2001-04-10 | 2001-04-10 | 2001-05-31 | 2001-06-19 | K 739 494 | 90 | 0 | 48.45 | K 739 494 | 290 | 0 | 48.45 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 61 | 61 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 122 | ML 15 E 1+0 | Cluj | MW | 280 | 0.6 | 47.5/0.6 | 60 | 15/84 | [6 empty] | RBS | [9 empty] | 1 | CJ184 | LUDUS | 102 | 0.6 | 47.5 | 58.5 | 15/89 | [6 empty] | 57* | SVF | 2001-04-10 | 847 | 2001-04-18 | 2001-04-18 | 2001-04-23 | VLAD | OK | 2001-04-10 |  | 2001-05-23 | 2001-05-25 | 30N03 Turda-Cluj |  | 2001-04-20 | Cristi CROITOR | Cosmorom | [32 empty] | 281 | Iernut | Mures | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CJ184 | LUDUS | Road Tg. Mures-Turda(5+1) | CJ047 Turda_RTC | Transilvania | 46 27 59 | 24 05 46 | 46 27 52.32 | 24 05 35.58 | Ludos (DN 15)-"Pe piatra Jezuin" | Csakany Iuliana - str. N. Grigorescu nr.39, Ludus/D-ul Mocanu (de la ferma) str. Nicolae Grigorescu nr. 96A tel. 065/411240 , 094591454 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [12 empty] | 0 | TN | 50 |  | N/A | TRANSDAT | OK | AXA | 2001-01-10 | 2001-03-20 | YesV | 2001-04-09 | Andrei | 2001-05-07 | 2001-04-10 |  |  |  |  | 2000-11-22 |  | 2000-12-18 | 2001-01-15 |  |  |  | 2001-03-26 | ICOM | TRY | 2001-03-21 | 2001-03-21 | 2001-03-27 | 2001-03-28 | 2001-04-02 |  | Yes | Bogdan Bogodai | 2001-05-09 | 2001-04-09 | 2001-04-09 | 2001-05-25 | 2001-06-19 | K 739 494 | 0 | 0 | 48.45 | K 739 494 | 90 | 0 | 48.45 | K 739 494 | 280 | 0 | 48.45 |  |  |  |  | N/A | 61 | 61 | 1 1/4" | 59.5 | 59.5 | 1 1/4" | 60 | 60 | 1 1/4" |  |  |  | 361 | ML 15 E 1+0 | Cluj | MW | 268 | 0.6 | 46.5 | 57 | 15/84 |  |  | 4U-1 |  |  |  | RBS | [9 empty] | 1 | CJ185 | LUNCANI | 88 | 0.6 | 48 | 57.5 | 15/89 | [6 empty] | 49* | TRYLON | 2001-03-26 | 757 | 2001-03-27 | 2001-03-28 | 2001-04-03 | IVAN | OK | 2001-04-09 |  | 2001-05-23 | 2001-05-25 | 30N03 Turda-Cluj |  | 2001-04-20 | Cristi CROITOR | Cosmorom | [32 empty] | 282 | Ludos | Mures | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CJ185 | LUNCANI | Road Tg. Mures-Turda(5+1) | CJ047 Turda_RTC | Transilvania | 46 27 48 | 23 56 52 | 46 28 05 | 23 57 16 | Comuna Luna , Sat Luncani,nr. 398 | Lascau Ioan, comuna Luna , sat Luncani, nr. 398, jud. Cluj/Lascau Ioan, comuna Luna , sat Luncani, nr. 398, jud. Cluj | 2102 | M | C+C+C+ | 2/2/2 | N/A | [12 empty] | 0 | TN | 50 |  | N/A | TRANSDAT | OK | ALMO | 2000-12-21 | 2001-03-10 | YesV | 2001-04-25 | Andrei | 2001-04-06 | 2001-05-03 |  |  |  | 2000-11-22 | 2000-11-22 |  | 2000-12-08 | 2001-01-15 |  |  |  | 2001-03-26 | ICOM | TRY | 2001-03-13 | 2001-03-13 | 2001-03-27 | 2001-04-02 | 2001-04-04 |  | Yes | Bogdan Bogodai | 2001-05-09 | 2001-05-09 | 2001-05-09 | 2001-06-15 | 2001-07-11 | K 739 494 | 130 | 0 | 50 | K 739 494 | 200 | 0 | 50 | K 739 494 | 300 | 0 | 50 |  |  |  |  | N/A | 60 | 60 | 1 1/4" | 61 | 61 | 1 1/4" | 59.5 | 59.5 | 1 1/4" |  |  |  | 361 | ML 15 E 1+0 | Cluj | MW | 314 | 1.2 | 48/1.2 | 50 | 15/84 |  |  | 2U-3 |  |  |  | RBS | [9 empty] | 1 | CJ046 | CIMITIRUL REFORMAT | 134 | 1.2 | 21/1.2 | 25 | 15/89 | [6 empty] | 57* | SVF | 2001-04-10 | 851 | 2001-03-28 | 2001-03-28 | 2001-04-03 | IVAN | OK | 2001-04-09 |  | 2001-05-23 | 2001-05-25 | 30N03 Turda-Cluj |  | 2001-04-20 | Cristi CROITOR | Cosmorom | [32 empty] | 282 | Luncani | Cluj | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CJ186 | CAMPIA TURZII_RTC | Road Tg. Mures-Turda(5+1) | CJ047 Turda_RTC | Transilvania | 46 32 20 | 23 53 05 | 46 32 38 | 23 53 14.8 | Sediul Romtelecom din Campia Turzii | Romtelecom/ | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [12 empty] | 15 | B | 15 | new pilonet18m | Room/Rack19" | PROTELCO | OK | ALMO | 2001-05-15 | 2001-06-22 | YesV | 2001-07-13 | Andrei | [6 empty] | 2001-03-28 |  | 2001-05-02 | 2001-06-08 |  |  |  | 2001-06-26 | ICOM | TRIAL | 2001-06-27 |  | 2001-06-05 | 2001-06-06 | 2001-06-07 | IVAN | Yes | Alexandru Toma | 2001-07-12 |  |  |  |  | K 739 494 | 40 | 0 | 32.3 | K 739 494 | 160 | 0 | 32.3 | K 739 494 | 280 | 0 | 32.3 |  |  |  |  | N/A | 45 | 45 | 7/8" | 45 | 45 | 7/8" | 45 | 45 | 7/8" |  |  |  | 270 | ML 15 E 1+0 | Cluj | MW | 289 | 1.2 | 31.2/1.2 | 43 | 15/84 |  | 4x2/8 | 4U-1(TMR9202) |  |  |  | TMR 9202 | XC60046 | [9 empty] | CJ046 | CIMITIRUL REFORMAT | 109 | 1.2 | 21/1.2 | 45 | 15/89 | [6 empty] | 78* | TRIAL | 2001-06-26 | 1048 | 2001-06-28 | 2001-06-30 | 2001-07-05 | IVAN | 2001-07-05 |  |  |  |  | 30N01 Turda-Cluj |  | 2001-04-20 | Petrica BURGHIU | CATALINA CIOCAN | [33 empty] | Canpia Turzii | Cluj | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CJ187 | FILPISU MARE | Road Reghin-Cluj(7) | CJ034 Reghin_RTC | Transilvania | 46 45 19.0 | 24 33 45.0 | 46 45 19.3 | 24 33 45.1 | Localitatea Filipsu Mare (DN16) | Primaria Breaza/Dl. Brassai Istvan, 095/955 713-primar si Szabo Andrei | MAXITE | M | 1 | 2 | 2PBC | [7 empty] | N/A | N/A |  |  |  |  | TN | 50 |  | TMR9000 | TRANSDAT | OK | DIEKAT | 2001-02-15 | 2001-05-09 | YesV | 2001-05-17 | Andrei |  | 2001-05-23 |  |  |  |  | 2000-11-22 |  | 2001-02-05 | 2001-02-20 |  |  |  | 2001-05-04 | ICOM | DIEKAT | 2001-05-04 | 2001-05-04 | 2001-05-07 | 2001-05-09 | 2001-05-10 | VLAD | Yes | Ion Soare | 2001-05-15 | 2001-05-31 | 2001-06-14 |  |  | AAU | 100 | 0 | 48.45 | AAU | 290 | 0 | 48.45 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 58 | 58 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 116 | ML 15 E 1+1 | Tg. Mures | MW | 72 | 0.6 | 47.5/0.6 | 57.5 | 15/84 | YES | 4x2/8 | 4U-1 |  |  |  | TMR 9000 | XC60034 | [9 empty] | CJ036 | TURN_RGA | 259 | 0.6 | 50 | 70 | 15/89 | [6 empty] | 63* | DIEKAT | 2001-05-04 | 884 | 2001-05-04 | 2001-05-07 | 2001-05-10 | IVAN | OK | 2001-06-14 |  | 2001-06-19 | 2001-07-10 | 30N02 |  | OK | Cristi CROITOR | Cosmorom | [32 empty] | 445 | Filipsu Mare | Mures | [6 empty] | 1 | 2 |  | 1 | 2
Phase_2 | CS | CJ188 | FARAGAU | Road Reghin-Cluj(7) | CJ034 Reghin_RTC | Transilvania | 46 45 20.9 | 24 27 35.1 | 46 45 20.9 | 24 27 35.1 | Localitatea Faragau (DN16) | Porav Petru, str. Carpinis, nr. 6, Reghin, jud. Mures/Porav Petru, str. Carpinis, nr. 6, tel. 065/ 523 070 | MAXITE | M | 1 | 2 | 2PBC | [7 empty] | N/A | N/A |  |  |  |  | TN | 50 |  | TMR9000 | TRANSDAT | OK | DIEKAT | 2001-02-14 | 2001-05-14 | YesV | 2001-06-07 | Andrei |  | 2001-06-14 |  |  |  |  | 2000-11-22 |  | 2001-01-30 | 2001-02-20 |  |  |  | 2001-05-04 | ICOM | DIEKAT | 2001-05-04 | 2001-05-04 | 2001-05-07 | 2001-05-08 | 2001-05-14 | PAUN | Yes | Ion Soare | 2001-05-16 | 2001-05-16 | 2001-06-14 |  |  | AAU | 70 | 0 | 48.45 | AAU | 270 | 0 | 48.45 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 58 | 58 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 116 | ML 23 E 1+1 | Tg. Mures | MW | 90 | 1.2 | 47.5/1.2 | 57.5 | 23/58 | YES | 4x2/8 | 4U-1 |  |  |  | TMR 9000 | XC60034 | [9 empty] | CJ187 | FILPISU MARE | 270 | 1.2 | 47.5/0.6 | 57.5 | 23/56 | [6 empty] | 63* | DIEKAT | 2001-05-04 | 882 | 2001-05-04 | 2001-05-07 | 2001-05-10 | PAUN | OK | 2001-06-14 |  | 2001-07-12 |  | 30N02 |  | OK | Cristi Croitor | Cosmorom | [32 empty] | 506 | Faragau | Mures | [6 empty] | 1 | 2 |  | 1 | 2
Phase_2 | CS | CJ189 | SILIVASU DE CAMPIE | Road Reghin-Cluj(7) | CJ034 Reghin_RTC | Transilvania | 46 46 48.1 | 24 19 11.9 | 46 46 47.7 | 24 19 12.29 | Localitatea Silivestru de Campie (DN16) | Tasca Ioan , Tagul Mures, str. Infratirii nr.10/Tasca Ioan , Tagul Mures, str. Infratirii nr.10 | MAXITE | M | 1 | 2 | 2PBC | [7 empty] | N/A | N/A |  |  |  |  | TN | 50 |  | TMR9000 | TRANSDAT | OK | DIEKAT | 2001-02-06 | 2001-05-09 | YesV | 2001-05-24 | Andrei | [6 empty] | 2000-11-22 |  | 2001-01-25 | 2001-02-20 |  |  |  | 2001-05-04 | ICOM | DIEKAT | 2001-05-04 | 2001-05-04 | 2001-05-07 | 2001-05-08 | 2001-05-14 | IVAN | Yes | Ion Soare | 2001-05-16 | 2001-05-16 | 2001-06-14 |  |  | AAU | 110 | 0 | 48.3 | AAU | 270 | 0 | 48.3 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 58.5 | 58.5 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 117 | ML 15 E 1+1 | Tg. Mures | MW | 104 | 0.6 | 48 | 57 | 15/84 | YES | 4x2/8 | 4U-1 |  |  |  | TMR 9000 | [10 empty] | CJ188 | FARAGAU | 284 | 0.6 | 47/1.2 | 57 | 15/89 | [6 empty] | 63* | DIEKAT | 2001-05-04 | 881 | 2001-05-04 | 2001-05-07 | 2001-05-10 | VLAD | OK | 2001-06-14 |  | 2001-07-12 |  | 30N03 |  | 2001-05-15 | Cristi CROITOR | Cosmorom | [32 empty] | 519 | Silivestru de Campie | Mures | [6 empty] | 1 | 2 |  | 1 | 2
Phase_2 | CS | CJ190 | SARMASEL DEAL | Road Reghin-Cluj(7) | CJ034 Reghin_RTC | Transilvania | 46 45 14.6 | 24 10 52.1 | 46 47 14.4 | 24 10 51.5 | Localitatea Sarmasel Deal (DN16) | Primaria Sarmasel, com. Sarmasu, str. Republicii, nr. 63/Primarul Gheorhe Floare si d-na Rusu Maria | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | N/A | N/A |  |  |  | 0 | TN | 50 |  | N/A | TRANSDAT | OK | DIEKAT | 2001-02-16 | 2001-05-07 | YesV | 2001-05-17 | Andrei |  | 2001-05-23 |  |  |  |  | 2000-11-22 |  | 2001-01-30 | 2001-02-21 |  |  |  | 2001-05-04 | ICOM | DIEKAT | 2001-05-04 | 2001-05-04 | 2001-05-07 | 2001-05-09 | 2001-05-10 | VLAD | Yes | Ion Soare | 2001-05-16 | 2001-05-16 | 2001-06-14 |  |  | K 739 494 | 120 | 0 | 48.45 | K 739 494 | 190 | 0 | 48.45 | K 739 494 | 300 | 0 | 48.45 |  |  |  |  | N/A | 60 | 60 | 1 1/4" | 61 | 61 | 1 1/4" | 61 | 61 | 1 1/4" |  |  |  | 364 | ML 15 E 1+0 | Tg. Mures | MW | 94 | 0.6 | 47/1.2 | 58.5 | 15/89 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [10 empty] | CJ189 | SILIVASU DE CAMPIE | 274 | 0.6 | 48 | 57 | 15/84 | [6 empty] | 63* | DIEKAT | 2001-05-04 | 880 | 2001-05-04 | 2001-05-07 | 2001-05-10 | IVAN | OK | 2001-06-14 |  | 2001-07-12 |  | 30N03 |  | 2001-05-15 | Cristi Croitor | Cosmorom | [32 empty] | 369 | Sarmasel | Mures | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CJ191 | ZORENI | Road Reghin-Cluj(7) | CJ034 Reghin_RTC | Transilvania | 46 47 19.9 | 24 03 04.4 | 46 47 19.5 | 24 03 41.2 | Localitatea Zorenii de Vale nr.99 | Tatar Teodor, tel. 094/218617/Tatar Teodor, tel. 094/218617-Zorenii de Vale nr.99 | MAXITE | M | 1 | 2 | 2PBC | [7 empty] | N/A | N/A |  |  |  |  | TN | 50 |  | TMR9000 | TRANSDAT | OK | DIEKAT | 2001-02-01 | 2001-04-12 | YesV | 2001-04-23 | Andrei | 2001-05-10 | 2001-05-03 |  |  |  |  | 2000-11-22 |  | 2001-01-16 | 2001-02-01 |  |  |  | 2001-04-03 | ICOM | DIEKAT | 2001-04-03 | 2001-04-03 | 2001-04-05 | 2001-04-11 | 2001-04-12 | IVAN | Yes | Ion Soare | 2001-05-16 | 2001-05-16 | 2001-06-14 |  |  | AAU | 80 | 0 | 48.45 | AAU | 300 | N/A | 48.45 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 120 | ML 15 E 1+0 | Tg. Mures | MW | 91 | 0.6 | 47/1.2 | 60 | 15/84 |  | 4x2/8 | 2U-3 |  |  |  | TMR 9000 | [10 empty] | CJ190 | SARMASEL DEAL | 271 | 0.6 | 47/1.2 | 59.5 | 15/89 | [6 empty] | 63* | DIEKAT | 2001-05-04 | 878 | 2001-05-04 | 2001-05-07 | 2001-05-10 | PAUN | OK | 2001-06-14 |  | 2001-07-12 |  | 30N03 |  | 2001-05-15 | Cristi CROITOR | Cosmorom | [32 empty] | 447 | Zoreni | Bistrita Nasaud | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CJ192 | MOCIU | Road Reghin-Cluj(7) | CJ034 Reghin_RTC | Transilvania | 46 47 59.7 | 23 59 55.3 | 46 47 59.7 | 23 59 55.2 | Localitatea Mociu , sat Turmas | Catinean Traian, Catinean Vladimir, Catinean Viorel, sat Turmas, com. Mociu, Jud. Mures, tel. 258 sau 094/648451/Catinean Traian, Catinean Vladimir, Catinean Viorel, sat Turmas, com. Mociu, Jud. Mures, tel. 258 sau 094/648451 | MAXITE | M | 1 | 2 | 2PBC | [7 empty] | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | TRANSDAT | OK | DIEKAT | 2001-02-01 | 2001-04-10 | YesV | 2001-04-23 | Andrei | 2001-05-07 | 2001-05-03 |  |  |  |  | 2000-11-22 |  | 2001-01-17 | 2001-02-01 |  |  |  | 2001-04-03 | ICOM | DIEKAT | 2001-04-03 | 2001-04-03 | 2001-04-05 | 2001-04-10 | 2001-04-11 | PAUN | Yes | Ion Soare | 2001-06-14 | 2001-06-16 | 2001-06-16 |  |  | AAU | 150 | 0 | 48.3 | AAU | 280 | 0 | 48.3 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 120 | ML 23 E 1+0 | Tg. Mures | MW | 107 | 0.6 | 47/0.6 | 60 | 23/58 |  | 4x2/8 | 2U-3 |  |  |  | TMR 9000 | [10 empty] | CJ191 | ZORENI | 287 | 0.6 | 47.5/0.6 | 60 | 23/56 | [6 empty] | 53* | DIEKAT | 2001-04-03 | 821 | 2001-04-05 | 2001-04-05 | 2001-04-18 | VLAD | OK | 2001-06-14 |  | 2001-07-12 |  | 30N03 |  | 2001-05-15 | Cristi CROITOR | Cosmorom | [32 empty] | 437 | Mociu | Cluj | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CJ193 | CORPADEA | Road Reghin-Cluj(7) | CJ034 Reghin_RTC | Transilvania | 46 48 19.1 | 23 49 55 | 46 48 25.6 | 23 51 29.3 | Localitaea Corpadea (DN 16), jud. Cluj | Primaria Apahida, jud. Cluj/Primaria Apahida, jud. Cluj | MAXITE | M | 1 | 2 | 2PBC | [7 empty] | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | TRANSDAT | OK | VECTOR | 2001-04-10 | 2001-05-20 | YesV | 2001-07-13 | Andrei | [6 empty] | 2000-11-22 |  | 2001-04-09 | OK |  |  |  | 2001-05-24 | ICOM | VECTOR | 2001-05-23 | 2001-05-23 | 2001-05-25 | 2001-06-02 | 2001-06-13 | PAUN | Yes | Ion Soare | 2001-06-16 | 2001-06-16 | 2001-06-16 |  |  | K 739 494 | 130 | 0 | 48.5 | K 739 494 | 280 | 0 | 48.5 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 120 | ML 15 E 1+0 | Tg. Mures | MW | 92 | 1.2 | 47 | 60 | 15/84 |  | 4x2/8 | 2U-3 |  |  |  | TMR 9000 | [10 empty] | CJ192 | MOCIU | 273 | 1.2 | 47/1.2 | 60 | 15/89 | [6 empty] | 71* | VECTOR | 2001-05-24 | 942 | 2001-04-24 | 2001-05-24 | 2001-06-07 | PAUN | OK | 2001-06-16 |  |  |  | 30N03 |  | 2001-05-15 | Cristi Croitor | COSMOROM | [32 empty] | 402 | Corpadea | Cluj | [7 empty] | 2 |  |  | 2
Phase_3 | CS | CJ200 | ALEEA BEGONIEI | Satu Mare | CJ073 Satu Mare_RTC | Maramures | 47 48 07.7 | 22 53 31.7 | 47 48 07.7 | 22 53 32.9 | Aleea Begoniei, bl. 3 | Asociatia de locatari bl 2 bl3 cartier 14 Mai | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | YES |  |  |  |  | 14.5 | B | 14.5 | T6m+T6m | N/A | PROTELCO | OK | ESROM | 2001-08-01 | 2001-08-20 |  |  | Marin | [6 empty] | 2001-06-21 |  | 2001-07-06 | 2001-07-11 | [14 empty] | CTR |  |  |  |  | K 739 494 | 0 | 0 | 19 | K 739 494 | 150 | 0 | 19 | K 739 494 | 250 | 0 | 19 | N/A | N/A | N/A | N/A | N/A | 20 | 20 | 7/8" | 18 | 18 | 7/8" | 18 | 18 | 7/8" | N/A | N/A | N/A | 112 | ML 38 E 1+0 | Oradea | MW | 210 | 0.3 | 18.5 | 17.5 | [18 empty] | CJ073 | SATU MARE_RTC | 29 | [26 empty] | Denis CIUCU | [34 empty] | Satu Mare | Satu Mare | [7 empty] | missing |  |  | missing
Phase_3 | CS | CJ202 | 1 DECEMBRIE | Tg. Mures(6) | CJ026 Tg. Mures_RTC | Transilvania | 46 32 00.5 | 24 35 17.2 |  |  |  |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [17 empty] | SVF |  | @ | 2001-08-15 | 2001-08-30 |  |  | Andrei |  |  | 2001-06-07 | [57 empty] | Tg. Mures | MW | [22 empty] | CJ027 | PANDURILOR | [27 empty] | SORIN UNTARU | SORIN UNTARU | [42 empty] | missing |  |  | missing
Phase_3 | CS | CJ203 | CUTEZANTEI | Tg. Mures(6) | CJ026 Tg. Mures_RTC | Transilvania | 46 32 22.8 | 24 35 01 |  |  |  |  | 2101 | M | C+ | 2 | 2101 | [17 empty] | SVF* | [6 empty] | Andrei* |  |  | 2001-06-07 | [57 empty] | Tg. Mures | MW | [22 empty] | CJ202 | 1 DECEMBRIE | [27 empty] | SORIN UNTARU | SORIN UNTARU | [42 empty] | missing |  |  | missing
Phase_3 | CS | CJ204 | CAMIN 14 | Cluj(5) | CJ054 Baritiu_RTC | Transilvania | 46 45 47.2 | 23 34 58.8 |  |  |  |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [17 empty] | PROTELCO |  | @ | 2001-08-15 | 2001-08-30 |  |  | Marin |  |  | 2001-06-07 | [57 empty] | Cluj | MW | [22 empty] | CJ207 | TITULESCU | [27 empty] | SORIN UNTARU | SORIN UNTARU | [42 empty] | missing |  |  | missing
Phase_3 | CS | CJ205 | ELECTROSIGMA | Cluj(5) | CJ054 Baritiu_RTC | Transilvania | 46 45 23.1 | 23 35 41.2 |  |  |  |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [17 empty] | PROTELCO* | [6 empty] | Marin* |  |  | 2001-06-07 | [57 empty] | Cluj | MW | [22 empty] | CJ055 | TAIETURA TURCULUI | [27 empty] | SORIN UNTARU | SORIN UNTARU | [42 empty] | missing |  |  | missing
Phase_3 | CS | CJ206 | MUSCEL | Cluj(5) | CJ054 Baritiu_RTC | Transilvania | 46 45 49.9 | 23 36 19.1 |  |  |  |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [17 empty] | PROTELCO* | [6 empty] | Marin* |  |  | 2001-06-07 | [57 empty] | Cluj | MW | [22 empty] | CJ055 | TAIETURA TURCULUI | [27 empty] | SORIN UNTARU | SORIN UNTARU | [42 empty] | missing |  |  | missing
Phase_3 | CS | CJ207 | TITULESCU | Cluj(5) | CJ054 Baritiu_RTC | Transilvania | 46 46 07.9 | 23 36 55.9 |  |  |  |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [17 empty] | PROTELCO | OK | E-GRUP | 2001-08-01 | 2001-08-20 |  |  | Marin |  |  | 2001-06-07 | [57 empty] | Cluj | MW | [22 empty] | CJ059 | GHEORGHIENI_2 | [27 empty] | SORIN UNTARU | SORIN UNTARU | [42 empty] | missing |  |  | missing
Phase_3 | CS | CJ208 | CIOBANULUI | Cluj(5) | CJ054 Baritiu_RTC | Transilvania | 46 45 21.5 | 23 32 53.5 |  |  |  |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [17 empty] | PROTELCO | OK | E-GRUP | 2001-08-01 | 2001-08-20 |  |  | Marin |  |  | 2001-06-07 | [57 empty] | Cluj | MW | [22 empty] | CJ055 | TAIETURA TURCULUI | [27 empty] | SORIN UNTARU | SORIN UNTARU | [42 empty] | missing |  |  | missing
Phase_3 | CS | CJ209 | SIGHISOAREI | Tg. Mures(6) | CJ026 Tg. Mures_RTC | Transilvania | 46 31 57.8 | 24 34 03.2 |  |  |  |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [17 empty] | SVF* | [6 empty] | Andrei* |  |  | 2001-06-07 | [57 empty] | Tg. Mures | MW | [22 empty] | CJ027 | PANDURILOR | [27 empty] | SORIN UNTARU | SORIN UNTARU | [42 empty] | missing |  |  | missing
Phase_3 | CS | CJ210 | DECEBAL | Tg. Mures(6) | CJ026 Tg. Mures_RTC | Transilvania | 46 33 27.5 | 24 32 43.9 |  |  |  |  | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [17 empty] | SVF | OK | E-GRUP | 2001-08-01 | 2001-08-20 |  |  | Andrei |  |  | 2001-06-07 | [57 empty] | Tg. Mures | MW | [22 empty] | CJ212 | MIHAI VITEAZU | [27 empty] | SORIN UNTARU | SORIN UNTARU | [42 empty] | missing |  |  | missing
Phase_3 | CS | CJ211 | KOOS | Tg. Mures(6) | CJ026 Tg. Mures_RTC | Transilvania | 46 31 38.8 | 24 33 17 |  |  |  |  | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [17 empty] | SVF | OK | E-GRUP | 2001-08-01 | 2001-08-20 |  |  | Andrei |  |  | 2001-06-07 | [57 empty] | Tg. Mures | MW | [22 empty] | CJ028 | GHEORGHE DOJA | [27 empty] | SORIN UNTARU | SORIN UNTARU | [42 empty] | missing |  |  | missing
Phase_3 | CS | CJ212 | MIHAI VITEAZU | Tg. Mures(6) | CJ026 Tg. Mures_RTC | Transilvania | 46 33 02.8 | 24 34 22.3 |  |  |  |  | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [17 empty] | SVF |  | @ | 2001-08-15 | 2001-08-30 |  |  | Andrei |  |  | 2001-06-07 | [57 empty] | Tg. Mures | MW | [22 empty] | CJ033 | PIATA TEATRULUI | [27 empty] | SORIN UNTARU | SORIN UNTARU | [42 empty] | missing |  |  | missing
Phase_3 | CS | CJ213 | TAPU | Road Copsa Mica-Teius(3) | CJ043 Alba Iulia_RTC | Transilvania | 46 04 22.3 | 24 04 34.6 |  |  |  |  | MAXITE | M | 1 | 2 | 2PBC | [17 empty] | DUAL |  | DUAL | 2001-08-15 | 2001-09-20 |  |  | Andrei |  |  | 2001-06-25 |  |  |  | 2001-06-25 |  |  |  |  | 2001-06-25 | [48 empty] | Cluj | MW | [22 empty] | CJ214 | BLAJ | [24 empty] | new01 Blaj-Alba Iulia+ new Alba Iulia-Cluj |  |  | Florin BELEA | Andrei DUMITRESCU
Phase_3 | CS | CJ214 | BLAJ | Road Copsa Mica-Teius(3) | CJ043 Alba Iulia_RTC | Transilvania | 46 10 44.1 | 23 55 56.6 |  |  |  |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [17 empty] | DUAL |  | DUAL | 2001-07-23 | 2001-08-10 |  |  | Andrei |  |  | 2001-06-25 |  |  |  | 2001-06-25 |  |  |  |  | 2001-06-25 | [17 empty] | K 739 494 |  |  |  | K 739 494 |  |  |  | K 739 707 | [22 empty] | Cluj | MW | [22 empty] | YJ231 | BLAJ_RTC | [24 empty] | new01 Blaj-Alba Iulia+ new Alba Iulia-Cluj |  |  | Florin BELEA | Andrei DUMITRESCU
Phase_3 | CS | CJ215 | CISTEI | Road Copsa Mica-Teius(3) | CJ085 Santimbru_RTC | Transilvania | 46 11 13.5 | 23 45 08 |  |  |  |  | MAXITE | M | 1 | 2 | 2PBC | [17 empty] | DUAL | OK | DUAL | 2001-08-01 | 2001-08-30 |  |  | Andrei |  |  | 2001-06-25 | 2001-07-05 |  |  | 2001-07-10 |  |  |  |  | 2001-06-25 | [47 empty] | ML 15 E 1+0 | Tg. Mures | MW | [12 empty] | XC60085 | [9 empty] | CJ085 | SINTIMBRU_RTC | [27 empty] | Florin BELEA | Andrei DUMITRESCU
Phase_3 | CS | CJ217 | TARNAVENI | Road Medias-Iernut | BV085 Medias_RTC | Transilvania | 46 20 29.1 | 24 16 03.6 |  |  |  |  | 2101 | M | C+ | 2 | 2101 | [27 empty] | 2001-07-12 | [8 empty] | 2001-07-12 | [47 empty] | ML 15 E 1+0* | Tg. Mures | MW | [22 empty] | CJ218 | HULA-BLAJEL
Phase_3 | CS | CJ218 | HULA-BLAJEL | Road Medias-Iernut | BV085 Medias_RTC | Transilvania | 46 11 15.6 | 24 19 52.5 |  |  |  |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [27 empty] | 2001-07-12 | [8 empty] | 2001-07-12 | [47 empty] | ML 38 E 1+0* | Tg. Mures | MW | [22 empty] | BV085 | MEDIAS_RTC
Phase_3 | CS | CJ219 | BAZNA | Cluj county | BV085 Medias_RTC | Transilvania | 46 11 47.8 | 24 16 28.7 |  |  |  |  | 2101 | M | C+ | 2 | 2101 | [27 empty] | 2001-07-12 | [8 empty] | 2001-07-12 | [47 empty] | ML 23 E 1+0* | Tg. Mures | MW | [22 empty] | CJ218 | HULA-BLAJEL
Phase_3 | CS | CJ221 | MOARA | Alba Iulia(5) | CJ043 Alba Iulia_RTC | Transilvania | 46 03 21.6 | 23 34 24.4 |  |  |  |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [27 empty] | 2001-07-12 | [8 empty] | 2001-07-12 | [47 empty] | ML 38 E 1+0* | Cluj | MW | [22 empty] | CJ069 | VICTORIEI | [27 empty] | SORIN UNTARU | SORIN UNTARU
Phase_3 | CS | CJ222 | SIMION BARNUTIU | Zalau(5+1) | CJ050 Zalau_RTC | Transilvania | 47 11 54.9 | 23 02 45 |  |  |  |  | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [27 empty] | 2001-07-12 | [8 empty] | 2001-07-12 | [47 empty] | ML 38 E 1+0* | Cluj | MW | [22 empty] | CJ053 | DEALUL NOIMAL | [27 empty] | SORIN UNTARU | SORIN UNTARU
Phase_3 | CS | CJ223 | ZALAU INTRARE | Zalau(5+1) | CJ050 Zalau_RTC | Transilvania | 47 10 06.7 | 23 04 16.8 |  |  |  |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [27 empty] | 2001-07-12 | [8 empty] | 2001-07-12 | [47 empty] | ML 38 E 1+0* | Cluj | MW | [22 empty] | CJ051 | SARMIS | [27 empty] | SORIN UNTARU | SORIN UNTARU
Phase_2 | CS | CR001 | GIURGIU_CTA2 | Giurgiu(2) | CR001Giurgiu_CTA2 | Muntenia | 44 54 27.91 | 25 58 19.19 | 43 54 27.0 | 25 58 17.8 | CTA 2 Tineretului, Strada Constantin Brancoveanu nr.1 DISPECERAT CONEL 046216434 | Romtelecom/Aurel VOCHITOAIA, 092/552 736 | 2202 | M/E | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-06-13 | N/A | N/A |  |  |  | N/A | B | 42 | Existing 42m tower | ROOM | PROTELCO | OK | FIBEC | 2000-04-20 | 2000-05-09 | YesV | 2000-05-09 | Doru | 2000-05-10 | 2000-05-10 |  |  |  | 2000-03-23 | 2000-03-22 |  | 2000-04-08 | 2000-04-14 |  |  |  | NA | YRO | NA | 2000-05-08 | 2000-05-08 | 2000-05-10 | 2000-05-10 | 2000-05-14 |  | Yes | Cristian Croitor | 2000-05-29 | 2000-06-07 | 2000-07-07 | 2000-08-02 | 2000-08-09 | K 739 494 | 12 | 0 | 40.5 | K 739 494 | 155 | 0 | 40.5 | K 739 494 | 227 | 0 | 40.5 |  |  |  |  | N/A | 61 | 61 | 1 1/4" | 61 | 61 | 1 1/4" | 61 | 61 | 1 1/4" |  |  |  | 366 | N/A | Baneasa | FO | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | TMR 9202 | 40001 | 2000-05-12 |  |  | 2001-06-25 |  |  | 30/2 pairs - indoor |  | 1 | BSC21 | BANEASA |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | ARANYOSI | OK | N/A |  | N/A | N/A | 30N01 Giurgiu-Baneasa |  | OK | Liviu CHIRCA | Cosmorom | [32 empty] | 20 | Giurgiu | Giurgiu | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | CR002 | PLOPSORU | Road Buc-Giurgiu(5) | CR001Giurgiu_CTA2 | Muntenia | 44 00 29.02 | 25 59 13.00 | 44 00 33.8 | 25 59 04.9 | Teren arabil, Sat Plopsoru Comuna Daia | Private/Pascu MARIA, proprietar | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-08-02 | N/A | N/A |  |  |  | N/A | TN | 40 | New 40m tower | N/A | PROTELCO | OK | FIBEC | 2000-04-20 | 2000-06-05 | YesV | 2000-06-05 | Doru | 2000-06-19 | 2000-06-07 |  |  |  | 2000-03-23 | 2000-03-22 |  | 2000-05-09 | 2000-05-09 |  |  |  | NA | YRO | NA | 2000-06-07 | 2000-05-08 | 2000-06-08 | 2000-06-08 | 2000-06-12 |  | Yes | Cristian Croitor | 2000-07-15 | 2000-07-07 | 2000-07-07 | 2000-08-02 | 2000-08-09 | K 739 494 | 0 | 0 | 38 | K 739 494 | 180 | 0 | 38 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 48 | 48 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 96 | ML 15 E 1+0 | Baneasa | MW | 2.7 | 0.6 | 37 | 47 | 15/84 |  |  | 2U-3 |  |  |  | RBS | [7 empty] | 3/2 pairs - outdoor |  |  | CR001 | GIURGIU_CTA2 | 5 | 0.6 | 39 | 61 | 15/89 | [6 empty] | N/A | YRO | N/A | 1/407 | 1.06.00-12.05.00 | 2000-06-13 | 2000-06-13 | RADU | OK | 2000-07-11 |  | 2000-08-01 | 2000-08-09 | 30N01 Giurgiu-Baneasa |  | OK | Liviu CHIRCA | Cosmorom | [32 empty] | 82 | Plopsoru | Giurgiu | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CR003 | UZUNU | Road Buc-Giurgiu(5) | CR001Giurgiu_CTA2 | Muntenia | 44 06 54.46 | 26 00 00.32 | 44 07 26.3 | 25 59 31.8 | sat Uzunu, DN 5 Km 37 | Socol Costel/Socol Costel, tel:092 392620 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-06-23 | N/A | N/A |  |  |  |  | TN | 40 | New 40m tower | N/A | PROTELCO | OK | FIBEC | 2000-05-11 | 2000-06-21 | YesV | 2000-06-21 | Doru | 2000-07-03 | 2000-07-05 |  |  |  | 2000-03-23 | 2000-03-22 |  | 2000-04-29 | 2000-05-17 |  |  |  | NA | YRO | NA | 2000-07-04 | 2000-07-05 | 2000-07-06 | 2000-07-07 | 2000-07-10 |  | Yes | Alexandru Bucur | 2000-07-15 | 2000-07-12 | 2000-07-12 | 2000-08-02 | 2000-09-07 | K 739 494 | 10 | 0 | 36.5 | K 739 494 | 190 | 0 | 36.5 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 55 | 55 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 110 | ML 15 E 1+0 | Baneasa | MW | 183 | 0.6 | 38.5 | 55 | 15/89 |  |  | 2U-3 |  |  |  | RBS | [10 empty] | CR002 | PLOPSORU | 185 | 0.6 | 37 | 47 | 15/84 | [6 empty] | N/A | YRO | N/A | 21/1 | 8.06.00-4.07.00 | 2000-07-09 | 2000-07-10 | PITURCESCU | OK | 2000-07-11 |  | 2000-08-01 | 2000-08-09 | 30N01 Giurgiu-Baneasa |  | OK | Liviu CHIRCA | Cosmorom | [32 empty] | 81 | Com. Calugareni | Giurgiu | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CR004 | ADUNATII-COPACENI_DRTV | Road Buc-Giurgiu(5) | CR001Giurgiu_CTA2 | Muntenia | 44 13 33.00 | 26 01 46.98 | 44 13 32.6 | 26 01 46.5 | DRTV Adunatii Copaceni, Giurgiu | DRTV/ | MAXITE | M | 1 | 2 | 2PBC | [6 empty] | 2000-06-13 | N/A | N/A |  |  |  | 60 | B | 60 | T4m+Border of Tower | N/A | PROTELCO | OK | FIBEC | 2000-05-12 | 2000-05-31 | YesV | 2000-05-31 | Doru | 2000-06-19 | 2000-06-02 |  |  |  | 2000-03-23 | 2000-03-22 |  | 2000-03-31 | 2000-05-09 |  |  |  | NA | YRO | NA | 2000-06-13 | 2000-06-14 | 2000-06-13 | 2000-06-13 | 2000-06-16 |  | Yes | Alexandru Bucur | 2000-07-15 | 2000-07-18 | 2000-07-18 | 2000-08-02 | 2000-08-09 | AAU | 25 | 0 | 57.5 | AAU | 195 | #N/A | 57.5 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 15 | 15 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 30 | ML 15 E 1+0 | Baneasa | MW | 195 | 0.6 | 64 | 35 | 15/84 |  |  | 2U-3 |  |  |  | N/A | [7 empty] | N/A/2 pairs - outdoor |  |  | CR003 | UZUNU | 15 | 0.6 | 38.5 |  | 15/89 | [6 empty] | N/A | YRO | N/A | 2001-04-21 | 13.06.00-4.07.00 | 2000-06-15 | 2000-07-10 | DINCA | OK | 2000-07-11 |  | 2000-11-20 | 2001-01-08 | 30N01 Giurgiu-Baneasa |  | OK | Liviu CHIRCA | #N/A | [32 empty] | 80 | Adunatii-Copaceni | Giurgiu | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CR005 | CIOROGARLA | Road Buc-Pitesti(8) | BU042 Chitila | Muntenia | 44 27 14.33 | 25 53 28.93 | 44 26 38 | 25 53 02 | Str. Scolii nr.2 | Constantin Iordache/ | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-07-18 | N/A | N/A |  |  |  | N/A | TN | 50 | 50m new tower | N/A | PROTELCO | OK | FIBEC | 2000-07-01 | 2000-07-31 | YesV | 2000-08-01 | Mugur | 2000-11-10 | 2000-08-03 |  |  |  | 2000-05-23 | 2000-05-03 |  | 2000-06-07 | 2000-06-12 |  |  |  | 2000-09-19 | YRO | Electotrade | 2000-08-23 | 23-08-00 | 2000-09-19 | 2000-09-21 | 2000-09-25 |  | Yes | Theo Radoi | 2001-02-28 | 2001-01-08 | 2001-01-08 | 2001-05-28 | 2001-06-19 | K 739 494 | 90 | 0 | 48 | K 739 494 | 290 | 0 | 48 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 66 | 66 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 132 | ML 15 E 1+0 | Dr. Taberei | MW | 51.82 | 1.2 | 47 | 65 | 15/89 |  |  | 4U-1 |  |  |  | RBS | [9 empty] | 1 | BU042 | CHITILA |  | 0.6 |  | 70 | 15/84 | [6 empty] | 4 | RADCOM | 2000-09-19 | 219 | 2000-09-19 | 2000-09-21 | 2000-09-25 | PAUN | OK | 2001-01-08 |  |  |  | Se mutape 30N01 de pe 30N02 Chitila-Dr.Taberei | Optimizare cand se va rupe lantul | OK | Mihai CONSTANTIN | CATALINA CIOCAN | [32 empty] | 97 | CIOROGARLA | Giurgiu | [7 empty] | 2 |  |  | 1
Phase_2 | CS | CR006 | PALANCA | Road Buc-Pitesti(8) | BU042 Chitila | Muntenia | 44 28 00.7 | 25 43 25.36 | 44 28 08 | 25 43 14 | sat Palanca, com. Floresti-Stoenesti / CONEL BOLINTINI 046270301 | Tronaru Adrian/Tronaru Adriantel tel. 093 359 945 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-06-20 | N/A | N/A |  |  |  | N/A | TN | 50 | 50m new tower | N/A | PROTELCO | OK | FIBEC | 2000-05-29 | 2000-07-21 | YesV | 2000-08-01 | Mugur | 2000-11-10 | 2000-08-03 |  |  |  | 2000-05-23 | O.K. |  | 2000-05-24 | 2000-06-07 |  |  |  | 2000-09-19 | YRO | Electotrade | 2000-08-23 | 23-08-00 | 2000-09-19 | 2000-09-21 | 2000-10-20 |  | Yes | Bogdan Bogodai | 2001-02-20 | 2001-02-20 | 2001-02-20 | 2001-04-17 | 2001-04-23 | K 739 494 | 90 | 0 | 48 | K 739 494 | 290 | 0 | 48 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 66 | 66 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 132 | ML 15 E 1+0 | Dr. Taberei | MW | 101.45 | 1.2 | 47 | 65 | 15/84 |  | 4x2/8 | 4U-1+2U-3 |  |  |  | RBS | [9 empty] | 1 | CR005 | CIOROGARLA | 281.56 | 1.2 | 47 | 65 | 15/89 | [6 empty] | 4 | RADCOM | 2000-09-19 | 218 | 2000-09-19 | 2000-09-21 | 2000-10-20 | DINCA | OK | 2001-02-20 |  | 2001-02-27 | 2001-03-02 | Se mutape 30N01 de pe 30N02 Chitila-Dr.Taberei | Optimizare cand se va rupe lantul | OK | SORIN UNTARU | Cosmorom | [32 empty] | 113 | PALANCA | Giurgiu | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CR007 | POIANA LUI STANGA | Road Buc-Pitesti(8) | BU042 Chitila | Muntenia | 44 30 22.19 | 25 34 30.31 | 44 30 19.9 | 25 34 55.4 | Poiana lui Stanca, com. Vanatorii Micii | proprietar Zamfir Alexandru/Zamfir Alexandru | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-06-20 | N/A | N/A |  |  |  | N/A | TN | 50 | New 50m tower | N/A | PROTELCO | OK | FIBEC | 2000-05-29 | 2000-06-30 | YesV | 2000-07-19 | Mugur | 2000-11-10 | 2000-07-21 |  |  |  | OK | O.K. |  | 2000-05-17 | 2000-05-24 |  |  |  | 2000-09-19 | YRO | Electotrade | 2000-08-15 | 2000-08-15 | 2000-09-19 | 2000-09-21 | 2000-09-25 |  | Yes | Bogdan Bogodai | 2001-02-20 | 2001-02-20 | 2001-02-20 |  |  | K 739 494 | 120 | 0 | 48 | K 739 494 | 310 | 0 | 48 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 65 | 65 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 130 | ML 15 E 1+0 | Dr. Taberei | MW | 111 | 1.2 | 47 | 54 | 15/89 |  |  | 4U-1 |  |  |  | RBS | [7 empty] | 3/2 pairs - outdoor |  | 1 | CR006 | PALANCA | 291 | 1.2 | 47 | 65 | 15/84 | [6 empty] | 4 | RADCOM | 2000-09-19 | 217 | 2000-09-19 | 2000-09-21 | 2000-09-25 | PAUN | OK | 2001-02-20 |  | 2001-02-27 | 2001-03-02 | Se mutape 30N01 de pe 30N02 Chitila-Dr.Taberei | Optimizare cand se va rupe lantul | OK | SORIN UNTARU | Cosmorom | [32 empty] | 126 | POIANA LUI STANGA | Giurgiu | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CR008 | SATU NOU | Road Buc-Pitesti(8) | CR197 Topoloveni_RTC | Muntenia | 44 35 28.23 | 25 28 49.61 | 44 35 39.5 | 25 28 41.7 | COMUNA Corbii Mari, sat Satu Nou | Consiliul local Corbii Mari/Sandulescu Nicolae-primarie tel. 093.369.628 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-06-20 | N/A | N/A |  |  |  |  | TN | 50 | New 50m tower | N/A | PROTELCO | OK | DUAL | 2000-06-01 | 2000-07-07 | YesV | 2000-07-19 | Mugur | 2000-09-12 | 2000-07-21 |  |  |  | 2000-05-02 | O.K. |  | 2000-05-17 | 2000-06-05 | Se schimba punctul de insertie |  |  | 2000-09-15 | YRO | Electotrade | 2000-08-22 | 22-08-00 | 2000-09-18 | 2000-09-19 | 2000-09-20 |  | Yes | Bogdan Bogodai | 2001-02-28 | 2001-02-28 | 2001-02-28 | 2001-03-12 | 2001-03-15 | K 739 494 | 160 | 0 | 48.7 | K 739 494 | 310 | 0 | 48.7 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 66 | 66 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 132 |  | Baneasa | MW | 141 | 1.2 | 48 | 64 | 23/56 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [9 empty] | 1 | CR007 | POIANA LUI STANGA | 320 | 1.2 |  | 65 | 23/58 | CR009 | [5 empty] | 4 | RADCOM | 2000-09-19 | 216 | 2000-09-19 | 2000-09-19 | 2000-09-20 | PAUN | OK | 2001-02-28 | Se schimba IP (CR197); Maria 20iun01 | 2001-05-03 | 2001-05-11 |  |  | OK | SORIN UNTARU | Cosmorom | [32 empty] | 150 | SATU NOU | Dambovita | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CR009 | GRECI | Road Buc-Pitesti(8) | CR197 Topoloveni_RTC | Muntenia | 44 39 32.85 | 25 20 35.17 | 44 39 58.5 | 25 20 31.6 | Comuna Petresti, sat Greci,str. Principala, jud.Dambovita | Osiac I Dumitru/Ion Ion - 094/ 357 638 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-08-09 | N/A | N/A |  |  |  | N/A | TN | 50 | New 50m tower | N/A | PROTELCO | OK | DUAL | 2000-06-14 | 2000-07-31 | YesV | 2000-08-01 | Mugur | 2000-10-03 | 2000-08-03 |  |  |  | 2000-05-02 | 2000-05-03 |  | 2000-05-17 | 2000-06-12 | Se schimba punctul de insertie |  |  | 2000-09-19 | YRO | Electotrade | 2000-08-22 | 22-08-00 | 2000-09-19 | 2000-09-21 | 2000-09-25 |  | Yes | Bogdan Bogodai | 2001-02-28 | 2001-02-28 | 2001-02-28 |  |  | K 739 494 | 120 | 0 | 48.7 | K 739 494 | 290 | 0 | 48.7 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 66 | 66 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 132 | ML 15 E 1+0 | Baneasa | MW | 125 | 1.2 | 48 | 65 | 15/84 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [9 empty] | 1 | CR008 | SATU NOU | 305 | 1.2 |  | 65 | 15/89 | CR010 | [5 empty] | 4 | RADCOM | 2000-09-19 | 215 | 2000-09-19 | 2000-09-21 | 2000-09-25 | PAUN | OK | 2001-02-28 | Se schimba IP (CR197); Maria 20iun01 | 2001-03-21 | 2001-04-06 |  |  | OK | SORIN UNTARU | Cosmorom | [32 empty] | 178 | GRECI | Dambovita | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CR010 | NEAJLOVELU | Road Buc-Pitesti(8) | CR197 Topoloveni_RTC | Muntenia | 44 41 55.24 | 25 11 52.34 | 44 41 55.24 | 25 11 52 34 | Comuna Neajlovelu |  | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-06-21 | N/A | N/A |  |  |  |  | TN | 50 | New 50m tower | N/A | ISAF | OK | TEHNOROB | 2000-06-05 | 2000-07-17 | YesV | 2000-07-19 | Mugur | 2000-08-04 | 2000-07-21 |  |  |  | 2000-04-14 | O.K. |  | 2000-05-22 | 2000-06-05 | Se schimba punctul de insertie |  |  | 2000-08-07 | YRO | TRY | 2000-07-24 | 2000-07-24 | 2000-08-08 | 2000-08-08 | 2000-08-11 |  | Yes | Bogdan Bogodai | 2001-03-05 | 2001-03-01 | 2001-03-01 | 2001-05-23 | 2001-05-28 | K 739 494 | 100 | 0 | 47 | K 739 494 | 280 | 0 | 47 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Baneasa | MW | 309 | 1.2 | 49 | 70 | 15/89 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [9 empty] | 1 | CR009 | GRECI | 129 | 1.2 | 49 | 70 | 15/84 | CR011 | [5 empty] | 4 | RADCOM | 2000-09-19 | 214 | 2000-09-19 | 2000-09-21 | 2000-09-25 | RADU | OK | 2001-03-05 | Se schimba IP (CR197); Maria 20iun01 |  | 2001-05-11 |  |  | OK | Mihai CONSTANTIN | Cosmorom | [32 empty] | 200 | NEAJLOVELU | Arges | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CR011 | CATEASCA | Road Buc-Pitesti(8) | CR197 Topoloveni_RTC | Muntenia | 44 46 07.21 | 25 04 34.86 | 44 46 07.5 | 25 04 42.6 | Com. Cateasca nr.28 - parohia Cateasca | Parohia com. Cateasca/Preotul Sarbu - Cateasca nr.28, tel: 28A | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-06-21 | N/A | N/A |  |  |  |  | TN | 50 | New 50m tower | N/A | ISAF | OK | TEHNOROB | 2000-06-05 | 2000-07-17 | YesV | 2000-07-19 | Mugur | 2000-08-04 | 2000-07-21 |  |  | 2001-06-22 | 2000-05-16 | O.K. |  | 2000-05-17 | 2000-06-05 | Se schimba punctul de insertie |  |  | 2000-08-07 | YRO | TRY | 2000-07-24 | 2000-07-24 | 2000-08-08 | 2000-08-08 | 2000-08-11 |  | Yes | Bogdan Bogodai | 2001-03-06 | 2001-03-06 | 2001-03-06 | 2001-04-27 | 2001-06-19 | K 739 494 | 140 | 0 | 47 | K 739 494 | 280 | 0 | 47 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Baneasa | MW | 129 | 1.2 | 49 | 70 | 15/84 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [7 empty] | N/A/N/A |  | 1 | CR010 | NEAJLOVELU | 309 | 1.2 | 49 | 70 | 15/89 | CR197 | [5 empty] | 1 | TRYLON | 2000-08-08 | 107 | 2000-08-08 | 2000-08-08 | 2000-08-11 | RADU | OK | 2001-03-01 | Se schimba IP (CR197); Maria 20iun01 | 2001-04-11 | 2001-04-17 |  |  | OK | Mihai CONSTANTIN | CATALINA CIOCAN | [32 empty] | 242 | CATEASCA | Arges | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CR013 | CENTRU_RTC | Pitesti(9) | CR013 Centru_RTC | Oltenia | 44 51 18 | 24 52 27 | 44 51 18 | 24 52 27.0 | Bdul Republicii, nr. 90 | Romtelecom Pitesti/Neacsu T. tel. 048/ 204222 | 2102 | M/E | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-06-14 | 2000-06-15 | N/A |  |  |  | 26.8 | B | 26.8 |  | N/A | PROTELCO | OK | FIBEC | 2000-05-14 | 2000-06-05 | YesV | 2000-06-06 | Doru | 2000-06-07 | 2000-06-08 |  |  |  | N/A | 2000-05-03 |  | 2000-05-03 | 2000-05-11 |  |  |  | 2000-06-19 | YRO | MIC | 2000-06-12 | 2000-06-13 | 2000-06-20 | 2000-06-20 | 2000-06-23 |  | Yes | Theo Radoi | 2000-09-04 | 2000-09-04 | 2000-09-04 | 2000-09-18 | 2000-09-21 | K 739 494 | 0 | 0 | 42.5 | K 739 494 | 120 | 0 | 42.5 | K 739 494 | 240 | 0 | 42.5 |  |  |  |  | N/A | 25 | 25 | 7/8" | 25 | 25 | 7/8" | 25 | 25 | 7/8" |  |  |  | 150 | N/A | Baneasa | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | 4U-1 |  |  |  | RBS | 40013 | 2001-06-27 |  | 41013 | [5 empty] | 1 | BSC21 | BSC BANEASA |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | ARANYOSI | OK | N/A |  | N/A | N/A | 30N01 Pitesti-Baneasa |  | OK | Mihai CONSTANTIN | CATALINA CIOCAN | [32 empty] | 290 | Pitesti | Arges | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | CR014 | TRIVALE | Pitesti(9) | CR013 Centru_RTC | Oltenia | 44 51 05.53 | 24 51 43 | 44 51 06 | 24 51 20 | Str. Libertatii Bl.12A | Asociatie de proprietari/Corbescu Constantin - Str. Libertatii Bl.12A, tel: 048/176 211 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-06-20 | 2000-06-15 | N/A |  |  |  | 31.4 | B | 35.22 | T4m+T4m | N/A | SVF | OK | ESROM | 2000-05-22 | 2000-06-06 | YesV | 2000-06-06 | Doru | 2000-09-04 | 2000-06-08 |  |  |  | 2000-05-12 | 2001-07-16 |  | 2000-05-15 | 2000-06-05 |  |  |  | 2000-08-22 | YRO | TRY | 2000-08-22 | 2000-08-22 | 2000-08-23 | 2000-08-24 | 2000-08-30 |  | Yes | Mihai Constantin | 2000-09-27 | 2000-09-27 | 2000-09-27 | 2000-10-18 | 2000-10-25 | K 739 494 | 0 | 0 | 38.5 | K 739 494 | 120 | 0 | 37.8 | K 739 494 | 240 | 0 | 38.5 |  |  |  |  | N/A | 18 | 18 | 7/8" | 20 | 20 | 7/8" | 18 | 18 | 7/8" |  |  |  | 112 | ML 38 E 1+1 | Baneasa | MW | 79.88 | 0.3 | 38.66 | 21 | 38/17 |  | 4x2/8 | 4U-1 |  |  |  | RBS | [9 empty] | 1 | CR013 | CENTRU_RTC | 260 | 0.3 | 44.3 | 25 | 38/13 | [6 empty] | 3 | TRYLON/YRO | 2000-08-22 | 145/25 | 22.08.00-4.07.00 | 2000-08-24 | 2000-08-30 | JOHN | OK | 2000-09-27 |  | 2000-10-18 | 2000-11-14 | 30N03 Pitesti-Baneasa |  | OK | Mihai CONSTANTIN | Cosmorom | [32 empty] | 320 | Pitesti | Arges | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CR015 | CRAIOVEI_CTA | Pitesti(9) | CR013 Centru_RTC | Oltenia | 44 50 48.8 | 24 52 33 | 44 50 49.0 | 24 52 33 | Romtelecom Arges | Romtelecom/Ionita Stefan tel. 048/64 2500 sau 048/250112 | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-06-19 | N/A | N/A |  |  |  | 12 | B |  |  |  | PROTELCO | OK | FIBEC | 2000-05-14 | 2000-06-06 | YesV | 2000-06-06 | Doru | 2000-06-07 | 2000-06-08 |  |  |  | N/A | 2000-05-03 |  | 2000-05-03 | 2000-05-11 |  |  |  | NA | YRO | NA | 2000-06-12 | 2000-06-13 | 2000-06-13 | 2000-06-13 | 2000-06-16 |  | Yes | Theo Radoi | 2000-09-04 | 2000-09-04 | 2000-09-04 | 2000-10-04 | 2000-11-14 | K 739 494 | 0 | 0 | 30 | K 739 494 | 120 | 0 | 30 | K 739 494 | 240 | 0 | 30 | N/A | N/A | N/A | N/A | N/A | 27 | 27 | 7/8" | 27 | 27 | 7/8" | 27 | 27 | 7/8" |  |  |  | 162 | ML 38 E 1+0 | Baneasa | MW | 352 | 0.3 |  | 30 | 38/17 |  |  | 2U-3 |  |  |  | N/A | XC41013 |  |  | XC41013 | [6 empty] | CR013 | CENTRU_RTC | 172 | 0.3 |  | 25 | 38/13 | [6 empty] | N/A | YRO | N/A | 23 | 2000-07-04 | 2000-06-16 | 2000-07-15 | DINCA | OK | 2000-09-01 |  | 2000-09-21 | 2000-09-01 | 30N05 Pitesti-Baneasa |  | OK | Mihai CONSTANTIN | Cosmorom | [32 empty] | 299 | Pitesti | Arges | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CR016 | REPUBLICII | Pitesti(9) | CR013 Centru_RTC | Oltenia | 44 51 07.31 | 24 53 19 | 44 50 48 | 24 53 31 | B-dul. Republicii Bl.S9D Sc.A | Asociatie de proprietari/Alexe Stelica - B-dul. Republicii Bl.S9D Sc.A, tel:048/220 851sau persoana de la ap. 37 (care a schimbat lacatul) | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-06-20 | Yes | N/A |  |  |  | 30 | B | 35 | T4.5m+T4.5m | N/A | SVF | OK | ESROM | 2000-05-22 | 2000-06-12 | YesV | 2000-06-12 | Doru | 2000-09-04 | 2000-06-16 |  |  |  | 2000-05-16 | 2000-05-03 |  | 2000-05-17 | 2000-06-07 |  |  |  | 2000-08-22 | YRO | TRY | 2000-08-22 | 2000-08-22 | 2000-08-23 | 2000-08-24 | 2000-08-30 |  | Yes | Mihai Constantin | 2000-09-27 | 2000-09-28 | 2000-09-28 | 2000-12-08 | 2001-01-08 | K 739 494 | 0 | 0 | 35.2 | K 739 494 | 120 | 0 | 35.2 | K 739 494 | 240 | 0 | 35.2 | N/A | N/A | N/A | N/A | N/A | 28 | 28 | 7/8" | 20 | 20 | 7/8" | 28 | 28 | 7/8" |  |  |  | 152 | ML 23 E 1+1 | Baneasa | MW | 331.3 | 0.6 | 35.2 | 28 | 23/56 | YES | 4x2/8 | 4U-1+2U-3 |  |  |  | RBS | [9 empty] | 1 | CR017 | VIILOR | 151.3 | 0.6 | 33.7 | 23 | 23/58 | [6 empty] | N/A / 78* | INTRACOM/YRO | N/A-26.06.01 | 85/997 | 31.07.00-27.06.01 | 2000-08-24 | 2000-08-30 | JOHN | OK | 2000-09-28 | Dublare suplimentara |  |  | 30N02 Pitesti-Baneasa |  | OK | Mihai CONSTANTIN | Cosmorom | [32 empty] | 260 | Pitesti | Arges | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CR017 | VIILOR | Pitesti(9) | CR013 Centru_RTC | Oltenia | 44 51 46.4 | 24 53 17 | 44 51 51 | 24 52 54 | Str. Viilor, Bl. U6 | Asociatie de proprietari/Ilie Lucian - Str. Viilor Bl.U6 Ap.29, tel: 092/583 638 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-06-20 | 2000-07-31 | N/A |  |  |  | 26 | B | 30.55 | T4m+T4m | N/A | SVF | OK | VECTOR | 2000-06-01 | 2000-06-16 | YesV | 2000-06-16 | Doru | 2000-07-27 | 2000-06-19 |  |  |  | 2000-05-12 | 2000-05-03 |  | 2000-05-15 | 2000-05-29 |  |  |  | 2000-07-31 | YRO | DIEKAT | 2000-07-21 | 2000-07-22 | 2000-08-01 | 2000-08-02 | 2000-08-14 |  | Yes | Mihai Constantin | 2000-09-27 | 2000-09-29 | 2000-09-29 | 2000-11-09 | 2000-11-22 | K 739 494 | 0 | 0 | 33.7 | K 739 494 | 120 | 0 | 34.5 | K 739 494 | 240 | 0 | 33.35 | N/A | N/A | N/A | N/A | N/A | 20 | 20 | 7/8" | 20 | 20 | 7/8" | 23 | 23 | 7/8" | N/A | N/A | N/A | 126 | ML 38 E 1+1 | Baneasa | MW | 211.21 | 0.3 | 33 | 24 | 38/17 |  |  | 2U-3 |  |  |  | RBS | [7 empty] | N/A/N/A |  | 1 | CR013 | CENTRU_RTC | 31 | 0.3 | 44.3 | 25 | 38/13 | [6 empty] | N/A / 78* | YRO/INTRACOM | N/A-26.06.01 | 85/998 | 31.07.00-27.06.01 | 2000-08-02 | 2000-08-14 | RADU | OK | 2000-09-28 | Dublare suplimentara |  |  | 30N02 Pitesti-Baneasa |  | OK | Mihai CONSTANTIN | Cosmorom | [32 empty] | 260 | Pitesti | Arges | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CR018 | NEGRU VODA | Pitesti(9) | CR013 Centru_RTC | Oltenia | 44 52 3.18 | 24 51 44 | 44 51 55 | 24 51 44 | Str. Negru Voda, bl. A1 (nr. 36) |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-06-20 | Yes | N/A |  |  |  | 30 | B | 33.5 | T3m+T3m | N/A | SVF | OK | PROFIL | 2000-06-01 | 2000-06-05 | YesV | 2000-06-06 | Doru | 2000-09-11 | 2000-06-08 |  |  |  | OK | 2001-07-16 |  | 2000-05-15 | 2000-06-05 |  |  |  | 2000-08-22 | YRO | TRY | 2000-08-22 | 2000-08-22 | 2000-08-23 | 2000-08-24 | 2000-08-30 |  | Yes | Mihai Constantin | 2000-09-29 | 2000-09-29 | 2000-09-29 | 2000-10-18 | 2000-10-25 | K 739 494 | 0 | 0 | 35.8 | K 739 494 | 120 | 0 | 35.8 | K 739 494 | 240 | 0 | 36 | N/A | N/A | N/A | N/A | N/A | 11 | 11 | 7/8" | 11 | 11 | 7/8" | 15 | 15 | 7/8" | N/A | N/A | N/A | 74 | ML 23 E 1+1 | Baneasa | MW | 203 | 0.6 | 36 | 15 | 23/56 |  | 4x2/8 | 4U-1 |  |  |  | RBS | [9 empty] | 1 | CR014 | TRIVALE | 23.4 | 0.6 | 38.66 | 21 | 23/58 | [6 empty] | 3 | TRYLON | 2000-08-22 | 145 | 2000-08-22 | 2000-08-24 | 2000-08-30 | JOHN | OK | 2000-09-28 |  | 2000-10-18 | 2000-11-14 | 30N04 Pitesti-Baneasa |  | OK | Mihai CONSTANTIN | Cosmorom | [32 empty] | 278 | Pitesti | Arges | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CR019 | GAVANA_CTA | Pitesti(9) | CR013 Centru_RTC | Oltenia | 44 52 16.9 | 24 50 46 | 44 52 16.9 | 24 50 46 | Str. 1 Decembrie 1918, Bl. 5MA Sc. A | Asociatie de proprietari/Berceanu Cosmin - Str. 1 Decembrie 1918 nr.13 Bl.C$ Sc.A, tel: 048/285 170 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-06-21 | Yes | N/A |  |  |  | 14.5 | B | 15.9 | 12m existing pylon | N/A | SVF | OK | ISAF | 2000-07-25 | 2000-08-08 | YesV | 2000-08-09 | Doru | 2000-10-06 | 2000-08-15 |  |  |  | 2000-06-08 | 2000-05-03 |  | 2000-07-15 | 2000-07-25 |  |  |  | 2000-08-22 | YRO | TRY | 2000-08-22 | 2000-08-22 | 2000-08-23 | 2000-08-24 | 2000-08-30 |  | Yes | Mihai Constantin | 2000-09-27 | 2000-10-19 | 2000-10-19 | 2000-11-09 | 2000-11-22 | K 739 494 | 0 | 0 | 26 | K 739 494 | 120 | 0 | 26 | K 739 494 | 240 | 0 | 26 | N/A | N/A | N/A | N/A | N/A | 18 | 18 | 7/8" | 18 | 18 | 7/8" | 18 | 18 | 7/8" | N/A | N/A | N/A | 108 | ML 23 E 1+0 | Baneasa | MW | 115 | 0.6 | 24.5/0.6 | 14.5 | 23/58 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [9 empty] | 1 | CR018 | NEGRU VODA | 295.47 | 0.6 |  |  | 23/56 | [6 empty] | 3 | TRYLON | 2000-08-22 | 148/146 | 2000-08-22 | 2000-08-24 | 2000-08-30 | JOHN | OK | 2000-09-28 |  | 2000-10-18 | 2000-11-14 | 30N01 Pitesti-Baneasa |  | OK | Mihai CONSTANTIN | Cosmorom | [32 empty] | 301 | Pitesti | Arges | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CR020 | DRTV PITESTI | Pitesti(9) | CR013 Centru_RTC | Oltenia | 44 52 48 | 24 50 07 | 44 52 48 | 24 50 07 | Str. Nicolae Balcescu nr.205 | George Motoc - Dir. DRTV, 313 89 43/D-nul. Popescu - 048/ 281 050 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-06-21 | N/A | N/A |  |  |  | 0 | TE | 52 | 52m existing tower | N/A | ISAF | OK | ESROM | 2000-05-22 | 2000-06-16 | YesV | 2000-06-16 | Doru | 2000-08-01 | 2000-06-19 |  |  |  | 2000-04-17 | 2000-05-03 |  | 2000-05-17 | 2000-06-05 |  |  |  | 2000-07-31 | YRO | DIEKAT | 2000-07-21 | 2000-07-22 | 2000-08-01 | 2000-08-02 | 2000-08-14 |  | Yes | Mihai Constantin | 2000-09-29 | 2000-09-29 | 2000-09-29 | 2000-10-18 | 2000-10-25 | K 739 494 | 0 | 0 | 43.8 | K 739 494 | 120 | 0 | 43.8 | K 739 494 | 240 | 0 | 43.8 | N/A | N/A | N/A | N/A | N/A | 51 | 51 | 1 1/4" | 51 | 51 | 1 1/4" | 51 | 51 | 1 1/4" | N/A | N/A | N/A | 306 | ML 23 E 1+1 | Baneasa | MW | 132 | 0.6 | 43 | 50 | 23/58 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [7 empty] | N/A/N/A |  | 1 | CR018 | NEGRU VODA |  | 0.6 | 36 | 15 | 23/56 | [6 empty] | N/A | YRO | N/A | 86 | 2000-08-01 | 2000-08-02 | 2000-08-14 | RADU | OK | 2000-09-29 |  | 2000-10-18 | 2000-11-14 | 30N04 Pitesti-Baneasa |  | OK | Mihai CONSTANTIN | Cosmorom | [32 empty] | 286 | Pitesti | Arges | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CR021 | MARACINENI | Pitesti(9) | CR013 Centru_RTC | Oltenia | 44 55 36 | 24 52 45.02 | 44 55 29.8 | 24 52 47.2 | Sos. Pitesti-Campulung Km 7-450 |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-06-21 | N/A | N/A |  |  |  | N/A | TN | 50 | New 50m tower | N/A | ISAF | OK | DUAL | 2000-06-01 | 2000-07-12 | YesV | 2000-07-19 | Doru | 2000-08-21 | 2000-07-21 |  |  |  | OK | 2000-05-03 |  | 2000-05-03 | 2000-06-05 |  |  |  | 2000-08-22 | YRO | TRY | 2000-08-22 | 2000-08-22 | 2000-08-23 | 2000-08-24 | 2000-08-30 |  | Yes | Mihai Constantin | 2000-09-27 | 2000-09-28 | 2000-09-28 | 2000-10-18 | 2000-10-25 | K 739 494 | 0 | 0 | 47 | K 739 494 | 120 | 0 | 47 | K 739 494 | 240 | 0 | 47 | N/A | N/A | N/A | N/A | N/A | 60 | 60 | 1 1/4" | 60 | 60 | 1 1/4" | 60 | 60 | 1 1/4" | N/A | N/A | N/A | 360 | ML 15 E 1+0 | Baneasa | MW | 194 | 0.6 | 52.7 | 62 | 15/84 |  |  | 2U-3 |  |  |  | RBS | [9 empty] | 1 | CR014 | TRIVALE | 13.95 | 0.6 | 38.6 | 21 | 15/89 | [6 empty] | 3 | TRYLON | 2000-08-22 | 147/145 | 2000-08-22 | 2000-08-24 | 2000-08-30 | JOHN | OK | 2000-09-27 | Ant si RAU add trebuiesc dezinstalate | 2000-10-18 | 2000-11-14 | 30N03 Pitesti-Baneasa |  | OK | Mihai CONSTANTIN | Cosmorom | [32 empty] | 284 | MARACINENI | Arges | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_3 | CS | CR022 | MIOVENI | Road Pitesti-Campulung | CR013 Centru_RTC | Oltenia | 44 56 00 | 24 56 57 | [40 empty] | 2001-07-16 | [52 empty] | ML 23 E 1+0 | Baneasa | MW | [22 empty] | CR021 | MARACINENI
Phase_2 | CS | CR024 | UNIRII_RTC | Craiova(8) | CR024 Unirii_RTC | Oltenia | 44 18 49.7 | 23 47 51.72 | 44 18 49.7 | 23 47 51.72 | Str. Unirii nr.69 | Rtc Craiova/Moisescu - 094/ 614 818 | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-07-26 | N/A | N/A |  |  |  | 10 | B | 30 | Pilonet 9m | Room | ISAF | OK | ISAF | 2000-06-25 | 2000-07-07 | YesV | 2000-07-13 | Mugur | 2000-08-02 | 2000-07-17 |  |  |  | N/A | 2000-05-10 |  | 2000-06-06 | 2000-06-27 |  |  |  | 2000-08-23 | YRO | ISAF | 2000-07-24 | 2000-07-24 | 2000-08-24 | 2000-08-29 | 2000-08-31 |  | Yes | Mihai Constantin | 2000-11-20 | 2000-11-17 | 2000-11-17 |  |  | K 739 494 | 115 | 0 | 37 | K 739 494 | 235 | 0 | 36.5 | K 739 494 | 355 | 0 | 37 |  |  |  |  | N/A | 51 | 51 | 1 1/4" | 51 | 51 | 1 1/4" | 51 | 51 | 1 1/4" |  |  |  | 306 | N/A | Craiova | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | 4U-1(TMR9202) |  |  |  | TMR 9202 | 40024 | [8 empty] | 1 | BSC23 | BSC CRAIOVA |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | JOHN | OK | N/A |  | N/A | N/A | LOCAL |  | OK | Cristian CROITOR | Cosmorom | [32 empty] | 88 | Craiova | Dolj | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | CR025 | AMARANDIA_RTC | Craiova(8) | CR025 Amarandia_RTC | Oltenia | 44 189 40 | 23 47 35.49 | 44 19 40.48 | 23 47 35.49 | Rtc Amarandia | Romtelecom/Banica Cristian - 092/ 784 471 | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-07-26 | N/A | N/A |  |  |  | 20 | B | 20 | 12m new pyilon | Room | ISAF | OK | ISAF | 2000-06-25 | 2000-07-07 | YesV | 2000-07-13 | Mugur | 2000-08-02 | 2000-07-17 |  |  |  | N/A | 2000-05-10 |  | 2000-06-05 | 2000-06-28 |  |  |  | 2000-08-23 | YRO | ISAF | 2000-07-24 | 2000-07-24 | 2000-08-24 | 2000-08-29 | 2000-08-31 |  | Yes | Mihai Constantin | 2000-11-20 | 2000-11-19 | 2000-11-19 |  |  | K 739 494 | 115 | 0 | 30 | K 739 494 | 235 | #N/A | 30 | K 739 494 | 355 | 0 | 30 |  |  |  |  | N/A | 53 | 53 | 1 1/4" | 53 | 53 | 1 1/4" | 53 | 53 | 1 1/4" |  |  |  | 328 | N/A | Craiova | FO | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | TMR 9202 | 40025 | [8 empty] | 1 | BSC23 | BSC CRAIOVA |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | JOHN | OK | N/A |  | N/A | N/A | 30N01 Amarandia-Craiova |  | OK | Cristian CROITOR | #N/A | [32 empty] | 103 | Craiova | Dolj | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | CR026 | SEVERINULUI | Craiova(8) | CR025 Amarandia_RTC | Oltenia | 44 19 48.38 | 23 46 39.57 | 44 19 48.38 | 23 46 39.57 | Str. Severinului Bl.319 | Asociatie de locatari/Dl. Oprea - Ap. 20 Et.5, 051/ 186 288 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-08-09 | Yes | N/A |  |  |  | 27 | B | 31.6 | C5.4m+C5.4m | N/A | ISAF | OK | ISAF | 2000-07-12 | 2000-07-25 | YesV | 2000-08-01 | Mugur | 2000-10-04 | 2000-08-03 |  |  |  | 2000-06-05 | 2000-05-10 |  | 2000-06-06 | 2000-07-12 |  |  |  | 2000-08-23 | YRO | ISAF | 2000-08-23 | 2000-08-24 | 2000-08-24 | 2000-08-29 | 2000-08-31 |  | Yes | Mihai Constantin | 2000-11-20 | 2000-11-18 | 2000-11-18 | 2000-12-08 | 2000-12-18 | K 739 494 | 115 | 0 | 33.6 | K 739 494 | 235 | 0 | 32 | K 739 494 | 355 | 0 | 33.6 |  |  |  |  | N/A | 34 | 34 | 7/8" | 34 | 34 | 7/8" | 35 | 35 | 7/8" |  |  |  | 206 | ML 23 E 1+1 | Craiova | MW | 105 | 0.6 | 39 | 36 | 23/58 | YES | 4x2/8 | 4U-1 |  |  |  | RBS | [9 empty] | 1 | CR025 | AMARADIA_RTC | 285 | 0.6 | 23 | 52 | 23/56 | [6 empty] | 1 | ISAF | 2000-08-23 | 150 | 2000-08-23 | 2000-08-29 | 2000-08-31 | JOHN | OK | 2000-11-10 |  | 2000-12-06 | 2000-12-18 | 30N01 Amarandia-Craiova |  | OK | Cristian CROITOR | Cosmorom | [32 empty] | 99 | Craiova | Dolj | [5 empty] | 1 | 1 | 2 | 1 | 1 | 2
Phase_2 | CS | CR027 | PIATA GARII | Craiova(8) | CR024 Unirii_RTC | Oltenia | 44 19 39.37 | 23 49 28.53 | 44 19 39.37 | 23 49 28.53 | Str. Piata Garii Bl. U Sc.2 | Asociatie de locatari - Sandu Dumitru - pres., 051/ 194 070/Ciobanu Ion - 051/ 191 483 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-10-20 | Yes | N/A |  |  |  | 34 | B | 37 | C5.4m+C5.4m | N/A | ISAF | OK | ISAF | 2000-10-25 | 2000-11-13 | YesV | 2000-11-28 | Mugur | 2000-11-28 | 2000-12-07 |  |  |  | 2000-06-05 | 2001-05-10 |  | 2000-06-05 | 2000-10-10 |  |  |  | 2000-11-10 | ICOM | TRY | 2000-10-09 | 2000-10-09 | 2000-11-13 | 2000-11-14 | 2000-11-15 |  | Yes | Cristian Croitor | 2000-11-20 | 2000-12-06 | 2000-12-06 | 2000-12-21 | 2001-01-08 | K 739 494 | 115 | 0 | 38.5 | K 739 494 | 235 | 0 | 37.5 | K 739 494 | 355 | 0 | 38.5 |  |  |  |  | N/A | 13 | 13 | 7/8" | 13 | 13 | 7/8" | 15 | 15 | 7/8" |  |  |  | 82 | ML 23 E 1+0 | Craiova | MW | 137 | 0.6 | 40 | 15 | 23/58 |  | 4x2/8 | 4U-1 |  |  |  | RBS | [9 empty] | 1 | CR029 | CALEA BUCURESTI | 317 | 0.6 | 32 | 24 | 23/56 | [6 empty] | 12/1 | TRYLON/ISAF | 10.11.00-23.08.00 | 281/153 | 17.11.00-23.08.00 | 2000-11-17 | 2000-11-20 | RADU | OK | 2000-12-06 |  | 2000-10-18 | 2001-01-08 | LOCAL |  | OK | Cristian CROITOR | Cosmorom | [32 empty] | 119 | Craiova | Dolj | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CR028 | CALEA BUCURESTI_2 | Craiova(8) | CR024 Unirii_RTC | Oltenia | 44 18 57.7 | 23 49 20.9 | 44 19 00.1 | 23 48 58.3 | Calea Bucuresti nr.18 bl. P45 | Asociatia de proprietari nr.18/D-nul. Licurici - presedinte, Et. 1, Ap. 5, 051/ 146 259 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-11-17 | Yes | N/A |  |  |  | 34 | B | 38 | C2.5m+C2.5m | N/A | ISAF | OK | ISAF | 2000-10-20 | 2000-11-13 | YesV | 2000-11-28 | Mugur | 2001-01-09 | 2000-12-07 |  |  |  | N/A | 2000-09-07 |  | 2000-09-25 | 2000-11-02 |  |  |  | 2000-11-10 | ICOM | TRY | 2000-11-10 | 2000-11-10 | 2000-11-13 | 2000-11-14 | 2000-11-17 |  | Yes | Cristian Croitor | 2000-11-20 | 2000-12-06 | 2000-12-06 | 2000-12-18 | 2001-01-08 | K 739 494 | 115 | 0 | 40 | K 739 494 | 235 | 0 | 40 | K 739 494 | 355 | 0 | 40 |  |  |  |  | N/A | 20 | 20 | 7/8" | 20 | 20 | 7/8" | 20 | 20 | 7/8" |  |  |  | 120 | ML 38 E 1+0 | Craiova | MW | 259 | 0.3 | 42 | 20 | 38/17 |  |  | 4U-1 |  |  |  | RBS | [9 empty] | 1 | CR024 | UNIRII_RTC | 78 | 0.3 | 36.5 | 47 | 38/13 | [6 empty] | 12/1 | TRYLON/ISAF | 10.11.00-23.08.00 | 374/152 | 17.11.00-23.08.00 | 2000-11-17 | 2000-11-20 | RADU | OK | 2000-12-06 |  | 2000-10-18 | 2001-01-08 | LOCAL |  | OK | Cristian CROITOR | CATALINA CIOCAN | [32 empty] | 106 | Craiova | Dolj | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CR029 | CALEA BUCURESTI | Craiova(8) | CR024 Unirii_RTC | Oltenia | 44 18 46.17 | 23 50 38.19 | 44 18 46.17 | 23 50 38.19 | Calea Bucuresti Bl.U6b | Asociatie de locatari/Vasile Nicolae - Calea Bucuresti Bl. U6b Ap.33, 051/ 437 209 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-08-09 | Yes | N/A |  |  |  | 27 | B | 31 | C5.4m+C5.4m | N/A | ISAF | OK | ISAF | 2000-07-12 | 2000-07-31 | YesV | 2000-08-01 | Mugur | 2000-10-04 | 2000-08-03 |  |  |  | 2000-06-05 | 2000-05-10 |  | 2000-06-05 | 2000-07-12 |  |  |  | 2000-08-23 | YRO | ISAF | 2000-08-22 | 2000-08-24 | 2000-08-24 | 2000-08-29 | 2000-08-31 |  | Yes | Cristian Croitor | 2000-11-20 | 2000-12-06 | 2000-12-06 | 2000-12-18 | 2001-01-08 | K 739 494 | 0 | 0 | 32.3 | K 739 494 | 235 | 0 | 32.3 | K 739 494 | 335 | 0 | 32.3 |  |  |  |  | N/A | 11 | 11 | 7/8" | 23.5 | 23.5 | 7/8" | 11 | 11 | 7/8" |  |  |  | 114 | ML 38 E 1+0 | Craiova | MW | 280 | 0.3 | 32 | 24 | 38/13 |  |  | 4U-1 |  |  |  | RBS | [9 empty] | 1 | CR028 | CALEA BUCURESTI_2 | 103 | 0.3 | 42 | 20 | 38/17 | [6 empty] | 1/13 | ISAF/TRYLON | 23.08.00-16.11.00 | 153/374 | 23.08.00-17.11.00 | 2000-11-17 | 2000-11-20 | JOHN | OK | 2000-12-06 |  | 2000-10-18 | 2001-01-08 | LOCAL |  | OK | Cristian CROITOR | CATALINA CIOCAN | [32 empty] | 135 | Craiova | Dolj | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CR030 | SPITALUL MILITAR | Craiova(8) | CR024 Unirii_RTC | Oltenia | 44 18 08.9 | 23 49 13.28 | 44 18 08.9 | 23 49 13.28 | Str. Caracal Bl.43 Sc.1 | Asociatie de locatari/ | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-09-06 | Yes | N/A |  |  |  | 33 | B | 36.65 | C3.5m+C3.5m | N/A | ISAF | OK | ISAF | 2000-07-12 | 2000-08-04 | YesV | 2000-08-10 | Mugur | 2000-09-29 | 2000-08-15 |  |  |  | 2000-06-05 | 2001-05-10 |  | 2000-06-06 | 2000-07-12 |  |  |  | 2000-08-23 | YRO | ISAF | 2000-08-23 | 2000-08-24 | 2000-08-24 | 2000-08-29 | 2000-08-31 |  | Yes | Mihai Constantin | 2000-11-20 | 2000-11-19 | 2000-11-19 | 2000-12-08 | 2000-12-18 | K 739 494 | 115 | 0 | 37 | K 739 494 | 235 | 0 | 37 | K 739 494 | 355 | 0 | 37 |  |  |  |  | N/A | 33 | 33 | 7/8" | 30 | 30 | 7/8" | 22 | 22 | 7/8" |  |  |  | 170 | ML 23 E 1+1 | Craiova | MW | 302 | 0.6 | 37 | 16 | 23/58 |  |  | 2U-3 |  |  |  | RBS | [9 empty] | 1 | CR024 | UNIRII_RTC | 125 | 0.6 | 36.5 | 47 | 23/56 | [6 empty] | 1 | ISAF | 2000-08-23 | 151 | 2000-08-23 | 2000-08-29 | 2000-08-31 | JOHN | OK | 2000-11-18 | PENDING |  |  | LOCAL |  | OK | Cristian CROITOR | Cosmorom | [32 empty] | 103 | Craiova | Dolj | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CR031 | ANTONESCU | Craiova(8) | CR024 Unirii_RTC | Oltenia | 44 18 8.92 | 23 47 55.11 | 44 18 11 | 23 47 46.3 | B-dul. Maresal I. Antonescu Bl. A7b Sc. A | Asociatia de proprietari nr.3/Adm. Barbulescu Florin - parter, 051/ 133 870, 051/ 423 827 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-11-17 | Yes | N/A |  |  |  | 30 | B | 33.5 | 9m new pylonet | N/A | ISAF | OK | ISAF | 2000-10-20 | 2000-11-30 | YesV | 2000-12-07 | Mugur | 2001-01-09 | 2000-12-14 |  |  |  |  | 2000-07-20 |  | 2000-09-21 | 2001-01-23 |  |  |  | 2000-12-14 | ICOM | SVF | 2000-11-23 | 2000-11-23 | 2000-12-19 | 2001-01-08 | 2001-01-11 |  | Yes | Bogdan Bogodai | 2001-02-14 | 2001-02-15 | 2001-02-15 |  |  | K 739 494 | 115 | 0 | 42 | K 739 494 | 235 | #N/A | 42 | K 739 494 | 355 | 0 | 42 |  |  |  |  | N/A | 20 | 20 | 7/8" | 20 | 20 | 7/8" | 20 | 20 | 7/8" |  |  |  | 120 | ML 23 E 1+0 | Craiova | MW | 6 | 0.6 | 42/0.3 | 20 | 23/58 |  |  | 2U-3 |  |  |  | RBS | [10 empty] | CR024 | UNIRII_RTC | 186 | 0.6 | 36.5 | 47 | 23/56 | [6 empty] | 21*/ | ORION/ISAF | 29.01.00- | 563/152 | 30.01.01-23.08.00 | 2001-02-01 | 2001-02-10 | DINCA | OK | 2001-02-14 | PENDING |  |  | LOCAL |  | OK | Cristian CROITOR | #N/A | [32 empty] | 79 | Craiova | Dolj | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CR035 | CERBU(OPTIMIZARE) | Road Pitesti-Craiova(8+2) | CR013 Centru_RTC | Oltenia | 44 45 16 | 24 49 46 | 44 45 14.8 | 24 49 50.718 | Teren privat com. Albota, sat Cerbu | Rodica a lui Ionel/Rodica a lui Ionel | 2102 | M | C+C+C+ | 2/2/2 | N/A | Warehouse | 2101 | M | C+ | 2 | 2101 |  |  |  |  | N/A | N/A | 0 | TN | 50 | Existing tower | N/A | ISAF | OK | DIEKAT | 2000-10-05 | 2000-11-10 | YesV | 2000-11-13 | Doru | 2001-01-29 | 2000-11-22 |  |  | 2001-06-08 | OK | 2000-07-19 |  | 2000-09-14 | OK |  |  |  | 2001-06-26 | ICOM |  |  |  | OK |  |  |  | Yes |  | OPTIMIZARE |  |  | 2001-07-10 | 2001-07-11 | K 739 494 | 35 | 0 | 50 | K 739 494 | 130 | 2 | 50 | K 739 494 | 220 | 0 | 50 | N/A | N/A | N/A | N/A | N/A | 55 | 55 | 1 1/4" | 55 | 55 | 1 1/4" | 55 | 55 | 1 1/4" | N/A | N/A | N/A | 330 | ML 15 E 1+1 | Baneasa | MW | 28 | 0.6 | 47/1.2 | 70 | 15/84 |  |  | 4U-1+2U-3 |  |  |  | RBS | 40035 | 2001-03-27 | [7 empty] | 1 | CR076 | SILOZ ALBOTA | 208 | 0.6 | 42/0.6 | 21 | 15/89 | [6 empty] | 15 | TRYLON | 2000-11-21 | 392 | 2000-11-21 | 2001-02-22 | 2001-02-23 |  |  |  |  | 2001-05-23 | 2001-05-25 | Mutat de pe 30N02 pe 30N07 Pitesti-Baneasa 30N06 Pitesti-Baneasa |  | OK | Cristian CROITOR | CATALINA CIOCAN | [21 empty] | 2000-11-10 | N/A | 2000-11-10 | ICOM | DIEKAT | 2000-11-16 |  | 2001-02-23 | 2001-02-23 | 2001-06-13 | 2001-07-11 | 278 | Cerbu | Arges | [5 empty] | 1 | 1 | 2 | 1 | 1 | 2
Phase_2 | CS | CR036 | MARGHIA | Road Pitesti-Craiova(8+2) | CR013 Centru_RTC | Oltenia | 44 40 18.2 | 24 44 12.7 | 44 40 17.51 | 24 44 10.01 | Com. Lunca Corbului sat Marghia |  | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-10-20 | N/A | N/A |  |  |  | 0 | TN | 50 |  | N/A | ISAF | OK | IMSAT | 2000-10-05 | 2000-11-28 | YesV | 2001-02-06 | Doru | 2001-03-06 | 2001-02-07 |  |  |  | OK | 2000-07-19 |  | 2000-09-14 | 2000-10-03 |  |  |  | 2000-12-15 | ICOM | IMSAT | 2000-11-30 | 2000-12-15 | 2000-12-19 | 2001-01-22 | 2001-01-25 |  | Yes | Bogdan Bogodai | 2001-03-14 | 2001-03-14 | 2001-03-14 |  |  | K 739 494 | 55 | 0 | 50 | K 739 494 | 225 | 0 | 50 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | 70 | 70 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 140 | ML 15 E 1+0 | Baneasa | MW | 40 | 1.2 | 47/1.2 | 70 | 15/89 |  | 4x2/8 | 4U-1 |  |  |  | RBS | [9 empty] | 1 | CR035 | CERBU | 220 | 1.2 | 47/1.2 | 70 | 15/84 | [6 empty] | 19* | ORION | 2001-01-24 | 524 | 2001-01-29 | 2001-02-01 | 2001-02-22 | DINCA | OK | 2001-03-14 |  | 2001-03-21 | 2001-04-06 | Mutat de pe 30N06 pe 30N07 Pitesti-Baneasa |  | 2001-07-11 | Cristian CROITOR | Cosmorom | [32 empty] | 261 | Lunca Corbului | Arges | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CR037 | OPTASI | Road Pitesti-Craiova(8+2) | CR013 Centru_RTC | Oltenia | 44 36 08.1 | 24 37 24.4 | 44 36 08.1 | 24 37 24.4 | Popas turistic Optas | Popas Optas - pres. Gont Nicusor/Petru Idoras | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-11-17 | N/A | N/A |  |  |  | 0 | TN | 50 |  | N/A | ISAF | OK | ORION | 2000-10-16 | 2001-01-31 | YesV | 2001-02-15 | Doru | 2001-02-12 | 2001-02-26 |  |  |  | OK | 2000-07-19 |  | 2000-10-03 | 2000-10-20 |  |  |  | 2001-01-08 | ICOM | ORION | 2001-01-08 | 2001-01-08 | 2001-01-09 | 2001-01-23 | 2001-01-25 |  | Yes | Bogdan Bogodai | 2001-03-14 | 2001-03-14 | 2001-03-14 |  |  | K 739 494 | 60 | 0 | 50 | K 739 494 | 210 | 0 | 50 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | 70 | 70 | 1 1/4" | N/A | N/A | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | 140 | ML 15 E 1+0 | Baneasa | MW | 46 | 1.2 | 47/1.2 | 60 | 15/84 |  |  | 4U-1 |  |  |  | RBS | [9 empty] | 1 | CR036 | MARGHIA | 226 | 1.2 | 47/1.2 | 70 | 15/89 | [6 empty] | 19* | ORION | 2001-01-24 | 525 | 2001-01-29 | 2001-02-01 | 2001-02-22 | DINCA | OK | 2001-03-14 | PENDING |  |  | Mutat de pe 30N06 pe 30N07 Pitesti-Baneasa |  | 2001-07-11 | Cristian CROITOR | Cosmorom | [32 empty] | 240 | Optas | Olt | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CR038 | JITARU | Road Pitesti-Craiova(8+2) | CR013 Centru_RTC | Oltenia | 44 34 20 | 24 33 24.6 | 44 34 37.69 | 24 34 14.48 | Turn de apa, com. Scornicesti, sat Jitaru | Cooperativa de consum Scornicesti/D-nul. Mutu Ion - 093/ 50 23 68 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-11-17 | N/A | N/A |  |  |  | 0 | TE | 30 | Turn apa+C3m+C3m+C3m | N/A | ISAF | OK | ORION | 2000-10-31 | 2000-11-24 | YesV | 2000-12-15 | Doru | 2000-11-27 | 2001-01-11 |  |  |  | OK | 2000-07-19 |  | 2000-10-04 | 2000-11-02 |  |  |  | 2000-11-27 | ICOM | IMSAT | 2000-11-27 | 2000-11-27 | 2000-11-28 | 2000-11-30 | 2000-12-02 |  | Yes | Bogdan Bogodai | 2001-03-14 | 2001-03-14 | 2001-03-14 |  |  | K 739 494 | 65 | 0 | 32 | K 739 494 | 220 | 0 | 32 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | 54 | 54 | 1 1/4" | 45 | 45 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A | 180 | ML 23 E 1+0 | Baneasa | MW | 44 | 0.6 | 33/1.2 | 45 | 23/58 |  |  | 4U-1 |  |  |  | RBS | [9 empty] | 1 | CR037 | OPTASI | 224 | 0.6 | 47/0.6 | 60 | 23/56 | [6 empty] | 19* | ORION | 2001-01-24 | 526 | 2001-01-29 | 2001-02-01 | 2001-02-22 | DINCA | OK | 2001-03-14 |  | 2001-04-11 | 2001-04-20 | Mutat de pe 30N06 pe 30N07 Pitesti-Baneasa |  | 2001-07-11 | Cristian CROITOR | Cosmorom | [32 empty] | 237 | Jitaru | Olt | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CR039 | PRISEACA - DRTv | Road Pitesti-Craiova(8+2) | CR040 Slatina_RTC | Oltenia | 44 28 38.1 | 24 25 51.2 | 44 28 38.1 | 24 25 51.2 | Sediul DRTv - Priseaca | DRTV/ | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-10-13 | N/A | N/A |  |  |  | 0 | TE | 87 | Tower | N/A | ISAF | OK | ORION | 2000-09-20 | 2000-10-04 | YesV | 2000-10-13 | Doru | 2000-11-10 | 2000-10-18 |  |  |  |  | 2000-07-19 |  | 2000-08-17 | 2000-09-08 |  |  |  | 2000-10-20 | ICOM | Electotrade | 2000-10-12 | 2000-10-12 | 2000-10-24 | 2000-10-25 | 2000-10-26 |  | Yes | Bogdan Bogodai | 2001-02-13 | 2001-02-13 | 2001-02-13 | 2001-03-15 | 2001-04-10 | K 739 494 | 50 | 0 | 40 | K 739 494 | 220 | 0 | 40 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Craiova | MW | 226 | 0.6 | 50/0.6 | 70 | 15/84 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [9 empty] | 1 | CR043 | CORNISEI | 46 | 0.6 | 40/0.6 |  | 15/89 | [6 empty] | 15 | TRYLON | 2000-11-21 | 391 | 2000-11-21 | 2000-11-22 | 2000-11-24 | PITURCESCU | OK | 2001-02-13 |  | 2001-02-27 | 2001-03-02 | 30N01 Slatina-Craiova |  | OK | Cristian CROITOR | Cosmorom | [32 empty] | 200 | Priseaca | Dolj | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | TM | CR040 | SLATINA_RTC | Slatina(3+1) | CR040 Slatina_RTC | Oltenia | 44 25 41.8 | 24 22 07.6 | 44 25 41.8 | 24 22 07.6 | Rtc - Str. Libertatii | Rtc Slatina - Dir. Tehnic Guinea, 049/ 403 869/Dl. Turcu - 049/ 404 127 | N/A | N/A | N/A | N/A | N/A | [7 empty] | N/A | N/A |  |  |  | N/A | B | 15 | T4.5m | N/A | ISAF | OK | FIBEC | 2000-07-12 | 2000-08-20 | YesV | 2000-08-24 | Mugur | 2000-09-06 | 2000-08-30 |  |  |  | N/A | 2000-05-29 |  | 2000-06-05 | 2000-07-05 |  |  |  | 2000-09-04 | YRO | MOB | N/A | N/A | 2000-09-05 | N/A | N/A |  | Yes | N/A | 2000-11-20 | 2000-11-24 | 2000-11-24 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A | Craiova | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | 4U-1 |  |  |  | TMR 9000 | 40040 | [6 empty] | 60/Indoor |  | 1 | BSC23 | BSC CRAIOVA |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PAUN | OK | N/A |  | N/A | N/A | N/A |  | OK | Cristian CROITOR | N/A | [32 empty] | 160 | Slatina | Olt | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | CR041 | INDEPENDENTEI | Slatina(3+1) | CR040 Slatina_RTC | Oltenia | 44 25 48.2 | 24 21 50 | 44 25 45.1 | 24 21 49.7 | Str. Independentei nr.19 Bl.T4 | Asociatie de locatari/ | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-09-06 | Yes | N/A |  |  |  | 35.2 | B | 35.2 | C3.5m+C3.5m+C3m | N/A | ISAF | OK | FIBEC | 2000-07-12 | 2000-09-18 | YesV | 2001-04-30 | Mugur | 2000-08-30 | 2001-05-03 |  |  |  | 2000-06-05 | 2000-05-29 |  | OK | 2000-07-12 |  |  |  | 2000-09-04 | YRO | MOB | 2000-09-04 | 2000-09-04 | 2000-09-05 | 2000-09-06 | 2000-09-08 |  | Yes | Ionut Grigorescu | 2000-11-20 | 2000-11-24 | 2000-11-24 | 2000-12-18 | 2001-01-08 | K 739 494 | 0 | 0 | 38 | K 739 494 | 120 | 0 | 38 | K 739 494 | 240 | 0 | 38 |  |  |  |  | N/A | 25 | 25 | 7/8" | 25 | 25 | 7/8" | 25 | 25 | 7/8" |  |  |  | 150 | ML 23 E 1+1 | Craiova | MW | 116 | 0.6 | 37 | 18 | 23/58 |  | 4x2/8 | 4U-1 |  |  |  | RBS | [9 empty] | 1 | CR040 | SLATINA_RTC | 296.38 | 0.6 | 18 | 10 | 23/56 | [6 empty] | 7 | MOBILCOM | 2000-09-04 | 168 | 2000-09-04 | 2000-09-06 | 2000-09-08 | PAUN | OK | 2000-11-23 |  | 2000-11-29 | 2001-01-10 | 30N01 Slatina-Craiova |  | OK | Cristian CROITOR | SORIN UNTARU | [32 empty] | 162 | Slatina | Olt | [5 empty] | 1 | 1 | 2 | 1 | 1 | 2
Phase_2 | CS | CR042 | A.I.CUZA | Slatina(3+1) | CR040 Slatina_RTC | Oltenia | 44 25 36 | 24 22 19.3 | 44 25 36 | 24 22 19.3 | Bd. A.I.Cuza(Rozelor) nr.30 Bl.GA21 | Asociatie locatari/Rusu Cristina - 049/ 431 900 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-09-06 | Yes | N/A |  |  |  | 33 | B | 36.25 | C5.4m+C5.4m | N/A | ISAF | OK | FIBEC | 2000-07-12 | 2000-08-20 | YesV | 2000-08-25 | Mugur | 2000-08-30 | 2000-08-30 |  |  |  | 2000-06-05 | 2000-05-29 |  | 2000-06-06 | 2000-07-12 |  |  |  | 2000-09-04 | YRO | MOB | 2000-09-04 | 2000-09-04 | 2000-09-05 | 2000-09-06 | 2000-09-10 |  | Yes | Ionut Grigorescu | 2000-11-20 | 2000-11-24 | 2000-11-24 | 2000-12-18 | 2001-01-08 | K 739 494 | 0 | 0 | 42 | K 739 494 | 110 | #N/A | 42 | K 739 494 | 240 | 0 | 42 |  |  |  |  | N/A | 7 | 7 | 7/8" | 13 | 13 | 7/8" | 17 | 17 | 7/8" |  |  |  | 74 | ML 23 E 1+0 | Craiova | MW | [7 empty] | 2U-3 |  |  |  | RBS | [9 empty] | 1 | CR041 | INDEPENDENTEI | [11 empty] | 7 | MOBILCOM | 2000-09-04 | 167 | 2000-09-04 | 2000-09-06 | 2000-09-10 | PAUN | OK | 2000-11-24 |  | 2000-11-29 | 2000-11-29 | 30N02 Slatina-Craiova |  | OK | Cristian CROITOR | SORIN UNTARU | [32 empty] | 160 | Slatina | Olt | [7 empty] | missing |  |  | missing
Phase_2 | CS | CR043 | CORNISEI | Slatina(3+1) | CR040 Slatina_RTC | Oltenia | 44 26 08.5 | 24 22 11.6 | 44 26 05.1 | 24 22 09.2 | Str. Cornisei nr.5 Bl.GA4 | Asociatie locatari - Gradinaru Ctin. - pres., Ap.51/Valceanu - Adm., Ap.8 Et.1 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-09-06 | Yes | N/A |  |  |  | 33 | B | 37 | T3.5m+T5.4m | N/A | ISAF | OK | FIBEC | 2000-07-21 | 2000-09-04 | YesV | 2001-05-18 | Mugur | 2000-08-30 | 2001-05-23 |  |  |  |  | 2000-05-29 |  | 2000-09-25 | 2000-09-25 |  |  |  | 2000-09-04 | YRO | MOB | 2000-09-04 | 2000-09-04 | 2000-09-05 | 2000-09-06 | 2000-09-08 |  | Yes | Ionut Grigorescu | 2000-11-20 | 2000-11-24 | 2000-11-24 | 2000-12-18 | 2001-01-08 | K 739 494 | 20 | 0 | 39 | K 739 494 | 140 | 0 | 38.6 | K 739 494 | 240 | 0 | 39 |  |  |  |  | N/A | 8 | 8 | 7/8" | 20 | 20 | 7/8" | 20 | 20 | 7/8" |  |  |  | 96 | ML 23 E 1+0 | Craiova | MW | 215 | 0.6 | 37 | 11 | 23/56 |  |  | 2U-3 |  |  |  | RBS | [9 empty] | 1 | CR041 | INDEPENDENTEI | 35 | 0.6 | 37 | 25 | 23/58 | [6 empty] | 7 | MOBILCOM | 2000-09-04 | 166 | 2000-08-31 | 2000-09-06 | 2000-09-08 | PAUN | OK | 2000-11-23 |  | 2000-11-29 | 2000-11-29 | 30N01 Slatina-Craiova |  | OK | Cristian CROITOR | SORIN UNTARU | [32 empty] | 162 | Slatina | Olt | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CR044 | GANEASA | Road Pitesti-Craiova(8+2) | CR040 Slatina_RTC | Oltenia | 44 23 52.8 | 24 16 59.9 | 44 23 52.8 | 24 16 59.9 | SC ALSAG SRL - Ferma zootehnica com. Ganeasa | SC ALSAG SRL - Ciobanu Nicolae, 049/ 42 47 53, 095/ 41 89 61/Dl. Sugubat - 049/ 41 56 30 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-11-17 | N/A | N/A |  |  |  | 0 | TN | 50 | Tower | N/A | ISAF | OK | SVF | 2000-09-11 | 2000-10-23 | YesV | 2000-11-13 | Doru | 2000-10-24 | 2000-11-22 |  |  |  |  | 2000-07-19 |  | 2000-08-17 | 2000-10-27 |  |  |  | 2000-11-01 | ICOM | SVF | 2000-10-23 | 2000-10-23 | 2000-11-01 | 2000-11-02 | 2000-11-03 |  | Yes | Bogdan Bogodai | 2000-12-30 | 2000-12-30 | 2000-12-30 | 2001-01-08 | 2001-01-10 | K 739 494 | 70 | 0 | 50 | K 739 494 | 250 | 0 | 50 | K 739 494 | 345 | 0 | 50 |  |  |  |  | N/A | 70 | 70 | 1 1/4" | 70 | 70 | 1 1/4" | 70 | 70 | 1 1/4" |  |  |  | 420 | ML 23 E 1+0 | Craiova | MW | 61 | 0.6 | 47 | 62 | 23/56 |  |  | 4U-1 |  |  |  | RBS | [9 empty] | 1 | CR041 | INDEPENDENTEI | 241 | 0.6 | 37/0.6 |  | 23/58 | [6 empty] | 11 | SVF | 2000-10-24 | 342 | 2000-10-24 | 2000-10-25 | 2000-11-03 | RADU | OK | 2000-12-30 |  | 2001-01-22 | 2001-01-22 | 30N02 Slatina-Craiova |  | OK | Cristian CROITOR | Cosmorom | [32 empty] | 120 | Ganeasa | Olt | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CR045 | ROBANESTI | Road Pitesti-Craiova(8+2) | CR075 Pielesti_RTC | Oltenia | 44 20 31.3 | 24 00 37 | 44 20 31.3 | 24 00 37 | Agrozootehnica SA Robanesti | Ferma zootehnica Robanesti/Mandrut Marinel - 092/ 23 11 14 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-10-20 | N/A | N/A |  |  |  | 0 | S | 19.2 | 9m pylonet | N/A | ISAF | OK | SVF | 2000-10-20 | 2000-11-06 | YesV | 2000-11-13 | Doru | 2000-11-03 | 2001-03-13 |  |  |  |  | 2000-07-19 |  | 2000-08-17 | 2000-10-30 |  |  |  | 2000-11-07 | ICOM | Electotrade | 2000-11-07 | 2000-11-07 | 2000-11-08 | 2000-11-08 | 2000-11-10 |  | Yes | Bogdan Bogodai | 2001-02-17 | 2001-02-16 | 2001-02-16 | 2001-03-15 | 2001-04-10 | K 739 494 | 80 | 0 | 26 | K 739 494 | 250 | 0 | 26 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 38 | 38 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 76 | ML 38 E 1+0 | Craiova | MW | 238 | 0.6 | 23/0.6 | 40 | 38/14 |  | 4X2/8 | 2U-3 |  |  |  | RBS | [10 empty] | CR075 | PIELESTI_RTC | 58 | 0.6 | 9.5/0.6 | 15 | 38/18 | [6 empty] | 15 | TRYLON | 2000-11-21 | 390 | 2000-11-22 | 2000-11-22 | 2001-02-18 | RADU | OK | 2001-02-16 |  |  |  | 30N01 Pielesti-Craiova |  | 2001-01-30 | Cristian CROITOR | Cosmorom | [32 empty] | 188 | Robanesti | Dolj | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CR046 | BALS | Road Pitesti-Craiova(8+2) | CR075 Pielesti_RTC | Oltenia | 44 21 34.3 | 24 11 23.1 | 44 21 34.3 | 24 11 23.1 | Str. Nicolae Balcescu nr. 195, Bl.M2, Sc.1 | Asociatie de proprietari/Borcan Ion - 049/ 451 782, Dinu Ileana - 049/ 451 237 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-11-17 | Yes | N/A |  |  |  | 31 | B | 34.2 | 9mnew pylonet | N/A | ISAF | OK | TEHNOROB | 2000-10-20 | 2000-10-27 | YesV | 2000-11-02 | Doru | 2000-11-07 | 2000-11-10 |  |  |  |  | 2000-07-19 |  | 2000-09-04 | 2000-10-20 |  |  |  | 2000-11-01 | ICOM | SVF | 2000-10-31 | 2000-11-01 | 2000-11-01 | 2000-11-02 | 2000-11-03 |  | Yes | Bogdan Bogodai | 2001-03-09 | 2001-03-10 | 2001-03-10 |  |  | K 739 494 | 90 | 0 | 42 | K 739 494 | 300 | 0 | 42 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 24 | 24 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 48 | N/A | Craiova | HDSL | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A |  |  |  | RBS | [7 empty] | 24/Indoor |  |  | CR075 | PIELESTI_RTC |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PITURCESCU | OK | N/A |  | N/A | N/A | HDSL+30N01 Bals-Pielesti+30N01 Pielesti-Craiova |  | 2001-02-21 | Cristian CROITOR | Petrica BURGHIU | [32 empty] | 164 | Bals | Olt | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | CR047 | VILCEA_RTC | Rm. Vilcea(5) | CR047 Valcea_RTC | Oltenia | 45 06 16 | 24 21 49.8 | 45 06 16 | 24 21 49.8 | Rtc Oficiul 1-Nord, Str. Calea lui Traian | Romtelecom - dir. Petre Dulca, Bd. T. Vladimirescu nr.6/Sorin Pecingine - sef centru, 092/ 848 178 | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-09-19 | N/A | N/A |  |  |  |  | B | 15 | 15m existing pylonet | Room | ISAF | OK | EL-MONT | 2000-07-19 | 2000-08-21 | YesV | 2000-08-09 | Mugur | 2000-08-18 | 2000-10-18 |  |  |  | 2000-06-06 | 2000-05-15 |  | 2000-06-06 | 2000-08-04 |  |  |  | 2000-08-18 | YRO | TRY | 2000-08-18 | 2000-08-16 | 2000-08-18 | 2000-08-19 | 2000-08-22 |  | Yes | Cristian Croitor | 2000-12-05 | 2000-11-29 | 2000-11-29 |  |  | K 739 494 | 0 | 0 | 28.5 | K 739 494 | 120 | 0 | 28.5 | K 739 494 | 240 | 0 | 28.5 |  |  |  |  | N/A | 50 | 50 | 1 1/4" | 51 | 51 | 1 1/4" | 52 | 52 | 1 1/4" |  |  |  | 306 | N/A | Craiova | FO | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | TMR 9202 | 40047 | 2001-05-11 | [7 empty] | 1 | BSC23 | BSC CRAIOVA |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | VLAD | OK | N/A |  | N/A | N/A | 30N02 Rm.Valcea-Craiova |  | OK | Cristian CROITOR | SORIN UNTARU | [32 empty] | 248 | Rm. Vilcea | Vilcea | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | CR048 | CALEA LUI TRAIAN | Rm. Vilcea(5) | CR047 Valcea_RTC | Oltenia | 45 05 45.05 | 24 21 50.8 | 45 05 46.7 | 24 21 42.7 | Str. Calea lui Traian Bl. S7/2 Sc.A | Asociatie de locatari/Preda Ionel - 094/ 147 345 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-09-09 | Yes | N/A |  |  |  | 27 | B | 31 | T4m+T3.5m | N/A | ISAF | OK | EL-MONT | 2000-07-20 | 2000-08-04 | YesV | 2000-08-09 | Mugur | 2000-08-18 | 2000-08-15 |  |  |  | 2000-06-05 | 2000-05-15 |  | 2000-06-05 | 2000-07-14 |  |  |  | 2000-08-18 | YRO | TRY | 2000-08-18 | 2000-08-16 | 2000-08-18 | 2000-08-19 | 2000-08-22 |  | Yes | Cristian Croitor | 2000-12-05 | 2000-11-30 | 2000-11-30 |  |  | K 739 494 | 0 | 0 | 28.6 | K 739 494 | 110 | 0 | 28.58 | K 739 494 | 195 | 0 | 28.5 |  |  |  |  | N/A | 10 | 10 | 7/8" | 17 | 17 | 7/8" | 17 | 17 | 7/8" |  |  |  | 88 | ML 23 E 1+1 | Craiova | MW | 10 | 0.6 | 30.1 | 11 | 23/58 | YES | 4x2/8 | 4U-1+2U-3 |  |  |  | RBS | [9 empty] | 1 | CR047 | VILCEA_RTC | 190 | 0.6 | 27 | 51 | 23/56 | [6 empty] | 2 | TRYLON | 18.08.00- | 130/840 | 2000-08-18 | 2000-08-19 | 2000-08-22 | VLAD | OK | 2000-11-30 | Dublare suplimentara | 2001-02-05 | 2001-02-06 | 30N01 Rm. Valcea-Craiova |  | OK | Cristian CROITOR | SORIN UNTARU | [32 empty] | 257 | Rm. Vilcea | Vilcea | [5 empty] | 1 | 1 | 2 | 1 | 1 | 2
Phase_2 | CS | CR049 | MATEI BASARAB | Rm. Vilcea(5) | CR047 Valcea_RTC | Oltenia | 45 06 67.8 | 24 21 51.1 | 45 06 50.9 | 24 21 50.1 | Str. Matei Basarab Bl.A3 Sc.B |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-09-19 | Yes | N/A |  |  |  | 36 | B | 36 | C5.4m+C5.4m | N/A | ISAF | OK | EL-MONT | 2000-07-19 | 2000-07-31 | YesV | 2000-08-09 | Mugur | 2000-08-18 |  |  |  |  | 2000-06-05 | 2000-05-15 |  | 2000-06-06 | 2000-07-07 |  |  |  | 2000-08-18 | YRO | TRY | 2000-08-18 | 2000-08-16 | 2000-08-18 | 2000-08-19 | 2000-08-22 |  | Yes | Cristian Croitor | 2000-12-05 | 2000-12-01 | 2000-12-01 |  |  | K 739 494 | 13 | 0 | 38.9 | K 739 494 | 120 | 0 | 38.9 | K 739 494 | 240 | 0 | 38.9 |  |  |  |  | N/A | 14 | 14 | 7/8" | 14 | 14 | 7/8" | 12 | 12 | 7/8" |  |  |  | 80 | ML 23 E 1+0 | Craiova | MW | 180 | 0.6 | 37 | 12 | 23/58 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [9 empty] | 1 | CR047 | VILCEA_RTC | 0 | 0.6 | 27 | 50 | 23/56 | [6 empty] | 2 | TRYLON | 18.08.00- | 131 | 2000-08-18 | 2000-08-19 | 2000-08-22 | VLAD | OK | 2000-12-01 |  | 2000-12-21 | 2001-01-08 | 30N02 Rm.Valcea-Craiova |  | OK | Cristian CROITOR | SORIN UNTARU | [32 empty] | 281 | Rm. Vilcea | Vilcea | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CR050 | MOPARIV | Rm. Vilcea(5) | CR047 Valcea_RTC | Oltenia | 45 06 38.3 | 24 22 47.2 | 45 07 52 | 24 22 05.9 | Fabrica de Paine Mopariv, Rm. Valcea, str. Timis nr.22 | Dir. Gen. Frincu Gheorghe - 094/ 235 417/Ing. Mocanu Catalin (sef. Mecanizare) | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-11-17 | Yes | N/A |  |  |  | 25 | B | 25 | S2m+T3.5m | N/A | ISAF | OK | EL-MONT | 2000-10-30 | 2000-11-03 | YesV | 2000-11-14 | Mugur | 2000-11-22 | 2000-11-22 |  |  |  |  | 2000-09-21 |  | 2000-10-09 | 2000-10-30 |  |  |  | 2000-11-10 | ICOM | Electotrade | 2000-11-10 | 2000-11-10 | 2000-11-13 | 2000-11-13 | 2000-11-14 |  | Yes | Cristian Croitor | 2000-12-05 | 2000-12-01 | 2000-12-01 |  |  | K 739 494 | 130 | 0 | 26.8 | K 739 494 | 355 | 0 | 26 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 10 | 10 | 7/8" | 10 | 10 | 7/8" | N/A | N/A | N/A |  |  |  | 40 | ML 23 E 1+0 | Craiova | MW | 191 | 0.6 | 28.5/0.3 | 19 | 23/56 |  |  | 2U-3 |  |  |  | RBS | [9 empty] | 1 | CR049 | MATEI BASARAB | 107 | 0.6 | 37/0.3 | 12 | 23/58 | [6 empty] | 10 | RADCOM | 2000-11-16 | 373 | 2000-11-17 | 2000-11-17 | 2000-11-24 | RADU | OK | 2000-12-01 |  | 2000-12-21 | 2001-01-08 | 30N02 Rm.Valcea-Craiova |  | OK | Cristian CROITOR | Cosmorom | [32 empty] | 268 | Rm. Vilcea | Vilcea | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CR051 | TINERETULUI | Rm. Vilcea(5) | CR047 Valcea_RTC | Oltenia | 45 05 34.7 | 24 22 19.8 | 45 05 35.1 | 24 22 20 | Str. Tineretului nr.7 Bl.A11/1 Sc.A |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-09-19 | Yes | N/A |  |  |  | 33 | B | 37.2 | C5.5m+C5.5m | N/A | ISAF | OK | EL-MONT | 2000-07-19 | 2000-07-31 | YesV | 2000-08-09 | Mugur | 2000-08-18 |  |  |  |  | 2000-06-06 | 2000-05-15 |  | 2000-06-06 | 2000-07-07 |  |  |  | 2000-08-18 | YRO | TRY | 2000-08-18 | 2000-08-16 | 2000-08-18 | 2000-08-19 | 2000-08-22 |  | Yes | Cristian Croitor | 2000-12-05 | 2000-11-30 | 2000-11-30 | 2001-02-13 | 2001-02-16 | K 739 494 | 0 | 0 | 39.9 | K 739 494 | 120 | 0 | 39.9 | K 739 494 | 220 | 0 | 39.9 |  |  |  |  | N/A | 20 | 20 | 7/8" | 28 | 28 | 7/8" | 28 | 28 | 7/8" |  |  |  | 152 | ML 23 E 1+1 | Craiova | MW | 294 | 0.6 | 42 | 20 | 23/56 | YES |  | 2x4U-1 |  |  |  | RBS | [9 empty] | 1 | CR048 | CALEA LUI TRAIAN | 114 | 0.6 | 28.37 | 14 | 23/58 | [6 empty] | 2 | TRYLON | 18.08.00- | 129/839 | 2000-08-18 | 2000-08-19 | 2000-08-22 | VLAD | OK | 2001-06-06 | PENDING |  |  | 30N01 Rm. Valcea-Craiova |  | OK | Cristian CROITOR | SORIN UNTARU | [32 empty] | 241 | Rm. Vilcea | Vilcea | [6 empty] | 1 | 2 |  | 1 | 2
Phase_2 | CS | CR052 | TURNU SEVERIN_RTC | Turnu Severin(4) | CR052 Turnul Severin_RTC | Oltenia | 44 37 28.5 | 22 39 10.7 | 44 37 28.5 | 22 39 10.7 | Str. Teodor Costescu nr.3-5 | RTC Turnu Severin/Eugen Negreanu (transmisiuni), 093/ 391 301 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-09-06 | N/A | N/A |  |  |  | 0 | TE | 50 | 50m existing tower | N/A | ISAF | OK | SVF | 2000-07-20 | 2000-08-09 | YesV | 2000-08-10 | Mugur | 2000-08-17 | 2000-08-15 |  |  |  | 2000-06-06 | 2000-05-20 |  | 2000-06-07 | 2000-08-04 |  |  |  | 2000-08-17 | YRO | SVF | 2000-08-17 | 2000-08-16 | 2000-08-18 | 2000-08-19 | 2000-08-22 |  | Yes | Mihai Constantin | 2000-11-23 | 2000-11-20 | 2000-11-20 |  |  | K 739 494 | 5 | 0 | 36 | K 739 494 | 110 | 0 | 44 | K 739 494 | 245 | 0 | 33 |  |  |  |  | N/A | 46 | 46 | 1 1/4" | 54 | 54 | 1 1/4" | 43 | 43 | 1 1/4" |  |  |  | 286 | N/A | Craiova | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | 4U-1 | 4U-1 |  |  | RBS | 40052 | [8 empty] | 1 | BSC23 | BSC CRAIOVA |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | RADU | OK | N/A |  | N/A | N/A | 30N02 Severin-Craiova |  | OK | Cristian CROITOR | SORIN UNTARU | [32 empty] | 47 | Turnu Severin | Mehedinti | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | CR053 | VLADIMIRESCU_1 | Turnu Severin(4) | CR052 Turnul Severin_RTC | Oltenia | 44 37 52.2 | 22 38 34.4 | 44 37 51.9 | 22 38 35 | B-dul. T. Vladimirescu nr.1 Bl.C | Asociatie de locatari nr.67 - Jianu Becheru Nicolae - presedinte/Ciocsirescu Constantin - Ap.11, 052/ 312 217 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-09-06 | Yes | N/A |  |  |  | 33 | B | 33 | T4m+T4m | N/A | ISAF | OK | SVF | 2000-07-10 | 2000-08-11 | YesV | 2000-08-10 | Mugur | 2000-08-17 | 2000-09-13 |  |  |  | 2000-06-06 | 2000-05-20 |  | 2000-06-07 | 2000-07-03 |  |  |  | 2000-08-17 | YRO | SVF | 2000-08-17 | 2000-08-16 | 2000-08-18 | 2000-08-19 | 2000-08-22 |  | Yes | Mihai Constantin | 2000-11-23 | 2000-11-20 | 2000-11-20 | 2000-12-06 | 2000-12-18 | K 739 494 | 5 | 0 | 39 | K 739 494 | 125 | 0 | 39 | K 739 494 | 245 | 0 | 39 |  |  |  |  | N/A | 19 | 19 | 7/8" | 19 | 19 | 7/8" | 21 | 21 | 7/8" |  |  |  | 114 | ML 23 E 1+0 | Craiova | MW | 132.5 | 0.6 | 39.4 | 24 | 23/58 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [9 empty] | 1 | CR052 | TURNU SEVERIN_RTC | 312 | 0.6 | 32.5 | 42 | 23/56 | [6 empty] | 5 | SVF | 2000-08-18 | 125 | 2000-08-17 | 2000-08-19 | 2000-08-22 | RADU | OK | 2000-11-20 |  | 2000-12-06 | 2000-12-18 | 30N03 Severin-Craiova |  | OK | Cristian CROITOR | SORIN UNTARU | [32 empty] | 58 | Turnu Severin | Mehedinti | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CR054 | VLADIMIRESCU_2 | Turnu Severin(4) | CR052 Turnul Severin_RTC | Oltenia | 44 37 56.4 | 22 39 59.4 | 44 37 56.4 | 22 39 59.4 | B-dul. T. Vladimirescu nr.130 Bl.IS 3B Sc.1 | Asociatie de locatari nr.67 - Civitu Nicolae Presedinte, Et.5 Ap.7, 052/ 322 631/Zaharia Tache _ Et4 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-09-06 | Yes | N/A |  |  |  | 29.8 | B | 29.8 | C3.5m+C3.5m | N/A | ISAF | OK | SVF | 2000-07-15 | 2000-08-11 | YesV | 2000-08-10 | Mugur | 2000-08-17 | 2000-09-13 |  |  |  | 2000-06-06 | 2000-05-20 |  | 2000-06-07 | 2000-07-12 |  |  |  | 2000-08-17 | YRO | SVF | 2000-08-17 | 2000-08-16 | 2000-08-18 | 2000-08-19 | 2000-08-22 |  | Yes | Mihai Constantin | 2000-11-23 | 2000-11-20 | 2000-11-20 | 2000-12-08 | 2001-01-08 | K 739 494 | 110 | 0 | 31.3 | K 739 494 | 230 | 0 | 31.3 | K 739 494 | 330 | 0 | 31.3 |  |  |  |  | N/A | 22 | 22 | 7/8" | 19 | 19 | 7/8" | 22 | 22 | 7/8" |  |  |  | 126 | ML 23 E 1+0 | Craiova | MW | 231 | 0.6 | 31 | 21 | 23/58 |  |  | 2U-3 |  |  |  | RBS | [9 empty] | 1 | CR052 | TURNU SEVERIN_RTC | 51 | 0.6 | 43.5 | 53 | 23/56 | [6 empty] | 5 | SVF | 2000-08-18 | 126 | 2000-08-17 | 2000-08-19 | 2000-08-22 | RADU | OK | 2000-11-21 |  | 2000-12-06 | 2000-12-18 | 30N02 Severin-Craiova |  | OK | Cristian CROITOR | SORIN UNTARU | [32 empty] | 52 | Turnu Severin | Mehedinti | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CR055 | REVOLUTIEI | Turnu Severin(4) | CR052 Turnul Severin_RTC | Oltenia | 44 38 15.8 | 22 38 56.1 | 44 38 15.8 | 22 38 56.1 | B-dul. Revolutiei 16/22 Dec. 1989 nr.3 Bl.B2 | Asociatie de locatari/Craciun Maria - Et.7 Ap.86 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-09-06 | Yes | N/A |  |  |  | 33 | B | 36.2 | C4m+C4m | N/A | ISAF | OK | SVF | 2000-07-20 | 2000-08-09 | YesV | 2000-08-10 | Mugur | 2000-08-17 | 2000-08-15 |  |  |  | 2000-06-06 | 2000-05-20 |  | 2000-06-07 | 2000-07-12 |  |  |  | 2000-08-17 | YRO | SVF | 2000-08-17 | 2000-08-16 | 2000-08-18 | 2000-08-19 | 2000-08-22 |  | Yes | Mihai Constantin | 2000-11-23 | 2000-11-21 | 2000-11-21 | 2000-12-06 | 2000-12-18 | K 739 494 | 90 | 0 | 36 | K 739 494 | 210 | 0 | 36 | K 739 494 | 330 | 0 | 36 |  |  |  |  | N/A | 30 | 30 | 7/8" | 11 | 11 | 7/8" | 30 | 30 | 7/8" |  |  |  | 142 | ML 23 E 1+0 | Craiova | MW | 168 | 0.6 | 36 | 12 | 23/58 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [9 empty] | 1 | CR052 | TURNU SEVERIN_RTC | 347 | 0.6 | 35.5 | 45 | 23/56 | [6 empty] | 5 | SVF | 2000-08-18 | 127 | 2000-08-17 | 2000-08-19 | 2000-08-22 | RADU | OK | 2000-11-20 |  | 2000-12-06 | 2000-12-18 | 30N03 Severin-Craiova |  | OK | Cristian CROITOR | SORIN UNTARU | [32 empty] | 70 | Turnu Severin | Mehedinti | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CR056 | CENTRAL_RTC | Tirgu Jiu(3) | CR056 Central_RTC | Oltenia | 45 02 32.8 | 23 16 18.4 | 45 02 32.8 | 23 16 18.4 | Str. Vasile Alexandri | Romtelecom/Aungurencei - sef serviciu transmisiuni, 053/ 217 310, 053/ 218 873 | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-09-06 | N/A | N/A |  |  |  | 10 | B | 18.5 | 16m existing tower+C3.5m+C3.5m | Room | ISAF | OK | SETRACO | 2000-07-12 | 2000-08-28 | YesV | 2000-09-21 | Mugur | 2000-09-01 | 2000-09-26 |  |  |  | N/A | 2000-06-05 |  | 2000-06-07 | 2000-06-30 |  |  |  | 2000-09-05 | YRO | TRY | 2000-09-01 | 2000-09-01 | 2000-09-05 | 2000-09-06 | 2000-09-11 |  | Yes | Ionut Grigorescu | 2000-11-23 | 2000-11-21 | 2000-11-21 | 2000-12-08 | 2001-01-08 | K 739 494 | 70 | 0 | 30.7 | K 739 494 | 190 | 0 | 30.7 | K 739 494 | 310 | 0 | 30.7 |  |  |  |  | N/A | 37 | 37 | 7/8" | 35 | 35 | 7/8" | 35 | 35 | 7/8" |  |  |  | 204 | N/A | Craiova | FO | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | TMR 9202 | 40056 | [9 empty] | BSC23 | BSC CRAIOVA |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PAUN | OK | N/A |  | N/A | N/A | 30N01 Tg.Jiu-Craiova |  | OK | Cristian CROITOR | SORIN UNTARU | [32 empty] | 200 | Tirgu Jiu | Gorj | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | CR057 | CTA_9 MAI | Tirgu Jiu(3) | CR057 CTA_9 MAI_RTC | Oltenia | 45 01 39.7 | 23 16 18.7 | 45 01 39.7 | 23 16 18.7 | RTC CTA - Of. 6 (9 mai), Str. 23 August nr.1 | RTC -Str. 23 August nr.1/ | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-09-06 | N/A | N/A |  |  |  | 16 | B | 18.5 | Pilon 9m | Room | ISAF | OK | SETRACO | 2000-07-12 | 2000-08-28 | YesV | 2000-09-21 | Mugur | 2000-09-01 | 2000-09-26 |  |  |  | N/A | 2000-06-05 |  | 2000-06-07 | 2001-03-02 |  |  |  | 2000-09-05 | YRO | TRY | 2000-09-01 | 2000-09-01 | 2000-09-05 | 2000-09-06 | 2000-09-08 |  | Yes | Cristian Croitor | 2000-12-07 | 2000-12-07 | 2000-12-07 | 2001-02-08 | 2001-02-16 | K 739 494 | 70 | 0 | 27.2 | K 739 494 | 190 | 0 | 27.5 | K 739 494 | 310 | 0 | 27.3 |  |  |  |  | N/A | 15 | 15 | 7/8" | 15 | 15 | 7/8" | 16 | 16 | 7/8" |  |  |  | 92 | N/A | Craiova | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | [5 empty] | XC40057 | [9 empty] | BSC23 | BSC CRAIOVA |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PAUN | OK | N/A |  | N/A | N/A | 30N02 Tg.Jiu CTA_9 Mai-Craiova |  | OK | Cristian CROITOR | SORIN UNTARU | [32 empty] | 197 | Tirgu Jiu | Gorj | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | CR058 | SILOZ | Tirgu Jiu(3) | CR056 Central_RTC | Oltenia | 45 04 17.4 | 23 18 28.3 | 45 04 17.4 | 23 18 28.3 | Str. Ciolarlau nr.7 Bl.B2 | SC COMP GORJ SA - Dir. Gen. Dirvan Dumitru, 053/ 226 330/Parvulescu - Dir. Comercial, 053/ 226 483, 094/ 594 882 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-09-06 | Yes | N/A |  |  |  | 47 | B | 47 | T4m, T4m | N/A | ISAF | OK | SETRACO | 2000-07-12 | 2000-08-28 | YesV | 2000-09-21 | Mugur | 2000-09-01 | 2000-09-26 |  |  |  | 2000-06-06 | 2000-06-05 |  | 2000-06-07 | 2001-05-09 |  |  |  | 2000-09-05 | YRO | TRY | 2000-09-05 | 2000-09-05 | 2000-09-05 | 2000-09-06 | 2000-09-08 |  | Yes | Ionut Grigorescu | 2000-11-23 | 2000-11-21 | 2000-11-24 | 2000-12-08 | 2001-01-08 | K 739 494 | 20 | 0 | 49.7 | K 739 494 | 220 | 0 | 49.8 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 16.5 | 16.5 | 7/8" | 16.5 | 16.5 | 7/8" | N/A | N/A | N/A |  |  |  | 65 | ML 23 E 1+0 | Craiova | MW | 221 | 0.6 | 48.5 | 20 | 23/58 |  |  | 2U-3 |  |  |  | RBS | [10 empty] | CR056 | CENTRAL_RTC | 41 | 0.6 | 30.7 | 37 | 23/56 | [6 empty] | 4 | TRYLON | 2000-09-05 | 174 | 2000-09-05 | 2000-09-06 | 2000-09-08 | PAUN | OK | 2000-11-21 |  |  |  | 30N01 Tg.Jiu Central-Craiova |  | OK | Ionut GRIGORESCU | SORIN UNTARU | [32 empty] | 223 | Tirgu Jiu | Gorj | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CR059 | ALEXANDRIA_RTC | Road Alexandria-Craiova(12+1) | CR059 Alexandria_RTC | Oltenia | 43 57 58.2 | 25 20 04.1 | 43 57 58.2 | 25 20 04.1 | Str. Dunarii nr.245 - RTC Centru | RTC Alexandria/Popescu (transmisiuni), 047/ 314 411 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-08-02 | 2000-08-02 | N/A |  |  |  | 0 | TE | 56 | 56m existing tower-C2.5mr+C2.5m+C2.5m | N/A | ISAF | OK | PROFIL | 2000-06-27 | 2000-07-07 | YesV | 2000-07-20 | Mugur | 2000-07-21 | 2000-07-21 |  |  |  | N/A | 2000-05-28 |  | 2000-06-07 | 2000-06-27 |  |  |  | 2000-08-03 | YRO | SVF | 2000-07-31 | 2000-07-31 | 2000-08-04 | 2000-08-05 | 2000-08-10 |  | Yes | Ion Soare | 2000-12-29 | 2000-12-27 | 2000-12-27 | 2001-01-08 | 2001-01-10 | K 739 494 | 0 | 0 | 50 | K 739 494 | 120 | #N/A | 50 | K 739 494 | 240 | 0 | 50 |  |  |  |  | N/A | 70 | 70 | 1 1/4" | 70 | 70 | 1 1/4" | 70 | 70 | 1 1/4" |  |  |  | 420 | N/A | Baneasa | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | 4U-1 |  |  |  | RBS | 40059 | 2001-06-25 | [7 empty] | 1 | BSC21 | BSC BANEASA |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | RADU | OK | N/A |  | N/A | N/A | 30N01 Alexandria-Baneasa |  | OK | Cristian CROITOR | #N/A | [32 empty] | 55 | Alexandria | Teleorman | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | CR060 | CRAITELOR | Targoviste(5) | CR063 Targoviste_RTC | Muntenia | 44 55 15.3 | 25 28 38.7 | 44 55 10 | 25 28 41.5 | Calea Bucuresti, bl.H1, sc.B | Asociatie de locatari/Marinescu- Ap.7, 045/ 218 176 | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-12-11 | N/A | N/A |  |  |  | 31.2 | B | 34.1 | C4m+C4m | Room | TRANSDAT | OK | MMK | 2000-11-15 | 2000-12-30 | YesV | 2001-06-05 | Doru | 2001-01-09 | 2001-06-14 |  |  |  |  | 2000-10-17 |  | 2000-11-09 | 2000-12-07 |  |  |  | 2001-02-01 | ICOM | ORION | 2001-01-26 | 2001-01-26 | 2001-02-05 | 2001-02-12 | 2001-02-13 |  | Yes | Theo Radoi | 2001-02-20 | 2001-02-20 | 2001-02-20 | 2001-04-24 | 2001-05-15 | K 739 494 | 140 | 0 | 34.6 | K 739 494 | 230 | 0 | 34.6 | K 739 494 | 320 | 0 | 34.6 |  |  |  |  | N/A | 17 | 17 | 7/8" | 17 | 17 | 7/8" | 13.5 | 13.5 | 7/8" |  |  |  | 105 | ML 23 E 1+0 | Baneasa | MW | 343 | 0.6 | 36.5 | 13.5 | 23/58 |  | 4x2/8 | 2U-3 | [14 empty] | CR152 | SILOZ TARGOVISTE | 163 | 0.6 | 57 (2) | 13 | 23/56 | [6 empty] | /14* | ORION | -21.12.00 | 556 | 2001-02-02 | 2001-02-06 | 2001-02-09 | RADU | OK | 2001-02-20 |  | 2001-02-27 | 2001-03-02 | 30N02 Targoviste-Baneasa |  | 2001-01-30 | Ionut GRIGORESCU | Cosmorom | [32 empty] | 271 | Targoviste | Dambovita | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CR061 | UNIRII | Targoviste(5) | CR063 Targoviste_RTC | Muntenia | 44 55 15.3 | 25 28 38.7 | 44 55 15.2 | 25 27 00.6 | B-dul. Unirii bl. 70, sc.A | Asociatie de locatari, nr. 110, bl. Unirii, bl. 7/Dl. Mirica - presedinte asociatie,bl. Unirii, bl.7, sc. B, et.7, ap. 73, 045/ 210 236 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-12-11 | Yes | N/A |  |  |  | 40 | B | 43.2 | C4m+C4m | N/A | TRANSDAT | OK | MMK | 2000-11-15 | 2000-12-30 | YesV | 2001-02-06 | Doru | 2001-07-06 | 2001-02-07 |  |  |  |  | 2000-10-17 |  | 2000-11-08 | 2000-12-07 |  |  |  | 2001-02-01 | ICOM | ORION | 2001-01-26 | 2001-01-26 | 2001-02-05 | 2001-02-13 | 2001-02-16 |  | Yes | Bogdan Bogodai | 2001-05-03 | 2001-05-03 | 2001-05-03 |  |  | K 739 494 | 0 | 0 | 44.5 | K 739 494 | 120 | 0 | 44.5 | K 739 494 | 210 | 0 | 44.5 |  |  |  |  | N/A | 19 | 19 | 7/8" | 14 | 14 | 7/8" | 18 | 18 | 7/8" |  |  |  | 102 | ML 38 E 1+0 | Baneasa | MW | 35 | 0.3 | 44 | 19 | 38/14 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [9 empty] | 1 | CR063 | TARGOVISTE_RTC | 215 | 0.3 | 46.5 | 64 | 38/18 | [6 empty] | /14* | ORION | -21.12.00 | 595 | 2001-02-01 | 2001-02-06 | 2001-02-09 | RADU | OK | 2001-05-03 |  | 2001-05-10 | 2001-05-25 | 30N03 Targoviste-Baneasa |  | 2001-01-30 | Ionut GRIGORESCU | Cosmorom | [32 empty] | 280 | Targoviste | Dambovita | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CR062 | POPESCU | Targoviste(5) | CR063 Targoviste_RTC | Muntenia | 44 55 53.8 | 25 26 44 | 44 55 53.6 | 25 26 43.6 | Str. Radu Popescu bl.23, sc. E | Asociatie de locatari/Dl. Paunescu - presedente asociatie, 045/ 632 531 | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-12-11 | N/A | N/A |  |  |  | 39.5 | B | 42.4 | C4m+C4m | Room | TRANSDAT | OK | SETRACO | 2000-11-15 | 2000-12-15 | YesV | 2001-03-23 | Doru | 2001-01-11 | 2001-03-29 |  |  |  |  | 2000-10-17 |  | 2000-11-08 | 2000-12-07 |  |  |  | 2000-12-14 | ICOM | ORION | 2000-12-14 | 2000-12-15 | 2000-12-19 | 2000-12-21 | 2001-01-09 |  | Yes | Theo Radoi | 2001-02-15 | 2001-02-15 | 2001-02-15 | 2001-04-24 | 2001-05-03 | K 739 494 | 10 | 0 | 43.7 | K 739 494 | 120 | 0 | 43.7 | K 739 494 | 220 | 0 | 43.7 |  |  |  |  | N/A | 6 | 6 | 7/8" | 6 | 6 | 7/8" | 6 | 6 | 7/8" |  |  |  | 36 | ML 38 E 1+0 | Baneasa | MW | 110 | 0.3 | 43.3 | 6 | 38/14 |  | 4x2/8 | 4U-1 |  |  |  | Indoor Comteck | [9 empty] | 1 | CR063 | TARGOVISTE_RTC | 290 | 0.3 | 47.5 | 64 | 38/18 | [6 empty] | 14* | ORION | 2000-12-21 | 496 | 2001-01-07 | 2001-01-08 | 2001-01-17 | CORBEANU | OK | 2001-02-15 |  | 2001-02-21 | 2001-03-02 | 30N02 Targoviste-Baneasa |  | 2001-01-30 | Ionut GRIGORESCU | Cosmorom | [32 empty] | 280 | Targoviste | Dambovita | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CR063 | TARGOVISTE_RTC | Targoviste(5) | CR063 Targoviste_RTC | Muntenia | 44 55 42.7 | 25 27 27.4 | 44 55 42.7 | 25 27 27.4 | Romtelecom, str. H. Radulescu | Romtelecom/ | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-12-11 | N/A | N/A |  |  |  | 8.25 | TE | 48.5 |  | Room | TRANSDAT | OK | SETRACO | 2000-11-15 | 2000-12-15 | YesV | 2001-06-11 | Doru | 2001-02-02 | 2001-06-14 |  |  |  | N/A | 2000-10-17 |  | 2000-11-07 | 2000-12-06 |  |  |  | 2000-12-14 | ICOM | ORION | 2000-12-14 | 2000-12-15 | 2000-12-19 | 2000-12-21 | 2001-01-09 |  | Yes | Theo Radoi | 2001-02-13 | 2001-02-13 | 2001-02-13 | 2001-04-24 | 2001-05-03 | K 739 494 | 0 | 0 | 42 | K 739 494 | 120 | 0 | 42 | K 739 494 | 240 | 0 | 42 |  |  |  |  | N/A | 58 | 58 | 1 1/4" | 57 | 57 | 1 1/4" | 55 | 55 | 1 1/4" |  |  |  | 340 | N/A | Baneasa | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | 4U-1(TMR9202) |  |  |  | TMR 9202 | [7 empty] | 30/Indoor |  | 1 | BSC21 | BSC BANEASA |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | CORBEANU | OK | N/A |  | N/A | N/A | 30N01 Targoviste-Baneasa |  | 2001-01-30 | Ionut GRIGORESCU | Cosmorom | [32 empty] | 281 | Targoviste | Dambovita | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | CR066 | TARTASESTI | Road Buc-Targoviste(4) | YR067 Racari_RTC | Muntenia | 44 34 32.7 | 25 51 34.9 | 44 34 32.7 | 25 51 34.9 | Com. Ciocanesti - siloz baza Ciocanesti | CEREAL COM SRL DAMBOVITA - str. Calea Domneasca nr.263/Dan Stanica - 045/ 620 919 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-12-11 | Yes | N/A |  |  |  | 49 | S | 49 | C5m+C5m | N/A | DIEKAT | OK | DIEKAT | 2000-11-15 | 2000-12-13 | YesV | 2000-12-19 | Andrei |  | 2001-01-10 |  |  |  |  | 2000-07-19 |  | 2000-11-10 | 2000-11-24 |  |  |  | 2000-12-15 | ICOM | DIEKAT | 2000-12-14 | 2000-12-15 | 2000-12-19 | 2000-12-22 | 2001-01-18 |  | Yes | Bogdan Bogodai | 2001-03-13 | 2001-03-13 | 2001-03-13 | 2001-06-29 | 2001-07-11 | K 739 494 | 130 | 0 | 51.2 | K 739 494 | 290 | 0 | 51.2 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 12 | 12 | 7/8" | 12 | 12 | 7/8" | N/A | N/A | N/A |  |  |  | 40 | ML 15 E 1+0 | Baneasa | MW | 300 | 1.2 | 49.5 | 6 | 15/89 | YES | 4x2/8 | 4U-1 |  |  |  | RBS | [9 empty] | 1 | CR067 | RACARI_DRTV | 120 | 1.2 | 35/0.6 | 55 | 15/84 | [6 empty] | 7* | DIEKAT | 2000-12-14 | 463 | 2000-12-15 | 2000-12-22 | 2001-01-18 | PAUN | OK | 2001-03-13 |  | 2001-04-11 | 2001-04-17 | 30N01 Racari-Baneasa |  | 2001-03-08 | Denis CIUCU | Cosmorom | [32 empty] | 115 | Tartasesti | Dambovita | [5 empty] | 1 | 1 | 2 | 1 | 1 | 2
Phase_2 | CS | CR067 | RACARI_DRTV | Road Buc-Targoviste(4) | YR067 Racari_RTC | Muntenia | 44 37 36.4 | 25 44 16 | 44 37 37.8 | 25 44 15.1 | DJ 71 Bucuresti-Targoviste, Str. Ana Ipatescu nr.121 | RTC Racari/ | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-10-13 | N/A | N/A |  |  |  | 0 | TE | 65 |  | N/A | DIEKAT | OK | DIEKAT | 2000-09-27 | 2000-10-10 | YesV | 2000-10-25 | Andrei | 2000-11-10 | 2000-12-08 |  |  |  | N/A | 2000-07-20 |  | 2000-08-21 | 2000-09-26 |  |  |  | 2000-10-20 | ICOM | Electotrade | 2000-10-12 | 2000-10-12 | 2000-10-24 | 2000-10-25 | 2000-10-26 |  | Yes | Bogdan Bogodai | 2001-03-13 | 2001-03-13 | 2001-03-13 | 2001-03-27 | 2001-04-10 | K 739 494 | 120 | 0 | 56 | K 739 494 | 300 | 0 | 56 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 75 | 75 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 150 | N/A | Baneasa | FO | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | RBS | [7 empty] | 50/outdoor |  | 1 | BSC21 | BSC BANEASA |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NITA | OK | N/A |  | N/A | N/A | 30N01 Racari-Baneasa |  | 2001-03-08 | Vasile MANEA | Cosmorom | [32 empty] | 130 | com. Racari | Dambovita | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | CR068 | MOARA NOUA | Road Buc-Targoviste(4) | YR067 Racari_RTC | Muntenia | 44 42 53.2 | 25 36 57.8 | 44 42 42.1 | 26 36 14 | Com. Crangasi, sat Moara Noua, sos. Buc-targoviste (DN71), Km 53 | Anastasescu Cornelia - 045/ 612 670/ | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-10-11 | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | DIEKAT | OK | DIEKAT | 2000-10-02 | 2000-10-31 | YesV | 2000-11-15 | Andrei | 2000-11-02 | 2000-10-06 |  |  |  |  | 2000-07-19 |  | 2000-09-18 | 2000-10-04 |  |  |  | 2000-10-20 | ICOM | Electotrade | 2000-10-06 | 2000-10-06 | 2000-11-03 | 2000-11-03 | 2000-11-04 |  | Yes | Bogdan Bogodai | 2001-03-13 | 2001-03-13 | 2001-03-13 | 2001-04-17 | 2001-04-23 | K 739 494 | 120 | 0 | 49 | K 739 494 | 340 | 0 | 49 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 62 | 62 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 124 | ML 15 E 1+0 | Baneasa | MW | 132 | 1.2 | 48 | 60 | 15/89 |  | 4x2/8 | 4U-1 |  |  |  | RBS | [9 empty] | 1 | CR067 | RACARI_DRTV | 312 | 1.2 | 40 | 55 | 15/84 | [6 empty] | 6 | RADCOM | 2000-10-26 | 395 | 2000-11-21 | 2000-11-22 | 2000-11-24 | NITA | OK | 2001-03-13 |  | 2001-03-21 | 2001-04-06 | 30N01 Racari-Baneasa |  | 2001-03-08 | Vasile MANEA | Cosmorom | [32 empty] | 168 | Moara Noua | Dambovita | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CR069 | ILFOVENI | Road Buc-Targoviste(4) | YR067 Racari_RTC | Muntenia | 44 49 39.8 | 25 33 39.7 | 44 49 59.5 | 25 33 24.1 | Sat Ilfoveni,Sos. Bucuresti-Targoviste (DN71), in dreptul indicatorului de iesire din Ilfoveni spre Bratesti | Dulea Ion - sat Cazaci/ | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-10-20 | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | DIEKAT | OK | DIEKAT | 2000-10-02 | 2000-10-31 | YesV | 2000-11-15 | Andrei | 2000-11-02 | 2000-11-22 |  |  |  |  | 2000-07-19 |  | 2000-08-29 | 2000-10-04 |  |  |  | 2000-10-31 | ICOM | DIEKAT | 2000-10-31 | 2000-10-31 | 2000-11-02 | 2000-11-02 | 2000-11-03 |  | Yes | Bogdan Bogodai | 2001-03-13 | 2001-03-13 | 2001-03-13 |  |  | K 739 494 | 160 | 0 | 49 | K 739 494 | 320 | 0 | 49 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 62 | 62 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 124 | ML 15 E 1+0 | Baneasa | MW | 164 | 1.2 | 47/1.2 | 60 | 15/84 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [9 empty] | 1 | CR068 | MOARA NOUA | 344 | 1.2 | 48/1.2 | 60 | 15/89 | [6 empty] | 16 | TRYLON | 2000-11-21 | 396 | 2000-11-21 | 2000-11-22 | 2000-11-24 | NITA | OK | 2001-03-13 |  | 2001-03-21 | 2001-04-06 | 30N01 Racari-Baneasa |  | 2001-03-08 | Vasile MANEA | Cosmorom | [32 empty] | 220 | Ilfoveni | Dambovita | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CR071 | VITANESTI | Road Buc-Alexandria(4) | CR059 Alexandria_RTC | Muntenia | 44 01 02.4 | 25 25 39.1 | 44 01 02.4 | 25 25 39.1 | Com. Vitanesti, sat Cocosu, sos. Alexandria-Bucuresti Km 9+400m | Ceausu Ioana - Com. Vitanesti, sat Cocosu, 047/ 331 093/Ceausu Ioana - 01/ 423 9004 | MAXITE | M | 1 | 2 | 2PBC | [6 empty] | 2000-12-11 | N/A | N/A |  |  |  |  | TN | 50 |  | Shelter | DIEKAT | OK | DIEKAT | 2000-10-20 | 2000-12-11 | YesV | 2000-12-14 | Andrei | 2000-12-13 | 2001-02-28 |  |  |  |  | 2000-07-19 |  | 2000-10-04 | 2000-11-10 |  |  |  | 2000-12-11 | ICOM | ORION | 2000-12-08 | N/A | 2000-12-19 | 2001-01-16 | 2001-02-23 |  | Yes | Ion Soare | 2001-04-13 | 2001-04-13 | 2001-04-13 | 2001-07-05 | 2001-07-11 | AAU | 60 | 0 | 45 | AAU | 235 | 0 | 45 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 58 | 58 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 116 | ML 15 E 1+1 | Baneasa | MW | 233 | 0.6 | 40/0.6 | 53 | 15/89 |  | 4x2/8 | 2U-3 | [13 empty] | 1 | CR059 | ALEXANDRIA_RTC | 52 | 0.6 |  | 65 | 15/84 | [6 empty] | 4* | DIEKAT | 2000-12-11 | 445 | 2000-12-12 | 2001-02-01 | 2001-02-16 | PAUN | OK | 2001-04-13 |  | 2001-05-17 | 2001-05-25 | 30N01 Alexandria-Baneasa |  | OK | Vasile MANEA | Cosmorom | [32 empty] | 81 | Vitanesti | Teleorman | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CR072 | DRAGANESTI-VLASCA_RTC | Road Buc-Alexandria(4) | CR059 Alexandria_RTC | Muntenia | 44 05 53.3 | 25 35 38.8 | 44 05 53.3 | 25 35 38.8 | DN6 Bucuresti-Alexandria, com. Draganesti-Vlasca | Romtelecom/ | MAXITE | M | 1 | 2 | 2PBC | [6 empty] | 2000-10-11 | N/A | N/A |  |  |  | 10 | TE | 75 | Tower | Room | DIEKAT | OK | DIEKAT | 2000-09-01 | 2000-09-15 | YesV | 2000-09-22 | Andrei | 2000-09-28 | 2000-10-06 |  |  |  | N/A | 2000-07-19 |  | 2000-08-01 | 2000-08-21 |  |  |  | 2000-09-18 | YRO | DIEKAT | 2000-09-18 | 2000-09-18 | 2000-09-19 | 2000-09-20 | 2000-09-22 |  | Yes | Ion Soare | 2001-04-13 | 2001-04-17 | 2001-04-17 |  |  | AAU | 70 | 0 | 60 | AAU | 235 | 0 | 60 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 70 | 70 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 130 | ML 15 E 1+0 | Baneasa | MW | 236 | 1.2 | 22/1.2 | 30 | 15/84 |  | 4x2/8 | 2U-3 |  |  |  | TMR 9000 | [9 empty] | 1 | CR071 | VITANESTI | 56 | 1.2 | 40/1.2 | 53 | 15/89 | [6 empty] | 9* | ORION | 2000-12-18 | 444 | 2000-12-18 | 2001-02-01 | 2001-02-16 | PAUN | OK | 2001-04-13 |  | 2001-05-03 | 2001-05-11 | 30N01 Alexandria-Baneasa |  | OK | Vasile MANEA | Cosmorom | [32 empty] | 80 | Draganesti Vlasca | Teleorman | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CR073 | GHIMPATI_RTC | Road Buc-Alexandria(4) | CR059 Alexandria_RTC | Muntenia | 44 11 28.8 | 25 46 55.2 | 44 11 28.8 | 25 46 55.2 | DN 6 Bucuresti Alexandria CONEL CALUGARENI 046/211481 | Romtelecom Mihailesti/ | MAXITE | M | 1 | 2 | 2PBC | [6 empty] | 2000-10-11 | N/A | N/A |  |  |  | 5 | TE | 52 | Tower | Room | DIEKAT | OK | DIEKAT | 2000-09-01 | 2000-09-15 | YesV | 2000-09-22 | Andrei | 2000-09-28 | 2000-12-08 |  |  |  | N/A | 2000-07-20 |  | 2000-07-28 | 2000-08-21 |  |  |  | 2000-09-18 | YRO | DIEKAT | 2000-09-18 | 2000-09-18 | 2000-09-19 | 2000-09-20 | 2000-09-21 |  | Yes | Ion Soare | 2001-04-13 | 2001-04-13 | 2001-04-13 |  |  | AAU | 35 | 0 | 50 | AAU | 210 | 0 | 50 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 120 | ML 15 E 1+0 | Baneasa | MW | 235 | 1.2 | 46 | 60 | 15/89 |  |  | 2U-3 |  |  |  | TMR 9000 | [9 empty] | 1 | CR072 | DRAGANESTI-VLASCA_RTC | 55 | 1.2 | 50 | 60 | 15/84 | [6 empty] | 5 | DIEKAT | 2000-09-18 | 213 | 2000-09-18 | 2001-09-19 | 2001-09-21 | PAUN | OK | 2001-04-13 | PENDING |  |  | 30N01 Alexandria-Baneasa |  | OK | Vasile MANEA | Cosmorom | [32 empty] | 74 | Ghimpati | Giurgiu | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CR074 | MIHAILESTI_RTC | Road Buc-Alexandria(4) | CR059 Alexandria_RTC | Muntenia | 44 19 19 | 25 54 17.3 | 44 19 19 | 25 54 17.3 | DN6 Bucuresti-Alexandria, Romtelecom Mihailesti | Romtelecom/ | MAXITE | M | 1 | 2 | 2PBC | [6 empty] | 2000-10-13 | N/A | N/A |  |  |  | 0 | TE | 45 |  | N/A | DIEKAT | OK | DIEKAT | 2000-10-02 | 2000-10-18 | YesV | 2000-12-05 | Andrei | 2001-05-07 | 2000-12-07 |  |  |  | N/A | 2000-07-24 |  | 2000-08-01 | 2000-10-04 |  |  |  | 2000-10-20 | ICOM | Electotrade | 2000-10-13 | 2000-10-13 | 2000-10-24 | 2000-10-28 | 2000-10-30 |  | Yes | Alexandru Toma | 2001-05-07 | 2001-05-23 | 2001-05-23 | 2001-05-25 | 2001-06-19 | AAU | 45 | 0 | 40 | AAU | 215 | 0 | 40 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 46 | 46 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 92 | ML 15 E 1+0 | Baneasa | MW | 214 | 1.2 | 44 | 51 | 15/84 |  | 4x2/8 | 4U-1 |  |  |  | N/A | [10 empty] | CR073 | GHIMPATI_RTC | 34 | 1.2 | 46 | 60 | 15/89 | [6 empty] | 6 | RADCOM | 2000-10-26 | 294 | 2000-10-13 | 2000-10-14 | 2000-10-30 | PAUN | OK | 2001-05-23 |  | 2001-06-06 | 2001-06-18 | 30N01 Alexandria-Baneasa |  | OK | Vasile MANEA | Cosmorom | [32 empty] | 81 | Mihailesti | Giurgiu | [7 empty] | 2 |  |  | 2
Phase_2 | TM | CR075 | PIELESTI_RTC | Road Pitesti-Craiova(8+2) | CR075 Pielesti_RTC | Oltenia | 44 19 33 | 23 58 25.5 | 44 19 32.8 | 23 58 25.3 | Oficiul postal Pielesti, Km 11 spre Bals | Oficiul postal Pielesti/Marica Valentin - Pielesti, 051/ 269 112 | N/A | N/A | N/A | N/A | N/A | [7 empty] | N/A | N/A |  |  |  | N/A | TN | 9 | 9m pylon | N/A | ISAF | OK | TEHNOROB | 2000-10-12 | 2000-10-25 | YesV | 2000-11-02 | Doru | 2000-10-25 | 2000-11-10 |  |  |  |  | 2000-08-03 |  | 2000-09-05 | 2000-09-25 |  |  |  | 2000-11-21 | ICOM | TRY | N/A | N/A | 2000-11-21 | N/A | N/A |  | Yes | N/A | 2001-02-17 | 2001-02-17 | 2001-02-18 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A | Craiova | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | 2U-3 |  |  |  | TMR 9000 | 40075 | [6 empty] | 40 2 p outdoor/ |  |  | BSC31 | BSC TIMISOARA | N/A | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PAUN | OK | N/A |  | N/A | N/A | 30N01 Pielesti-Craiova |  | 2001-02-21 | SORIN UNTARU | N/A | [32 empty] | 160 | Craiova | Dolj | [7 empty] | Site Near=Insertion Point
Phase_2 | TM | CR076 | SILOZ ALBOTA | Road Pitesti-Craiova(8+2) | CR013 Centru_RTC | Oltenia | 44 47 39 | 24 51 33 | 44 48 32.4 | 24 51 52.6 | Statiunea pt. Cercetari plante tehnice Albota Pitesti, DN 65, Km121, Pitesti - Slatina |  | N/A | N/A | N/A | N/A | N/A | [7 empty] | N/A | N/A |  |  |  | N/A | S | 40 | C3m | N/A | ISAF | OK | DIEKAT | 2000-09-11 | 2000-09-29 | YesV | 2000-10-06 | Doru | 2000-11-10 | 2000-10-13 |  |  |  | OK | 2001-07-16 |  | 2000-08-21 | 2000-09-11 |  |  |  | 2000-10-24 | ICOM | SVF | N/A | N/A | 2000-10-24 | N/A | N/A |  | Yes | N/A | 2001-02-23 | 2001-02-23 | 2001-02-23 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | ML 23 E 1+1 | Baneasa | MW | 19 | 0.6 | 42.5 | 20 | 23/56 | YES | 4x2/8 | 4U-1 |  |  |  | TMR 9000 | [9 empty] | 1 | CR016 | REPUBLICII |  | 0.6 |  | 35 | 23/58 | [6 empty] | 11 | SVF | 2000-10-24 | 343 | 2000-10-24 | 2000-11-22 | 2000-11-24 | PAUN | OK | 2001-02-23 | PENDING |  |  | N/A |  | N/A | Cristian CROITOR | Cosmorom | [32 empty] | 350 | Albota | Arges | [6 empty] | 1 | 2 |  | 1 | 2
Phase_2 | CS | CR077 | BEHARCA | Road Craiova-Turnu Severin(12+1) | CR079 Filiasi_RTC | Oltenia | 44 26 31 | 23 40 59.8 | 44 26 28.7 | 23 41 11.7 | Com. Almaj, sat Beharca, Km 16+300m, sos. Craiova-Filiasi(E70) | Potirniche D. Iancu, com. Almas, sat Beharca/Potirniche D. Iancu, com. Almas, sat Beharca | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-11-17 | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | DIEKAT | OK | DIEKAT | 2000-10-16 | 2000-12-07 | YesV | 2000-12-14 | Andrei | 2000-12-13 | 2000-12-20 |  |  |  |  | 2000-08-03 |  | 2000-10-04 | 2000-10-30 |  |  |  | 2000-12-11 | ICOM | DIEKAT | 2000-12-08 | 2000-12-08 | 2000-12-19 | 2000-12-20 | 2001-01-01 |  | Yes | Alexandru Toma | 2001-04-30 | 2001-04-30 | 2001-04-30 | 2001-05-15 | 2001-05-25 | K 739 494 | 110 | 0 | 49 | K 739 494 | 300 | 0 | 49 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 23 E 1+0 | Craiova | MW | 318 | 1.2 | 48/1.2 | 58 | 23/58 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [9 empty] | 1 | CR078 | BRADESTI | 139 | 1.2 | 49/1.2 | 60 | 23/56 | [6 empty] | 52* | ORION | 2001-04-03 | 815 | 2001-04-04 | 2001-04-04 | 2001-04-12 | DINCA | OK | 2001-04-30 |  | 2001-05-10 | 2001-05-25 | 30N02 Filiasi-Craiova |  | 2001-02-23 | Cristian CROITOR | Petrica BURGHIU | [32 empty] | 100 | Beharca | Dolj | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CR078 | BRADESTI | Road Craiova-Turnu Severin(12+1) | CR079 Filiasi_RTC | Oltenia | 44 30 08.5 | 23 36 44.3 | 44 30 08.5 | 23 36 44.3 | Com. Bradesti, sat Valea Rea | Cenciu Marin - crescatorie iepuri, com. Bradesti/Cenciu Marin - crescatorie iepuri, com. Bradesti | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-11-17 | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | DUAL | OK | DUAL | 2000-10-16 | 2000-12-18 | YesV | 2000-12-20 | Andrei | 2001-01-11 | 2001-01-10 |  |  |  |  | 2000-08-03 |  | 2000-10-06 | 2000-11-02 |  |  |  | 2000-12-18 | ICOM | ORION | 2000-12-18 | 2000-12-18 | 2000-12-22 | 2001-01-15 | 2001-01-17 |  | Yes | Alexandru Toma | 2001-04-30 | 2001-04-30 | 2001-04-30 | 2001-05-15 | 2001-05-25 | K 739 494 | 135 | 0 | 44 | K 739 494 | 300 | 0 | 44 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Craiova | MW | 315 | 0.6 | 49/1.2 | 60 | 15/84 |  |  | 2U-3 |  |  |  | RBS | [9 empty] | 1 | CR218 | FILIASI DEAL | 135 | 0.6 | 49 | 70 | 15/89 | [6 empty] | 52* | ORION | 2001-04-03 | 814 | 2001-04-04 | 2001-04-04 | 2001-04-12 | DINCA | OK | 2001-04-30 |  | 2001-05-21 | 2001-05-25 | 30N02 Filiasi-Craiova |  | 2001-02-23 | Cristian CROITOR | Petrica BURGHIU | [32 empty] | 121 | Valea Rea | Dolj | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | TM | CR079 | FILIASI_RTC | Road Craiova-Turnu Severin(12+1) | CR079 Filiasi_RTC | Oltenia | 44 33 18.5 | 23 31 10.8 | 44 33 22.21 | 23 30 53.29 | Str. Racoteanu nr.198 | Romtelecom/Dl. Dorin Popescu (sef transmisiuni) | N/A | N/A | N/A | N/A | N/A | [12 empty] | N/A | B | 12 | C4.8m | Room/TMR9202 | SETRACO | OK | SETRACO | 2001-03-21 | 2001-04-03 | YesV | 2001-04-05 | Andrei | 2001-04-06 | 2001-04-19 |  |  |  |  | 2000-11-17 |  | 2000-12-22 | 2001-03-20 |  |  |  | 2001-04-03 | ICOM | ORION | N/A | N/A | 2001-04-04 | N/A | N/A |  | Yes | N/A | 2001-04-30 | 2001-04-30 | 2001-04-30 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A | Craiova | FO | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | TMR 9202 | 40079 | 2001-04-04 | [5 empty] | 10/Indoor |  | 1 | BSC31 | BSC TIMISOARA | N/A | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | RADU | OK | N/A |  | N/A | N/A | N/A |  | 2001-02-23 | Marius LUNGU | Cosmorom | [32 empty] | 120 | Filiasi | Dolj | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | CR080 | CAP BUTOIESTI | Road Craiova-Turnu Severin(12+1) | CR079 Filiasi_RTC | Oltenia | 44 34 47.3 | 23 23 19.1 | 44 34 45.5 | 23 23 28 | CAP com. Butoiesti, sat Jugastru | CAP Butoiesti/Cinciu Razvan - CAP Butoiesti, 092/ 292 902 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-10-20 | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | SVF | OK | SVF | 2000-09-18 | 2000-10-20 | YesV | 2000-11-13 | Andrei | 2000-10-24 | 2000-11-22 |  |  |  |  | 2000-08-03 |  | 2000-09-21 | 2000-10-03 |  |  |  | 2000-10-23 | ICOM | SVF | 2000-10-23 | 2000-10-23 | 2000-10-24 | 2000-10-25 | 2000-10-30 |  | Yes | Alexandru Toma | 2001-04-30 | 2001-04-29 | 2001-04-29 | 2001-05-23 | 2001-05-31 | K 739 494 | 105 | 0 | 49.5 | K 739 494 | 290 | 0 | 49.5 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 70 | 70 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 140 | ML 15 E 1+0 | Craiova | MW | 105 | 1.2 | 47/1.2 | 70 | 15/84 |  |  | 4U-1 |  |  |  | RBS | [9 empty] | 1 | CR218 | FILIASI DEAL | 281 | 1.2 | 48 | 70 | 15/89 | [6 empty] | 52* | ORION | 2001-04-03 | 813 | 2001-04-04 | 2001-04-04 | 2001-04-11 | DINCA | OK | 2001-04-29 |  | 2001-05-21 | 2001-05-25 | 30N02 Filiasi-Craiova |  | 2001-02-23 | Cristian CROITOR | CATALINA CIOCAN | [32 empty] | 116 | Butoiesti | Mehedinti | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CR081 | LUNCA BANULUI | Road Craiova-Turnu Severin(12+1) | CR079 Filiasi_RTC | Oltenia | 44 35 56.3 | 23 17 23.4 | 44 36 02 | 23 17 23 | Com. Stangaceana, Km. 9 Filiasi-Strehaia | SLAVYA CONSTRUCT SRL Turceni, bl.43, sc.1, et.3 ap.13/Stefanoiu Eugen - administrator | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-11-17 | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | SVF | OK | SVF | 2000-10-06 | 2000-11-25 | YesV | 2000-11-28 | Andrei | 2001-01-09 | 2000-12-07 |  |  |  |  | 2000-08-03 |  | 2000-09-28 | 2000-10-16 |  |  |  | 2000-11-01 | ICOM | SVF | 2000-10-31 | 2000-11-01 | 2000-11-01 | 2000-11-20 | 2000-11-25 |  | Yes | Alexandru Toma | 2001-05-01 | 2001-04-29 | 2001-04-29 | 2001-05-09 | 2001-05-28 | K 739 494 | 110 | 0 | 49.5 | K 739 494 | 295 | 0 | 49.5 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 70 | 70 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 140 | ML 23 E 1+0 | Craiova | MW | 105 | 1.2 | 48 | 70 | 23/58 |  | 4x2/8 | 4U-1 |  |  |  | RBS | [9 empty] | 1 | CR080 | CAP BUTOIESTI | 285 | 1.2 | 47 | 70 | 23/56 | [6 empty] | 12 | SVF | 2001-01-11 | 355 | 2000-11-01 | 2000-11-01 | 2000-11-02 | DINCA | OK | 2001-04-29 |  | 2001-05-10 | 2001-05-25 | 30N02 Filiasi-Craiova |  | 2001-02-23 | Cristian CROITOR | Cosmorom | [32 empty] | 120 | Lunca Banului | Mehedinti | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CR082 | STREHAIA | Road Craiova-Turnu Severin(12+1) | CR052 Turnul Severin_RTC | Oltenia | 44 37 23.3 | 23 11 58.8 | 44 37 23.3 | 23 11 58.8 | Sectia de drumuri si poduri DJOP, Str. Republicii 219 | Sectia de drumuri si poduri DJOP Mehedinti, Strehaia/Stinga Mircea = DJOP Str. Republicii nr.219, Strehaia, 095/ 628 525, 052/ 370 024 | MUTAT | M | C+ | 2 | 2101 | [6 empty] | 2000-11-17 | N/A | N/A |  |  |  |  | TN | 40 |  | N/A | IASSID | OK | IASSID | 2000-10-20 | 2000-11-27 | YesV | 2000-12-13 | Andrei | 2001-01-17 | 2000-12-14 |  |  |  |  | 2000-08-03 |  | 2000-09-26 | 2000-10-24 |  |  |  | 2000-12-15 | ICOM | ORION | 2000-11-29 | 2000-12-15 | 2000-12-22 | 2001-01-16 | 2001-01-17 |  | Yes |  | 2101 MOVED TO BV094 |  |  |  |  | K 739 494 | 105 | 0 | 35 | K 739 494 | 245 | 0 | 35 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 120 | ML 15 E 1+0 | Craiova | MW | 249 | 1.2 | 37/1.2 | 65 | [7 empty] | N/A | [10 empty] | CR083 | TIMNA | 69 | 1.2 | 49/1.2 | 75 | [20 empty] | 30N01 Severin-Craiova |  | 2001-02-06 | Cristian CROITOR | Cosmorom | [32 empty] | 142 | Strehaia | Mehedinti | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CR083 | TIMNA | Road Craiova-Turnu Severin(12+1) | CR052 Turnul Severin_RTC | Oltenia | 44 35 22.3 | 23 03 13.3 | 44 35 26.1 | 23 04 46.1 | Extravilan sat Valea Ursului | Proprietar Anghelescu Gheorghe/Anghelescu Gheorghe | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-11-17 | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | IASSID | OK | IASSID | 2000-10-16 | 2000-12-30 | YesV | 2001-01-30 | Andrei | 2001-02-26 | 2001-02-01 |  |  |  |  | 2000-08-03 |  | 2000-10-04 | 2000-10-24 | [6 empty] | 2001-01-26 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 70 | 0 | 47.5 | K 739 494 | 275 | 0 | 47.5 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 70 | 70 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 140 | ML 15 E 1+0 | Craiova | MW | 263 | 1.2 | 49/1.2 | 75 | [7 empty] | RBS | [10 empty] | CR084 | IGIROASA | 82 | 1.2 | 50/1.2 | 62 | [20 empty] | 30N01 Severin-Craiova |  | 2001-02-06 | Cristian CROITOR | Cosmorom | [32 empty] | 184 | com. Timna | Mehedinti | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CR084 | IGIROASA | Road Craiova-Turnu Severin(12+1) | CR052 Turnul Severin_RTC | Oltenia | 44 34 44.5 | 22 57 16.9 | 44 34 44.5 | 22 57 16.9 | Km 28 spre Turnu Severin, sat Igiroasa | Fam. Iliescu - Tirgoviste, Dimmbovita/Fam. Iliescu | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-10-20 | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | ISAF | OK | FIBEC | 2000-09-25 | 2000-12-07 | YesV | 2000-12-14 | Andrei | 2001-01-11 | 2000-12-20 |  |  |  |  | 2000-08-03 |  | 2000-09-13 | 2000-09-26 |  |  |  | 2000-12-11 | ICOM | DIEKAT | 2000-12-08 | 2000-12-18 | 2000-12-19 | 2000-12-20 | 2000-12-28 |  | Yes | Alexandru Toma | 2001-03-13 | 2001-03-13 | 2001-03-13 |  |  | K 739 494 | 80 | 0 | 47 | K 739 494 | 300 | 0 | 47 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Craiova | MW | 282 | 1.2 | 50/1.2 | 62 | 15/89 | [6 empty] | RBS | [10 empty] | CR085 | BALOTA_DRTV | 102 | 0.6 | 75/1.2 | 60 | 15/84 | [6 empty] | 8* | SVF | 2000-12-15 | 467 | 2000-12-18 | 2001-01-15 | 2001-01-18 | DINCA | OK | 2001-03-13 | PENDING |  |  | 30N01 Severin-Craiova |  | 2001-02-06 | Cristian CROITOR | Cosmorom | [32 empty] | 264 | Igiroasa | Mehedinti | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CR085 | BALOTA_DRTV | Road Craiova-Turnu Severin(12+1) | CR052 Turnul Severin_RTC | Oltenia | 44 36 01.2 | 22 49 09.6 | 44 36 01.2 | 22 49 09.6 | DRTV Balota | Directia DRTV Timisoara - Aleea Demetriade nr.1 Timisoara/Iliescu Marin, 092/ 979 297 - Stochina Dorin, sef statie, 092/ 424 630 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-11-17 | N/A | N/A |  |  |  | 0 | TE | 206 |  | N/A | ISAF | OK | ISAF | 2000-10-26 | 2000-11-29 | YesV | 2001-04-19 | Andrei | 2001-01-09 | 2001-04-19 |  |  |  |  | 2000-08-03 |  | 2000-09-08 | 2000-10-20 |  |  |  | 2000-12-15 | ICOM | SVF | 2000-11-30 | 2000-12-15 | 2000-12-19 | 2001-01-08 | 2001-01-12 |  | Yes | Alexandru Toma | 2001-03-13 | 2001-03-13 | 2001-03-13 | 2001-06-07 | 2001-06-19 | K 739 494 | 75 | 0 | 61.5 | K 739 494 | 300 | 0 | 61.5 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 77 | 77 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 154 | ML 15 E 1+0 | Craiova | MW | 277 | 0.6c | 75/1.2 | 60 | 15/84h |  | 4x2/8 | 4U-1 |  |  |  | RBS | [9 empty] | 1 | CR086 | SILOZ SIMIAN | 97 | 0.6c | 47.45 | 30 | 15/89h | [6 empty] | 8* | SVF | 2000-12-15 | 468 | 2001-02-22 | 2001-02-22 | 2001-03-01 | DINCA | OK | 2001-03-13 |  | 2001-05-03 | 2001-05-11 | 30N01 Severin-Craiova |  | 2001-02-06 | Cristian CROITOR | Petrica BURGHIU | [32 empty] | 361 | Balota | Mehedinti | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CR086 | SILOZ SIMIAN | Road Craiova-Turnu Severin(12+1) | CR052 Turnul Severin_RTC | Oltenia | 44 36 30.1 | 22 43 47 | 44 36 30.1 | 22 43 47 | Terasa superioara si inferioara a silozului din incinta AGROSEM Mehedinti | SC SEMROM OLTENIA SA - Craiova, str. Nicolae Romanescu nr.39, sucursala AGROSEM Mehedinti, str. Craiovei nr.271, com. Simian/Dir. Andritescu Emanoil, 094/ 625 830, 094/ 625 831, 052/ 338 404, 052/ 338 401 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-11-17 | Yes | N/A |  |  |  | 31 | S | 44 | T3.5m+T3.5m | N/A | ISAF | OK | ISAF | 2000-10-30 | 2000-12-15 | YesV | 2000-12-20 | Andrei | 2001-01-09 | 2001-01-10 |  |  |  |  | 2000-08-03 |  | 2000-10-16 | 2000-10-30 |  |  |  | 2000-12-15 | ICOM | SVF | 2000-12-14 | 2000-12-14 | 2000-12-19 | 2001-01-18 | 2001-01-19 |  | Yes | Alexandru Toma | 2001-03-13 | 2001-03-13 | 2001-03-13 |  |  | K 739 494 | 90 | 0 | 46.15 | K 739 494 | 300 | 0 | 46.2 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 26 | 26 | 7/8" | 26 | 26 | 7/8" | N/A | N/A | N/A |  |  |  | 104 | ML 23 E 1+1 | Craiova | MW | 286 | 0.6 | 47.48/0.6 | 30 | 23/58 | YES | 4x2/8 | 4U-1 | 4U-1 |  |  | RBS | [9 empty] | 1 | CR052 | TURNU SEVERIN_RTC | 106 | 0.6 | 32.5/1.2 | 42 | 23/56 | [6 empty] | 8* | SVF | 2000-12-15 | 465 | 2001-02-22 | 2001-02-22 | 2001-03-01 | DINCA | OK | 2001-03-13 | PENDING |  |  | 30N01 Severin-Craiova |  | 2001-02-06 | Cristian CROITOR | Cosmorom | [32 empty] | 57 | Turnu Severin | Mehedinti | [6 empty] | 1 | 2 |  | 1 | 2
Phase_2 | CS | CR087 | FABRICA DE BERE | Road Craiova-Turnu Severin(12+1) | CR025 Amarandia_RTC | Oltenia | 44 20 58.3 | 23 45 29.3 | 44 20 58.3 | 23 45 29.3 | Str. Nicolae Titulescu nr.176 | Dir. Ghita Dan - 093/ 388 511/Badescu Traian - 051/ 431 292 | 2101 | M | C+ | 2 | 2101 | [12 empty] | 30 | S | 42 | C8m | N/A | DIEKAT | OK | DIEKAT | 2001-01-19 | 2001-02-05 | YesV | 2001-02-14 | Andrei | 2001-02-21 | 2001-02-26 |  |  |  |  | 2000-08-10 |  | 2001-01-08 | 2001-02-01 |  |  |  |  | ICOM |  | 2001-02-06 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 140 | 0 | 46.5 | K 739 494 | 330 | 0 | 46.5 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 58 | 58 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 116 | ML 38 E 1+0 | Craiova | MW | 146 | 0.6 | 47.5/0.6 | 59 | [7 empty] | RBS | [10 empty] | CR026 | SEVERINULUI | 327 | 0.6 | 34/0.6 | [21 empty] | 30N01 Amarandia-Craiova |  | OK | Cristian CROITOR | Cosmorom | [32 empty] | 95 | Craiova | Dolj | [7 empty] | 2 |  | 1 | 2
Phase_2 | CS | CR090 | PORTILE DE FIER_1 | Road Turnu Severin-Orsova(2) | CR094 Orsova_RTC | Oltenia | 44 40 28.7 | 22 31 58.9 | 44 40 29.2 | 22 31 57.7 | Turn de control - Hidrocentrala Portile de Fier 1 | Sucursala Hidrocentrale Portile de Fier - Str. I.G. Bizicescu nr.2 Drobeta Turnu Severin/Dir. I. Trimbitas, Cazanacli Cristian - Hidrocentrala Portile de Fier 1 - 092/ 21 20 18 si 052/311627 | MAXITE | M | 1 | 2 | 2PBC | [7 empty] | N/A | N/A |  |  |  | 35 | B | 35 | C3.5m+C3.5m+C3m | N/A | ISAF | OK | CRAAL | 2001-03-08 | 2001-04-05 | YesV | 2001-05-16 | Adi | 2001-05-07 | 2001-05-23 |  |  |  |  | 2000-09-20 |  | 2000-11-13 | 2001-03-27 |  |  |  | 2001-04-10 | ICOM | ORION | 2001-04-10 | 2001-04-10 | 2001-04-11 | 2001-06-05 | 2001-06-06 | PAUN | Yes | Bogdan Bogodai | 2001-06-11 | 2001-05-12 | 2001-05-12 |  |  | AAU | 135 | 0 | 40 | AAU | 315 | 0 | 40 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 14 | 14 | 1/2" | 11 | 11 | 1/2" | N/A | N/A | N/A |  |  |  | 50 | ML 15 E 1+0 | Craiova | MW | 305 | 0.6 | 39 | 10.5 | 15/84 |  |  | 2U-3 | [13 empty] | 1 | CR091 | ALION | 125 | 0.6 | 27.5 | 30 | 15/89 | [6 empty] | 58* | ORION | 2001-04-10 | 843 | 2001-04-11 | 2001-04-11 | 2001-06-07 | PAUN | OK | 2001-06-11 |  | 2001-07-12 |  | 30N01 Orsova-Craiova |  | 2001-02-06 | SORIN UNTARU | Cosmorom | [32 empty] | 74 | Drobeta Turnu Severin | Mehedinti | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CR091 | ALION | Road Turnu Severin-Orsova(2) | CR094 Orsova_RTC | Oltenia | 44 43 20.2 | 22 26 08.7 | 44 43 20.2 | 22 26 08.7 | Dealul Alion | /Medjind Danila - str. Cernei nr.24, Orsova, 052/ 362 279 | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  |  | TN | 30 |  | N/A | ISAF | OK | SVF | 2000-10-20 | 2000-12-08 | YesV | 2001-01-24 | Andrei | 2001-01-11 | 2000-01-24 |  |  |  |  | 2000-09-25 |  | 2000-11-07 | OK |  |  |  | 2000-11-30 | ICOM | SVF | 2000-11-30 | 2000-11-30 | 2000-11-30 | 2000-12-02 | 2000-12-21 |  | Yes | Alexandru Toma | 2001-03-14 | 2001-03-14 | 2001-03-14 |  |  | K 739 494 | 310 | 0 | 28.5 | K 739 494 | 110 | #N/A | 28.5 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 31 | 31 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 62 | ML 38 E 1+0 | Craiova | MW | 282 | 0.3 | 24/0.6 | 26 | 38/18 |  |  | 4U-1 |  |  |  | RBS | [9 empty] | 1 | CR094 | ORSOVA_RTC | 102 | 0.3 | 13.9/0.3 | 20 | 38/14 | [6 empty] | 9* | ORION | 2000-12-18 | 420 | 2000-12-18 | 2001-01-05 | 2001-03-11 | DINCA | OK | 2001-03-14 |  | 2001-06-19 | 2001-07-10 | 30N01 Orsova-Craiova |  | 2001-02-06 | SORIN UNTARU | Cosmorom | [32 empty] | 316 | Alion | Mehedinti | [7 empty] | 2 |  | 1 | 2
Phase_2 | CS | CR092 | HOTEL DIERNA | Orsova(1+1) | CR094 Orsova_RTC | Oltenia | 44 43 26.1 | 22 23 54.2 | 44 43 26.1 | 22 23 54.2 | Hotel Dierna, str. 1 Decembrie 1918, nr.18 | SC Unita SA - Timisoara/Cotea ion - Hotel Dierna, Orsova, 052/ 361 875 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-11-17 | Yes | N/A |  |  |  | 28 | B | 37 | T6m+T6m | N/A | SVF | OK | COMARK | 2000-11-03 | 2000-11-29 | YesV | 2000-12-13 | Andrei | 2001-01-11 | 2000-12-14 |  |  |  |  | 2000-09-18 |  | OK | 2000-11-03 |  |  |  | 2000-11-30 | ICOM | SVF | 2000-11-30 | 2000-11-30 | 2000-11-30 | 2000-11-28 | 2000-12-04 |  | Yes | Alexandru Toma | 2001-03-14 | 2001-03-14 | 2001-03-14 |  |  | K 739 494 | 90 | 0 | 32.5 | K 739 494 | 210 | 0 | 32.5 | K 739 494 | 305 | 0 | 32.5 |  |  |  |  | N/A | 33 | 33 | 7/8" | 10 | 10 | 7/8" | 10 | 10 | 7/8" |  |  |  | 106 | ML 38 E 1+0 | Craiova | MW | 92 | 0.3 | 32.1/0.3 | 33 | 38/14 |  |  | 2U-3 |  |  |  | RBS | [9 empty] | 1 | CR091 | ALION | 272 | 0.3 | 20 | 35 | 38/18 | [6 empty] | 9* | ORION | 2000-12-18 | 441 | 2000-12-18 | 2001-01-05 | 2001-01-15 | DINCA | OK | 2001-03-14 |  | 2001-06-19 | 2001-07-10 | 30N01 Orsova-Craiova |  | 2001-02-06 | SORIN UNTARU | Cosmorom | [32 empty] | 78 | Orsova | Mehedinti | [7 empty] | 2 |  |  | 2
Phase_2 | TM | CR094 | ORSOVA_RTC | Orsova(1+1) | CR094 Orsova_RTC | Oltenia | 44 43 41.6 | 22 24 00.5 | 44 43 41.6 | 22 24 00.5 | RTC Orsova | Romtelecom/ | N/A | N/A | N/A | N/A | N/A | [6 empty] | N/A | N/A | N/A |  |  |  | N/A | B | 12 | S2m | Room | SVF | OK | SVF | 2000-10-26 | 2000-11-22 | YesV | 2000-12-15 | Andrei | 2001-03-14 | 2000-12-20 |  |  |  | N/A | 2000-09-22 |  | 2000-10-04 | 2000-11-15 |  |  |  | 2000-12-18 | ICOM | ORION | N/A | N/A | 2001-01-05 | N/A | N/A |  | Yes | N/A | 2001-03-14 | 2001-03-14 | 2001-03-14 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A | Craiova | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | 4U-1 |  |  |  | Indoor Comteck | 40094 | [6 empty] | 4/Indoor |  | 1 | BSC31 | BSC TIMISOARA | N/A | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | VLAD | OK | N/A |  | N/A | N/A | N/A |  | 2001-02-06 | SORIN UNTARU | Cosmorom | [32 empty] | 78 | Orsova | Mehedinti | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | CR096 | BARBATEASCA | Road Bucuresti-Buftea-Ploiesti(6) | BX523 Ploiesti Vest_CTA | Muntenia | 44 38 14.5 | 25 54 10.1 | 44 38 13.4 | 25 54 11.1 | Iesire din sat Barbateasca spre Butimanu | Stan Dumitra - sat Barbateasca, com. Crevedia/Stan Dumitra - sat Barbateasca, com. Crevedia | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-12-11 | N/A | N/A |  |  |  | 0 | TN | 50 |  | N/A | PROTELCO | OK | MMK | 2000-11-03 | 2001-01-23 | YesV | 2001-02-06 | Mugur | 2001-01-17 | 2001-02-07 |  |  |  | OK | 2000-09-27 |  | 2000-10-30 | 2000-11-10 | [6 empty] | 2001-01-26 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 170 | 0 | 47 | K 739 494 | 330 | 0 | 47 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 58 | 58 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 116 | ML 15 E 1+0 | Baneasa | MW | 355 | 1.2 | 49/1.2 | 60 | [7 empty] | RBS | XC30523/2 | [9 empty] | CR097 | BUJOREANCA | 175 | 1.2 | 39/1.2 | 50 | [20 empty] | 30N07 Ploiesti Vest-Baneasa |  | OK | Cristian CROITOR | Petrica BURGHIU | [32 empty] | 120 | Barbateasca | Dambovita | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CR097 | BUJOREANCA | Road Bucuresti-Buftea-Ploiesti(6) | BX523 Ploiesti Vest_CTA | Muntenia | 44 43 55.5 | 25 53 25.9 | 44 43 49.9 | 25 52 53 | Sat Bujoreanca nr.850, com. Cornesti CONEL MORENI 045/666009 | Preda O. Dumitru - sat Bujoreanca, com. Cornesti, nr.850/Graniceru Ion - 093/386 679 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-12-11 | N/A | N/A |  |  |  | 0 | TN | 40 |  | N/A | PROTELCO | OK | SVF | 2000-10-26 | 2000-11-25 | YesV | 2000-12-06 | Mugur | 2001-01-09 | 2001-02-07 |  |  |  | OK | 2000-10-02 |  | 2000-10-25 | 2001-03-14 |  |  |  | 2000-11-23 | ICOM | SVF | 2000-11-23 | 2000-11-23 | 2000-11-24 | 2000-11-24 | 2000-11-27 |  | Yes | Alexandru Toma | 2001-04-13 | 2001-04-13 | 2001-04-13 |  |  | K 739 494 | 0 | 0 | 38 | K 739 494 | 170 | 0 | 38 | K 739 494 | 260 | 0 | 39 |  |  |  |  | N/A | 49 | 49 | 1 1/4" | 49 | 49 | 1 1/4" | 49 | 49 | 1 1/4" |  |  |  | 294 | ML 15 E 1+0 | Baneasa | MW | 5 | 1.2 | 39/1.2 | 50 | 15/84 |  | 4X2/8 | 4U-1 |  |  |  | RBS | [9 empty] | 1 | CR098 | COCORASTI | 186 | 1.2 | 47/1.2 | 60 | 15/89 | [6 empty] | 49* | DIEKAT | 2001-03-26 | 760 | 2001-03-27 | 2001-03-27 | 2001-04-04 | PITURCESCU | OK | 2001-04-13 |  | 2001-05-03 | 2001-05-11 | 30N06 Pliesti Vest-Baneasa |  | 2001-03-02 | Cristian CROITOR | [33 empty] | 126 | Bujoreanca | Dambovita | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CR098 | COCORASTI | Road Bucuresti-Buftea-Ploiesti(6) | BX523 Ploiesti Vest_CTA | Muntenia | 44 5018.5 | 25 54 18.2 | 44 49 48.5 | 25 53 45.7 | Cocorasti Colt(stadion) | Primaria Manesti, Judetul Prahova/Consilier comunal Pantazi Ioan - Cocorasti Colt, 094/ 374 056 | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  | 0 | TN | 50 |  | N/A | PROTELCO | OK | EL-MONT | 2001-02-15 | 2001-03-23 | YesV | 2001-04-04 | Mugur | 2001-04-17 | 2001-04-06 |  |  |  | OK | 2000-09-27 |  | 2001-02-01 | 2001-03-14 |  |  |  | 2001-03-26 | ICOM | DIEKAT | 2001-03-22 | 2001-03-22 | 2001-03-27 | 2001-03-27 | 2001-04-02 |  | Prov | Alexandru Toma | 2001-04-12 | 2001-04-12 | 2001-04-12 | 2001-05-23 | 2001-05-28 | K 739 494 | 0 | 0 | 48 | K 739 494 | 170 | 0 | 48 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 |  | Baneasa | MW | 32 | 0.6 | 47/0.6 | 60 | 15/89 |  |  | 2U-3 |  |  |  | RBS | [9 empty] | 1 | BX503 | PLOIESTI VEST | 212 | 0.6 | 30/0.6 | 50 | 15/84 | [6 empty] | 49* | DIEKAT | 2001-03-26 | 761 | 2001-03-27 | 2001-03-27 | 2001-04-04 | VLAD | OK | 2001-04-12 | PENDING |  |  | 30N06 Pliesti Vest-Baneasa |  | 2001-03-02 | Cristian CROITOR | COSMOROM | [32 empty] | 160 | Cocorasti Colt | Prahova | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CR099 | GIURGIU | Giurgiu(2) | CR001Giurgiu_CTA2 | Muntenia | 43 53 33.9 | 25 57 55.9 | 43 53 33.2 | 25 57 55.2 | Str. Bucuresti, bl.6/300 | As. De proprietari nr.19 - str. Vasile Alecsandri nr.19 bl. 1/300/Dinicu Gheorghe - str. Vasile Alecsandri nr.19 bl,1/300, 046/ 216 532 | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-12-11 | N/A | N/A |  |  |  | 26.6 | B | 29.6 | C4m+C4m | Room | PROTELCO | OK | GIRARDOT | 2000-10-16 | 2000-10-26 | YesV | 2000-11-08 | Doru | 2000-11-10 | 2000-11-10 |  |  |  |  | 2000-08-15 |  | 2000-09-27 | 2000-10-16 |  |  |  | 2000-10-26 | ICOM | Electotrade | 2000-10-26 | 2000-10-27 | 2000-10-27 | 2000-10-27 | 2000-10-30 |  | Yes | Ion Soare | 2001-03-05 | 2001-03-05 | 2001-03-05 |  |  | K 739 494 | 7 | 0 | 31.7 | K 739 494 | 139 | 0 | 31.5 | K 739 494 | 239 | 0 | 32.1 |  |  |  |  | N/A | 20 | 20 | 7/8" | 20 | 20 | 7/8" | 28 | 28 | 7/8" |  |  |  | 136 | ML 23 E 1+0 | Baneasa | MW | 7 | 0.6 | 31 | 19.5 | 23/56 |  | 4X2/8 | 4U-1+2U-3 | [13 empty] | 1 | CR001 | GIURGIU_CTA2 | 197 | 0.6 | 30 | 65 | 23/58 | [6 empty] | 6* | RADCOM | 2000-10-26 | 349 | 2000-10-27 | 2000-10-28 | 2000-10-30 | VLAD | OK | 2001-05-03 |  | 2001-04-11 | 2001-04-17 | 30N02 Giurgiu-Baneasa |  | 2001-02-26 | Cristian CROITOR | Cosmorom | [32 empty] | 18 | Giurgiu | Giurgiu | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CR100 | SILOZ ZAHARUL | Road Craiova-Calafat(11) | CR024 Unirii_RTC | Oltenia | 44 15 16.2 | 23 46 58.3 | 44 15 16.2 | 23 46 58.3 | SC Zaharul SA, com. Podari |  | 2101 | M | C+ | 2 | 2101 | [12 empty] | 30 | B | 30 | T4.5m | N/A | DIEKAT | OK | DUAL | 2000-12-14 | 2001-01-15 | YesV | 2001-02-06 | Andrei | 2001-01-23 | 2001-02-07 |  |  |  | 2000-10-25 | 2000-11-14 |  | 2000-11-29 | 2000-12-15 | [6 empty] | 2001-01-30 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 40 | 0 | 35.3 | K 739 494 | 210 | 0 | 35.3 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 15 | 15 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 30 | ML 15 E 1+0 | Craiova | MW | 11 |  | 34 | 15 | [7 empty] | RBS | [10 empty] | CR031 | ANTONESCU | 190 | 0.6 | 43/0.6 | 21 | [20 empty] | LOCAL |  | OK | Marius LUNGU | Cosmorom | [32 empty] | 78 | Podari | Dolj | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CR101 | FERMA GREACA | Road Craiova-Calafat(11) | CR024 Unirii_RTC | Oltenia | 44 12 45.9 | 23 40 16.38 | 44 12 45.9 | 23 40 16.4 | Ferma Greaca, soseaua Craiova-Calafat Km16 | SC AGROIND CRAIOVA SA/Ing.Mocanu Constantin-sef ferma; Director Calota-tel.051/124 308, 095 654 574 | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | DIEKAT | OK | DUAL | 2000-12-15 | 2001-02-16 | YesV | 2001-02-21 | Andrei | 2001-03-26 | 2001-02-28 |  |  |  |  | 2000-11-14 |  | 2000-12-11 | 2001-01-09 | [6 empty] | 2001-02-19 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 60 | 0 | 50 | K 739 494 | 220 | 0 | 50 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+1 | Craiova | MW | 71 |  | 49 | 60 | [7 empty] | RBS | [10 empty] | CR146 | COSOVENI | 252 |  | 46 | 60 | [20 empty] | LOCAL |  |  | Marius LUNGU | Cosmorom | [32 empty] | 142 | Sos. Craiova - Calafat | Dolj | [6 empty] | 1 | 2 |  | 1 | 2
Phase_2 | CS | CR102 | RADOVAN | Road Craiova-Calafat(11) | CR024 Unirii_RTC | Oltenia | 44 09 52.81 | 23 37 28.02 | 44 09 54.7 | 23 37 28.1 | Comuna Radovan | Primaria Radovan/Viceprimar Grecu Ilie -226 011; 226 223 | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  |  | TN | 40 |  | N/A | DIEKAT | OK | DUAL | 2000-12-19 | 2001-02-16 | YesV | 2001-02-21 | Andrei | 2001-03-26 | 2001-02-28 |  |  |  |  | 2000-11-14 |  | 2000-11-29 | 2000-12-21 | [6 empty] | 2001-02-19 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 40 | 0 | 40 | K 739 494 | 250 | 0 | 40 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 52 | 52 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 104 | ML 15 E 1+1 | Craiova | MW | 35 | 0.6 | 39/0.6 | 50 | [7 empty] | RBS | [10 empty] | CR101 | FERMA GREACA | 215 | 0.6 | 49/0.6 | 60 | [20 empty] | LOCAL |  |  | Marius LUNGU | Cosmorom | [32 empty] | 126 | Com Radovan | Dolj | [6 empty] | 1 | 2 |  | 1 | 2
Phase_2 | CS | CR103 | PERISOR | Road Craiova-Calafat(11) | CR024 Unirii_RTC | Oltenia | 44 08 45.81 | 23 29 51.51 | 44 08 41.0 | 23 30 00.4 | Comuna Perisor | Primaria Perisor/Primar Parvu Marin | MAXITE | M | 1 | 2 | 2PBC | [7 empty] | N/A | N/A |  |  |  |  | TN | 50 |  | N/A/TMR9000 | DIEKAT | OK | DUAL | 2001-02-02 | 2001-03-07 | YesV | 2001-04-02 | Andrei | 2001-03-26 | 2001-05-04 |  |  |  |  | 2000-09-27 |  | 2001-01-19 | 2001-02-21 |  |  |  | 2001-03-13 | ICOM | SVF | 2001-03-13 | 2001-03-13 | 2001-03-14 | 2001-03-15 | 2001-03-19 |  | Prov |  | RBS 2101 CR102 |  |  |  |  | AAU | 100 | 0 | 50 | AAU | 250 | 0 | 50 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 120 | ML 15 E 1+1 | Craiova | MW | 77 | 1.2 | 49/1.2 | 60 | [18 empty] | CR102 | RADOVAN | 257 |  | 39 | 50 | [20 empty] | LOCAL |  |  | Marius LUNGU | Cosmorom | [32 empty] | 119 | Comuna Perisor | Dolj | [6 empty] | 1 | 2 |  | 1 | 2
Phase_2 | CS | CR104 | GIUBEGA | Road Craiova-Calafat(11) | CR024 Unirii_RTC | Oltenia | 44 07 18.77 | 23 23 15.79 | 44 07 23.1 | 23 23 14.2 | Giubega, tarla 40, parcela 43 | Marcu Virginia - Giubeca/Marcu Virginia - Giubeca | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  |  | TN | 40 |  | N/A | DIEKAT | OK | EL-MONT | 2000-12-15 | 2001-02-15 | YesV | 2001-02-21 | Andrei | 2001-02-23 | 2001-03-06 |  |  |  |  | 2000-09-27 |  | 2000-12-11 | 2001-01-09 | [6 empty] | 2001-02-16 |  |  |  |  | GATA-2101 | Prov |  | RBS 2101 |  |  |  |  | K 739 494 | 70 | 0 | 40 | K 739 494 | 240 | 0 | 40 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 50 | 50 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 100 | ML 15 E 1+1 | Craiova | MW | 73 |  | 39 | 50 | [7 empty] | RBS | [10 empty] | CR103 | PERISOR | 253 | 0.6 | 49/0.6 | 60 | [20 empty] | LOCAL |  |  | COSMOROM | Cosmorom | [32 empty] | 121 | Gilgea | Dolj | [6 empty] | 1 | 2 |  | 1 | 2
Phase_2 | CS | CR105 | GALICEA | Road Craiova-Calafat(11) | CR024 Unirii_RTC | Oltenia | 44 05 51.75 | 23 17 32.91 | 44 05 49.8 | 23 17 36.9 | Com Galicea Mare | Primaria Galicea Mare/Ciovica Octavian-viceprimar | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | DIEKAT | OK | EL-MONT | 2000-11-22 | 2001-02-15 | YesV | 2001-02-21 | Andrei | 2001-02-19 | 2001-03-06 |  |  |  |  | 2000-09-27 |  | 2000-11-01 | 2000-11-29 | [6 empty] | 2001-02-16 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 90 | 0 | 50 | K 739 494 | 250 | 0 | 50 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 50 | 50 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 100 | ML 15 E 1+0 | Craiova | MW | 71 |  | 49 | 60 | [7 empty] | RBS | [10 empty] | CR104 | GIUBEGA | 252 |  | 39 | 50 | [20 empty] | LOCAL |  |  | Marius LUNGU | Cosmorom | [32 empty] | 74 | Com Galicea Mare | Dolj | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CR106 | MOTATEI | Road Craiova-Calafat(11) | CR024 Unirii_RTC | Oltenia | 44 04 48.4 | 13 12 38.4 | 44 04 44.1 | 23 12 24.4 | Com. Motatei, tarla 300, parcela 15 | Sfetcu Elena , comuna Motatei, jud. Dolj/Sfetcu Elena , comuna Motatei, jud. Dolj | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  |  | TN | 40 |  | N/A | DIEKAT | OK | EL-MONT | 2000-12-15 | 2001-02-15 | YesV | 2001-02-21 | Andrei |  | 2001-03-06 |  |  |  |  | 2000-11-14 |  | 2000-12-11 | 2001-01-09 | [6 empty] | 2001-02-16 |  |  |  |  | GATA-2101 | Prov |  | RBS 2101 |  |  |  |  | K 739 494 | 170 | 0 | 40 | K 739 494 | 320 | 0 | 40 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 50 | 50 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 100 |  | Craiova | MW | 74 |  | 39 | 50 | [7 empty] | RBS | [10 empty] | CR105 | GALICEA | 254 |  | 49 | 60 | [20 empty] | LOCAL |  |  | Marius LUNGU | Cosmorom | [33 empty] | Motatei | Dolj | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CR107 | MAGLAVIT | Road Craiova-Calafat(11) | CR024 Unirii_RTC | Oltenia | 44 00 58.72 | 23 05 31.66 | 44 01 02.9 | 23 05 42.3 | Sos Craiova-Calafat Km72 | Bacu Ion, co0m. Maglavit, str. 6, nr. 848/Bacu Ioan, Maglavit, str.6 nr.818 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [12 empty] | 0 | TN | 50 |  | N/A | DIEKAT | OK | SETRACO | 2000-12-15 | 2001-03-10 | YesV | 2001-03-30 | Andrei | 2001-04-17 | 2001-05-04 |  |  |  |  | 2000-11-14 |  | 2000-12-11 | 2001-01-09 |  |  |  | 2001-03-26 | ICOM | ORION | 2001-03-13 | 2001-03-13 | 2001-03-27 | 2001-03-28 | 2001-04-02 |  | Yes |  | RBS 2101 CR106 |  |  |  |  | K 739 494 | 0 | 0 | 50 | K 739 494 | 70 | 0 | 50 | K 739 494 | 260 | 0 | 50 |  |  |  |  | N/A | 60 | 60 | 1 1/4" | 60 | 60 | 1 1/4" | 60 | 60 | 1 1/4" |  |  |  | 360 | ML 15 E 1+0 | Craiova | MW | 53 |  | 49 | 60 |  |  |  | 2U-3 |  |  |  | RBS | [10 empty] | CR106 | MOTATEI | 233 |  | 39 | 50 | [20 empty] | LOCAL |  |  | Marius LUNGU | Cosmorom | [32 empty] | 50 | Maglavit | Dolj | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CR108 | CALAFAT_RTC | Road Craiova-Calafat(11) | CR024 Unirii_RTC | Oltenia | 43 59 41.1 | 22 56 20.7 | 43 59 41.1 | 22 56 20.7 | Str. Traian nr.44 | Romtelecom/ | 2202 | M | C+C+ | 2/2 | 2202 | [7 empty] | N/A | N/A |  |  |  | 10 | B | 15.4 | 15m new pylonet | Room | DIEKAT | OK | SETRACO | 2000-11-14 | 2001-01-19 | YesV | 2001-01-29 | Andrei | 2001-02-02 | 2001-02-26 |  |  |  | N/A | 2000-11-14 |  | 2000-11-03 | 2000-11-28 |  |  |  | 2001-02-01 | ICOM | ORION | 2001-01-26 | 2001-01-26 | 2001-02-05 | 2001-02-13 | 2001-02-16 |  | Yes |  | RBS 2101 CR106 |  |  |  |  | K 739 494 | 80 | 0 | 30 | K 739 494 | 180 | 0 | 30 | N/A | N/A | N/A | N/A |  |  |  |  | N/A | 38 | 38 | 7/8" | 38 | 38 | 7/8" | N/A | N/A | N/A |  |  |  | 152 | ML 15 E 1+0 | Craiova | MW | 79 | 1.2 | 27/1.2 | 36 | 15/89 |  |  | 2U-3 | [14 empty] | CR107 | MAGLAVIT | 259 | 1.2 | 49 | 60 | 15/84 | [6 empty] | 49* | ORION | 2001-03-26 | 759 | 2001-03-27 | 2001-03-30 | 2001-04-04 | [6 empty] | LOCAL |  |  | Marius LUNGU | CATALINA CIOCAN | [32 empty] | 43 | Calafat | Dolj | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CR109 | VALEA URSULUI | Road Pitesti-Rm. Valcea(6) | CR013 Centru_RTC | Oltenia | 44 53 31.6 | 24 45 22.9 | 44 53 01.4 | 24 45 00.4 | Sat Mica, com. Bascov | Sima I. Gheorghe - sat Mica, com. Bascov, nr.96/Sima I. Gheorghe - sat Mica, com. Bascov, nr.96 | 2202 | M | C+C+ | 2/2 | 2202 |  | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A |  |  |  | 0 | TN | 50 | 50m tower | Shelter | DIEKAT | OK | DIEKAT | 2000-12-21 | 2001-04-17 | YesV | 2001-04-27 | Mugur |  | 2001-05-03 | 2001-07-06 |  |  | OK | 2000-10-16 |  | 2000-12-13 | 2001-03-14 | S-a schimbat RBS din 2101-2202 |  |  | 2001-07-17 | ICOM |  | 2001-07-13 | [5 empty] | Yes | [6 empty] | K 739 494 | 80 | 0 | 50 | K 739 494 | 140 | 0 | 50 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 60 | 60 | 1 1/4" | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | 240 | ML 15 E 1+1 | Baneasa | MW | 102 |  | 48 | 60 | [7 empty] | RACK 19" de livrat | XC41013 |  |  | XC41013 | [6 empty] | CR020 | DRTV PITESTI | 282 | 0.6 | 40/0.6 | [21 empty] | 30N05 Pitesti-Baneasa |  | OK | Cristian CROITOR | Cosmorom | [32 empty] | 326 | Mica | Arges | [6 empty] | 1 | 2 |  | 1 | 2
Phase_2 | CS | CR110 | DRAGANU | Road Pitesti-Rm. Valcea(6) | CR013 Centru_RTC | Oltenia | 44 57 21 | 24 42 14.5 | 44 57 25.4 | 24 42 15 | Com. Draganu, Dumbravesti, 3.1Km de E81 | Dumitra Caprescu - com. Draganu, Dumbravesti/Oprea Ioana - str. Bailor, bl. D30, sc. A, Ap.1 - 048/ 212 526 | MUTAT | M | C+ | 2 | 2101 | [6 empty] | 2000-12-11 | N/A | N/A |  |  |  | 0 | TN | 50 |  | N/A | DIEKAT | OK | DIEKAT | 2000-11-13 | 2000-12-22 | YesV | 2001-01-30 | Mugur | 2001-05-10 | 2001-02-01 |  |  |  | OK | 2000-10-16 |  | 2000-11-06 | 2000-11-24 |  |  |  | 2000-12-28 | ICOM | DIEKAT | 2000-12-27 | 2001-01-10 | 2001-01-11 | 2001-01-12 | 2001-01-18 |  | Yes |  | 2101 MOVED TO BV095 |  |  |  |  | K 739 494 | 150 | 0 | 49 | K 739 494 | 300 | 0 | 49 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Baneasa | MW | 150 | 1.2 | 48/1.2 | 58 | [7 empty] | N/A | XC41013 |  |  | XC41013 | [6 empty] | CR109 | VALEA URSULUI | 330 |  | 48 | 60 | [20 empty] | 30N05 Pitesti-Baneasa |  | OK | Cristian CROITOR | Cosmorom | [32 empty] | 403 | Draganu | Arges | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CR111 | MORARESTI | Road Pitesti-Rm. Valcea(6) | CR013 Centru_RTC | Oltenia | 45 00 38.5 | 24 34 04.8 | 45 00 27.9 | 24 33 38.1 | Com. Moraresti | Ungureanu Elena - sat Moraresti/Ungureanu Gelu - sat Moraresti, 092/ 641 452 | 2202 | M | C+C+ | 2/2 | 2202 |  | N/A | N/A | N/A | N/A | N/A | 2000-12-11 | N/A | N/A |  |  |  | 0 | TN | 50 |  | Shelter | DIEKAT | OK | ESROM | 2000-11-15 | 2001-03-22 | YesV | Respins | Mugur | 2001-04-17 |  | 2001-07-06 |  |  | OK | 2000-10-16 |  | 2000-11-08 | 2000-11-24 | S-a schimbat RBS din 2101-2202 |  |  | 2001-07-17 | ICOM |  | 2001-03-26 | [5 empty] | Yes | [6 empty] | K 739 494 | 110 | 0 | 49 | K 739 494 | 300 | 0 | 49 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 60 | 60 | 1 1/4" | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | 240 | ML 23 E 1+0 | Baneasa | MW | 109 | 0.6 | 48/0.6 | 58 | [7 empty] | RACK 19" de livrat | [10 empty] | CR126 | LINTESTI | 289 |  | 47 | 57 | [20 empty] | new08 |  | 2001-07-29 | Cristian CROITOR | Cosmorom | [32 empty] | 520 | Moraresti | Arges | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CR112 | MILCOIU | Road Pitesti-Rm. Valcea(6) | CR013 Centru_RTC | Oltenia | 45 03 50.3 | 24 28 12.8 | 45 02 53.8 | 24 27 29.7 | Sat Milcoiu, com. Milcoiu - Punctul "Caminul Casei" | Andrei Gh. Marin - Rm. Valcea, str. Ostroveni nr.1, bl.A23, sc.E, ap.9/Andrei Gh. Marin - Rm. Valcea, str. Ostroveni nr.1, bl.A23, sc.E, ap.9 | 2202 | M | C+C+ | 2/2 | 2202 |  | N/A | N/A | N/A | N/A | N/A | 2000-12-11 | N/A | N/A |  |  |  | 0 | TN | 50 |  | Shelter | DIEKAT | OK | ESROM | 2000-11-20 | 2001-03-22 | YesV | 2001-04-19 | Mugur | 2001-04-17 | 2001-04-19 |  |  |  | OK | 2000-10-16 |  | 2000-11-08 | 2000-11-24 | S-a schimbat RBS din 2101-2202 |  |  | 2001-07-17 | ICOM |  | 2001-03-26 | [5 empty] | Yes | [6 empty] | K 739 494 | 150 | 0 | 49 | K 739 494 | 330 | 0 | 49 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 60 | 60 | 1 1/4" | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | 240 | ML 15 E 1+0 | Baneasa | MW | 120 |  | 48 | 58 | [7 empty] | RACK 19" de livrat | [10 empty] | CR111 | MORARESTI | 300 | 1.2 | 48/1.2 | 58 | [20 empty] | new08 |  | 2001-07-29 | Cristian CROITOR | Cosmorom | [32 empty] | 403 | Valcea | Valcea | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CR113 | CENTURA RM. VALCEA | Road Pitesti-Rm. Valcea(6) | CR047 Valcea_RTC | Oltenia | 45 04 43.2 | 24 23 15.3 | 45 04 27.3 | 24 23 23.1 | Sat Racovita Noua, com. Budesti | Pusera Ana - sat racovita Noua, com. Budesti/Pusera Ana - sat racovita Noua, com. Budesti | 2102 | M | C+C+C+ | 2/2/2 | N/A | [12 empty] | 0 | TN | 50 |  | N/A | DIEKAT | OK | ESROM | 2000-11-28 | 2001-04-05 | YesV | 2001-05-03 | Mugur | 2001-04-17 | 2001-05-03 |  |  |  |  | 2000-10-16 |  | OK | 2000-11-28 |  |  |  | 2001-04-09 | ICOM | TRY | 2001-04-09 | 2001-04-09 | 2001-04-10 | 2001-04-19 | 2001-04-20 |  | Yes | Alexandru Toma | 2001-04-29 | 2001-04-28 | 2001-04-28 | 2001-05-31 | 2001-06-19 | K 739 494 | 120 | 0 | 49 | K 739 494 | 260 | 0 | 49 | K 739 494 | 355 | 0 | 49 |  |  |  |  | N/A | 60 | 60 | 1 1/4" | 60 | 60 | 1 1/4" | 60 | 60 | 1 1/4" |  |  |  | 360 | ML 38 E 1+1 | Craiova | MW | 323 | 0.6 | 48 | 58 | 38/17 | YES | 4x2/8 | 4U-1 |  |  |  | RBS | [9 empty] | 1 | CR051 | TINERETULUI | 143 | 0.6 | 39/0.6 | 28 | 38/13 | [6 empty] | 56* | TRYLON | 2001-04-09 | 837 | 2001-04-10 | 2001-04-12 | 2001-04-18 | PAUN | OK | 2001-04-28 |  | 2001-05-10 | 2001-05-25 | 30N03 Rm. Valcea-Craiova |  | OK | Cristian CROITOR | CATALINA CIOCAN | [32 empty] | 229 | Racovita Noua | Valcea | [5 empty] | 1 | 1 | 2 | 1 | 1 | 2
Phase_2 | CS | CR115 | DAESTI | Road Rm. Valcea-Sibiu(3+1) | CR116 Calimanesti_RTC | Oltenia | 45 12 33.5 | 24 22 41.3 | 45 12 34.2 | 24 22 41.5 | Localitatea Daesti, jud. Valcea | Vacalie Florea - Localitatea Daesti/Dragan Cornel - 093/ 316 974 | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  |  | TN | 50 | 50m tower | N/A | ORION | OK | ORION | 2000-11-29 | 2001-02-15 | YesV | 2001-02-15 | Mugur | 2001-03-26 | 2001-02-26 |  |  |  |  | 2001-07-16 |  | 2000-11-22 | 2000-12-11 | [6 empty] | 2001-01-18 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 200 | 0 | 50 | K 739 494 | 300 | 0 | 50 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 70 | 70 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 140 | ML 15 E 1+0 | Craiova | MW | 347 |  | 48 | 55 | [7 empty] | RBS | [10 empty] | ZR117 | COZIA_DRTV | 167 |  | 11.5 | 47 | [20 empty] | 30N01 Calimanesti-Craiova |  | 2001-03-20 | Cristian CROITOR | Cosmorom | [32 empty] | 96 | Daesti | Valcea | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CR116 | CALIMANESTI_RTC | Road Rm. Valcea-Sibiu(3+1) | CR116 Calimanesti_RTC | Oltenia | 45 14 45.6 | 24 20 19.5 | 45 14 45.6 | 24 20 19.5 | Calimanesti, jud. Valcea | Romtelecom/D-l Antone , administrator RTC Valcea, tel. 050/704134 | 2202 | M | C+C+ | 2/2 | 2202 | [7 empty] | N/A | N/A |  |  |  | 10 | B | 13 | 18m new pylonet | Room | ORION | OK | ORION | 2000-12-21 | 2001-02-05 | YesV | 2001-02-15 | Mugur | 2001-02-06 | 2001-02-26 |  |  |  | N/A | 2001-07-16 |  | 2000-12-04 | 2001-01-23 |  |  |  | 2001-02-02 | ICOM | ORION | 2001-01-18 | 2001-01-16 | 2001-02-05 | 2001-02-06 | 2001-02-09 |  | Yes | Alexandru Toma | 2001-04-13 | 2001-04-24 | 2001-04-24 | 2001-05-28 | 2001-06-19 | K 739 494 | 180 | 0 | 30 | K 739 494 | 335 | 0 | 30 | N/A | N/A | N/A | N/A |  |  |  |  | N/A | 45 | 45 | 7/8'' | 45 | 45 | 7/8'' | N/A | N/A | N/A |  |  |  | 180 | N/A | Craiova | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | 2U-3 |  |  |  |  | 40116 | [9 empty] | BSC31 | BSC TIMISOARA | N/A | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | DINCA | OK | N/A |  | N/A | N/A | 30N01 Calimanesti-Craiova |  | 2001-03-20 | Cristian CROITOR | CATALINA CIOCAN | [32 empty] | 293 | Calimanesti | Valcea | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | CR118 | HOTEL COZIA | Road Rm. Valcea-Sibiu(3+1) | CR116 Calimanesti_RTC | Oltenia | 45 16 01.0 | 24 19 08.2 | 45 16 01.0 | 24 19 08.20 | Hotel Cozia | S.C.Calimanesti-Caciulata S.A. Calea lui Traian nr.413/Director General Necsoiu-094 692 049; 050/ 751 138 | 2101 | M | C+ | 2 | 2101 | [7 empty] | YES |  |  |  |  | 37.3 | B | 40 | C4m+C4m? |  | DUAL | OK | DUAL | 2001-03-08 | 2001-04-03 | YesV | 2001-04-19 | Mugur |  | 2001-04-19 |  |  |  |  | 2001-07-16 |  | 2001-02-26 | 2001-03-20 | [6 empty] | 2001-04-09 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 150 | 0 | 43.95 | K 739 494 | 330 | 0 | 43.95 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 50 | 50 | 7/8" | 32 | 32 | 7/8" | N/A | N/A | N/A |  |  |  | 164 | ML 15 E 1+0 | Craiova | MW | 18 |  | 39.1 | 20 | [7 empty] | RBS | [10 empty] | ZR117 | COZIA_DRTV | 198 |  | 19 | 46 | [20 empty] | 30N01 Calimanesti-Craiova |  | 2001-03-20 | Cristi Croitor | Cosmorom | [32 empty] | 286 | Caciulata | Valcea | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CR119 | VLADESTI | Road Rm. Valcea-Olanesti(2+1) | CR047 Valcea_RTC | Oltenia | 45 06 54.2 | 24 18 30.3 | 45 07 34.9 | 24 16 10.5 | Intravilan comuna Vladesti | Guiu Gheorghe - com. Vladesti, 092/ 544 419/Guiu Gheorghe - com. Vladesti, 092/ 544 419 | 2101 | M | C+ | 2 | 2101 | [13 empty] | TN | 50 |  | N/A | DUAL | OK | DUAL | 2001-04-10 | 2001-05-14 | YesV | 2001-05-16 | Mugur |  | 2001-05-23 |  |  |  |  | 2001-02-21 |  | 2001-03-05 | 2001-05-09 | [6 empty] | 2001-05-16 |  |  |  |  | GATA-2101 | Prov |  | RBS 2101 |  |  |  |  | K 739 494 | 125 | 0 | 48.25 | K 739 494 | 290 | 0 | 48.25 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 23 E 1+0 | Craiova | MW | 126 |  | 54 | 70 | [7 empty] | RBS | [10 empty] | CR048 | CALEA LUI TRAIAN | 296 | 0.6 | 28.3/0.6 | 14 | [20 empty] | 30N01 Rm. Valcea-Craiova |  | OK | Denis CIUCU | Cosmorom | [32 empty] | 294 | Vladesti | Valcea | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CR120 | OLANESTI_DRTV | Road Rm. Valcea-Olanesti(2+1) | YR121 Olanesti_RTC | Oltenia | 45 11 49 | 24 15 25 | 46 11 49.4 | 25 15 25.1 | DRTV Olanesti | DRTv Olanesti/ | 2102 | M | C+C+ | 2/2 | N/A | [12 empty] | 0 | TE | 23 |  | N/A | DUAL | OK | DUAL | 2001-05-15 | 2001-06-15 | YesV | 2001-07-04 | Mugur |  | 2001-06-12 | [6 empty] | 2001-05-25 | OK |  |  | 1095 | 2001-07-09 | ICOM | SVF | 2001-07-09 | 2001-07-10 | 2001-07-10 | 2001-07-11 | 2001-07-13 | VLAD |  |  | CW NOT READY |  |  |  |  | K 739 494 | 190 | 0 | 20 | K 739 494 | 260 | 0 | 20 | N/A | N/A | N/A | N/A |  |  |  |  | N/A | 25 | 25 | 7/8" | 25 | 25 | 7/8" | N/A | N/A | N/A |  |  |  | 100 | ML 38 E 1+0 | Craiova | MW | 301 | 0.3 | 19 | 25 | 38/18 | N/A | 4x2/8 | 2U-3 |  |  |  | RBS | [9 empty] | 1 | YR121 | OLANESTI_RTC | 121 | 1.2 | 9.25/1.2 | 17 | 38/14 | [6 empty] | 79* | SVF | 2001-07-09 | 1071 |  | 2001-07-12 | 2001-07-13 | VLAD | [5 empty] | 30N01 Rm. Valcea-Craiova |  |  | Dragos NICULESCU | Cosmorom | [33 empty] | Sat Olanesti | Valcea | [7 empty] | 2 |  | 1 | 2
Phase_2 | CS | CR122 | GOVORA(USG) | Road Rm. Valcea-Slatina(8) | CR047 Valcea_RTC | Oltenia | 45 02 00.4 | 24 17 23.3 | 45 01 59.5 | 24 17 24 | Uzinele Sodice Govora, DN 64 Km 44 | Uzinele sodice Govora/Dir. Ing. Lupsoiu P. - 094/ 538 846 | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [7 empty] | N/A | N/A |  |  |  | 70.3 | B | 70.3 | C3m+C3m | Room | PROTELCO | OK | SETRACO | 2000-11-20 | 2000-12-22 | YesV | 2001-02-06 | Mugur | 2001-02-02 | 2001-02-07 |  |  |  |  | 2000-10-16 |  | 2000-11-15 | 2000-11-28 |  |  |  | 2000-12-28 | ICOM | DIEKAT | 2000-12-27 | 2001-01-10 | 2001-01-11 | 2001-02-06 | 2001-02-08 |  | Yes | Alexandru Toma | 2001-04-29 | 2001-04-28 | 2001-04-28 |  |  | K 739 494 | 50 | 0 | 67.4 | K 739 494 | 200 | 0 | 67.4 | K 739 494 | 300 | 0 | 67.4 |  |  |  |  | N/A | 47 | 47 | 1 1/4" | 67 | 67 | 1 1/4" | 67 | 67 | 1 1/4" |  |  |  | 362 | ML 15 E 1+1 | Craiova | MW | 57 | 0.6 | 66.6 | 47 | 15/84 | YES | 4x2/8 |  |  |  |  | TMR 9202 | [9 empty] | 1 | CR113 | CENTURA RM. VALCEA | 237 | 0.6 | 48 | 58 | 15/89 | [6 empty] | 56* | TRYLON | 2001-04-09 | 838 | 2001-04-12 | 2001-04-12 | 2001-04-18 | PAUN | OK | 2001-04-28 |  | 2001-05-10 | 2001-05-25 | 30N03 Rm. Valcea-Craiova |  | OK | Cristian CROITOR | Cosmorom | [32 empty] | 207 | Govora | Valcea | [5 empty] | 1 | 1 | 2 | 1 | 1 | 2
Phase_2 | CS | CR123 | PAUSESTI | Road Rm. Valcea-Tg.Jiu(11+4) | CR124 Govora_RTC | Oltenia | 45 05 02.8 | 24 09 04.1 | 45 05 03.1 | 24 09 06.6 | sat Pausesti, com. Pausesti, punctul "La ziua Alba" | Parvulescu Vasile - com. Pausesti/Parvulescu Vasile - com. Pausesti | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | PROTELCO | OK | ECO | 2001-03-08 | 2001-05-18 | Yes |  | Mugur | [6 empty] | 2000-10-16 |  | 2000-11-06 | 2001-03-20 | [6 empty] | 2001-05-24 |  |  |  |  | GATA-2101 |  |  | RBS 2101 |  |  |  |  | K 739 494 | 110 | 0 | 48 | K 739 494 | 260 | 0 | 48 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 38 E 1+1 | Craiova | MW | 103 |  | 47 | 60 | [7 empty] | RBS | [10 empty] | CR124 | GOVORA_RTC | 283 | 0.6 | 18.7/0.6 | 31 | [20 empty] | new01 Govora-Craiova |  | 2001-08-01 | Cristian CROITOR | Cosmorom | [32 empty] | 486 | Pausesti | Valcea | [7 empty] | 2 |  |  | 2
Phase_2 | TM | CR124 | GOVORA_RTC | Road Rm. Valcea-Tg.Jiu(11+4) | CR124 Govora_RTC | Oltenia | 45 04 47.8 | 24 10 36 | 45 04 51 | 24 10 40.8 | Str. Tudor Vladimirescu nr.171, Baile Govora | Romtelecom/Pecingine Sorin - sef centru RTC, 050/ 710 410 | N/A | N/A | N/A | N/A | N/A | [12 empty] | N/A | B | 13 | T6m | Room | PROTELCO | OK | IMSAT | 2000-11-14 | 2000-12-22 | YesV | 2001-03-28 | Mugur | 2001-02-19 | 2001-05-04 |  |  |  | N/A | 2000-10-16 |  | 2000-11-02 | 2000-11-28 | [6 empty] | N/A | N/A |  |  |  |  | Prov |  | RBS 2101 CR123 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A | Craiova | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | [5 empty] | 40124 | [6 empty] | 7/Indoor |  |  | BSC31 | BSC TIMISOARA | N/A | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  | Cristian CROITOR | Cosmorom | [32 empty] | 343 | Govora | Valcea | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | CR125 | NEGRULESTI | Road Rm. Valcea-Tg.Jiu(11+4) | CR124 Govora_RTC | Oltenia | 45 08 19 | 24 04 25.3 | 45 08 18.0 | 24 04 24.1 | Com. Costesti, Sat Costesti, punctul "Ponoare" | Ungureanu Paraschiva , Com Costesti, Sat Costesti, Jud.Valcea/Ungureanu Paraschiva , Com Costesti, Sat Costesti, Jud.Valcea | 2101 | M | C+ | 2 | 2101 | [13 empty] | TN | 40 |  | N/A | PROTELCO | OK | TEHNOROB | 2000-11-15 | 2001-01-10 | YesV | 2001-02-06 | Mugur | 2001-02-23 | 2001-02-07 |  |  |  | 2000-10-26 | 2000-10-16 |  | 2000-11-09 | 2000-11-28 | [6 empty] | 2001-01-26 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 110 | 0 | 38 | K 739 494 | 260 | 0 | 38 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 50 | 50 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 100 | ML 23 E 1+1 | Craiova | MW | 135 |  | 37 | 49 | [7 empty] | RBS | [10 empty] | CR123 | PAUSESTI | 315 |  | 47 | 60 | [20 empty] | new01 Govora-Craiova |  | 2001-08-01 | Cristian CROITOR | Cosmorom | [32 empty] | 489 | Costesti | Valcea | [6 empty] | 1 | 2 |  |  | 2
Phase_2 | CS | CR126 | LINTESTI | Road Pitesti-Rm. Valcea(6) | CR013 Centru_RTC | Oltenia | 44 59 55.2 | 24 37 01.4 | 44 59 51.5 | 24 36 54.5 | Sat Lintesti, com. Cotmeana, punctul "tarini" | Primaria Cotmeana/Barbulescu Mircea, primar | 2202 | M | C+C+ | 2/2 | 2202 |  | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A |  |  |  | 0 | TN | 50 |  | Shelter | DIEKAT | OK | DIEKAT | 2000-11-20 | 2001-02-24 | YesV | 2001-03-07 | Mugur | 2001-03-06 | 2001-03-13 | 2001-07-06 |  |  | OK | 2000-10-27 |  | 2000-11-09 | 2001-02-01 | S-a schimbat RBS din 2101-2202 |  |  | 2001-07-17 | ICOM |  | 2001-02-28 | [5 empty] | Yes | [6 empty] | K 739 494 | 130 | 0 | 49 | K 739 494 | 270 | 0 | 49 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 60 | 60 | 1 1/4" | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | 240 | ML 15 E 1+0 | Baneasa | MW | 125 |  | 47 | 57 | [7 empty] | RACK 19" de livrat | [10 empty] | CR110 | DRAGANU | 305 | 1.2 | 48/1.2 | 58 | [20 empty] | new08 |  | 2001-07-29 | Cristian CROITOR | Cosmorom | [32 empty] | 478 | Cotmeana | Arges | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CR127 | HOREZU | Road Rm. Valcea-Tg.Jiu(11+4) | CR124 Govora_RTC | Oltenia | 45 08 27.7 | 23 58 47.9 | 45 08 22.8 | 23 58 33.0 | Horezu, Str.Tudor Vladimirescu, Jud.Valcea | Primaria Horezu;Str. 1 Decembrie nr.7/Buse Nicolae - 050/ 861 034 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-12-11 | N/A | N/A |  |  |  | 0 | TN | 50 |  | N/A | PROTELCO | OK | TEHNOROB | 2000-11-15 | 2001-01-10 | YesV | 2001-02-06 | Mugur | 2001-02-23 | 2001-02-07 |  |  |  |  | 2000-10-16 |  | 2000-11-13 | 2000-11-27 |  |  |  | 2001-02-01 | ICOM | ORION | 2001-01-26 | 2001-01-26 | 2001-02-05 | 2001-02-10 | 2001-02-13 |  | Yes |  | RBS 2101 CR125 |  |  |  |  | K 739 494 | 0 | 0 | 48 | K 739 494 | 100 | 0 | 48 | K 739 494 | 250 | 0 | 48 |  |  |  |  | N/A | 60 | 60 | 1 1/4" | 60 | 60 | 1 1/4" | 60 | 60 | 1 1/4" |  |  |  | 360 | ML 15 E 1+0 | Craiova | MW | 92 | 1.2 | 47/1.2 | 59 | [7 empty] | RBS | [10 empty] | CR125 | NEGRULESTI | 272 |  | 37 | 49 | [20 empty] | new02 Govora-Craiova |  | 2001-08-01 | Cristian CROITOR | Cosmorom | [32 empty] | 484 | Horezu | Valcea | [6 empty] | 1 | 2 |  | 1 | 2
Phase_2 | CS | CR128 | MILOSTEA | Road Rm. Valcea-Tg.Jiu(11+4) | CR124 Govora_RTC | Oltenia | 45 08 06 | 23 51 39 | 45 07 58.4 | 23 51 22.1 | Sat Milostea DN 67 Km 56+0.2 | Primaria com. Slatioara/Primar com. Slatioara | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-12-11 | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | PROTELCO | OK | TEHNOROB | 2000-11-15 | 2001-01-20 | YesV | 2001-02-06 | Mugur | 2001-02-23 | 2001-02-07 |  |  |  |  | 2000-10-16 |  | 2000-11-13 | 2000-11-27 | [6 empty] | 2001-01-26 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 100 | 0 | 48 | K 739 494 | 280 | 0 | 48 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Craiova | MW | 86 |  | 47 | 59 | [7 empty] | RBS | [10 empty] | CR127 | HOREZU | 266 |  | 47 | 59 | [20 empty] | new02 Govora-Craiova |  | 2001-08-01 | Cristian CROITOR | Cosmorom | [32 empty] | 561 | Milostea | Valcea | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CR129 | POIENARI | Road Rm. Valcea-Tg.Jiu(11+4) | CR124 Govora_RTC | Oltenia | 45 08 23.8 | 23 46 00.9 | 45 08 25.4 | 23 46 07.5 | Sat Poienari, com. Bumbesti Pitic | Iliescu Gheorghe/Iliescu Gheorghe | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-12-11 | [5 empty] | 0 | TN | 50 |  | N/A | PROTELCO | OK | GIRARDOT | 2000-11-14 | 2001-03-12 | YesV | 2001-04-02 | Mugur | 2001-04-17 | 2001-05-04 |  |  |  |  | 2000-10-16 |  | 2000-11-06 | 2000-11-27 |  |  |  | 2001-03-19 | ICOM | DIEKAT | 2001-03-13 | 2001-03-13 | 2001-03-20 | 2001-03-23 | 2001-03-24 |  | Yes |  | RBS 2101 CR128 |  |  |  |  | K 739 494 | 0 | 0 | 48 | K 739 494 | 100 | 0 | 48 | K 739 494 | 260 | 0 | 48 |  |  |  |  | N/A | 60 | 60 | 1 1/4" | 60 | 60 | 1 1/4" | 60 | 60 | 1 1/4" |  |  |  | 360 | ML 15 E 1+0 | Craiova | MW | 94 |  | 47 | 59 | [7 empty] | RBS | [10 empty] | CR128 | MILOSTEA | 274 |  | 47 | 59 | [20 empty] | new02 Govora-Craiova |  | 2001-08-01 | Cristian CROITOR | Cosmorom | [32 empty] | 522 | Poienari | Gorj | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CR130 | BALCESTI | Road Rm. Valcea-Tg.Jiu(11+4) | CR133 Gilort | Oltenia | 45 06 52.1 | 23 38 55.9 | 45 06 54.7 | 23 38 53.3 | Sat Peresti , Comuna Balcesti | Troi C. Ion , Com. Bengesti-Ciocodia, sat Peresti si Paunescu Veronica/Troi C. Ion , Com. Bengesti-Ciocodia, sat Peresti si Paunescu Veronica | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | PROTELCO | OK | GIRARDOT | 2000-12-19 | 2001-03-12 | YesV | 2001-04-30 | Mugur |  | 2001-05-03 |  |  |  |  | 2000-10-16 |  | 2000-12-08 | 2001-01-16 | [6 empty] | 2001-03-13 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 60 | 0 | 48 | K 739 494 | 230 | 0 | 48 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Craiova | MW | 222 | 1.2 | 47/1.2 | 59 | [7 empty] | RBS | XC40133 | [9 empty] | CR131 | CAMPU MARE | 41 |  | 47.5 | 59 | [20 empty] | 30N01 Tg. Carbunesti-Craiova |  | 2001-04-12 | Cristian CROITOR | Petrica BURGHIU | [32 empty] | 408 | Pausesti | Gorj | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CR131 | CAMPU MARE | Road Rm. Valcea-Tg.Jiu(11+4) | CR133 Gilort | Oltenia | 45 02 42.2 | 23 33 47.5 | 45 02 14.7 | 23 32 59 | Sat Campu Mare, com. Scoarta | Paunas Marieta-sat Campu Mare, com. Scoarta/Paunas Marieta-sat Campu Mare, com. Scoarta | MAXITE | M | 1 | 2 | 2PBC | [7 empty] | N/A | N/A |  |  |  |  | TN | 50 |  | N/A/TMR9000 | PROTELCO | OK | COMARK | 2001-02-01 | 2001-03-15 | YesV | 2001-04-04 | Mugur | 2001-03-23 | 2001-04-10 |  |  |  |  | 2000-10-16 |  | 2000-12-07 | 2000-12-21 |  |  |  | 2001-03-19 | ICOM | DIEKAT | 2001-03-14 | 2001-03-14 | 2001-03-20 | 2001-03-20 | 2001-03-23 |  | Prov | Mircea Mihut | 2001-05-16 | 2001-05-16 |  |  |  | AAU | 35 | 0 | 48.5 | AAU | 240 | 0 | 48.5 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 120 | ML 15 E 1+0 | Craiova | MW | 204 | 0.6 | 47.5 | 59 | 15/84 |  |  | 2U-3 |  |  |  |  | XC40133 | [9 empty] | CR132 | TG. CARBUNESTI | 24 | 0.6 | 47/1.2 | 58 | 15/89 | [6 empty] | 48* | DIEKAT | 2001-03-26 | 752 | 2001-03-26 | 2001-03-26 | 2001-03-28 | DINCA | OK | 2001-05-16 | PENDING |  |  | 30N01 Tg. Carbunesti-Craiova |  | 2001-04-12 | Cristian CROITOR | CATALINA CIOCAN | [32 empty] | 480 | Campu Mare | Gorj | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CR132 | TG. CARBUNESTI | Road Rm. Valcea-Tg.Jiu(11+4) | CR133 Gilort | Oltenia | 44 57 50.3 | 23 30 40.5 | 44 57 51 | 23 30 48.5 | Tarla 6, parcela 185/1, str. Crizantemelor, Tg. Carbunesti | Dogaru Ovidiu - str. Trandafirilor, bl.B6, sc.1, et.3, ap.4, 053/ 378 026/Dogaru Ovidiu - str. Trandafirilor, bl.B6, sc.1, et.3, ap.4, 053/ 378 026 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | N/A | N/A |  |  |  | 0 | TN | 50 |  | N/A | PROTELCO | OK | COMARK | 2001-01-10 | 2001-02-20 | YesV | 2001-04-09 | Mugur | 2001-03-23 | 2001-04-10 |  |  |  |  | 2000-11-20 |  | 2000-12-12 | 2001-01-16 |  |  |  | 2001-03-20 | ICOM | DIEKAT | 2001-02-19 | 2001-02-19 | 2001-03-21 | 2001-03-20 | 2001-03-23 |  | Yes | Mircea Mihut | 2001-05-13 | 2001-05-12 | 2001-05-12 |  |  | K 739 494 | 30 | 0 | 48 | K 739 494 | 140 | 0 | 48 | K 739 494 | 280 | 0 | 48 |  |  |  |  | N/A | 59 | 59 | 1 1/4" | 59 | 59 | 1 1/4" | 59 | 59 | 1 1/4" |  |  |  | 294 | ML 38 E 1+0 | Craiova | MW | 188 | 0.3 | 47.5 | 58.5 | 38/17 |  |  | 4U-1 |  |  |  | RBS | XC40133 | [9 empty] | CR133 | GILORT | 354 | 0.3 |  | 25 | 38/13 | [6 empty] | 46* | DIEKAT | 2001-03-20 | 656 | 2001-03-20 | 2001-03-20 | 2001-03-28 | DINCA | OK | 2001-05-13 | PENDING |  |  | 30N01 Tg. Carbunesti-Craiova |  | 2001-04-12 | Marius LUNGU | Cosmorom | [32 empty] | 229 | Tg. Carbunesti | Gorj | [7 empty] | 2 |  |  | 2
Phase_2 | TM | CR133 | GILORT | Road Rm. Valcea-Tg.Jiu(11+4) | CR133 Gilort | Oltenia | 44 57 27.9 | 23 30 43.7 | 44 57 30.3 | 23 30 38.5 | Str. Trandafirilor nr.136A, Tg. Carbunesti | CONSUMCOOP Tg. Carbunesti - Str. Trandafirilor nr. 136A/Novac Pantelimon - presedinte, 053/ 378 018 | N/A | N/A | N/A | N/A | N/A | [12 empty] | N/A | B | 19.65 | T4.5m | N/A | PROTELCO | OK | COMARK | 2000-11-22 | 2000-12-14 | YesV | 2001-02-06 | Mugur | 2001-02-02 | 2001-02-07 |  |  |  | 2000-11-06 | 2000-10-16 |  | 2000-11-07 | OK |  |  |  | 2001-03-02 | ICOM | DIEKAT | N/A | N/A | N/A | N/A | N/A |  | Yes | N/A | 2001-05-13 | 2001-05-13 | 2001-05-13 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A | Craiova | HDSL | N/A | N/A | N/A | N/A | N/A |  | N/A | 2U-3 |  |  |  |  | 40133 | 2001-05-07 | [8 empty] | BSC23 | BSC CRAIOVA |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | DINCA | OK | N/A |  | N/A | N/A | 30N01 Tg. Carbunesti-Craiova |  | 2001-04-12 | Cristian CROITOR | Cosmorom | [32 empty] | 210 | Tg. Carbunesti | Gorj | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | CR134 | COPACIOSA | Road Rm. Valcea-Tg.Jiu(11+4) | CR133 Gilort | Oltenia | 45 01 28.9 | 23 26 45.1 | 45 01 26.7 | 23 26 45.2 | Sat Lintea, com. Copaciosa | Dobran Sebastian - str. Rm. Valcea nr.6, bl.S20, ap.9, Bucuresti/Dobran Sebastian - str. Rm. Valcea nr.6, bl.S20, ap.9, Bucuresti | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-12-11 | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | PROTELCO | OK | IMSAT | 2000-11-13 | 2001-02-05 | YesV | 2001-02-22 | Mugur |  | 2001-02-28 |  |  |  |  | 2000-10-16 |  | 2000-11-06 | 2000-11-23 |  |  |  |  | ICOM |  | 2001-02-06 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 100 | 0 | 48 | K 739 494 | 275 | 0 | 48 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Craiova | MW | 143 |  | 47/ | 59 | [7 empty] | RBS | XC40133 | [9 empty] | CR132 | TG. CARBUNESTI | 322 | 1.2 | 47/1.2 | 58 | [20 empty] | 30N01 Tg. Carbunesti-Craiova |  | 2001-04-12 | Cristian CROITOR | COSMOROM | [32 empty] | 259 | Lintea | Gorj | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CR135 | DRAGOIENI | Road Rm. Valcea-Tg.Jiu(11+4) | CR057 CTA_9 MAI_RTC | Oltenia | 45 02 29.1 | 23 21 12.2 | 45 02 27.8 | 23 21 13.4 | Com. Dragoieni, DN67 | Cosmorom/Cosmorom | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | PROTELCO | OK | IMSAT | 2000-12-09 | 2001-03-07 | YesV | 2001-03-15 | Mugur |  | 2001-03-21 |  |  |  |  | 2000-11-07 |  | 2000-11-29 | 2000-12-18 | [6 empty] | 2001-02-20 |  |  |  |  | GATA-2101 |  |  | RBS 2101 |  |  |  |  | K 739 494 | 120 | 0 | 48 | K 739 494 | 260 | 0 | 48 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Craiova | MW | 257 |  | 47 | 59 | [7 empty] | RBS | XC40057 | [9 empty] | CR057 | CTA_9 MAI | 77 | 0.6 | 27/0.6 | 18 | [20 empty] | 30N02 Tg.Jiu CTA_9 Mai-Craiova |  | OK | Cristian CROITOR | Cosmorom | [32 empty] | 234 | Dragoieni | Gorj | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CR136 | BUZESCU | Road Alexandria-Craiova(12+1) | CR059 Alexandria_RTC | Oltenia | 44 00 19.8 | 25 14 07.7 | 44 00 44.9 | 25 13 34.2 | Stadion, Com Buzescu | Primaria Buzescu/Traistaru Valentin-primar-047 330 635; 093 640 122 | 2102 | M | C+C+C+ | 2/2/2 | N/A | RBS-S.Aq. | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A |  |  |  | 0 | TN | 50 |  | N/A | DIEKAT | OK | DIEKAT | 2001-01-18 | 2001-02-12 | YesV | 2001-02-16 | Andrei | 2001-04-17 | 2001-02-26 |  |  | 2001-06-08 |  | 2000-09-27 |  | 2001-01-09 | 2001-01-19 |  |  |  | 2001-07-17 | ICOM |  | 2001-07-13 | [5 empty] | Prov |  | OPTIMIZARE |  |  |  |  | K 739 494 | 10 | 0 | 50 | K 739 494 | 115 | 0 | 50 | K 739 494 | 280 | 0 | 50 | N/A | N/A | N/A | N/A | N/A | 60 | 60 | 1 1/4" | 60 | 60 | 1 1/4" | 60 | 60 | 1 1/4" | N/A | N/A | N/A | 360 | ML 15 E 1+1 | Baneasa | MW | 121 | 1.2 | 49/1.2 | 60 | [7 empty] | RBS | [10 empty] | CR059 | ALEXANDRIA_RTC | 301 | 1.2 | 49/1.2 | 70 | [20 empty] | 30N02 Alexandria-Baneasa |  | OK | Marius LUNGU | [33 empty] | 60 | Com.Buzescu | Teleorman | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CR137 | PERETU | Road Alexandria-Craiova(12+1) | CR059 Alexandria_RTC | Oltenia | 44 02 30.62 | 25 05 38.87 | 44 02 49.9 | 25 05 51.1 | Com. Peretu | SC LOTSEM, str. Victor Antonescu nr. 15/Dir. Craciun Tudor - 094/ 326 441 | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | DIEKAT | OK | DIEKAT | 2000-12-15 | 2001-02-09 | YesV | 2001-02-14 | Andrei | 2001-03-06 | 2001-02-26 |  |  |  |  | 2000-10-27 |  | 2000-12-07 | 2000-12-21 | [6 empty] | 2001-02-12 |  |  |  |  | GATA-2101 | Prov |  | RBS 2101 |  |  |  |  | K 739 494 | 120 | 0 | 50 | K 739 494 | 300 | 0 | 50 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Baneasa | MW | 110 |  | 49 | 60 | [7 empty] | RBS | [10 empty] | CR136 | BUZESCU | 290 | 1.2 | 49/1.2 | 60 | [20 empty] | 30N02 Alexandria-Baneasa |  | OK | Marius LUNGU | Cosmorom | [32 empty] | 79 | Peretu | Teleorman | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CR138 | ROSIORII DE VEDE | Road Alexandria-Craiova(12+1) | CR216 Rosiori_RTC | Oltenia | 44 06 41.96 | 24 59 38.42 | 44 06 38.7 | 24 59 38.2 | Str. Dunarii bl.D4 | Asociatie de locatari/Serban Ion adm. - 047/ 466 142 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | Yes | N/A |  |  |  | 31.8 | B | 31.8 | T6m+C4.5m | N/A | DIEKAT | OK | DIEKAT | 2001-01-24 | 2001-02-12 | YesV | 2001-02-21 | Andrei | 2001-04-17 | 2001-02-28 |  |  |  |  | 2000-10-09 |  | 2001-01-09 | 2001-01-29 |  |  |  | 2001-02-14 | ICOM | DIRDATES | 2001-02-14 | 2001-02-14 | 2001-02-19 | 2001-02-20 | 2001-03-24 |  | Yes | Bogdan Bogodai | 2001-04-10 | 2001-04-10 | 2001-04-10 |  |  | K 739 494 | 30 | 0 | 35 | K 739 494 | 140 | 0 | 35 | K 739 494 | 330 | 0 | 35 |  |  |  |  | N/A | 10 | 10 | 7/8" | 10 | 10 | 7/8" | 10 | 10 | 7/8" |  |  |  | 60 | ML 38 E 1+0 | Craiova | MW | 278 | 0.3 | 37 | 12 | 38/18 |  |  | 2U-3 |  |  |  | RBS | [9 empty] | 1 | CR216 | ROSIORII_RTC | 112 | 0.3 | 12 | 48 | 38/14 | [6 empty] | 26* | DIRDATES | 2001-02-14 | 628 | 2001-02-15 | 2001-03-15 | 2001-03-20 | PAUN | OK | 2001-04-10 | PENDING |  |  | 30N01 Rosiori-Craiova |  | 2001-03-27 | Cosmorom | Cosmorom | [32 empty] | 106 | Rosiori de Vede | Teleorman | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CR139 | F-ca.DE ULEI | Road Alexandria-Craiova(12+1) | CR216 Rosiori_RTC | Oltenia | 44 06 39.47 | 24 58 29.58 | 44 06 45 | 24 58 31 | Str. Oltului, nr. 75, Rosiori de Vede , Teleorman | SC Rosiori SA , str4. Oltului nr. 75, Rosiori de Vede/Dir. Manolache Aurel , tel. 047/466801 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | YES |  |  |  |  | 39 | S | 47 | C 5.3m+C 4.2m | N/A | DIEKAT | OK | DIEKAT | 2001-05-11 | 2001-05-30 | YesV | 2001-06-15 | Andrei |  | 2001-06-26 |  |  |  |  | 2000-10-09 |  | 2001-05-09 | OK |  |  |  | 2001-06-06 | ICOM | TRY | 2001-06-04 | 2001-06-04 | 2001-06-05 | 2001-06-06 | 2001-06-11 | IVAN | Yes | Ion Soare | 2001-06-19 | 2001-06-19 | 2001-06-19 | 2001-06-29 | 2001-07-11 | K 739 494 | 20 | 0 | 48.65 | K 739 494 | 130 | 0 | 49.65 | K 739 494 | 290 | 0 | 48.65 |  |  |  |  | N/A | 45 | 45 | 7/8'' | 46 | 46 | 7/8'' | 48 | 48 | 7/8'' |  |  |  | 278 | ML 38 E 1+0 | Craiova | MW | 87 | 0.3 | 47.3 | 45 | 38/17 | [6 empty] | RBS | [9 empty] | 1 | CR138 | ROSIORII DE VEDE | 267 | 0.3 | 37 |  | 38/13 | [6 empty] | 73* | TRYLON | 2001-06-06 | 827 | 2001-06-06 | 2001-06-07 | 2001-06-11 |  |  | 2001-06-19 |  |  |  | 30N01 Rosiori-Craiova |  | 2001-03-27 | Cosmorom | Cosmorom | [32 empty] | 93 | Rosiori de Vede | Teleorman | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CR140 | MIHAESTI | Road Alexandria-Craiova(12+1) | CR216 Rosiori_RTC | Oltenia | 44 07 22.67 | 24 47 52.38 | 44 07 28.1 | 24 47 54 | Com. Mihaesti, cvartal nr. 65 P10 | Stavaru George, com. Mihaiesti/Stavaru George, com. Mihaiesti | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-12-11 | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | DIEKAT | OK | DIEKAT | 2000-11-07 | 2000-12-22 | YesV | 2001-02-06 | Andrei | 2001-02-21 | 2001-02-07 |  |  |  |  | 2000-10-09 |  | 2000-11-01 | 2000-11-13 | [6 empty] | 2000-12-27 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 95 | 0 | 50 | K 739 494 | 265 | 0 | 50 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Craiova | MW | 96 | [10 empty] | RBS | [10 empty] | CR139 | F-ca.DE ULEI | 276 | 1.2 | 47.3 | 48 | [20 empty] | 30N01 Rosiori-Craiova |  | 2001-03-27 | Cosmorom | Cosmorom | [32 empty] | 116 | Mihaesti | Olt | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CR141 | RADOMIRESTI | Road Alexandria-Craiova(12+1) | CR216 Rosiori_RTC | Oltenia | 44 06 39 | 24 40 30.32 | 44 07 17.39 | 24 40 31 | Comuna Radomiresti | Primaria Radomiresti, comuna Radomiresti/Primar Dragoescu Florica, Inspector Babadag Ioana | 2101 | M | C+ | 2 | 2101 | [13 empty] | TN | 50/6mp |  | N/A | DIEKAT | OK | CONDOR | 2001-03-19 | 2001-05-30 | YesV |  | Andrei | [6 empty] | 2000-10-09 |  | 2001-03-14 | 2001-04-10 | [6 empty] | 2001-06-05 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 707 | 100 | 0 | 49 | K 739 494 | 270 | 0 | 49 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 120 | ML 15 E 1+0 | Craiova | MW | 88 | 1.2 | 46/1.2 | 60 | [7 empty] | RBS | [10 empty] | CR140 | MIHAESTI | 266 | [23 empty] | new02 |  |  | Cosmorom | Cosmorom | [32 empty] | 120 | Radomiresti | Olt | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CR142 | STOENESTI | Road Alexandria-Craiova(12+1) | CR143 Caracal_RTC | Oltenia | 44 07 07.52 | 24 29 14.34 | 44 06 47.2 | 24 29 32.1 | Comuna Stoenesti | Gheorghe Vasile Petre, Comuna Stoenesti, jud. Olt/Gheorghe Vasile Petre, Comuna Stoenesti, jud. Olt | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | DIEKAT | OK | COMARK | 2001-01-15 | 2001-02-15 | YesV | 2001-03-30 | Andrei | 2001-03-23 | 2001-05-04 |  |  |  |  | 2000-11-14 |  | 2000-12-13 | 2001-01-10 |  |  |  | 2001-04-10 | ICOM | SVF | 2001-02-19 | 2001-04-10 | 2001-04-18 | 2001-04-26 | 2001-04-27 |  | Yes | Ion Soare | 2001-05-07 | 2001-05-07 | 2001-05-07 |  |  | K 739 494 | 80 | 0 | 50 | K 739 494 | 270 | 0 | 50 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 |  | Craiova | MW | 269 | 0.6 | 49/1.2 | 60 | 15/89 | YES | 4x2/8 |  |  |  |  | RBS | [9 empty] | 1 | CR143 | CARACAL_RTC | 88 | 0.6 | 40 | 65 | 15/84 | [6 empty] | 57* | SVF | 2001-04-10 | 654 | 2001-04-18 | 2001-04-18 | 2001-04-29 | RADU | OK | 2001-05-07 |  | 2001-05-17 | 2001-05-25 | 30N01 Caracal-Craiova |  | 2001-02-09 | Cosmorom | Cosmorom | [32 empty] | 67 | Stoenesti | Olt | [5 empty] | 1 | 1 | 2 | 1 | 1 | 2
Phase_2 | CS | CR143 | CARACAL_RTC | Road Alexandria-Craiova(12+1) | CR143 Caracal_RTC | Oltenia | 44 06 41.7 | 24 20 52.5 | 44 06 41.7 | 24 20 52.5 | B-dul. Antonius Caracalla nr.27 Caracal | Romtelecom/ | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-12-11 | N/A | N/A |  |  |  | 0 | TE | 45 |  | Room | DIEKAT | OK | COMARK | 2000-11-15 | 2000-12-15 | YesV | 2001-04-09 | Andrei | 2001-02-02 | 2001-04-10 |  |  |  | N/A | 2000-11-14 |  | 2000-11-09 | 2000-11-27 |  |  |  | 2000-12-14 | ICOM | ORION | 2000-12-14 | 2000-12-15 | 2000-12-19 | 2001-02-12 | 2001-02-13 |  | Yes | Ion Soare | 2001-03-09 | 2001-03-09 | 2001-03-09 |  |  | K 739 494 | 0 | 0 | 38 | K 739 494 | 120 | 0 | 38 | K 739 494 | 240 | 0 | 38 |  |  |  |  | N/A | 65 | 65 | 1 1/4" | 65 | 65 | 1 1/4" | 65 | 65 | 1 1/4" |  |  |  | 390 | N/A | Craiova | FO | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | TMR 9202 | 40143 | 2001-05-07 | [5 empty] | 25/Indoor |  | 1 | BSC23 | BSC CRAIOVA |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | DINCA | OK | N/A |  | N/A | N/A | 30N01 Caracal-Craiova |  | 2001-02-09 | Marius LUNGU | CATALINA CIOCAN | [32 empty] | 114 | Caracal | Olt | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | CR144 | DIOSTI | Road Alexandria-Craiova(12+1) | CR143 Caracal_RTC | Oltenia | 44 06 49.41 | 24 10 58.78 | 44 06 54.3 | 24 11 16 | Diosti | Gheorghe I. Gheorghe - 54 (prin centrala Diosti)/Gheorghe I. Gheorghe - 54 (prin centrala Diosti) | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-12-11 | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | DIEKAT | OK | CRAAL | 2000-11-07 | 2001-02-20 | YesV |  | Andrei | [6 empty] | 2000-10-09 |  | 2000-11-01 | 2000-11-13 |  |  |  | 2001-05-24 | ICOM | VECTOR | 2001-02-20 | 2001-02-20 | 2001-02-21 | 01.07.01 | 04.07.01 | PAUN |  |  | OK NEXT WEEK |  |  |  |  | K 739 494 | 90 | 0 | 50 | K 739 494 | 310 | 0 | 50 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Craiova | MW | 92 | 1.2 |  | 60 | 15/89 |  |  | 2U-3 |  |  |  | RBS | XC40143 | [9 empty] | CR143 | CARACAL_RTC | 272 | 1.2 | 40 | 65 | 15/84 | [6 empty] | 71* | VECTOR | 2001-05-24 | 955 | 2001-05-24 | 03.07.01 | 04.07.01 | PAUN | 2001-07-04 |  |  |  |  | 30N02 Caracal-Craiova |  | OK | Cosmorom | Cosmorom | [32 empty] | 139 | Extravilan com.Diosti | Dolj | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CR145 | LEU - SILOZ | Road Alexandria-Craiova(12+1) | CR143 Caracal_RTC | Oltenia | 44 12 05.47 | 24 01 57.72 | 44 12 05.3 | 24 01 57.7 | Com. Leu | CEREAL COM Dolj/Parvu Eugen - 092/ 208 509 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | Yes | N/A |  |  |  | 35 | B | 35 | T6m+T6m | N/A | DIEKAT | OK | CRAAL | 2000-11-15 | 2001-04-05 | YesV | 2001-07-04 | Andrei | 2001-07-06 | 2001-06-12 |  |  |  |  | 2000-10-09 |  | 2000-11-03 | 2000-12-14 |  |  |  | 2001-05-24 | ICOM | VECTOR | 2000-12-14 | 2000-12-14 | 2001-02-21 | 02.07.01 | 05.07.01 | PAUN | Yes |  | OK NEXT WEEK |  |  |  |  | K 739 494 | 130 | 0 | 40.3 | K 739 494 | 220 | 0 | 40.3 | K 739 494 | 295 | 0 | 40.3 |  |  |  |  | N/A | 25 | 25 | 7/8" | 25 | 25 | 7/8" | 25 | 25 | 7/8" |  |  |  | 150 | ML 15 E 1+0 | Craiova | MW | 128 | 1.2 | 39 | 25 | 15/84 |  | 4x2/8 | 2U-3 |  |  |  | RBS | XC40143 | [9 empty] | CR144 | DIOSTI | 307 | 1.2 |  | 60 | 15/89 | [6 empty] | 71* | VECTOR | 2001-05-24 | 954 | 2001-05-24 | 04.07.01 | 05.07.01 | PAUN | NO LOS |  | Antena MW obturata |  |  | 30N02 Caracal-Craiova |  | OK | Cosmorom | Cosmorom | [32 empty] | 160 | Leu | Dolj | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CR146 | COSOVENI | Road Craiova-Calafat(11) | CR024 Unirii_RTC | Oltenia | 44 14 43.73 | 23 56 04.67 | 44 16 13 | 23 54 19 | Sat Carcea, com. Cosoveni, jud. Dolj | Mertoiu Ion - sat Carcea, com. Cosoveni/Mertoiu Ion - sat Carcea, com. Cosoveni | 2101 | M | C+ | 2 | 2101 | [13 empty] | TN | 50/6mp |  | N/A | DIEKAT | OK | CRAAL | 2001-03-21 | 2001-05-30 | YesV | Respins | Andrei | 2001-07-06 | [5 empty] | 2000-11-14 |  | 2001-03-21 | 2001-04-10 | [6 empty] | 2001-06-05 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 140 | 0 | 49 | K 739 494 | 310 | 0 | 49 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 120 |  | Craiova | MW | 302 |  | 46 | 60 | [7 empty] | RBS | [10 empty] | CR030 | SPITALUL MILITAR | 122 | 0.6 | 37/0.6 | [21 empty] | LOCAL |  |  | Marius Lungu | COSMOROM | [32 empty] | 163 | Carcea | Dolj | [6 empty] | 1 | 2 |  | 1 | 2
Phase_2 | CS | CR148 | STOENESTI | Road Ploiesti-Targoviste(4) | BX523 Ploiesti Vest_CTA | Muntenia | 44 55 30.8 | 25 51 40.4 | 44 55 30.8 | 25 51 40.4 | Stoenesti nr.137 | Grigore Petre - sat Stoenesti nr.137/Grigore Petre - sat Stoenesti nr.137 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-12-11 | N/A | N/A |  |  |  | 0 | TN | 50 |  | N/A | IMSAT | OK | FIBEC | 2000-11-15 | 2001-02-21 | YesV | 2001-03-30 | Doru | 2001-02-23 | 2001-05-04 |  |  |  | OK | 2000-09-25 |  | 2000-11-09 | 2001-01-04 | [6 empty] | 2001-02-20 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 70 | 0 | 48.25 | K 739 494 | 260 | 0 | 48.25 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Baneasa | MW | 86 |  | 47.2 | 58 | [7 empty] | RBS | [10 empty] | BX503 | PLOIESTI VEST | 265 | 1.2 | 48/1.2 | [21 empty] | 30N08 Ploiesti Vest-Baneasa |  | 2001-07-03 | Cosmorom | Cosmorom | [32 empty] | 214 | Stoenesti | Dambovita | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CR149 | IL CARAGIALE | Road Ploiesti-Targoviste(4) | BX523 Ploiesti Vest_CTA | Muntenia | 44 54 31.6 | 25 44 17.2 | 44 54 31.6 | 25 44 17.2 | Extravilan Com. I.L. CARAGIALE,zona "STEGULETE",jud. DAMBOVITA | STEFAN STELIANA com. I.L. CARAGIALE/STEFAN STELIANA | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-12-11 | N/A | N/A |  |  |  | 0 | TN | 50 | Tower | N/A | IMSAT | OK | FIBEC | 2000-11-15 | 2001-03-23 | YesV | Respins | Doru | 2001-04-06 |  |  |  |  | 2000-10-05 | 2000-09-25 |  | 2000-11-13 | 2000-12-21 | [6 empty] | 2001-02-20 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 70 | 0 | 48.3 | K 739 494 | 280 | 0 | 48.3 | N/A | N/A | N/A | N/A |  |  |  |  | YES | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Baneasa | MW | 81 |  | 36.8 | 50 | [7 empty] | RBS | [10 empty] | CR148 | STOENESTI | 261 |  | 47.2 | 58 | [20 empty] | 30N08 Ploiesti Vest-Baneasa |  | 2001-07-03 | Cosmorom | Cosmorom | [32 empty] | 225 | Ion Luca Caragiale | Dambovita | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CR150 | MIJA | Road Ploiesti-Targoviste(4) | CR063 Targoviste_RTC | Muntenia | 44 54 51.28 | 25 39 48.2 | 44 54 51.2 | 25 39 48.2 | Extravilan Mija | Primaria IL Caragiale/Primar Nastase Adrian, localitatea IL Caragiale | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | IMSAT | OK | FIBEC | 2000-11-29 | 2001-03-08 | YesV | 2001-04-06 | Doru | 2001-03-23 | 2001-04-10 |  |  |  |  | 2000-09-25 |  | 2000-11-23 | 2000-12-05 | [6 empty] | 2001-03-13 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 90 | 0 | 48.25 | K 739 494 | 270 | 0 | 48.25 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Baneasa | MW | 285 |  | 38 | 50 | [7 empty] | RBS | [10 empty] | CR151 | RAZVAD | 105 | 1.2 | 36.8/1.2 | 50 | [20 empty] | 30N01 Targoviste-Baneasa |  | 2001-01-30 | Denis CIUCU | Cosmorom | [32 empty] | 243 | Ghirdoveni | Dambovita | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CR151 | RAZVAD | Road Ploiesti-Targoviste(4) | CR063 Targoviste_RTC | Muntenia | 44 54 51.2 | 25 39 52.6 | 44 56 00.5 | 25 31 21.7 | Intravilan Razvad, str. Garii | Dimulescu Gheorghe/Dimulescu Gheorghe | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-12-11 | N/A | N/A |  |  |  | 0 | TN | 50 |  | N/A | IMSAT | OK | FIBEC | 2000-11-07 | 2001-02-05 | YesV | 2001-03-06 | Doru | 2001-02-12 | 2001-03-13 |  |  |  |  | 2000-09-01 |  | 2000-10-27 | 2000-11-20 |  |  |  | 2001-02-06 | ICOM | ORION | 2001-02-06 | 2001-02-05 | 2001-02-07 | 2001-02-12 | 2001-02-13 |  | Yes | Bogdan Bogodai | 2001-03-15 | 2001-03-15 | 2001-03-15 | 2001-04-17 | 2001-04-23 | K 739 494 | 20 | 0 | 48.30 | K 739 494 | 120 | 0 | 48.30 | K 739 494 | 280 | 0 | 48.30 |  |  |  |  | N/A | 60 | 60 | 1 1/4" | 60 | 60 | 1 1/4" | 60 | 60 | 1 1/4" |  |  |  | 360 | ML 23 E 1+0 | Baneasa | MW | 263 | 0.6 | 36.8/1.2 | 50 | 23/56 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [9 empty] | 1 | CR063 | TARGOVISTE_RTC | 84 | 0.6 | 48 | 64 | 23/58 | [6 empty] | 24* | ORION |  | 604 | 2001-02-06 | 2001-02-06 | 2001-02-13 | RADU | OK | 2001-03-15 |  | 2001-03-21 | 2001-04-06 | 30N01 Targoviste-Baneasa |  | 2001-01-30 | Cosmorom | Cosmorom | [32 empty] | 270 | Razvad | Dambovita | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CR152 | SILOZ TARGOVISTE | Targoviste(5) | CR063 Targoviste_RTC | Muntenia | 44 57 06.11 | 25 27 38.99 | 44 56 53.7 | 25 27 57.5 | Siloz Comcereal Dambovita SA | COMCEREAL DAMBOVITA SA - dir. Nedelcu ghe./dir. Tehnic Sandru Ion, dir. Ec. Tache Viorel; 045/ 631 298, 045/ 631 248/COMCEREAL DAMBOVITA SA - dir. Nedelcu Ghe./dir. Tehnic Sandru Ion, dir. Ec. Tache Viorel; 045/ 631 298, 045/ 631 248 | 2101 | M | C+ | 2 | 2101 | [7 empty] | Yes | N/A |  |  |  | 55 | S | 55 | T4.5m+T4.5m | N/A | IMSAT | OK | MULTISERV | 2000-12-08 | 2000-12-20 | YesV | 2000-12-21 | Doru | 2000-12-22 | 2001-01-10 |  |  |  |  | 2000-11-30 |  | 2000-11-30 | 2000-12-11 |  |  |  | 2000-12-28 | ICOM | ORION | 2000-12-20 | 2001-01-08 | 2001-01-09 | 2001-01-10 | 2001-01-12 |  | Yes | Theo Radoi | 2001-02-14 | 2001-02-14 | 2001-02-14 |  |  | K 739 494 | 140 | 0 | 57.4 | K 739 494 | 310 | 0 | 58 (3) | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 15 | 15 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 30 | ML 23 E 1+0 | Baneasa | MW | 198 | 0.6 | 57 (2) | 13 | 23/56 |  |  | 4U-1 |  |  |  | RBS | [9 empty] | 1 | CR063 | TARGOVISTE_RTC | 17 | 0.6 | 30 | 47 | 23/58 | [6 empty] | 14* | ORION |  | 495 | 2001-01-29 | 2001-02-06 | 2001-02-06 | PRUNARU | OK | 2001-03-14 |  | 2001-03-21 | 2001-03-02 | 30N02 Targoviste-Baneasa |  | 2001-01-30 | Denis CIUCU | Cosmorom | [32 empty] | 280 | Targoviste | Dambovita | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CR153 | DOICESTI | Road Targoviste-Sinaia(6) | CR063 Targoviste_RTC | Muntenia | 45 00 10.7 | 25 23 59.31 | 45 00 08.9 | 25 23 55.1 | Str. Aleea Sibiului nr.1, Uzina Electrica Doicesti | Uzina Electrica Doicesti - Dir. Gen. Ing. Zsolti/Uzina Electrica Doicesti - Dir. Gen. Ing. Zsolti | 2101 | M | C+ | 2 | 2101 | [7 empty] | Yes | N/A |  |  |  | 45 | B | 45 | T4.5m+T4.5m | N/A | IMSAT | OK | MMK | 2000-11-27 | 2001-01-31 | YesV | 2001-03-21 | Doru | 2001-02-13 | 2001-03-29 |  |  |  |  | 2000-09-28 |  | 2000-11-20 | 2000-12-04 |  |  |  | 2001-02-16 | ICOM | SVF | 2001-02-02 | 2001-02-02 | 2001-02-19 | 2001-02-28 | 2001-03-03 |  | Yes | Bogdan Bogodai | 2001-03-15 | 2001-03-15 | 2001-03-15 |  |  | K 739 494 | 40 | 0 | 48 | K 739 494 | 150 | 0 | 48 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 23 | 23 | 7/8" | 25 | 25 | 7/8" | N/A | N/A | N/A |  |  |  | 96 | ML 15 E 1+1 | Baneasa | MW | 150 | 0.6c | 48 | 25 | 15/84 | YES | 4x2/8 | 2U-3 |  |  |  | RBS | [9 empty] | 1 | CR063 | TARGOVISTE_RTC | 330 | 0.6c | 48 | 64 | 15/89 | [6 empty] | 28* | SVF |  | 612 | 2001-02-01 | 2001-02-02 | 2001-02-03 | PAUN | OK | 2001-03-15 |  | 2001-05-17 | 2001-05-25 | 30N05 Targoviste-Baneasa |  | 2001-01-30 | Denis CIUCU | Cosmorom | [32 empty] | 359 | Doicesti | Dambovita | [5 empty] | 1 | 1 | 2 | 1 | 1 | 2
Phase_2 | CS | CR154 | PUCIOASA_RTC | Road Targoviste-Sinaia(6) | CR063 Targoviste_RTC | Muntenia | 45 04 23.2 | 25 26 05.4 | 45 04 23.2 | 25 26 05.4 | RTC Pucioasa | Romtelecom/ | 2202 | M | C+C+ | 2/2 | 2202 | [7 empty] | N/A | N/A |  |  |  | 5 | B | 16.35 | 18 new pylonet | Room | IMSAT | OK | MMK | 2000-11-16 | 2000-12-18 | YesV | 2001-02-06 | Doru | 2001-01-09 | 2001-02-07 |  |  |  | N/A | 2000-09-29 |  | 2000-11-07 | 2000-12-06 |  |  |  | 2000-12-18 | ICOM | ORION | 2000-12-18 | 2000-12-18 | 2000-12-22 | 2001-02-01 | 2001-02-02 |  | Yes | Bogdan Bogodai | 2001-03-16 | 2001-03-16 | 2001-03-16 |  |  | K 739 494 | 190 | 0 | 32.65 | K 739 494 | 330 | 0 | 32.4 | N/A | N/A | N/A | N/A |  |  |  |  | N/A | 40 | 40 | 7/8" | 40 | 40 | 7/8" | N/A | N/A | N/A |  |  |  | 160 | ML 15 E 1+0 | Baneasa | MW | 200 | 0.6c | 21.35 | 35 | 15/89h |  |  | 4U-1 |  |  |  | Indoor Comteck | [9 empty] | 1 | CR153 | DOICESTI | 20 | 0.6c | 47.5 | 23 | 15/84h | [6 empty] | 28* | SVF |  | 611 | 2000-02-01 | 2001-02-02 | 2001-02-03 | PRUNARU | OK | 2001-03-16 |  | 2001-04-11 | 2001-04-20 | 30N05 Targoviste-Baneasa |  | 2001-01-30 | Denis CIUCU | Cosmorom | [32 empty] | 398 | Pucioasa | Dambovita | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CR155 | MALU ROSU | Road Targoviste-Sinaia(6) | CR063 Targoviste_RTC | Muntenia | 45 07 11.98 | 25 24 23.11 | 45 07 18.1 | 25 24 22.9 | Cariera Malu Rosu, Cucuteni(alimentat din ROMCIF Fieni) | Patrusca Enache, Motaeni, sat Cucuteni/Patrusca Enache, Motaeni, sat Cucuteni | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-12-11 | N/A | N/A |  |  |  | 0 | TN | 40 |  | N/A | IMSAT | OK | EL-MONT | 2000-11-20 | 2000-12-22 | YesV | 2001-02-01 | Doru | 2001-01-17 | 2001-02-01 |  |  |  |  | 2000-09-28 |  | 2000-11-15 | 2000-11-27 |  |  |  | 2000-12-28 | ICOM | ORION | 2000-12-27 | 2001-01-08 | 2001-01-09 | 2001-01-10 | 2001-01-12 |  | Prov | Bogdan Bogodai | 2001-03-16 | 2001-03-16 | 2001-03-16 | 2001-04-19 | 2001-04-23 | K 739 494 | 50 | 0 | 38.25 | K 739 494 | 170 | 0 | 0 | K 739 494 | 340 | 0 | 38.25 |  |  |  |  | N/A | 50 | 50 | 1 1/4" | 50 | 50 | 1 1/4" | 50 | 50 | 1 1/4" |  |  |  | 300 | ML 23 E 1+0 | Baneasa | MW | 157 | 0.6 | 37.5 | 50 | 23/56 |  | 4x2/8 | 4U-1 |  |  |  | RBS | [9 empty] | 1 | CR154 | PUCIOASA_RTC | 337 | 0.6 | 19.35 | 35 | 23/58 | [6 empty] | 19 | ORION |  | 522 | 2001-01-29 | 2001-02-01 | 2001-02-15 | PRUNARU | OK | 2001-03-16 |  | 2001-04-11 | 2001-04-17 | 30N05 Targoviste-Baneasa |  | 2001-01-30 | Denis CIUCU | Cosmorom | [32 empty] | 563 | Malu Rosu | Dambovita | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CR156 | BUCIUMENI | Road Targoviste-Sinaia(6) | CR063 Targoviste_RTC | Muntenia | 45 09 02.8 | 25 27 04.8 | 45 09 15.6 | 25 27 25.3 | Inravilan in comuna Buciumeni, nr. 626 | Nica Maria - com. Buciumeni nr.626/Nica Maria - com. Buciumeni nr.626 | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | IMSAT | OK | EL-MONT | 2000-11-29 | 2001-01-10 | YesV | 2001-02-01 | Doru | 2001-01-17 | 2001-02-01 |  |  |  | 2000-11-10 | 2000-11-13 |  | 2000-11-22 | 2000-12-05 | [6 empty] | 2001-01-26 |  |  |  |  | GATA-2101 | Prov |  | RBS 2101 |  |  |  |  | K 739 494 | 220 | 0 | 48.25 | K 739 494 | 340 | 0 | 48.25 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 23 E 1+0 | Baneasa | MW | 227 |  | 47.2 | 60 | [7 empty] | RBS | [10 empty] | CR155 | MALU ROSU | 47 |  | 37.5 | 50 | [20 empty] | 30N04 Targoviste-Baneasa |  | 2001-01-30 | Denis CIUCU | [33 empty] | 479 | Buciumeni | Dambovita | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CR157 | MOROIENI | Road Targoviste-Sinaia(6) | CR063 Targoviste_RTC | Muntenia | 45 13 27.1 | 25 25 46.4 | 45 13 27.1 | 25 25 46.4 | Intravilan Moroieni | Cosmorom/ | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | IMSAT | OK | EL-MONT | 2000-12-13 | 2001-01-20 | YesV | 2001-02-06 | Doru | 2001-01-29 | 2001-02-07 |  |  |  | 2000-10-15 | 2000-10-25 |  | 2000-11-27 | 2000-12-11 | [6 empty] | 2001-01-26 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 35 | 0 | 48.25 | K 739 494 | 170 | 0 | 48.25 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Baneasa | MW | 164 |  | 47 | 60 | [7 empty] | RBS | [10 empty] | CR156 | BUCIUMENI | 344 |  | 47.5 | 60 | [20 empty] | 30N04 Targoviste-Baneasa |  | 2001-01-30 | Petrica BURGHIU | Cosmorom | [32 empty] | 594 | Moroeni | Dambovita | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CR158 | COTA 1000 | Road Targoviste-Sinaia(6) | BX521 Sinaia_CTA | Muntenia | 45 18 54.6 | 23 31 27.7 |  |  |  |  | 2101 | M | C+ | 2 | 2101 | [17 empty] | IMSAT | OK | EL-MONT | 2001-08-01 | 2001-08-30 | CROM |  | Doru | [5 empty] | 2000-10-09 | 2000-09-25 | [17 empty] | CTR | [13 empty] | 0 | 0 | 0 |  |  |  |  | Yes | [12 empty] | 0 | ML 23 E 1+0 | Dr. Taberei | MW | [11 empty] | RBS | [10 empty] | BX513 | SINAIA_1400 | [24 empty] | 30N01 Sinaia-Dr.Taberei |  | OK | Denis CIUCU | COSMOROM | [32 empty] | 1645 | [9 empty] | 2 |  |  | missing
Phase_2 | CS | CR160 | BABENI | Road Rm. Valcea-Slatina(8) | CR047 Valcea_RTC | Oltenia | 44 55 35.8 | 24 14 04.6 | 44 54 58.6 | 24 13 32 | Sat Marcea Deal, com. Ionesti / CONEL DRAGASANI 050810351 | Cioconea Crinu-Rm. Valcea, str.1Mai | 2102 | M | C+C+C+ | 2/2/2 | N/A | [12 empty] | 0 | TN | 50 |  | N/A | DIEKAT | OK | DIEKAT | 2001-03-08 | 2001-05-14 | YesV | 2001-05-29 | Mugur | 2001-06-06 | 2001-05-31 |  |  |  |  | 2000-10-16 |  | 2001-03-01 | 2001-03-19 |  |  |  | 2001-05-10 | ICOM | DIEKAT | 2001-05-10 | 2001-05-10 | 2001-05-11 | 2001-05-16 | 2001-05-28 | PAUN | Prov | Alexandru Toma | 2001-06-06 | 2001-06-06 | 2001-06-06 |  |  | K 739 494 | 20 | 0 | 49.3 | K 739 494 | 175 | 0 | 49.3 | K 739 494 | 300 | 0 | 49.3 |  |  |  |  | N/A | 60 | 60 | 1 1/4" | 60 | 60 | 1 1/4" | 60 | 60 | 1 1/4" |  |  |  | 360 | ML 15 E 1+1 | Craiova | MW | 21 | 1.2 | 48/1.2 | 57 | 15/89 HP | YES | 4x2/8 | 4U-1 |  |  |  | RBS | [9 empty] | 1 | CR122 | GOVORA(USG) | 200 | 1.2 | 66.6 | 67 | 15/84 HP | [6 empty] | 66* | DIEKAT | 2001-05-11 | 917 | 2001-05-11 | 2001-05-11 | 2001-05-25 | PAUN | OK | 2001-06-06 |  | 2001-07-12 |  | 30N04 Rm. Valcea-Craiova |  | OK | Toma Alexandru | Petrica BURGHIU | [32 empty] | 193 | Sat. Marcea | Valcea | [6 empty] | 1 | 2 |  | 1 | 2
Phase_2 | CS | CR161 | IONESTI | Road Rm. Valcea-Slatina(8) | CR047 Valcea_RTC | Oltenia | 44 51 40.3 | 24 13 40.4 | 44 51 56.7 | 24 13 44.5 | Com Ionesti | Neagoe Vasile Com Ionesti, Jud Valcea -095/036 265/Neagoe Vasile Com Ionesti, Jud Valcea -095/036 265 | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | DIEKAT | OK | DIEKAT | 2000-11-27 | 2001-02-28 | YesV | 2001-04-06 | Mugur |  | 2001-04-10 |  |  |  |  | 2000-10-16 |  | 2000-11-21 | 2000-11-29 | [6 empty] | 2001-03-02 |  |  |  |  | GATA-2101 | Prov |  | RBS 2101 |  |  |  |  | K 739 494 | 10 | 0 | 49.3 | K 739 494 | 160 | 0 | 49.30 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Craiova | MW | 4 |  | 47 | 57 | [7 empty] | RBS | [10 empty] | CR160 | BABENI | 178 | 1.2 | 48/1.2 | 57 | [20 empty] | new05 |  |  | Toma Alexandru | Cosmorom | [32 empty] | 201 | Com Ionesti | Valcea | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CR162 | ZAVIDENI | Road Rm. Valcea-Slatina(8) | CR047 Valcea_RTC | Oltenia | 44 45 05.8 | 24 14 54.4 | 44 45 14.7 | 24 14 46.1 | Sat Zavideni,Com Prundeni | Dodinca Joita , Dragasani, str. Gib. Mihaiescu, nr. 20, bl. 52, ap. 52, ap. 8/Dodinca Joita , Dragasani, str. Gib. Mihaiescu, nr. 20, bl. 52, ap. 52, ap. 8 | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | DIEKAT | OK | DIEKAT | 2000-12-15 | 2001-02-28 | YesV | 2001-03-07 | Mugur | 2001-04-17 | 2001-03-13 |  |  |  |  | 2000-10-16 |  | 2000-12-07 | 2000-12-21 | [6 empty] | 2001-03-02 |  |  |  |  | GATA-2101 | Prov |  | RBS 2101 |  |  |  |  | K 739 494 | 0 | 0 | 49.3 | K 739 494 | 175 | 0 | 49.3 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Craiova | MW | 352 | 1.2 | 48/1.2 | 57 | [7 empty] | RBS | [10 empty] | CR161 | IONESTI | 172 |  | 47 | 57 | [20 empty] | new05 |  |  | Toma Alexandru | [33 empty] | 171 | Sat Zavideni | Valcea | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CR163 | DRAGASANI | Road Rm. Valcea-Slatina(8) | CR047 Valcea_RTC | Oltenia | 44 39 40.6 | 24 15 38.2 | 44 39 40.6 | 24 15 38.2 | Str. Tudor Vladimirescu, Dragasani, jud. Valcea | Romtelecom/ | 2102 | M | C+C+C+ | 2/2/2 | N/A | [12 empty] | 0 | TE | 40 |  | N/A | DIEKAT | OK | DUAL | 2001-04-10 | 2001-05-11 | YesV | 2001-05-16 | Mugur | 2001-06-06 | 2001-05-23 |  |  |  | N/A | 2000-10-16 |  | 2001-04-09 | 2001-05-02 |  |  |  | 2001-05-10 | ICOM | DIEKAT | 2001-05-10 | 2001-05-10 | 2001-05-11 | 2001-05-20 | 2001-05-21 |  | Yes |  | RBS 2101 CR162 |  |  |  |  | K 739 494 | 0 | 0 | 32 | K 739 494 | 175 | 0 | 32 | K 739 494 | 270 | 0 | 32 |  |  |  |  | N/A | 40 | 40 | 7/8" | 40 | 40 | 7/8" | 40 | 40 | 7/8" |  |  |  | 240 | ML 15 E 1+0 | Craiova | MW | 355 |  | 30 | 38 | [7 empty] | RBS | [10 empty] | CR162 | ZAVIDENI | 174 | 1.2 | 48/1.2 | 57 | [20 empty] | new05 |  |  | Toma Alexandru | Cosmorom | [42 empty] | 2 |  |  | 2
Phase_2 | CS | CR164 | GRADINARI | Road Rm. Valcea-Slatina(8) | CR040 Slatina_RTC | Oltenia | 44 33 48.0 | 24 16 07.06 | 44 33 45.8 | 24 16 06.9 | Com Gradinari, sat Gradinari | Heroaica Aurel, Str.Primaverii, nr.6, Dragasani, jud Olt-050 812 511/Heroaica Aurel, Str.Primaverii, nr.6, Dragasani, jud Olt-050 812 511 | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | DIEKAT | OK | SVF | 2000-11-27 | 2001-04-06 | YesV | 2001-05-28 | Mugur | 2001-05-07 | 2001-05-30 |  |  |  |  | 2000-10-16 |  | 2000-11-21 | 2000-11-30 | [6 empty] | 2001-05-03 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 0 | 0 | 49.30 | K 739 494 | 170 | 0 | 49.3 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Craiova | MW | 182 | 1.2 | 47 | 57 | [7 empty] | RBS | [10 empty] | CR165 | COLIBASI | 5 | 1.2 | 47/1.2 | 58 | [23 empty] | Toma Alexandru | Cosmorom | [32 empty] | 141 | Com Gradinari | Olt | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CR165 | PLESOIU | Road Rm. Valcea-Slatina(8) | CR040 Slatina_RTC | Oltenia | 44 28 23.3 | 24 15 47.1 | 44 30 08.3 | 24 15 47.1 | Sat Colibasi,com. Strejesti, jud. Olt | Otava Dorin, Pitesti, str. Nicolae Balcescu, Bl.D1, sc.C, Ap.8/Otava Dorin, Pitesti, str. Nicolae Balcescu, Bl.D1, sc.C, Ap.8 | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | DIEKAT | OK | EMONTAJ | 2001-03-08 | 2001-04-17 | YesV | 2001-04-26 | Mugur | 2001-06-06 | 2001-05-03 |  |  |  |  | 2000-10-16 |  | 2001-03-01 | 2001-03-19 | [6 empty] | 2001-04-19 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 170 | 0 | 49.3 | K 739 494 | 350 | 0 | 49.30 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Craiova | MW | 171 | 1.2 | 47/1.2 | 58 | [7 empty] | RBS | [10 empty] | CR044 | GANEASA | 349 | 1.2 | 47/1.2 | 62 | [23 empty] | Cristian CROITOR | COSMOROM | [32 empty] | 119 | Com Plesoiu | Olt | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CR166 | OTESANI | Road Horezu-Craiova(9) | CR124 Govora_RTC | Oltenia | 45 05 06.9 | 24 01 36.8 | 45 05 11 | 24 01 38.2 | Comuna Otesani, Punctul Secatura | Lungu Florea, Com. Otesani, jud. Valcea/Lungu Florea, Com. Otesani, jud. Valcea | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  |  | TN | 30 |  | N/A | PROTELCO | OK | FIBEC | 2000-12-15 | 2001-03-23 | YesV | 2001-05-17 | Mugur |  | 2001-05-23 |  |  |  |  | 2000-10-16 |  | 2000-12-05 | 2000-12-21 | [6 empty] | 2001-03-26 |  |  |  |  | GATA-2101 |  |  | RBS 2101 |  |  |  |  | K 739 494 | 190 | 0 | 28.5 | K 739 494 | 330 | 0 | 28.5 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 40 | 40 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 80 | ML 15 E 1+0 | Craiova | MW | 329 |  | 27.7 | 40 | [7 empty] | RBS | [10 empty] | CR127 | HOREZU | 149 |  | 47/1.2 | 59 | [20 empty] | new01 Govora-Craiova |  | 2001-08-01 | Cristi CROITOR | Cosmorom | [32 empty] | 460 | Otesani | Valcea | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CR167 | DAESTI | Road Rm. Valcea-Slatina(8) | CR124 Govora_RTC | Oltenia | 44 57 44.6 | 24 07 17.7 | 44 57 42 | 24 07 10 | Sat Daesti, comuna Popesti | Lupescu Nicolae, sat Daesti, com. Popesti/Lupescu Nicolae | 2102 | M | C+C+C+ | 2/2/2 | N/A | [12 empty] | 0 | TN | 50 |  | N/A | PROTELCO | OK | FIBEC | 2000-12-09 | 2001-03-20 | YesV | 2001-06-08 | Mugur | 2001-05-07 | 2001-06-13 |  |  |  |  | 2000-10-16 |  | 2000-11-30 | 2000-12-18 |  | 2001-07-10 |  | 2001-03-26 | ICOM | ORION | 2001-03-21 | 2001-03-21 | 2001-03-27 | 2001-03-28 | 2001-04-04 |  | Prov |  | LOS |  |  |  |  | K 739 494 | 150 | 0 | 48.5 | K 739 494 | 230 | 0 | 48.5 | K 739 494 | 310 | 0 | 48.5 |  |  |  |  | N/A | 59 | 59 | 1 1/4" | 59 | 59 | 1 1/4" | 59 | 59 | 1 1/4" |  |  |  | 354 | ML 15 E 1+0 | Craiova | MW | 114 | 0.6 | 47.5 | 58 | 15/84 HP |  |  | 2U-3 |  |  |  | RBS | [6 empty] | Se muta echipamentul pe az coresp link-ului cu CR270 |  |  |  | CR270 | CARSTANESTI |  | 0.6 | 48/1.2 | 57 | 15/89 HP(se muta de la CR160 la CR270) | [6 empty] | 66* | DIEKAT | 2001-05-11 | 918 | 2001-05-11 | 2001-05-11 | 2001-05-25 | [6 empty] | new01 Govora-Craiova |  | 2001-08-01 | Cristi Croitor | Cosmorom | [32 empty] | 301 | Popesti | Valcea | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CR168 | CUIENI | Road Horezu-Craiova(9) | CR025 Amarandia_RTC | Oltenia | 44 53 31.6 | 24 04 19.3 | 44 53 31.6 | 24 04 19.3 | Com. Roiesti, sat Cuieni | Ciuca Florica, com. Roiesti, sat Cuieni/Ciuca Florica, com. Roiesti, sat Cuieni | 2102 | M | C+C+C+ | 2/2/2 | N/A | [12 empty] | 0 | TN | 50 |  | N/A | PROTELCO | OK | SVF | 2000-12-15 | 2001-03-05 | YesV | 2001-03-15 | Mugur |  | 2001-03-21 |  |  |  |  | 2000-10-16 |  | 2000-12-08 | 2000-12-22 |  |  |  | 2001-03-13 | ICOM | SVF | 2001-03-07 | 2001-03-07 | 2001-03-14 | 2001-03-15 | 2001-03-19 |  |  |  | RBS 2101 CR169 |  |  |  |  | K 739 494 | 10 | 0 | 48.5 | K 739 494 | 200 | 0 | 48.5 | K 739 494 | 300 | 0 | 48.5 |  |  |  |  | N/A | 60 | 60 | 1 1/4" | 60 | 60 | 1 1/4" | 60 | 60 | 1 1/4" |  |  |  | 360 | ML 15 E 1+0 | Craiova | MW | 208 |  | 47.5 | 59 | [7 empty] | RBS | [10 empty] | CR169 | BECSANI | 27 | 1.2 | 37.7/1.2 | 50 | [23 empty] | Cristian CROITOR | Cosmorom | [32 empty] | 319 | Cuieni | Valcea | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CR169 | BECSANI | Road Horezu-Craiova(9) | CR025 Amarandia_RTC | Oltenia | 44 48 56.3 | 24 00 53.8 | 44 49 12.9 | 24 01 10.3 | Sat Dejoi, com. Fartasesti | Primaria com. Fartasesti, jud Valcea/Dl. Voicescu Nicolae - primar, Dl. Popa Doru-secreatar, D-na. Stanciucu Elisabeta - contabil | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  |  | TN | 40 |  | N/A | PROTELCO | OK | EL-MONT | 2001-02-15 | 2001-03-27 | YesV | 2001-04-04 | Mugur | 2001-04-17 | 2001-04-10 |  |  |  | 2000-12-07 | 2000-12-07 |  | 2001-02-01 | 2001-02-20 | [6 empty] | 2001-03-29 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 20 | 0 | 38.5 | K 739 494 | 200 | 0 | 38.5 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 50 | 50 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 100 | ML 15 E 1+0 | Craiova | MW | 167 | 1.2 | 37.7/1.2 | 50 | [7 empty] | RBS | [10 empty] | CR170 | BOTORANI | 347 |  | 48 | 59 | [23 empty] | Cristi CROITOR | Petrica BURGHIU | [32 empty] | 248 | Fartasesti | Valcea | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CR170 | BOTORANI | Road Horezu-Craiova(9) | CR025 Amarandia_RTC | Oltenia | 44 44 43.5 | 24 02 14.3 | 44 44 42.1 | 24 02 14 | Sat Botorani, com. Maciuca | Maria Florian - sat Botorani/Maria Florian - sat Botorani | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | N/A | N/A |  |  |  | 0 | TN | 50 |  | N/A | PROTELCO | OK | EL-MONT | 2000-11-22 | 2000-12-22 | YesV | 2001-01-30 | Mugur | 2001-01-17 | 2001-02-01 |  |  |  |  | 2000-10-16 |  | 2000-11-17 | 2000-11-30 |  |  |  | 2000-12-28 | ICOM | ORION | 2000-12-27 | 2001-01-08 | 2001-01-09 | 2001-01-10 | 2001-01-17 |  | Prov |  | RBS 2101 CR171 |  |  |  |  | K 739 494 | 90 | 0 | 49.4 | K 739 494 | 235 | 0 | 49.4 | K 739 494 | 330 | 0 | 49.4 |  |  |  |  | N/A | 60 | 60 | 1 1/4" | 60 | 60 | 1 1/4" | 60 | 60 | 1 1/4" |  |  |  | 360 | ML 15 E 1+1 | Craiova | MW | 214 | 1.2 | 48 | 59 | 15/84 | YES | 4x2/8 | 4U-1 |  |  |  | RBS | [10 empty] | CR171 | BALCESTI | 34 | 1.2 | 47.5 | 59 | 15/89 | [6 empty] | 15* | ORION |  | 498 | 2001-01-29 | 2001-02-01 | 2001-02-15 | [9 empty] | Cristian CROITOR | Petrica BURGHIU | [32 empty] | 320 | Botorani | Valcea | [6 empty] | 1 | 2 |  | 1 | 2
Phase_2 | CS | CR171 | BALCESTI | Road Horezu-Craiova(9) | CR025 Amarandia_RTC | Oltenia | 44 39 24.9 | 23 57 11.8 | 44 39 15.6 | 23 57 17.5 | Com Balcesti, sat Palei, punctul "Dealul Raii", tarla 34, parcela 20/45 | Nicolaescu Niculita - com. Balcesti, sat palei/Nicolaescu Niculita - com. Balcesti, sat palei | MUTAT | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | PROTELCO | OK | EL-MONT | 2000-11-22 | 2000-12-22 | YesV | 2001-02-01 | Mugur | 2001-01-17 | 2001-02-01 |  |  |  |  | 2000-10-16 |  | 2000-11-17 | 2000-11-29 |  |  |  | 2000-12-28 | ICOM | ORION | 2000-12-27 | 2001-01-10 | 2001-01-11 | 2001-01-12 | 2001-01-17 |  | Yes |  | 2101 MOVED |  |  |  |  | K 739 494 | 30 | 0 | 48.5 | K 739 494 | 200 | 0 | 48.5 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 120 | ML 15 E 1+1 | Craiova | MW | 197 |  | 47.5 | 59 |  |  |  | 4U-1 |  |  |  | N/A | [10 empty] | CR172 | BULZESTI | 17 |  | 47.3 | 60 | [23 empty] | Cristian CROITOR | Petrica BURGHIU | [32 empty] | 289 | Balcesti | Valcea | [6 empty] | 1 | 2 |  | 1 | 2
Phase_2 | CS | CR172 | BULZESTI | Road Horezu-Craiova(9) | CR025 Amarandia_RTC | Oltenia | 44 30 51.9 | 23 53 37.3 | 44 30 49.7 | 23 53 44.3 | Com. Bulzesti, sat Gura Racului, tarla 77, parcela 144 | Popescu Aurelian - Craiova, str. Brazda lui Novac, bl.H3, sc.1, ap.15/Popescu Aurelian - Craiova, str. Brazda lui Novac, bl.H3, sc.1, ap.15 | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | PROTELCO | OK | COMARK | 2000-11-22 | 2001-02-08 | YesV | 2001-03-27 | Mugur | 2001-02-12 | 2001-03-29 |  |  |  |  | 2000-10-16 |  | 2000-11-17 | 2000-11-30 | [6 empty] | 2001-02-12 |  |  |  |  | GATA-2101 | Prov |  | RBS 2101 |  |  |  |  | K 739 494 | 20 | 0 | 48.5 | K 739 494 | 200 | 0 | N/A | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+1 | Craiova | MW | 199 |  | 47.3 | 60 | [7 empty] | RBS | [10 empty] | CR173 | SIMNIC_DRTV | 19 |  | 60 | 70 | [23 empty] | Cristian CROITOR | [33 empty] | 200 | Bulzesti | Dolj | [6 empty] | 1 | 2 |  | 1 | 2
Phase_2 | CS | CR173 | SIMNIC_DRTV | Road Horezu-Craiova(9) | CR025 Amarandia_RTC | Oltenia | 44 22 06 | 23 49 25 | 44 22 06.8 | 23 49 25.8 | DRTV Simnic | DRTv Timisoara/ | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  | 0 | TE | 75 |  | N/A | PROTELCO | OK | COMARK | 2000-12-22 | 2001-02-05 | YesV | 2001-03-14 | Mugur | 1900-01-10 | 2001-03-21 |  |  |  | N/A | 2000-10-16 |  | 2000-11-17 | 2000-12-11 | [6 empty] | 2001-02-12 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 20 | 0 | 48.5 | K 739 494 | 200 | 0 | 48.5 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 23 E 1+1 | Craiova | MW | 209 |  | 32.2 | 42 | [7 empty] | RBS | [10 empty] | CR025 | AMARADIA_RTC | 29 | 0.6 | 32/0.6 | 53 | [23 empty] | Cristian CROITOR | Cosmorom | [32 empty] | 184 | Simniceni | Dolj | [6 empty] | 1 | 2 |  | 1 | 2
Phase_2 | CS | CR174 | DRAGUTESTI | Road Tg.Jiu-Filiasi(8) | CR057 CTA_9 MAI_RTC | Oltenia | 44 57 11 | 23 11 47.2 | 44 57 37.8 | 23 12 24.6 | Intravilan, sat Carbesti, comuna Dragutesti | Cornea Gh. Ion, sat Carbesti, comuna Dragutesti/Cornea Gh. Ion, sat Carbesti, comuna Dragutesti | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | IMSAT | OK | IMSAT | 2001-01-18 | 2001-03-15 | YesV | 2001-05-04 | Mugur | 2001-04-06 | 2001-05-09 |  |  |  |  | 2000-10-12 |  | 2001-01-11 | 2001-01-19 | [6 empty] | 2001-03-15 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 30 | 0 | 48.25 | K 739 494 | 250 | 0 | 48.25 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Craiova | MW | 35 |  | 47 | 60 | [7 empty] | RBS | XC40057 | [9 empty] | CR057 | CTA_9 MAI | 216 | 0.6 | 27/0.6 | 18 | [20 empty] | 30N02 Tg.Jiu CTA_9 Mai-Craiova |  | OK | Cristian CROITOR | Cosmorom | [32 empty] | 196 | Dragutesti | Gorj | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CR175 | BRADET_DRTV | Road Tg.Jiu-Filiasi(8) | CR057 CTA_9 MAI_RTC | Oltenia | 44 53 00 | 23 04 52.2 | 44 53 00 | 23 04 52.2 | sat Timiseni, com Farcasesti, tarla 10 | Trotea Mihai, sat Bradet, jud. Gorj, tel. 053/376507/Trotea Mihai, sat Bradet, jud. Gorj, tel. 053/376507 | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  | 0 | TE | 69 |  | N/A | IMSAT | OK | ARGOS | 2001-05-11 | 2001-06-15 | YesV | 2001-07-05 | Mugur |  | 2001-06-12 |  |  |  | N/A | 2000-10-16 |  | 2001-05-09 | OK | [6 empty] | 2001-07-13 |  |  |  |  | GATA-2101 |  |  | RBS 2101 |  |  |  |  | K 739 494 | 40 | 0 | 49.5 | K 739 494 | 135 | 0 | 49.5 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 56 | 56 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 112 | ML 15 E 1+0 | Craiova | MW | 49 | 1.2 | 40/1.2 | 47 | [7 empty] | RBS | XC40057 | [9 empty] | CR174 | DRAGUTESTI | 229 |  | 47 | 60 | [20 empty] | 30N02 Tg.Jiu CTA_9 Mai-Craiova |  | OK | Cristian CROITOR | Petrica BURGHIU | [32 empty] | 365 | Bradet | Gorj | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CR176 | MOI | Road Tg.Jiu-Filiasi(8) | CR057 CTA_9 MAI_RTC | Oltenia | 44 54 01.1 | 23 12 25.7 | 44 54 06.3 | 23 12 29 | Com. Moi | Robescu Geneta - sat Moi, com. Balteni/Robescu Geneta - sat Moi, com. Balteni | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | IMSAT | OK | IMSAT | 2000-12-08 | 2001-02-25 | YesV | 2001-03-08 | Mugur | 2001-03-06 | 2001-03-13 |  |  |  | 2000-11-24 | 2000-10-16 |  | 2000-12-04 | 2000-12-12 | [6 empty] | 2001-02-27 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 135 | 0 | 48.5 | K 739 494 | 260 | 0 | 48.5 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Craiova | MW | 260 |  | 47.3 | 60 | [7 empty] | RBS | XC40057 | [9 empty] | CR175 | BRADET_DRTV | 79 | 1.2 | 38/1.2 | 45 | [20 empty] | 30N02 Tg.Jiu CTA_9 Mai-Craiova |  | OK | Cristian CROITOR | Cosmorom | [32 empty] | 163 | Moinesti | Gorj | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CR177 | BALTENI | Road Tg.Jiu-Filiasi(8) | CR079 Filiasi_RTC | Oltenia | 44 50 48.9 | 23 17 33.8 | 44 51 01.1 | 23 17 48.8 | Com. Balteni, sat Pesteana Jiu | Ispas Elena - com. Balteni, sat Pesteana Jiu/Ispas Elena - com. Balteni, sat Pesteana Jiu | 2102 | M | C+C+C+ | 2/2/2 | N/A | [12 empty] | 0 | TN | 50 |  | N/A | IMSAT | OK | MULTISERV | 2000-11-29 | 2001-03-12 | YesV | 2001-03-29 | Mugur | 2001-04-06 | 2001-05-04 |  |  |  |  | 2000-10-27 |  | 2000-11-23 | 2000-12-12 |  |  |  | 2001-03-26 | ICOM | VECTOR | 2001-03-13 | 2001-03-13 | 2001-03-27 | 2001-03-28 | 2001-04-02 |  | Yes |  | RBS 2101 CR179 |  |  |  |  | K 739 494 | 60 | 0 | 48.3 | K 739 494 | 150 | 0 | 48.3 | K 739 494 | 310 | 0 | 48.3 |  |  |  |  | N/A | 60 | 60 | 1 1/4" | 60 | 60 | 1 1/4" | 60 | 60 | 1 1/4" |  |  |  | 360 | ML 15 E 1+0 | Craiova | MW | 148 |  | 47 | 50 | [7 empty] | RBS | [10 empty] | CR179 | PLOPSORU | 327 |  | 47 | 60 | [20 empty] | 30N01 Filiasi-Craiova |  | 2001-02-23 | Cristian CROITOR | Petrica BURGHIU | [32 empty] | 147 | Balteni | Gorj | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CR178 | TICLENI | Road Tg.Jiu-Filiasi(8) | CR079 Filiasi_RTC | Oltenia | 44 52 45.2 | 23 24 50.9 | 44 52 50.3 | 23 24 53.6 | Extravilan com. Ticleni, punctul "La Releu" | Ticleanu Constantin si Ungureanu Constantin/Ticleanu Constantin si Ungureanu Constantin | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | IMSAT | OK | MULTISERV | 2000-11-28 | 2001-02-20 | YesV | 2001-03-08 | Mugur | 2001-02-26 | 2001-03-13 |  |  |  |  | 101/16 |  | 2000-11-17 | 2000-12-04 | [6 empty] | 2001-02-21 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 25 | 0 | 48.3 | K 739 494 | 250 | 0 | 48.3 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Craiova | MW | 249 |  | 47 | 60 | [7 empty] | RBS | [10 empty] | CR177 | BALTENI | 69 |  | 47 | 50 | [20 empty] | 30N01 Filiasi-Craiova |  | 2001-02-23 | Cristian CROITOR | Cosmorom | [32 empty] | 232 | Ticleni | Gorj | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CR179 | PLOPSORU | Road Tg.Jiu-Filiasi(8) | CR079 Filiasi_RTC | Oltenia | 44 46 20.1 | 23 21 25.2 | 44 46 20.1 | 23 21 25.2 | Intravilan sat Sardanesti, com. Plopsoru | Vaduva Gheorghe, Comuna Plopsoru, sat Sardanesti, jud. Gorj/Vaduva Gheorghe, Comuna Plopsoru, sat Sardanesti, jud. Gorj | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | IMSAT | OK | AQUA | 2000-12-08 | 2001-02-19 | YesV | 2001-03-08 | Mugur | 2001-05-07 | 2001-03-13 |  |  |  |  | 2000-10-16 |  | 2000-12-14 | 2000-12-11 | [6 empty] | 2001-02-20 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 150 | 0 | 48.30 | K 739 494 | 320 | 0 | 48.3 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Craiova | MW | 155 |  | 47 | 60 | [7 empty] | RBS | [10 empty] | CR180 | CEPLEA | 335 | 1.2 | 47/1.2 | 60 | [20 empty] | 30N01 Filiasi-Craiova |  | 2001-02-23 | Cristian CROITOR | Cosmorom | [32 empty] | 140 | Plopsoru | Gorj | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CR180 | CEPLEA | Road Tg.Jiu-Filiasi(8) | CR079 Filiasi_RTC | Oltenia | 44 41 28.2 | 23 24 34.6 | 44 41 28.2 | 23 24 34.6 | Intraviran Localitatea Ceplea | Primaria Comunei Plopsoru, sat Ceplea/Primarul Grigore Petre | 2102 | M | C+C+C+ | 2/2/2 | N/A | [12 empty] | 0 | TN | 50 |  | N/A | IMSAT | OK | AQUA | 2001-01-25 | 2001-03-12 | YesV | 2001-05-18 | Mugur | 2001-05-07 | 2001-05-23 |  |  |  |  | 2000-10-16 |  | 2000-12-14 | 2001-01-17 |  |  |  | 2001-03-26 | ICOM | VECTOR | 2001-03-13 | 2001-03-13 | 2001-03-27 | 2001-03-28 | 2001-04-02 | IVAN | Yes | Ion Soare | 2001-06-20 | 2001-06-20 | 2001-06-20 | 2001-06-29 | 2001-07-11 | K 739 494 | 160 | 0 | 48.3 | K 739 494 | 270 | 0 | 48.3 | K 739 494 | 340 | 0 | 48.3 |  |  |  |  | N/A | 60 | 60 | 1 1/4" | 60 | 60 | 1 1/4" | 60 | 60 | 1 1/4" |  |  |  | 360 | ML 15 E 1+0 | Craiova | MW | 145 | 0.6 | 47/1.2 | 60 | 15/89 |  |  | 4U-1 |  |  |  | RBS | [9 empty] | 1 | CR181 | CAPU DEALULUI | 325 | 0.6 | 47/1.2 | 60 | 15/84 | [6 empty] | 71* | VECTOR | 2001-05-24 | 959 | 2001-05-24 |  |  |  |  | 2001-06-20 |  |  |  | 30N03 Filiasi-Craiova |  | 2001-02-23 | Cristian CROITOR | CATALINA CIOCAN | [32 empty] | 144 | Gorj | Gorj | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CR181 | CAPU DEALULUI | Road Tg.Jiu-Filiasi(8) | CR079 Filiasi_RTC | Oltenia | 44 37 40.3 | 23 28 14.4 | 44 37 41.5 | 23 28 19.9 | Extravilan Comuna Branesti, sat Capul Dealului | Procopie Lucian/Procopie Lucian-Com. Branesti, sat Capu Dealului | 2101 | M | C+ | 2 | 2101 | [6 empty] | N/A | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | IMSAT | OK | DUAL | 2000-12-01 | 2001-02-16 | YesV | 2001-03-08 | Mugur | 2001-03-14 | 2001-03-14 |  |  |  |  | 2000-10-16 |  | 2000-11-23 | 2000-12-15 |  |  |  | 2001-05-24 | ICOM | VECTOR | 2001-02-19 | 2001-02-19 | 2001-05-25 | 2001-06-13 | 2001-06-20 | IVAN | Yes | Ion Soare | 2001-06-20 | 2001-06-20 | 2001-06-20 | 2001-06-29 | 2001-07-11 | K 739 494 | 160 | 0 | 48.25 | K 739 494 | 330 | 0 | 48.25 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 55 | 55 | 7/8'' | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+1 | Craiova | MW | 148 | 0.6 | 47/0.6 | 60 | 15/84 | YES | 4x2/8 | 4U-1 |  |  |  | RBS | [9 empty] | 1 | CR218 | FILIASI DEAL | 328 | 0.6 | 46.5 | 70 | 15/89 | [6 empty] | 71* | VECTOR | 2001-05-24 | 958 | 2001-05-24 |  |  |  |  | 2001-06-20 |  |  |  | 30N03 Filiasi-Craiova |  | 2001-02-23 | Cristian CROITOR | CATALINA CIOCAN | [32 empty] | 118 | Capu Dealului | Gorj | [6 empty] | 1 | 2 |  | 1 | 2
Phase_2 | CS | CR182 | BUMBESTI | Road Tg. Jiu-Petrosani(1) | CR056 Central_RTC | Banat | 45 10 35.5 | 23 23 19.2 | 45 10 46.7 | 23 23 11.2 | Intravilan Com.Bumbesti Jiu | Ciobea Zanfira, comuna Musetescu, jud. Gorj/Ciobea Zanfira, comuna Musetescu, jud. Gorj | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | IMSAT | OK | TENDORI | 2001-03-08 | 2001-05-30 | YesV | 2001-07-05 | Mugur |  | 2001-06-12 |  |  |  |  | 2000-10-16 |  | 2001-02-21 | 2001-03-14 | [6 empty] | 2001-06-05 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 200 | 0 | 48.25 | K 739 494 | 350 | 0 | 48.25 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Craiova | MW | 209 | 1.2 | 47/1.2 | 60 | [7 empty] | RBS | [10 empty] | CR058 | SILOZ | 29 | 1.2 | 48/1.2 | 20? | [20 empty] | 30N01 Tg.Jiu Central-Craiova |  | OK | Cristian CROITOR | [33 empty] | 347 | Gorj | Gorj | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CR184 | LAPUSATA | Road Horezu-Craiova(9) | CR025 Amarandia_RTC | Oltenia | 44 56 29.6 | 24 00 02 | 44 56 39.2 | 23 59 38.9 | Comuna Lapusata, sat Serbanesti | Bondoc Lenuta, comuna Lapusata, sat Serbanesti/Bondoc Lenuta, comuna Lapusata, sat Serbanesti | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | PROTELCO | OK | GIRARDOT | 2000-12-09 | 2001-03-23 | YesV | 2001-05-17 | Mugur | 2001-05-07 | 2001-05-23 |  |  |  |  | 2000-10-16 |  | 2000-11-30 | 2000-12-21 | [6 empty] | 2001-03-26 | 2001-03-26 |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 140 | 0 | 48.5 | K 739 494 | 340 | 0 | 48.5 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 59 | 59 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 118 | ML 15 E 1+0 | Craiova | MW | 135 | 1.2 | 47.5/1.2 | 58 | [7 empty] | RBS | [10 empty] | CR168 | CUIENI | 315 |  | 47.5 | 59 | [23 empty] | Cristi CROITOR | Cosmorom | [32 empty] | 314 | Lapusata | Valcea | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CR185 | ULMETU | Road Horezu-Craiova(9) | CR025 Amarandia_RTC | Oltenia | 44 00 09.4 | 23 58 44 | 45 00 08.9 | 23 58 44 | Comuna Copaceni, sat Ulmetu | Cinca Ionela, Rm. Valcea bl. 55, sc.A, ap. 4, jud.Valcea/Cinca Ionela, Rm. Valcea bl. 55, sc.A, ap. 4, jud.Valcea | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | PROTELCO | OK | CONDOR | 2001-03-06 | 2001-06-30 | in exec |  | Mugur | [6 empty] | 2000-10-16 |  | 2000-12-22 | 2001-03-14 | [14 empty] | RBS 2101 |  |  |  |  | K 739 494 | 160 | 0 | 48.5 | K 739 494 | 330 | 0 | 48.5 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Craiova | MW | 163 | 1.2 | 47.7/1.2 | 59 | [7 empty] | RBS | [10 empty] | CR184 | LAPUSATA | 343 |  | 47.5 | 58 | [23 empty] | Cristi CROITOR | Cosmorom | [32 empty] | 400 | Ulmetu | Valcea | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CR187 | COMBINAT TARGOVISTE | Road Targoviste-Gaiesti(4) | CR063 Targoviste_RTC | Muntenia | 44 54 30.5 | 25 26 56.1 |  |  |  |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [17 empty] | DIEKAT | OK | APOLLO | 2001-08-01 | 2001-08-20 | DL |  | Doru | [5 empty] | 2000-11-23 | [18 empty] | CTR | [13 empty] | 0 | 0 | 0 | [17 empty] | 0 | ML 38 E 1+0 | Baneasa | MW | 0 | [10 empty] | RBS | [10 empty] | CR061 | UNIRII | 180 |  | 44 | 19 | [23 empty] | Petrica BURGHIU | COSMOROM | [32 empty] | 279 | [8 empty] | 1 | 2 |  |  | 2
Phase_2 | CS | CR188 | VIISOARA | Road Targoviste-Gaiesti(4) | CR063 Targoviste_RTC | Muntenia | 44 51 30.5 | 25 24 56.1 | 44 51 16.3 | 25 24 11.8 | DN 72 Targoviste-Gaesti km. 19+450 | Popa Ioan/Popa Ioan , Primaria Lucieni, tel. 045/630071 | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | DIEKAT | OK | VECTOR | 2001-01-16 | 2001-02-22 | YesV | 2001-03-20 | Doru | 2001-07-06 | 2001-03-29 |  |  |  |  | 2000-11-19 |  | 2001-01-11 | 2001-01-23 | [6 empty] | 2001-02-23 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 40 | 0 | 49.3 | K 739 494 | 200 | 0 | 49.3 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Baneasa | MW | 31 |  | 41.5 | 49 | [7 empty] | RBS | [10 empty] | CR187 | COMBINAT TARGOVISTE | 210 | [26 empty] | Petrica BURGHIU | Cosmorom | [32 empty] | 278 | Viisoara | Dambovita | [6 empty] | 1 | 2 |  |  | 2
Phase_2 | CS | CR189 | PICIOR DE MUNTE | Road Targoviste-Gaiesti(4) | CR190 Gaiesti_RTC | Muntenia | 44 46 23.4 | 25 23 03.5 | 44 46 31.6 | 25 23 12.5 | Com. Dragodana, sat Picior de Munte | Stoica Gheorghe, com. Dragodana, sat Picior de Munte-094/ 902 465/Stoica Gheorghe, com. Dragodana, sat Picior de Munte-094/ 902 465 | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | DIEKAT | OK | VECTOR | 2000-12-22 | 2001-02-22 | YesV | 2001-04-09 | Doru | 2001-02-21 | 2001-04-10 |  |  |  |  | 2000-11-19 |  | 2000-12-06 | 2001-01-09 | [6 empty] | 2001-02-23 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 20 | 0 | 49.3 | K 739 494 | 210 | 0 | 49.3 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Baneasa | MW | 219 |  | 48 | 58 | [7 empty] | RBS | [10 empty] | CR190 | GAIESTI_RTC | 39 | 0.6 | 26 | 23 | [23 empty] | Petrica BURGHIU | Cosmorom | [32 empty] | 234 | Picior de Munte | Dambovita | [7 empty] | 2 |  | 1 | 2
Phase_2 | CS | CR190 | GAIESTI_RTC | Road Targoviste-Gaiesti(4) | CR190 Gaiesti_RTC | Muntenia | 44 43 11.6 | 25 19 14.6 | 44 43 11.6 | 25 19 14.6 | Romtelecom, Str. 13 Septembrie nr.6 | Romtelecom/ | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | Yes | N/A |  |  |  | 15 | B | 15 | 19m new pilonet | N/A | DIEKAT | OK | APOLLO | 2000-12-19 | 2001-01-31 | YesV | 2001-03-20 | Doru | 2001-02-05 | 2001-03-29 |  |  |  | N/A | 2000-11-22 |  | 2000-11-29 | 2000-12-19 |  |  |  | 2001-02-01 | ICOM | ORION | 2001-02-01 | 2001-02-01 | 2001-02-05 | 2001-02-13 | 2001-02-16 |  | Yes | Theo Radoi | 2001-03-24 | 2001-03-24 | 2001-03-24 | 2001-04-24 | 2001-05-03 | K 739 494 | 105 | 0 | 34 | K 739 494 | 220 | 0 | 34 | K 739 494 | 315 | 0 | 34 |  |  |  |  | N/A | 31 | 31 | 7/8" | 31 | 31 | 7/8" | 31 | 31 | 7/8" |  |  |  | 186 | N/A | Baneasa | FO | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | RBS | 40190 | [6 empty] | 50/outdoor |  |  | BSC21 | BANEASA |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PAUN | OK | N/A |  | N/A | N/A | 30N01 Gaiesti-Baneasa |  | 2001-03-23 | Petrica BURGHIU | Cosmorom | [32 empty] | 192 | Gaesti | Dambovita | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | CR191 | TURN CONEL | Road Pitesti-Curtea de Arges(4+1) | YR191 Curtea de Arges_RTC | Muntenia | 45 08 44.1 | 24 40 30.9 | 45 08 44.1 | 25 40 30.9 | B-ul Basarabilor, Nr. 82-84, Curtea de Arges, jud. Arges | Conel Arges/Ing. Vlaicu Valeria, tel. 048/7222100 Interior259 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [12 empty] | 0 | TE | 52 |  | N/A | ISAF | OK | EL-MONT | 2001-04-10 | 2001-05-05 | YesV | 2001-05-16 | Doru |  | 2001-05-23 |  |  |  |  | 2000-11-19 |  | 2001-03-27 | 2001-04-18 |  |  |  | 2001-05-09 | ICOM | ORION | 2001-05-09 | 2001-05-09 | 2001-05-15 | 2001-06-12 | 2001-06-13 |  | Yes |  | 2MB/S |  |  |  |  | K 739 494 | 0 | 0 | 50 | K 739 494 | 190 | 0 | 50 | K 739 494 | 280 | 0 | 50 |  |  |  |  | N/A | 55 | 55 | 1 1/4" | 55 | 55 | 1 1/4" | 55 | 55 | 1 1/4" |  |  |  | 330 | ML 38 E 1+0 | Baneasa | MW | 164 | 0.3 | 30/0.3 | 40 | [7 empty] | RBS | [10 empty] | YR191 | CURTEA DE ARGES_RTC | 343 | [23 empty] | 30N01 Curtea de Arges-Baneasa |  | 2001-06-27 | Petrica BURGHIU | Cosmorom | [33 empty] | Curtea de Arges | Arges | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CR192 | ZIGONENI | Road Pitesti-Curtea de Arges(4+1) | YR191 Curtea de Arges_RTC | Muntenia | 45 05 27.1 | 24 40 30.2 | 45 05 21.5 | 24 40 32.4 | Sat Zigoneni, com. Baiculesti | Pungoci Mircea - Pitesti, str. Negru Voda nr.46, Bl. C1, sc.C, ap.6/Pungoci Mircea - Pitesti, str. Negru Voda nr.46, Bl. C1, sc.C, ap.6/048/218561 | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | ISAF | OK | ISAF | 2001-03-08 | 2001-05-24 | Yes |  | Doru | [6 empty] | 2000-11-19 |  | 2001-02-21 | 2001-03-14 | [6 empty] | 5/28/2001(Nu se va livra echipament) |  |  |  |  | GATA-2101 | Yes |  | LOS |  |  |  |  | K 739 494 | 160 | 0 | 49 | K 739 494 | 350 | 0 | 49 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 55 | 55 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 110 |  | Baneasa | Nu are line of site | [11 empty] | RBS | [10 empty] | No | [25 empty] | 30N01 Curtea de Arges-Baneasa |  | 2001-06-27 | Petrica BURGHIU | [33 empty] | 116 | Zigoneni | Arges | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | CR193 | VALCELE | Road Pitesti-Curtea de Arges(4+1) | CR013 Centru_RTC | Muntenia | 44 59 48.2 | 24 44 09.4 | 44 59 53.5 | 24 44 07.3 | Sat Valcele, com. Merisani | Cristescu Constanta, Pitesti, str. Craiovei Bl.P4 Ap.31/Cristescu Constanta, Pitesti, str. Craiovei Bl.P4 Ap.31 | 2101 | M | C+ | 2 | 2101 | [12 empty] | 0 | TN | 50 |  | N/A | ISAF | OK | ISAF | 2001-03-08 | 2001-05-24 | Yes |  | Doru | [5 empty] | OK | 2000-11-19 |  | 2001-03-01 | 2001-04-09 | [6 empty] | 2001-05-28 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 150 | 0 | 50 | K 739 494 | 330 | 0 | 50 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | 55 | 55 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 110 | ML 15 E 1+0 | Baneasa | MW | 151 | 1.2 | 47/1.2 | 52 | [7 empty] | RBS | XC41013 |  |  | XC41013 | [6 empty] | CR194 | DOBROGOSTEA | 331 | 1.2 | 47/1.2 | 57 | [20 empty] | 30N05 Pitesti-Baneasa |  | OK | Petrica BURGHIU | Cosmorom | [32 empty] | 345 | Valcele | Arges | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CR194 | DOBROGOSTEA | Road Pitesti-Curtea de Arges(4+1) | CR013 Centru_RTC | Muntenia | 44 55 27.5 | 24 47 34.2 | 44 55 27.5 | 24 47 34.2 | Loc. Dobrogostea | Cristache Gheorghina/Cristache Gheorghina, sat Dobrogostea | 2101 | M | C+ | 2 | 2101 | [12 empty] | 0 | TN | 50 |  | N/A | ISAF | OK | DIRDATES | 2001-03-08 | 2001-05-31 | YesV | 2001-07-04 | Doru |  | 2001-06-12 |  |  |  | OK | 2000-11-19 |  | 2001-03-01 | 2001-04-09 | [6 empty] | 2001-06-05 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 150 | 0 | 49 | K 739 494 | 340 | 0 | 49 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 23 E 1+0 | Baneasa | MW | 146 | 0.6 | 47/0.6 | 57 | [7 empty] | RBS | [10 empty] | CR020 | DRTV PITESTI | 326 | 0.6 | 50/0.6 | [21 empty] | 30N04 Pitesti-Baneasa |  | OK | Petrica BURGHIU | Cosmorom | [32 empty] | 312 | Dobrogostea | Arges | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CR196 | BILCIURESTI_RTC | Road Bucuresti-Buftea-Ploiesti(6) | BX523 Ploiesti Vest_CTA | Muntenia | 44 45 04.2 | 25 47 57 | 44 45 04.2 | 25 47 57 | Romtelecom Bilciulesti, Comuna Bilciulesti | Romtelecom (Enache Costica, loc. Bilciuresti)/Romtelecom (Enache Costica, loc. Bilciuresti) | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | N/A | N/A |  |  |  | 0 | TE | 42 |  | Room | DIEKAT | OK | APOLLO | 2001-01-09 | 2001-01-30 | YesV | 2001-03-23 | Doru | 2001-02-13 | 2001-03-29 |  |  |  | N/A | 2000-11-19 |  | 2000-11-29 | 2001-01-09 |  |  |  | 2001-02-01 | ICOM | SVF | 2001-02-01 | 2001-02-01 | 2001-02-06 | 2001-02-09 | 2001-02-19 |  | Yes | Alexandru Toma | 2001-04-13 | 2001-04-13 | 2001-04-13 | 2001-06-06 | 2001-06-19 | K 739 494 | 150 | 0 | 40 | K 739 494 | 250 | 0 | 40 | K 739 494 | 350 | 0 | 40 |  |  |  |  | N/A | 45 | 45 | 7/8" | 45 | 45 | 7/8" | 45 | 45 | 7/8" |  |  |  | 270 | ML 23 E 1+0 | Baneasa | MW | 106 | 0.6 | 37.8 | 49 | 23/58 |  | 4X2/8 | 2U-3 |  |  |  | RBS | [9 empty] | 1 | CR097 | BUJOREANCA | 286 | 0.6 | 38/0.6 | 60 | 23/56 | [6 empty] | 22* | SVF | 2001-02-01 | 593 | 2001-02-05 | 2001-02-05 | 2001-02-12 | VLAD | OK | 2001-04-13 |  | 2001-05-03 | 2001-05-11 | 30N06 Pliesti Vest-Baneasa |  | 2001-03-02 | Petrica BURGHIU | Petrica BURGHIU | [32 empty] | 144 | Bilciuresti | Dambovita | [7 empty] | 2 |  |  | 2
Phase_3 | CS | CR197 | TOPOLOVENI_RTC | Road Gaiesti-Pitesti(2) | CR197 Topoloveni_RTC | Muntenia | 44 48 30 | 25 05 01 |  |  |  |  | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [17 empty] | SETRACO* | [6 empty] | Mugur* |  |  | 2001-06-07 | [56 empty] | N/A | Baneasa | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | [15 empty] | BSC21 | BSC BANEASA | N/A | N/A | N/A | N/A | N/A | [10 empty] | N/A | N/A | N/A |  |  | N/A | [6 empty] | Dragos BICIU | Leonard BANU | [42 empty] | Site Near=Insertion Point
Phase_3 | CS | CR198 | VALEA MARE | Road Gaiesti-Pitesti(2) | CR190 Gaiesti_RTC | Muntenia | 44 46 36.31 | 25 12 55.22 |  |  |  |  | MAXITE | M | 1 | 2 | 2PBC | [17 empty] | SETRACO |  | @ | 2001-08-10 | 2001-09-20 |  |  | Mugur |  |  | 2001-06-07 | [56 empty] | ML 15 E 1+0 | Baneasa | MW | [22 empty] | CR190 | GAIESTI_RTC | 306 |  | 28 | 25 | [23 empty] | Dragos BICIU | Leonard BANU | [42 empty] | missing |  |  | 2
Phase_3 | CS | CR199 | MATASARU | Road Gaiesti-Tartasesti(3) | CR190 Gaiesti_RTC | Muntenia | 44 42 40 | 25 25 30 | 44 42 41.4 | 25 25 31.2 | Sat Cretulesti | Dumitru Marin | MAXITE | M | 1 | 2 | 2PBC | [12 empty] | 0 | TN | 50 |  | N/A/TMR9000 | PERFECT | OK | AXA | 2001-08-01 | 2001-08-30 |  |  | Mugur |  |  | 2001-06-07 |  |  | OK |  |  | 2001-07-04 | [20 empty] | AAU | 130 | 0 | 48.5 | AAU | 280 | 0 | 48.5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | 65 | 65 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 130 | ML 15 E 1+0 | Baneasa | MW | 277 | 0.6 | 46 | 45 | [18 empty] | CR190 | GAIESTI_RTC | 97 |  | 27 | 24 | [23 empty] | Dragos BICIU | Leonard BANU | [32 empty] | 191 | Com. Matasaru | Dambovita | [7 empty] | missing |  |  | 2
Phase_3 | CS | CR200 | TITU | Road Gaiesti-Tartasesti(3) | CR190 Gaiesti_RTC | Muntenia | 44 39 25.08 | 25 34 34.18 |  |  |  |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [17 empty] | PERFECT | OK | AXA | 2001-08-01 | 2001-08-30 |  |  | Mugur |  |  | 2001-06-07 | [56 empty] | ML 15 E 1+0 | Baneasa | MW | [22 empty] | CR199 | MATASARU | [27 empty] | Dragos BICIU | Leonard BANU | [42 empty] | missing |  |  | missing
Phase_3 | CS | CR202 | LUNGULETU | Road Gaiesti-Tartasesti(3) | YR067 Racari_RTC | Muntenia | 44 36 17 | 25 40 11.1 |  |  |  |  | MAXITE | M | 1 | 2 | 2PBC | [17 empty] | PERFECT |  | @ | 2001-08-15 | 2001-09-20 |  |  | Mugur |  |  | 2001-06-07 | [56 empty] | ML 15 E 1+0* | Baneasa | MW | [22 empty] | CR066 | TARTASESTI | 281 |  | 49.5/1.2 | [24 empty] | Dragos BICIU | Leonard BANU | [42 empty] | missing |  | 1 | 2
Phase_2 | CS | CR203 | VIISOARA_RTC | Road Zimnicea-Tg.Magurele(2) | CR204 Zimnicea_RTC | Muntenia | 43 46 53.2 | 25 10 24.9 | 43 46 53.2 | 25 10 24.9 | Romtelecom, Viisoara | Romtelecom/ | 2202 | M | C+C+C+ | 2/2/2 | 2202 | RBS-S.Aq. | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A |  |  |  | 0 | TE | 60 | Existing tower | Room/TMR9202 | DIEKAT | OK | ORION | 2001-01-18 | 2001-02-08 | YesV | 2001-02-14 | Eugen | 2001-02-12 | 2001-02-26 |  |  | 2001-06-08 | N/A | OK |  | 2001-01-04 | 2001-01-19 |  |  |  | 2001-07-17 | ICOM |  | 2001-07-13 | [5 empty] | Yes |  | OPTIMIZARE |  |  |  |  | K 739 494 | 0 | 0 | 46 | K 739 494 | 120 | 0 | 46 | K 739 494 | 230 | 0 | 46 | N/A | N/A | N/A | N/A | N/A | 60 | 60 | 1 1/4" | 60 | 60 | 1 1/4" | 60 | 60 | 1 1/4" | N/A | N/A | N/A | 360 | ML 15 E 1+0 | Baneasa | MW | 132 | 1.2 | 50/1.2 | 60 | [18 empty] | CR204 | ZIMNICEA_RTC | 312 |  | 40 | 50 | [20 empty] | new01 Zimnicea-Baneasa |  | 2001-07-20 | CW-Eugen | Cosmorom | [32 empty] | 61 | Viisoara | Teleorman | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CR204 | ZIMNICEA_RTC | Road Zimnicea-Tg.Magurele(2) | CR204 Zimnicea_RTC | Muntenia | 43 39 17 | 25 22 02 | 43 39 17 | 25 22 02 | Romtelecom, str. M. Viteazul, nr. 43 | Romtelecom/ | 2202 | M | C+C+C+ | 2/2/2 | 2202 | RBS-S.Aq. | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A |  |  |  | 0 | TE | 48 | Existing tower | Room/TMR9202 | DIEKAT | OK | VECTOR | 2001-01-15 | 2001-01-30 | YesV | 2001-03-23 | Eugen | 2001-02-05 | 2001-03-29 |  |  | 2001-06-08 | N/A | OK |  | 2000-12-18 | 2001-01-10 |  |  |  | 2001-06-26 | ICOM |  | 2001-06-27 | [5 empty] | Yes |  | OPTIMIZARE |  |  |  |  | K 739 494 | 80 | 0 | 46 | K 739 494 | 350 | 0 | 46 | K 739 494 | 280 | 0 | 46 | N/A | N/A | N/A | N/A | N/A | 44 | 44 | 7/8" | 46 | 46 | 7/8" | 46 | 46 | 7/8" | N/A | N/A | N/A | 274 | N/A | Baneasa | FO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [5 empty] | 40204 | [6 empty] | 40/outdoor |  |  | BSC21 | BSC BANEASA |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | new01 Zimnicea-Baneasa |  | 2001-07-20 | CW-Eugen | [33 empty] | 31 | Zimnicea | Teleorman | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | CR206 | GREACA_RTC | Giurgiu area(2) | CR001Giurgiu_CTA2 | Muntenia | 44 06 38.7 | 26 19 56.6 | 44 06 38.7 | 26 19 56.6 | Romtelecom Greaca | Romtelecom/ | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  | 0 | TE | 30 | Giurgiu area(2) | Giurgiu area(2) | DIEKAT | OK | AXA | 2000-12-13 | 2001-01-15 | YesV | 2001-03-13 | Doru | 2001-07-06 | 2001-03-19 |  |  |  | N/A | 4-Dec-00 |  | 7-Dec-00 | 9-Ian-01 | [6 empty] | 2001-01-30 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 70 | 0 | 27 | K 739 494 | 260 | 0 | 27 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 35 | 35 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 70 | N/A | Baneasa | RR | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | RBS | [10 empty] | CR001 | GIURGIU_CTA2 | RR | N/A |  |  | N/A | [10 empty] | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 30N02 Giurgiu-Baneasa |  | 2001-02-26 | Ionut GRIGORESCU | Cosmorom | [32 empty] | 48 | Greaca | Giurgiu | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CR207 | IZVOARELE_RTC | Road Buc-Pitesti(8) | CR059 Alexandria_RTC | Muntenia | 44 02 22 | 25 46 35 | 44 02 22 | 25 46 35 | Romtelecom, Izvoarele | Romtelecom/ | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  | 0 | TE | 50 |  | N/A | DIEKAT | OK | AXA | 2000-12-19 | 2001-01-15 | YesV | 2001-03-13 | Doru | 2001-07-06 | 2001-03-19 |  |  |  | N/A | 2000-12-04 |  | 2000-12-14 | 2001-02-01 | [6 empty] | 2001-01-30 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 130 | 0 | 46 | K 739 494 | 330 | 0 | 46 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 55 | 55 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 110 | ML 15 E 1+0 | Baneasa | MW | 294 | [10 empty] | RBS | [7 empty] | 20/2 pairs - outdoor |  |  | CR072 | DRAGANESTI-VLASCA_RTC | [24 empty] | new03 Alexandria-Baneasa |  |  | Ionut GRIGORESCU | Cosmorom | [32 empty] | 80 | Izvoarele | Giurgiu | [7 empty] | 2 |  |  | 2
Phase_2 | CS | CR208 | COSTESTI_RTC | Road Pitesti-Rosiorii de Vede(3) | CR013 Centru_RTC | Oltenia | 44 40 09 | 24 52 46 | 44 40 09 | 24 52 46 | Romtelecom, Costesti | Romtelecom/Dl. Ion Necula - 092/ 858032 | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  | 0 | TE | 65.75 |  | N/A | SVF | OK | SVF | 2000-12-15 | 2000-12-22 | YesV | 2001-02-01 | Eugen | 2001-01-11 | 2001-02-13 |  |  |  | OK | 2001-07-16 |  | 2000-12-18 | 2001-01-09 |  |  |  | 2000-12-28 | ICOM | SVF | 2000-12-27 | 2001-01-10 | 2001-01-11 | 2001-01-12 | 2001-01-19 |  | Yes | Theo Radoi | 2001-03-20 | 2001-03-20 | 2001-03-20 | 2001-04-17 | 2001-04-23 | K 739 494 | 0 | 0 | 51.5 | K 739 494 | 170 | 0 | 51.5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | 63 | 63 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 126 | ML 15 E 1+0 | Baneasa | MW | 337 | 0.6c | 48/0.6 | 60 | 15/89h |  | 4x2/8 | 4U-1 |  |  |  | RBS | XC40035 | [8 empty] | 1 | CR035 | CERBU | 157 | 0.6c | 47 | 70 | 15/84h | [6 empty] | 15* | SVF | 2001-01-08 | 499 | 2001-02-22 | 2001-02-22 | 2001-03-08 | PAUN | OK | 2001-03-20 |  | 2001-05-23 | 2001-05-25 | 30N06 Pitesti-Baneasa |  | 2001-02-26 | Cristian CROITOR | COSMOROM | [32 empty] | 244 | Costesti | Arges | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CR211 | BUZOIESTI_RTC | Road Pitesti-Rosiorii de Vede(3) | CR013 Centru_RTC | Oltenia | 44 35 36 | 24 55 50 | 44 35 36 | 24 55 50 | Romtelecom, Buzoiesti | Romtelecom/D-na. Dumitrescu Elena - int. 65B | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  | 0 | TE | 52 |  | N/A | SVF | OK | SVF | 2000-12-15 | 2000-12-22 | YesV | 2001-02-01 | Eugen | 2001-01-11 | 2001-02-26 |  |  |  | OK | 2001-07-16 |  | 2000-12-18 | 2001-02-01 |  |  |  | 2000-12-28 | ICOM | SVF | 2000-12-27 | 2001-01-10 | 2001-01-11 | 2001-01-12 | 2001-01-19 |  | Yes | Theo Radoi | 2001-03-20 | 2001-03-20 | 2001-03-20 |  |  | K 739 494 | 160 | 0 | 46 | K 739 494 | 330 | 0 | 46 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | 58 | 58 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 116 | ML 15 E 1+0 | Baneasa | MW | 334 | 0.6c | 44/0.6 | 56 | 15/84h |  |  | 4U-1 |  |  |  | RBS | XC40035 | [9 empty] | CR208 | COSTESTI_RTC | 154 | 0.6c | 48/0.6 | 60 | 15/89h | [6 empty] | 15* | SVF | 2001-01-08 | 500 | 2001-02-22 | 2001-02-22 | 2001-03-08 | PAUN | OK | 2001-03-20 |  | 2001-05-23 | 2001-05-25 | 30N06 Pitesti-Baneasa |  | 2001-02-26 | Cristian CROITOR | [33 empty] | 199 | Buzoiesti | Arges | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_3 | CS | CR213 | SUSENI | Arges county | CR013 Centru_RTC | Transilvania | 44 42 39 | 24 57 02 |  |  |  |  | 2202 | M | C+C+ | 2/2 | 2202 | [17 empty] | ROMPSAR* | [6 empty] | Mugur* |  |  | 2001-06-07 |  |  |  | 2001-07-16 | [52 empty] | ML 23 E 1+0 | Baneasa | MW | [12 empty] | XC40035 | [9 empty] | CR208 | COSTESTI_RTC | [24 empty] | 30N06 Pitesti-Baneasa |  |  | Dragos BICIU | Leonard BANU | [42 empty] | missing |  |  | missing
Phase_2 | CS | CR214 | UNGHENI_RTC | Road Pitesti-Rosiorii de Vede(3) | CR013 Centru_RTC | Oltenia | 44 29 46 | 24 57 48 | 44 29 46 | 24 57 48 | Romtelecom, Ungheni | Romtelecom/Dl. Neacsu Cornel - int63 prin Caldararu | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  | 0 | TE | 52 |  | N/A | SVF | OK | SVF | 2000-12-15 | 2000-12-22 | YesV | 2001-03-14 | Eugen | 2001-01-11 | 2001-03-19 |  |  |  | OK | 2001-07-16 |  | 2000-12-18 | 2001-01-09 |  |  |  | 2000-12-28 | ICOM | SVF | 2000-12-27 | 2001-01-10 | 2001-01-11 | 2001-01-12 | 2001-01-19 |  | Yes | Theo Radoi | 2001-03-21 | 2001-03-21 | 2001-03-21 |  |  | K 739 494 | 10 | 0 | 50 | K 739 494 | 180 | 0 | 50 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | 58 | 58 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 116 | ML 15 E 1+0 | Baneasa | MW | 346 | 0.6c | 48 | 56 | 15/89h |  |  | 4U-1 |  |  |  | RBS | XC40035 | [8 empty] | 1 | CR211 | BUZOIESTI_RTC | 166 | 0.6c | 44/0.6 | 56 | 15/84h | [6 empty] | 15* | SVF | 2001-01-08 | 501 | 2001-02-22 | 2001-02-22 | 2001-03-08 | PAUN | OK | 2001-03-21 |  | 2001-05-23 | 2001-05-25 | 30N06 Pitesti-Baneasa |  | 2001-02-26 | Cristian CROITOR | Cosmorom | [32 empty] | 182 | Ungheni | Arges | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | TM | CR216 | ROSIORII_RTC | Road Alexandria-Craiova(12+1) | CR216 Rosiori_RTC | Oltenia | 44 06 43.67 | 24 59 21.4 | 44 06 43.67 | 24 59 21.4 | Romtelecom, Str. Oltului, nr. 9 | Romtelecom/D-l Pietreanu | N/A | N/A | N/A | N/A | N/A | [12 empty] | N/A | B | 18.5 | C3m | N/A | SETRACO | OK | SETRACO | 2001-01-29 | 2001-02-05 | YesV | Respins | Andrei |  | 2001-02-15 |  |  |  | N/A | 2000-11-14 |  | 2000-12-19 | 2001-01-22 |  |  |  | 2001-03-14 | ICOM | DIRDATES | N/A | N/A | 2001-03-15 | N/A | N/A |  | Yes | N/A | 2001-04-10 | 2001-04-10 | 2001-04-10 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A | Craiova | FO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 4U-1 |  |  |  | N/A | 40216 | 2001-06-07 | [5 empty] | 15/outdoor |  | 1 | BSC31 | BSC TIMISOARA | N/A | N/A | N/A | N/A | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PAUN | OK | N/A |  | N/A | N/A | N/A |  | 2001-03-27 | Marius LUNGU | Cosmorom | [32 empty] | 108 | Rosiorii de Vede | Teleorman | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | CR217 | DRAGANESTI OLT_RTC | Road Alexandria-Craiova(12+1) | CR143 Caracal_RTC | Oltenia | 44 09 20 | 24 31 30 | 44 09 20 | 24 31 30 | Romtelecom, Draganesti Olt | Romtelecom/ | 2202 | M | C+C+ | 2/2 | 2202 | [12 empty] | 10 | B | 18.4 | 9m new pylonet | Room | DIEKAT | OK | DIEKAT | 2001-01-22 | 2001-02-28 | YesV | 2001-05-16 | Andrei | 2001-04-17 | 2001-05-23 |  |  |  | N/A | 2000-11-24 |  | 2000-12-04 | 2001-01-25 |  |  |  | 2001-03-15 | ICOM | DIEKAT | 2001-03-02 | 2001-03-02 | 2001-03-20 | 2001-03-21 | 2001-03-23 |  | Yes | Ion Soare | 2001-05-08 | 2001-05-08 | 2001-05-08 | 2001-05-23 | 2001-05-28 | K 739 494 | 145 | 0 | 26 | K 739 494 | 300 | 0 | 26 | N/A | N/A | N/A | N/A |  |  |  |  | N/A | 40 | 40 | 7/8" | 40 | 40 | 7/8" | N/A | N/A | N/A |  |  |  | 160 |  | Craiova | MW | 209 | 0.6 | 27/0.6 | 45 | 23/58 |  | 4x2/8 | 2U-3 |  |  |  | Indoor Comteck | [7 empty] | 15/indoor |  | 1 | CR142 | STOENESTI | 29 | 0.6 | 48/0.6 | 60 | 23/56 | [6 empty] | 57* | SVF | 2001-04-10 | 853 | 2001-04-18 | 2001-04-18 | 2001-04-29 | RADU | OK | 2001-05-08 |  | 2001-05-10 | 2001-05-25 | 30N01 Caracal-Craiova |  | 2001-02-09 | Marius LUNGU | Cosmorom | [32 empty] | 72 | Draganesti Olt | Olt | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | CR218 | FILIASI DEAL | Road Craiova-Turnu Severin(12+1) | CR079 Filiasi_RTC | Oltenia | 44 33 31.5 | 23 31 55.55 | 44 33 31.5 | 23 31 55.55 | Extravilan orasul Filiasi | Staicu Constantina , str. Tudor Vladimirescu, nr. 35/Staicu Constantina , str. Tudor Vladimirescu, nr. 35 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [12 empty] | 0 | TN | 50 |  | N/A | DUAL | OK | DUAL | 2001-03-08 | 2001-04-03 | YesV | 2001-06-14 | Andrei | 2001-06-06 | 2001-06-22 |  |  |  |  | 2000-11-17 |  | 2001-02-28 | 2001-03-14 |  |  |  | 2001-04-03 | ICOM | ORION | 2001-04-03 | 2001-04-03 | 2001-04-04 | 2001-04-05 | 2001-04-09 |  | Yes | Alexandru Toma | 2001-04-29 | 2001-04-29 | 2001-04-29 |  |  | K 739 494 | 130 | 0 | 45.7 | K 739 494 | 270 | 0 | 43.2 | K 739 494 | 340 | 0 | 43.2 |  |  |  |  | N/A | 60 | 60 | 1 1/4" | 60 | 60 | 1 1/4" | 60 | 60 | 1 1/4" |  |  |  | 360 | ML 38 E 1+1 | Craiova | MW | 256 | 0.6 | 46.5 | 70 | 38/18 | YES | 4x2/8 | 4U-1 | 4U-1 |  |  | TMR 9000 | [9 empty] | 1 | CR079 | FILIASI_RTC | 76 | 0.6 | 17.2/0.3 | 55 | 38/14 | [6 empty] | 52* | ORION | 2001-04-03 | 812 | 2001-04-04 | 2001-04-04 | 2001-04-12 | RADU | OK | 2001-04-29 |  | 2001-05-21 | 2001-05-25 | 30N03 Filiasi-Craiova |  | 2001-02-23 | Cristian CROITOR | Cosmorom | [32 empty] | 158 | Filiasi | Dolj | [5 empty] | 1 | 1 | 2 | 1 | 1 | 2
Phase_3 | CS | CR224 | BRATOVOIESTI | Road Craiova-Bechet(3) | CR024 Unirii_RTC | Oltenia | 44 08 31.5 | 23 54 14.1 | 44 08 31.5 | 23 54 14.1 | Sat Prunet, com. Bratovoiesti | Staicu Constantina , str. Tudor Vladimirescu, nr. 35/Staicu Constantina , str. Tudor Vladimirescu, nr. 35 | 2101 | M | C+ | 2 | 2101 | [13 empty] | TN | 50 |  | N/A | PROTELCO | OK | EL-MONT | 2001-07-12 | 2001-08-10 | in exec |  | Mugur |  |  | 2001-03-06 |  |  |  | 2001-03-23 |  | 2001-04-09 | 2001-05-09 | [14 empty] | RBS 2101 |  |  |  |  | K 739 494 | 150 | 0 | 49 | K 739 494 | 320 | 0 | 49 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 59 | 59 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 118 |  | Craiova | MW | 0 | 1.2 | 35 | 59 | [7 empty] | RBS | [10 empty] | CR146 | COSOVENI | 180 | 1.2 | 49 | 60 | [20 empty] | LOCAL |  |  | Marius LUNGU | Anghel CATALIN | [32 empty] | 70.4 | Prunet | Dolj | [7 empty] | 3 |  |  | 3
Phase_3 | CS | CR226 | CACIULATESTI | Road Craiova-Bechet(3) | CR024 Unirii_RTC | Oltenia | 43 57 03.73 | 23 56 46.16 | 43 57 59.4 | 23 57 14.6 | Comuna Caciulesti | Flueran Ion, comuna Dobresti | 2102 | M | C+C+ | 2/2 | N/A | [12 empty] | 0 | TN | 50 |  | N/A | PROTELCO | OK | EL-MONT | 2001-06-10 | 2001-07-06 | YesV |  | Mugur |  |  | 2001-03-06 |  |  | N/A | 2001-03-23 |  | 2001-05-25 | 2001-06-14 | [6 empty] | 2001-07-13 | [7 empty] | CW NOT STARTED |  |  |  |  | K 739 494 | 190 | 0 | 47.5 | K 739 494 | 350 | 0 | 48.7 | N/A | N/A | N/A | N/A |  |  |  |  | N/A | 59 | 59 | 1 1/4" | 59 | 59 | 1 1/4" | N/A | N/A | N/A |  |  |  | 236 | ML 15 E 1+0 | Craiova | MW | 350 | 1.2 | 47.5 | 59 | [7 empty] | N/A | [10 empty] | CR224 | BRATOVOIESTI | 170 | 1.2 | 47 | 45 | [20 empty] | LOCAL |  |  | Marius LUNGU | Anghel CATALIN | [32 empty] | 102.5 | Caciulesti | Dolj | [7 empty] | 3 |  |  | 3
Phase_3 | CS | CR228 | BECHET | Road Craiova-Bechet(3) | CR024 Unirii_RTC | Oltenia | 43 47 27.17 | 23 57 37.13 | 43 47 21.8 | 23 57 37 | Extravilan com. Bechet, parcela 1, tarla17 | Doporica Marin, com. Bechet | 2102 | M | C+C+C+ | 2/2/2 | N/A | [12 empty] | 0 | TN/6mp | 50 |  | N/A | PROTELCO | OK | EL-MONT | 2001-05-17 | 2001-06-07 | YesV | 2001-06-14 | Mugur |  | 2001-06-26 | 2001-03-06 | No |  | OK | 2001-03-24 |  | OK | 2001-05-03 | [6 empty] | 2001-06-14 |  |  |  |  | NO-CIPRIAN |  |  | CW CR226 |  |  |  |  | K 739 494 | 100 | 0 | 48.7 | K 739 494 | 190 | 0 | 48.7 | K 739 494 | 320 | 0 | 48.7 |  |  |  |  | N/A | 59 | 59 | 1 1/4" | 59 | 59 | 1 1/4" | 59 | 59 | 1 1/4" |  |  |  | 354 | ML 15 E 1+0 | Craiova | MW | 237 | 1.2 | 47.5 | 59 | [7 empty] | N/A | [10 empty] | CR226 | CACIULATESTI | 176 | 1.2 | 49.2 | 59 | [20 empty] | LOCAL |  |  | Marius LUNGU | Anghel CATALIN | [32 empty] | 37 | Bechet | Dolj | [7 empty] | 3 |  |  | 3
Phase_3 | CS | CR229 | DABULENI | Road Turnu Magurele-Bechet(4) | CR024 Unirii_RTC | Oltenia | 43 48 08.25 | 24 05 02.61 | 43 48 10.1 | 24 05 00.7 | DRTV Dabuleni | DRTV Timisoara | 2102 | M | C+C+C+ | 2/2/2 | N/A | [12 empty] | 0 | TE | 40 |  | TMR9000 | SVF | OK | SVF | 2001-07-01 | 2001-08-20 | in exec |  | Mugur |  |  | 2001-03-06 |  |  | OK |  |  | OK | 2001-05-14 | [14 empty] | CW NOT STARTED |  |  |  |  | K 739 494 | 20 | 0 | 35.6 | K 739 494 | 120 | 0 | 34.9 | K 739 494 | 250 | 0 | 34.9 |  |  |  |  | N/A | 39.5 | 39.5 | 7/8" | 39.5 | 39.5 | 7/8" | 39.5 | 39.5 | 7/8" |  |  |  | 237 | ML 15 E 1+0 | Craiova | MW | 330 | 0.6 | 36.2 | 41 | [18 empty] | CR228 | BECHET | 83 | 0.6 | 48 | 59 | [20 empty] | LOCAL |  |  | Marius LUNGU | Anghel CATALIN | [33 empty] | Dabuleni | Dolj | [7 empty] | 3 |  |  | 3
Phase_3 | CS | CR230 | GROJDIBODU | Road Turnu Magurele-Bechet(4) | CR143 Caracal_RTC | Oltenia | 43 45 23 | 24 15 07.6 | 43 45 31.5 | 24 15 30.5 | Intravilan Grojdibodu | Stanescu Gigi, loc. Grajdibodu | 2101 | M | C+ | 2 | 2101 | [12 empty] | 0 | TN | 50 |  | N/A | SVF | OK | SVF | 2001-05-08 | 2001-05-25 | YesV | 2001-06-14 | Mugur |  | 2001-06-26 | 2001-03-06 |  |  | 2001-03-27 | 2001-03-23 |  | OK | 2001-05-07 | [6 empty] | 2001-05-28 |  |  |  |  | GATA-2101 |  |  | RBS 2101 |  |  |  |  | K 739 494 | 90 | 0 | 49.5 | K 739 494 | 290 | 0 | 49.5 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 130 | ML 15 E 1+0* | Craiova | MW | 85 | 1.2 | 47.5 | 63 | [7 empty] | N/A | [10 empty] | CR232 | CORABIA | 265 | 1.2 | 42.8 | 51 | [20 empty] | new03 |  |  | Marius LUNGU | Anghel CATALIN | [33 empty] | Grojdibodu | Olt | [7 empty] | 3 |  |  | 3
Phase_3 | CS | CR232 | CORABIA | Road Turnu Magurele-Bechet(4) | CR143 Caracal_RTC | Oltenia | 43 46 24.89 | 24 30 06.99 | 43 46 25.1 | 24 30 07.8 | Romtelecom Corabia. Str. 1 Mai | Romtelecom Corabia | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [7 empty] | N/A |  |  |  |  | 0 | TE | 52.5 |  | Room | SVF | OK | SVF | 2001-05-16 | 2001-05-25 | YesV | 2001-06-06 | Mugur |  |  | 2001-03-06 |  |  | OK | 2001-03-23 |  | OK | 2001-05-14 |  |  | 1902-09-01 | 2001-05-15 | ICOM | SVF | 2001-05-15 |  | 2001-05-17 | 18.05.01 | 20.05.01 |  |  |  | RBS 2101 CR234 |  |  |  |  | K 739 494 | 0 | 0 | 47 | K 739 494 | 90 | 0 | 47 | K 739 494 | 270 | 0 | 47 |  |  |  |  | N/A | 50 | 50 | 1 1/4" | 50 | 50 | 1 1/4" | 50 | 50 | 1 1/4" |  |  |  | 300 | ML 15 E 1+0* | Craiova | MW | 339 | 0.6 | 45 | 54 | [7 empty] | TMR 9202 | [10 empty] | CR233 | VISINA | 159 | 0.6 | 48.2/0.6 | 50 | [20 empty] | new03 |  |  | Vasile PETCU | Biciu DRAGOS | [33 empty] | Corabia | Olt | [7 empty] | 3 |  |  | 3
Phase_3 | CS | CR233 | VISINA | Road Caracal-Corabia(2) | CR143 Caracal_RTC | Oltenia | 43 52 27 | 24 25 55 | 43 52 57.3 | 24 27 11.3 | Comuna Visina | Primaria comunei Visina | 2102 | M | C+C+ | 2/2 | N/A | [12 empty] | 0 | TN | 50m/3mp |  | N/A | PROTELCO | OK | EL-MONT | 2001-06-20 | 2001-07-06 | YesV |  | Mugur |  |  | 2001-03-06 |  |  | 2001-04-09 | 2001-03-23 |  | 2001-04-17 | 2001-05-09 | [6 empty] | 2001-07-11 | [7 empty] | CW NOT STARTED |  |  |  |  | K 739 494 | 160 | 0 | 48.7 | K 739 494 | 330 | 0 | 48.7 | N/A | N/A | N/A | N/A |  |  |  |  | N/A | 55 | 55 | 1 1/4" | 55 | 55 | 1 1/4" | N/A | N/A | N/A |  |  |  | 220 | ML 15 E 1+0* | Craiova | MW | 352 | 1.2 | 40/1.2 | 45 | [7 empty] | N/A | [10 empty] | CR234 | VLADILA SILOZ | [24 empty] | new03 |  |  | Marius Negu | Catalin ANGHEL | [32 empty] | 52.5 | Visina | Olt | [7 empty] | 3 |  |  | missing
Phase_3 | CS | CR234 | VLADILA SILOZ | Road Caracal-Corabia(2) | CR143 Caracal_RTC | Oltenia | 43 59 44.35 | 24 25 31.26 | 43 59 44.4 | 24 25 32 | Terasa siloz Frasinet, com. Vladila-Traian | CERELCOM SA Olt str. Aleea Muncii nr.2/ dir.gen. Gramescu Pantelie Stafan si dir. Ec. Luta Florea | 2101 | M | C+ | 2 | 2101 | [7 empty] | YES |  |  |  |  | 47.2 | S | 47.2 | S4m+S4m | N/A | PROTELCO | OK | EL-MONT | 2001-05-17 | 2001-06-05 | YesV | 2001-06-14 | Mugur |  | 2001-06-26 | 2001-03-06 | No |  | OK | 2001-03-23 |  | OK | 2001-05-02 | [6 empty] | 2001-06-13 |  |  |  |  | GATA2101 |  |  | RBS 2101 |  |  |  |  | K 739 494 | 190 | 0 | 48.8 | K 739 494 | 350 | 0 | 48.8 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 11.5 | 11.5 | 7/8" | 30 | 30 | 7/8" | N/A | N/A | N/A |  |  |  | 83 |  | Craiova | MW | 22 | 1.2 | 48 | 30 | [7 empty] | N/A | XC40143 | [9 empty] | CR142 | STOENESTI | [24 empty] | 30N02 Caracal-Craiova |  | OK | Marius Negu | Catalin ANGHEL | [33 empty] | Vadila-Traian | Olt | [7 empty] | 3 |  |  | missing
Phase_3 | CS | CR236 | ISLAZ | Road Turnu Magurele-Bechet(4) | CR059 Alexandria_RTC | Oltenia | 43 44 20 | 24 44 50 | 43 44 21.6 | 24 44 46.8 | Intravilan Islaz | SC VINALCOOL SA Rosiori-loc. Islaz | 2101 | M | C+ | 2 | 2101 | [12 empty] | 0 | TN | 50 |  | N/A | SVF | OK | SVF | 2001-07-12 | 2001-08-10 | in exec |  | Mugur |  |  | 2001-03-06 |  |  | 2001-03-27 | 2001-03-23 |  | 2001-05-16 | [15 empty] | RBS 2101 |  |  |  |  | K 739 494 | 90 | 0 | 49.5 | K 739 494 | 290 | 0 | 49.5 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 65 | 65 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 130 | ML 15 E 1+0* | Baneasa | MW | 72 | 1.2 | 40.8 | 56 | [7 empty] | N/A | [10 empty] | CR238 | MOTEL | [24 empty] | new05 Alexandria-Baneasa |  |  | Marius LUNGU | Anghel CATALIN | [32 empty] | 32.8 | Islaz | Teleorman | [7 empty] | 3 |  |  | missing
Phase_3 | CS | CR237 | HOTEL TURRIS | Turnu Magurele | CR059 Alexandria_RTC | Oltenia | 43 44 53 | 24 52 11 | 43 44 51.8 | 24 52 12.6 | B-ul Independentei, nr. 1 | SC Hotel Turris | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | YES |  |  |  |  | 40.5 | B | 40.5 | S4m+S4m+S4m | N/A | SVF | OK | SVF | 2001-05-16 | 2001-05-21 | YesV | 2001-06-06 | Mugur |  |  | 2001-03-06 |  |  | OK | 2001-03-23 |  | OK | 2001-05-14 |  |  | 1902-09-02 | 2001-05-15 | ICOM | SVF | 2001-05-15 | 2001-05-15 | 2001-05-17 | 20.05.01 | 22.05.01 |  |  |  | CTR CR238 |  |  |  |  | K 739 494 | 90 | 0 | 42.1 | K 739 494 | 170 | 0 | 42.1 | K 739 494 | 310 | 0 | 42.1 |  |  |  |  | N/A | 30 | 30 | 7/8" | 28 | 28 | 7/8" | 26 | 26 | 7/8" |  |  |  | 168 | ML 23 E 1+0* | Baneasa | MW | 49 | 0.6 | 40.9 | 30 | [18 empty] | CR238 | MOTEL | 229 | [23 empty] | new05 Alexandria-Baneasa |  |  | Marius LUNGU | Anghel CATALIN | [33 empty] | Turnu Magurele | Teleorman | [7 empty] | 3 |  |  | 3
Phase_3 | CS | CR238 | MOTEL | Road Alexandria-Turnu Magurele(3) | CR059 Alexandria_RTC | Oltenia | 43 46 39 | 24 54 59 |  |  |  |  | 2102 | M | C+C+ | 2/2 | N/A | [12 empty] | 0 | TN | 40 |  |  | SVF* |  | SVF* |  |  |  |  | Mugur* |  |  | 2001-03-06 |  |  |  | 2001-03-23 | [17 empty] | CTR | [35 empty] | Baneasa | MW | 64 | [21 empty] | CR239 | CRANGU | 244 | 1.2 | 48 | 63 | [20 empty] | new05 Alexandria-Baneasa |  |  | Marius LUNGU | Anghel CATALIN | [42 empty] | 3 |  |  | 3
Phase_3 | CS | CR239 | CRANGU | Road Alexandria-Turnu Magurele(3) | CR059 Alexandria_RTC | Oltenia | 43 50 11 | 24 04 51 | 43 50 14.7 | 25 05 14.4 | Extravilan Crangu | Otomega Stelian - loc. Crangu | MAXITE | M | 1 | 2 | 2PBC | [12 empty] | 0 | TN | 50 |  | N/A/TMR9000 | SVF | OK | SVF | 2001-05-21 | 2001-05-25 | YesV | 2001-06-14 | Mugur |  | 2001-06-26 | 2001-03-06 |  |  | 2001-03-27 | 2001-03-23 |  | 2001-05-14 | 2001-05-14 | [6 empty] | 2001-05-28 |  |  |  |  | GATA-MAXITE |  |  | MAXITE |  |  |  |  | AAU | 50 | 0 | 49.5 | AAU | 260 | 0 | 49.5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | 65 | 65 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 130 | ML 15 E 1+1* | Baneasa | MW | 49 | 1.2 | 47 | 63 | [18 empty] | CR240 | IAS ALEXANDRIA | 229 | 1.2 | 39 | 60 | [20 empty] | new05 Alexandria-Baneasa |  |  | Marius LUNGU | Anghel CATALIN | [32 empty] | 92.5 | Crangu | Teleorman | [7 empty] | 3 |  |  | 3
Phase_3 | CS | CR240 | IAS ALEXANDRIA | Road Alexandria-Turnu Magurele(3) | CR059 Alexandria_RTC | Oltenia | 43 57 45 | 25 16 48 | 43 57 45.3 | 25 16 46.1 | SC VOGEL&NOOT | SC VOGEL & NOOT/Patron Ulmeanu Stefan - 094/ 499 799 | 2101 | M | C+ | 2 | 2101 | [12 empty] | 0 | TN | 40 |  | N/A/TMR9000 | SVF | OK | SVF | 2001-05-21 | 2001-05-25 | YesV | 2001-07-09 | Mugur |  | 2001-06-12 | 2001-03-06 |  |  | 2001-03-27 | 2001-03-23 |  | OK | 2001-05-14 | [6 empty] | 2001-05-28 |  |  |  |  | GATA-2101 |  |  | RBS 2101 |  |  |  |  | K 739 494 | 60 | 0 | 39 | K 739 494 | 240 | 0 | 39 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 46 | 46 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 120 | ML 15 E 1+1 (PS)* | Baneasa | MW | 322 | 0.6 | 39 | 60 | [7 empty] | TMR 9000 | [10 empty] | CR136 | BUZESCU | [24 empty] | new04 Alexandria-Baneasa |  |  | Marius LUNGU | Anghel CATALIN | [33 empty] | Alexandria | Teleorman | [6 empty] | 1 | 3 |  |  | missing
Phase_3 | CS | CR241 | STADION | Craiova(7) | CR024 Unirii_RTC | Oltenia | 44 18 49 | 23 47 30 |  |  |  |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | YES | [9 empty] | PROTELCO |  | @ | 2001-08-01 | 2001-09-10 |  |  | Mugur |  |  | 2001-04-25 | [21 empty] | CTR | [34 empty] | ML 38 E 1+0* | Craiova | MW | 85 | [21 empty] | CR024 | UNIRII_RTC | [24 empty] | LOCAL |  |  | Dragos BICIU | Dragos BICIU | [42 empty] | 3 |  |  | missing
Phase_3 | CS | CR242 | CRAIOVITA | Craiova(7) | CR025 Amarandia_RTC | Oltenia | 44 20 25 | 23 46 45 | 44 20 21.6 | 23 46 51 | Aleea Brebeneilor, bl.10 | Asociatia de locatari nr2 | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [7 empty] | YES |  |  |  |  | 30 | B | 33.4 | new pylonet 9m | Room/Rack19" | PROTELCO | OK | CRAAL | 2001-07-12 | 2001-07-25 | in exec |  | Mugur |  |  | 2001-04-25 |  |  | N/A |  |  | 2001-06-12 | 2001-06-25 | [14 empty] | CW NOT STARTED |  |  |  |  | K 739 494 | 0 | 0 | 41 | K 739 494 | 120 | 0 | 41 | K 739 494 | 240 | 0 | 41 | N/A | N/A | N/A | N/A | N/A | 22 | 22 | 7/8" | 22 | 22 | 7/8" | 22 | 22 | 7/8" | N/A | N/A | N/A | 132 | ML 38 E 1+0 | Craiova | MW | 147 | 0.3 | 40.5 | 22 | [18 empty] | CR025 | AMARANDIA_RTC | [27 empty] | Dragos BICIU | Dragos BICIU | [33 empty] | Craiova | Dolj | [7 empty] | 3 |  |  | missing
Phase_3 | CS | CR243 | BRAZDA | Craiova(7) | CR025 Amarandia_RTC | Oltenia | 44 19 39 | 23 48 06 | 44 19 39 | 23 49 06 | Str. 1 Decembrie 1918 bl C8D | Asociatia de proprietari nr.27, str Brazda lui Novac | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [7 empty] | YES |  |  |  |  | 30.2 | B | 35 | T4m+T4m+T4m | Room/Rack19" | PROTELCO | OK | CRAAL | 2001-07-12 | 2001-07-25 | in exec |  | Mugur |  |  | 2001-04-25 | [5 empty] | 2001-06-12 | 2001-06-25 | [14 empty] | CW NOT STARTED |  |  |  |  | K 739 494 | 0 | 0 | 34 | K 739 494 | 120 | 0 | 34 | K 739 494 | 240 | 0 | 34 | N/A | N/A | N/A | N/A | N/A | 34 | 34 | 7/8" | 34 | 34 | 7/8" | 34 | 34 | 7/8" | N/A | N/A | N/A | 204 | ML 38 E 1+0 | Craiova | MW | 263 | 0.3 | 33.7 | 20 | [18 empty] | CR025 | AMARANDIA_RTC | [27 empty] | Dragos BICIU | Dragos BICIU | [33 empty] | Craiova | Dolj | [7 empty] | 3 |  |  | missing
Phase_3 | CS | CR244 | METRO CRAIOVA | Road Craiova-Slatina | CR024 Unirii_RTC | Oltenia | 44 18 44.9 | 23 53 23.12 | [16 empty] | YES | [9 empty] | PROTELCO |  | @ | 2001-08-01 | 2001-09-10 |  |  | Mugur |  |  | 2001-05-07 |  |  |  | 2001-05-15 | [17 empty] | CTR | [34 empty] | ML 15 E 1+0* | Craiova | MW | [22 empty] | CR146 | COSOVENI | [27 empty] | Dragos BICIU | Catalin ANGHEL | [32 empty] | 170.5 | [9 empty] | 3 |  |  | missing
Phase_3 | CS | CR245 | LIBERTATII | Ramnicu Valcea(3) | CR047 Valcea_RTC | Oltenia | 45 06 09.8 | 24 22 34.2 | 45 06 15 | 24 22 57 | Str. Eroilor, bl.A17, sc.D | Asociatia de locatari ai bl. A17 | 2202 | M | C+C+ | 2/2 | 2202 | [7 empty] | YES |  |  |  |  | 22 | B | 22 | C6m+C6m | Room | ISAF | OK | SETRACO | 2001-08-01 | 2001-08-20 |  |  | Mugur |  |  | 2001-04-25 | 2001-06-07 |  | N/A | 2001-05-11 |  | 2001-07-09 | [15 empty] | CTR |  |  |  |  | K 739 494 | 10 | 0 | 29.4 | K 739 494 | 240 | 0 | 28.8 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 20 | 20 | 7/8" | 30 | 30 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A | 100 |  | Craiova | MW | 310 | 0.6 | 29 | 22 | [18 empty] | CR047 | VILCEA_RTC | 130 | [26 empty] | Dragos BICIU | Dragos BICIU | [33 empty] | Ramnicu Valcea | Valcea | [7 empty] | missing |  |  | missing
Phase_3 | CS | CR246 | MIHAI VITEAZU | Ramnicu Valcea(3) | CR047 Valcea_RTC | Oltenia | 45 06 35.34 | 24 22 11.28 |  |  |  |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | YES | [9 empty] | ISAF | OK | SETRACO | 2001-08-01 | 2001-08-20 |  |  | Mugur |  |  | 2001-04-25 |  |  |  | 2001-05-11 | [17 empty] | CTR | [34 empty] | ML 38 E 1+0 | Craiova | MW | [22 empty] | CR049 | MATEI BASARAB | [27 empty] | Dragos BICIU | Dragos BICIU | [42 empty] | missing |  |  | missing
Phase_3 | CS | CR247 | FAVIL | Ramnicu Valcea(3) | CR047 Valcea_RTC | Oltenia | 45 04 18 | 24 20 36 | 45 04 12.6 | 24 20 34.6 | Str. Depozitelor, nr.10 | Favil SA | 2102 | M | C+C+ | 2/2 | N/A | [7 empty] | YES |  |  |  |  | 0 | B | 45 | 5xS4m | N/A | ISAF | OK | SETRACO | 2001-07-05 | 2001-07-19 | in exec |  | Mugur |  |  | 2001-04-25 |  |  | N/A | 2001-05-11 |  | 2001-06-08 | 2001-06-25 | [14 empty] | CW NOT STARTED |  |  |  |  | K 739 707 | 30 | 0 | 47.5 | K 739 707 | 230 | 0 | 47.5 | K 739 707 | 30 | 0 | 47.5 | K 739 707 | 230 | 0 | 47.5 | N/A | 75 | 75 | 1 1/4" | 80 | 80 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | 310 | ML 23 E 1+0 | Craiova | MW | 78 | 0.6 | 47.2 | 75 | [18 empty] | CR113 | CENTURA RM. VALCEA | [27 empty] | Dragos BICIU | Dragos BICIU | [33 empty] | Rm. Valcea | Valcea | [7 empty] | 3 |  |  | missing
Phase_3 | CS | CR248 | GORJPAN | Targu Jiu(2) | CR056 Central_RTC | Oltenia | 45 02 58 | 23 16 53.4 | 45 02 58.1 | 23 16 52.8 | Str. Ecaterina Teodoroiu, nr.88 | SC Gorj Pan SA | 2102 | M | C+C+ | 2/2 | N/A | [7 empty] | YES |  |  |  |  | 22 | B | 26 | S6m+S6m | N/A | NUTEX | OK | ARGOS | 2001-07-12 | 2001-07-25 | in exec |  | Mugur |  |  | 2001-04-25 | [5 empty] | 2001-06-12 | 2001-06-25 | [14 empty] | CW NOT STARTED |  |  |  |  | K 739 494 | 10 | 0 | 30.5 | K 739 494 | 210 | 0 | 26.5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 30.5 | 30.5 | 7/8" | 26.5 | 26.5 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A | 114 |  | Craiova | MW | 221 | 0.3 | 26.15 | 22.5 | [7 empty] | N/A | [10 empty] | CR056 | CENTRAL_RTC | 41 | [23 empty] | new03 Tg.Jiu Central-Craiova |  |  | Dragos BICIU | Dragos BICIU | [33 empty] | Tg. Jiu | Gorj | [7 empty] | 3 |  |  | missing
Phase_3 | CS | CR249 | NICOLAE TITULESCU | Targu Jiu(2) | CR056 Central_RTC | Oltenia | 45 01 37.56 | 23 16 35.7 | 45 01 38.7 | 23 16 34 | Str Nicolaie Titulescu , bl. 12 sc.1 | Asociatia de locatari nr103 | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [7 empty] | YES |  |  |  |  | 31.7 | B | 31 | T4.5m+T4.5m+T4.5m | Room/Rack19" | NUTEX | OK | ARGOS | 2001-07-12 | 2001-07-25 | in exec |  | Mugur |  |  | 2001-04-25 |  |  | N/A |  |  | 2001-06-12 | 2001-06-25 | [14 empty] | CW NOT STARTED |  |  |  |  | K 739 707 | 60 | 0 | 33 | K 739 494 | 210 | 0 | 37.3 | K 739 494 | 310 | 0 | 37.3 | N/A | N/A | N/A | N/A | N/A | 20 | 20 | 7/8" | 28 | 28 | 7/8" | 13 | 13 | 7/8" | N/A | N/A | N/A | 122 | ML 38 E 1+0 | Craiova | MW | 9 | 0.3 | 32.7 | 19 | [18 empty] | CR248 | GORJPAN | 188 | 0.3 | 25.5 | 18 | [20 empty] | new03 Tg.Jiu Central-Craiova |  |  | Dragos BICIU | Dragos BICIU | [33 empty] | Tg. Jiu | Gorj | [7 empty] | 3 |  |  | 3
Phase_3 | CS | CR250 | PIATA UNIRII | Craiova(7) | CR025 Amarandia_RTC | Oltenia | 44 19 15 | 23 47 45 | 44 19 14.4 | 23 47 45.2 | Calea Bucuresti, bl.M3, sc1, Piata Unirii | Asociatia de locatari , Piata Unirii | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | YES |  |  |  |  | 31 | B | 31 | 3xT4.5m | N/A | PROTELCO | OK | CORA | 2001-07-12 | 2001-07-25 | in exec |  | Mugur |  |  | 2001-04-25 |  |  | N/A |  |  | 2001-06-08 | 2001-06-25 | [14 empty] | CW NOT STARTED |  |  |  |  | K 739 494 | 0 | 0 | 33 | K 739 494 | 120 | 0 | 33 | K 739 494 | 240 | 0 | 33 | N/A | N/A | N/A | N/A | N/A | 32 | 32 | 7/8" | 35 | 35 | 7/8" | 20 | 20 | 7/8" | N/A | N/A | N/A | 174 | ML 38 E 1+0 | Craiova | MW | 333 | 0.3 | 32.6 | 31.6 | [18 empty] | CR025 | AMARANDIA_RTC | 153 | [26 empty] | Dragos BICIU | Dragos BICIU | [33 empty] | Craiova | Dolj | [7 empty] | 3 |  |  | missing
Phase_3 | CS | CR251 | DAEWOO | Craiova(7) | CR024 Unirii_RTC | Oltenia | 44 17 36.3 | 23 50 43.54 | 44 17 54.2 | 23 51 18.5 | Str. Prelungirea Caracal, Km. 3 | SC Cerealcom SA | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [7 empty] | YES |  |  |  |  | 50 | B | 56 | T6m+T4m | Room/TMR9202 | PROTELCO | OK | CORA | 2001-07-18 | 2001-08-07 | in exec |  | Mugur |  |  | 2001-04-25 |  |  | N/A |  |  | 2001-07-09 | [15 empty] | CTR |  |  |  |  | K 739 494 | 130 | 0 | 60.7 | K 739 494 | 250 | 0 | 58.7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 30 | 30 | 7/8" | 55 | 55 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | 170 | ML 38 E 1+0 | Craiova | MW | 298 | 0.3 | 58.2 | 45 | [18 empty] | CR030 | SPITALUL MILITAR | 118 | [23 empty] | LOCAL |  |  | Dragos BICIU | Dragos BICIU | [33 empty] | Craiova | Dolj | [7 empty] | 3 |  |  | missing
Phase_3 | CS | CR252 | ALUTA | Slatina(2) | CR040 Slatina_RTC | Oltenia | 44 25 18 | 24 23 04 |  |  |  |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | YES | [5 empty] | B |  |  |  | SETRACO | OK | @ | 2001-08-01 | 2001-09-10 |  |  | Mugur |  |  | 2001-04-26 | 2001-07-05 |  |  | 2001-07-05 |  |  |  |  | 2001-07-05 | [12 empty] | CTR | [34 empty] | ML 38 E 1+0* | Craiova | MW | 297 | [21 empty] | CR042 | A.I.CUZA | [27 empty] | Dragos BICIU | Catalin ANGHEL | [42 empty] | 3 |  |  | missing
Phase_3 | CS | CR253 | TITULESCU | Slatina(2) | CR040 Slatina_RTC | Oltenia | 44 25 54.33 | 24 21 22.5 |  |  |  |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | YES | [5 empty] | B |  |  |  | SETRACO |  | @ | 2001-08-01 | 2001-09-10 |  |  | Mugur |  |  | 2001-04-26 | [21 empty] | CTR | [34 empty] | ML 38 E 1+0 | Craiova | MW | 108 | [21 empty] | CR041 | INDEPENDENTEI | [27 empty] | Dragos BICIU | Catalin ANGHEL | [42 empty] | 3 |  |  | missing
Phase_3 | CS | CR254 | COZIA STATIA METEO_RTC | Road Rm. Valcea-Talmaciu(9) | CR116 Calimanesti_RTC | Oltenia | 45 19 21.1 | 24 20 15.5 |  |  |  |  | 2202 | M | C+C+ | 2/2 | 2202 | [17 empty] | DIEKAT |  | DUAL | 2001-08-01 | 2001-09-10 |  |  | Mugur |  |  | 2001-05-16 |  |  |  | 2001-07-16 | [17 empty] | CTR | [34 empty] | ML 38 E 1+1 | Craiova | MW | [22 empty] | ZR117 | COZIA_DRTV | [27 empty] | Dragos BICIU | Daniel BICIU | [42 empty] | missing |  |  | missing
Phase_3 | CS | CR255 | GARA LOTRU | Road Rm. Valcea-Talmaciu(9) | CR116 Calimanesti_RTC | Oltenia | 45 21 04.3 | 24 16 23.1 | 45 21 04 | 24 16 23 | Com Boita | Marinescu Dumitru | MAXITE | M | 1 | 2 | 2PBC | [12 empty] | 0 | TN | 50 |  | TMR9000 | DIEKAT | OK | DUAL | 2001-08-01 | 2001-08-30 |  |  | Mugur |  |  | 2001-05-16 |  |  |  | 2001-07-16 |  | 2001-07-09 | [15 empty] | MAXITE |  |  |  |  | AAU | 80 | 0 | 49 | AAU | 160 | 0 | 49 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | 60 | 60 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Craiova | MW | 122 | 0.6 | 36 | 45 | [18 empty] | CR254 | COZIA STATIA METEO_RTC | 302 | [26 empty] | Dragos BICIU | Daniel BICIU | [32 empty] | 364 | Boita | Valcea | [7 empty] | missing |  |  | missing
Phase_3 | CS | CR256 | CAINENI_1 | Road Rm. Valcea-Talmaciu(9) | CR116 Calimanesti_RTC | Oltenia | 45 28 54.6 | 24 17 54.8 |  |  |  |  | MAXITE | M | 1 | 2 | 2PBC | [17 empty] | DIEKAT | OK | DUAL | 2001-08-01 | 2001-08-30 |  |  | Mugur |  |  | 2001-05-16 |  |  |  | 2001-07-16 | [17 empty] | MAXITE | [34 empty] | ML 15 E 1+0 | Craiova | MW | [22 empty] | CR254 | COZIA STATIA METEO_RTC | [27 empty] | Dragos BICIU | Daniel BICIU | [42 empty] | missing |  |  | missing
Phase_3 | CS | CR257 | CAINENI_2 | Road Rm. Valcea-Talmaciu(9) | CR116 Calimanesti_RTC | Oltenia | 45 30 22.5 | 24 17 42 | 45 32 21 | 24 17 42 | Com. Caineni | Primaria Caineni | 2101 | M | C+ | 2 | 2101 | [12 empty] | 0 | TN | 15 |  | N/A | DIEKAT | OK | DIEKAT | 2001-08-01 | 2001-09-10 |  |  | Mugur |  |  | 2001-05-16 |  |  | N/A | 2001-07-16 |  | 2001-07-09 | [15 empty] | RBS 2101 |  |  |  |  | K 739 494 | 180 | 0 | 14 | K 739 494 | 320 | 0 | 14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | 18 | 18 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 36 | ML 38 E 1+0 | Craiova | MW | 174 | 0.3 | 14 | 15 | [18 empty] | CR256 | CAINENI_1 | 354 | [26 empty] | Dragos BICIU | Daniel BICIU | [32 empty] | 594 | Com. Caineni | Valcea | [7 empty] | missing |  |  | missing
Phase_3 | CS | CR258 | RAUL VADULUI | Road Rm. Valcea-Talmaciu(9) | CR116 Calimanesti_RTC | Oltenia | 45 31 01.4 | 24 16 42.1 | 45 31 02.4 | 24 16 42 | Sat Raul Vadului | Canini Gheorghe | 2101 | M | C+ | 2 | 2101 | [12 empty] | 0 | TN | 15 |  | N/A | DIEKAT | OK | DIEKAT | 2001-08-01 | 2001-08-30 |  |  | Mugur |  |  | 2001-05-16 |  |  | N/A | 2001-07-16 |  | 2001-07-09 | [15 empty] | RBS 2101 |  |  |  |  | K 739 494 | 110 | 0 | 14 | K 739 494 | 340 | 0 | 14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | 18 | 18 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 36 | ML 38 E 1+0 | Craiova | MW | 133 | 0.3 | 11 | 15 | [18 empty] | CR257 | CAINENI_2 | 313 | 0.3 | 10 | 15 | [23 empty] | Dragos BICIU | Daniel BICIU | [32 empty] | 378 | Com Caineni | Valcea | [7 empty] | missing |  |  | missing
Phase_3 | CS | CR259 | VALEA FRATELUI | Road Rm. Valcea-Talmaciu(9) | CR116 Calimanesti_RTC | Oltenia | 45 32 49 | 24 16 04 | 45 32 49 | 24 16 04 | Sat Raul Vadului | Iova Elena | 2101 | M | C+ | 2 | 2101 | [12 empty] | 0 | TN | 40 |  | N/A | DIEKAT | OK | DIEKAT | 2001-08-01 | 2001-08-30 |  |  | Mugur |  |  | 2001-05-16 |  |  | N/A | 2001-07-16 |  | 2001-07-09 | [15 empty] | MAXITE |  |  |  |  | K 739 494 | 145 | 0 | 39 | K 739 494 | 330 | 0 | 39 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | 50 | 50 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 100 | ML 23 E 1+0 | Craiova | MW | 166 | 0.3 | 36 | 40 | [18 empty] | CR258 | RAUL VADULUI | 346 | [26 empty] | Dragos BICIU | Daniel BICIU | [32 empty] | 390 | Caineni | Valcea | [7 empty] | missing |  |  | missing
Phase_3 | CS | CR260 | TRANSALEX | Alexandria(2) | CR059 Alexandria_RTC | Oltenia | 43 57 21.9 | 25 20 52.1 | 43 57 21.9 | 25 20 52.1 | Str. Dunarii nr.201 | SC Tranxalex SA | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | YES |  |  |  |  | 0 | TE | 31 | T4m+T3m | N/A | ROMPSAR | OK | ROMPSAR | 2001-08-01 | 2001-08-20 |  |  | Mugur |  |  | 2001-05-28 |  |  | OK | 2001-06-05 |  | 2001-07-04 | [15 empty] | CTR |  |  |  |  | K 739 494 | 10 | 0 | 33.4 | K 739 494 | 120 | 0 | 33.4 | K 739 494 | 290 | 0 | 33.4 | N/A | N/A | N/A | N/A | N/A | 44 | 44 | 7/8" | 44 | 44 | 7/8" | 43 | 43 | 7/8" | N/A | N/A | N/A | 262 | ML 23 E 1+0 | Baneasa | MW | 278 | 0.6 | 33.8 | 44.5 | [18 empty] | CR240 | IAS ALEXANDRIA | 97 | [23 empty] | new04 Alexandria-Baneasa |  |  | Marius LUNGU | George JUMARA | [33 empty] | Alexandria | Teleorman | [7 empty] | missing |  |  | missing
Phase_3 | CS | CR261 | BLOC L4 | Alexandria(2) | CR059 Alexandria_RTC | Oltenia | 43 58 36.9 | 25 19 11.4 |  |  |  |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | YES | [9 empty] | ROMPSAR |  | ROMPSAR | 2001-08-01 | 2001-09-10 |  |  | Mugur |  |  | 2001-05-28 |  |  |  | 2001-05-28 | [17 empty] | CTR | [34 empty] | ML 23 E 1+0 | Baneasa | MW | [22 empty] | CR240 | IAS ALEXANDRIA | [24 empty] | new04 Alexandria-Baneasa |  |  | Marius LUNGU | George JUMARA | [42 empty] | missing |  |  | missing
Phase_3 | CS | CR262 | TRAIAN | Road Giurgiu-Tg. Magurele(4) | CR059 Alexandria_RTC | Oltenia | 43 45 54.8 | 24 58 58.4 | 43 45 54 | 24 58 58 | Comuna Traian | Primaria Comunei Traian | MAXITE | M | 1 | 2 | 2PBC | [12 empty] | 0 | TN | 40 |  | N/A/TMR9000 | ISAF |  | VECTOR | 2001-08-15 | 2001-09-20 |  |  | Mugur |  |  | 2001-05-28 |  |  | OK | 2001-05-28 |  | 2001-07-04 | [15 empty] | MAXITE |  |  |  |  | AAU | 115 | 0 | 39 | AAU | 260 | 0 | 39 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | 45 | 45 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 90 | ML 23 E 1+0 | Baneasa | MW | 284 | 0.6 | 31.5 | 42 | [18 empty] | CR238 | MOTEL | 104 | [23 empty] | new05 Alexandria-Baneasa |  |  | Marius LUNGU | Dan VARTOPEANU | [32 empty] | 59.7 | Traian | Teleorman | [7 empty] | missing |  |  | missing
Phase_3 | CS | CR263 | SMARDIOASA | Road Alexandria-Zimnicea(1) | CR059 Alexandria_RTC | Oltenia | 43 49 38.7 | 25 25 16 | 43 49 38.7 | 25 25 16 | Loc Smardioasa | Trifu Dumitru | 2102 | M | C+C+C+ | 2/2/2 | N/A | [12 empty] | 0 | TN | 50 |  | N/A | SETRACO | OK | AXA | 2001-07-12 | 2001-08-10 | in exec |  | Mugur |  |  | 2001-05-28 |  |  | OK | 2001-05-28 |  | OK | 2001-07-04 | [14 empty] | CTR |  |  |  |  | K 739 494 | 120 | 0 | 49 | K 739 494 | 210 | 0 | 49 | K 739 494 | 350 | 0 | 49 | N/A | N/A | N/A | N/A | N/A | 65 | 65 | 1 1/4" | 65 | 65 | 1 1/4" | 65 | 65 | 1 1/4" | N/A | N/A | N/A | 390 | ML 15 E 1+0 | Baneasa | MW | 338 | 1.2 | 45 | 62 | [18 empty] | CR260 | TRANSALEX | 158 | [26 empty] | Marius LUNGU | George JUMARA | [32 empty] | 79.5 | Smardioasa | Teleorman | [7 empty] | missing |  |  | missing
Phase_3 | CS | CR264 | BUJORU | Road Giurgiu-Tg. Magurele(4) | CR204 Zimnicea_RTC | Oltenia | 43 41 50.8 | 25 31 22.9 |  |  |  |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [17 empty] | ISAF |  | VECTOR | 2001-08-01 | 2001-09-10 |  |  | Mugur |  |  | 2001-05-28 |  |  |  | 2001-05-28 | [17 empty] | CTR | [34 empty] | ML 15 E 1+0 | Baneasa | MW | [22 empty] | CR204 | ZIMNICEA_RTC | [27 empty] | Marius LUNGU | George JUMARA | [42 empty] | missing |  |  | 2
Phase_3 | CS | CR265 | GAUJANI | Road Giurgiu-Tg. Magurele(4) | CR204 Zimnicea_RTC | Oltenia | 43 44 55.4 | 25 42 26.2 | 43 44 59 | 25 42 47 | Loc. Gaujani | Primaria Comunei Gaujani | MAXITE | M | 1 | 2 | 2PBC | [12 empty] | 0 | TN | 40 |  | N/A/TMR9000 | ISAF |  | VECTOR | 2001-08-15 | 2001-09-20 |  |  | Mugur |  |  | 2001-05-28 |  |  | OK | 2001-05-28 |  | 2001-07-04 | [15 empty] | RBS 2101 |  |  |  |  | AAU | 65 | 0 | 39 | AAU | 230 | 0 | 39 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | 46 | 46 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 92 | ML 15 E 1+0 | Baneasa | MW | 250 | 1.2 | 37 | 44 | [18 empty] | CR264 | BUJORU | 69 | [26 empty] | Marius LUNGU | George JUMARA | [32 empty] | 32.9 | Gaujani | Giurgiu | [7 empty] | missing |  |  | missing
Phase_3 | CS | CR266 | MALU | Road Giurgiu-Tg. Magurele(4) | CR204 Zimnicea_RTC | Oltenia | 43 49 14.1 | 25 49 04.9 | 43 49 11 | 25 49 01.6 | Sat Malu | Feraru Elena | MAXITE | M | 1 | 2 | 2PBC | [12 empty] | 0 | TN | 40 |  | N/A/TMR9000 | ISAF | OK | VECTOR | 2001-08-01 | 2001-08-30 |  |  | Mugur |  |  | 2001-05-28 |  |  | OK | 2001-05-28 |  | 2001-07-04 | [15 empty] | RBS 2101 |  |  |  |  | AAU | 55 | 0 | 39 | AAU | 205 | 0 | 39 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | 50 | 50 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 100 | ML 15 E 1+0 | Baneasa | MW | 228 | 0.6 | 35 | 38 | [18 empty] | CR265 | GAUJANI | 48 | 0.6 | 37 | 44 | [23 empty] | Marius LUNGU | George JUMARA | [32 empty] | 23.9 | Com. Vedea | Giurgiu | [7 empty] | missing |  |  | missing
Phase_3 | CS | CR267 | BOTOROAGA_SILOZ | Teleorman county(2) | CR059 Alexandria_RTC | Oltenia | 44 09 13.4 | 25 33 04.1 | 44 09 13.3 | 25 33 05 | Incinta Siloz Tarnavele | SC Comcereal Galati SA | 2202 | M | C+C+ | 2/2 | 2202 | [7 empty] | YES | [5 empty] | 40 | 45 | C-3m+C-3m | Room | SETRACO | OK | APOLLO | 2001-08-01 | 2001-08-20 |  |  | Mugur |  |  | 2001-05-28 |  |  | OK | 2001-05-28 |  | 2001-07-04 | [15 empty] | RBS 2101 |  |  |  |  | K 739 494 | 160 | 0 | 44.7 | K 739 494 | 340 | 0 | 44.7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 6 | 6 | 7/8" | 23.5 | 23.5 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A | 59 | ML 15 E 1+0 | Baneasa | MW | 354 | 1.2 | 44 | 23.5 | [18 empty] | CR268 | VIDELE_SILOZ | 173 | [23 empty] | new03 Alexandria-Baneasa |  |  | Marius LUNGU | Dan VARTOPEANU | [33 empty] | Com Botoroaga | Teleorman | [7 empty] | missing |  |  | missing
Phase_3 | CS | CR268 | VIDELE_SILOZ | Teleorman county(2) | CR059 Alexandria_RTC | Oltenia | 44 18 58.1 | 25 31 53.7 |  |  |  |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | YES | [9 empty] | SETRACO |  | @ | 2001-08-01 | 2001-09-10 |  |  | Mugur |  |  | 2001-05-28 |  |  |  | 2001-05-28 | [17 empty] | CTR | [34 empty] | ML 15 E 1+0 | Baneasa | MW | [22 empty] | CR073 | GHIMPATI_RTC | [24 empty] | new03 Alexandria-Baneasa |  |  | Marius LUNGU | Dan VARTOPEANU | [42 empty] | missing |  |  | missing
Phase_3 | CS | CR270 | CARSTANESTI | Road Rm. Valcea-Tg.Jiu | CR124 Govora_RTC | Oltenia | 45 02 15.6 | 24 02 38.2 |  |  |  |  | MAXITE | M | 1 | 2 | 2PBC | [17 empty] | SVF |  | @ | 2001-09-01 | 2001-09-30 |  |  | Mugur |  | 2001-07-10 | [9 empty] | 2001-07-10 | [47 empty] | ML 23 E 1+0* | Craiova | MW | [22 empty] | CR166 | OTESANI | [24 empty] | new01 Govora-Craiova |  | 2001-08-01 | Sorin UNTARU | Sorin UNTARU
Phase_3 | CS | CR271 | OLTENI SILOZ | Teleorman | CR059 Alexandria_RTC | Oltenia | 44 11 23.2 | 25 18 06.3 |  |  |  |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [17 empty] | SVF |  | @ | 2001-09-01 | 2001-09-30 |  |  | Mugur |  |  | 2001-07-10 | [8 empty] | 2001-07-10 | [47 empty] | ML 15 E 1+0* | Baneasa | MW | [22 empty] | CR071 | VITANESTI | [27 empty] | Marius LUNGU | Dan VARTOPEANU
Phase_3 | CS | CR272 | POSTEI | Road Pitesti-Campulung | CR013 Centru_RTC | Oltenia | 44 57 32.3 | 24 56 54.4 | [40 empty] | 2001-07-16 | [52 empty] | ML 38 E 1+0 | Baneasa | MW | [22 empty] | CR022 | MIOVENI
Phase_3 | CS | CR273 | DEALU FRUMOS | Road Pitesti-Campulung | CR013 Centru_RTC | Oltenia | 45 01 54.5 | 24 58 52 | [40 empty] | 2001-07-16 | [52 empty] | ML 15 E 1+0 | Baneasa | MW | [22 empty] | CR272 | POSTEI
Phase_3 | CS | CR902 | LIPSCANI | Craiova(7) | CR024 Unirii_RTC | Oltenia | 44 18 54 | 23 47 55 |  |  |  |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | YES | [9 empty] | PROTELCO |  | @ | 2001-08-01 | 2001-09-10 |  |  | Mugur |  |  | 2001-04-25 | [21 empty] | CTR | [34 empty] | N/A | Craiova | HDSL | N/A | N/A | N/A | N/A | N/A |  | N/A | [15 empty] | CR024 | UNIRII_RTC | N/A | N/A |  |  | N/A | [10 empty] | N/A | N/A | N/A |  |  | N/A | [6 empty] | Dragos BICIU | Dragos BICIU | [42 empty] | Site Near=Insertion Point
Phase_3 | CS | CR903 | UNIREA | Craiova(7) | CR024 Unirii_RTC | Oltenia | 44 19 05.2 | 23 49 40.2 |  |  |  |  | MICRO | M | 1 | 2 | N/A | [7 empty] | YES | [9 empty] | PROTELCO |  | @ | 2001-08-01 | 2001-09-10 |  |  | Mugur |  |  | 2001-04-25 | 2001-06-07 |  |  | 2001-06-07 | [17 empty] | CTR | [34 empty] | N/A | Craiova | HDSL | N/A | N/A | N/A | N/A | N/A |  | N/A | [15 empty] | CR024 | UNIRII_RTC | N/A | N/A |  |  | N/A | [10 empty] | N/A | N/A | N/A |  |  | N/A | [6 empty] | Dragos BICIU | Dragos BICIU | [42 empty] | Site Near=Insertion Point
Phase_3 | TM | IU001 | VALEA CASCADELOR | Bucuresti(x) | BU032 CNT_2 | Muntenia | 44 25 51 | 26 00 15 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | [12 empty] | N/A | [18 empty] | 2001-05-22 | [22 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | ML 38 E 1+0 | Dr. Taberei | MW | 147 | 0.3 |  | 60 | 38/17 | [17 empty] | BU117 | VALEA ARGESULUI |  | 0.3 |  | 30 | 38/13 | [6 empty] | 70* | ICOM | 2001-05-23 | 948 | OK | OK | OK | OK | OK |  |  | 2001-06-19 | 2001-07-10 |  |  |  | Petrica BURGHIU | N/A | [32 empty] | 92 | [9 empty] | 3 |  |  | 2
Phase_1 | MSC/BSC | MSC01 | CNT2_MSC | Bucuresti |  | Muntenia | [5 empty] | Romtelecom/ | [25 empty] | OK |  |  | OK | [19 empty] | Yes | Yes | Yes |  |  |  | Yes | Yes | Yes | Yes | Yes | [30 empty] | N/A | Dr. Taberei | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | [15 empty] | N/A |  |  | N/A |  |  | N/A | [6 empty] | OK | OK | OK | OK | OK | N/A | N/A | OK | OK | N/A | [43 empty] | Yes | [6 empty] | Site Near=Insertion Point
Phase_2 | MSC/BSC | MSC01 | EXTENSION MSC (Drumul Taberei) | Bucuresti |  | Muntenia | [41 empty] | 2001-02-12 |  |  | N/A | N/A | [8 empty] | Yes | Yes | Yes |  |  |  | Yes | Yes | Yes | Yes | Yes | [30 empty] | N/A | Dr. Taberei | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | [15 empty] | N/A |  |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [44 empty] | Yes | [5 empty] | Site Near=Insertion Point
Phase_2 | MSC/BSC | MSC02 | MSC Baneasa | Bucuresti |  | Muntenia | [41 empty] | 2001-02-12 |  |  | N/A | N/A | [8 empty] | Yes | Yes | Yes |  |  |  | Yes | Yes | Yes | Yes | Yes | [30 empty] | N/A | Baneasa | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | [15 empty] | N/A |  |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [43 empty] | Yes | [6 empty] | Site Near=Insertion Point
Phase_2 | MSC/BSC | MSC03 | MSC TIMISOARA | Timisoara |  | Banat | [41 empty] | 2001-02-12 |  |  | N/A | N/A | [8 empty] | Yes | Yes | Yes |  |  |  | Yes | Yes | Yes | Yes | Yes | [30 empty] | N/A | Timisoara | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | [15 empty] | N/A |  |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [43 empty] | Yes | [6 empty] | Site Near=Insertion Point
Phase_2 | MSC/BSC | MSC04 | MSC CLUJ | Cluj |  | Transilvania | [41 empty] | 2001-02-12 |  |  | N/A | N/A | [8 empty] | Yes | Yes | Yes |  |  |  | Yes | Yes | Yes | Yes | Yes | [30 empty] | N/A | Cluj | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | [15 empty] | N/A |  |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [43 empty] | Yes | [6 empty] | Site Near=Insertion Point
Phase_2 | CS | TM001 | VINTU DE JOS | Road Deva-Sebes(5) | TM003 Orastie_RTC | Banat | 45 58 15.1 | 23 26 41.6 | 45 58 11 | 23 26 38.9 | Comuna Savarsin, Extravilan Vintu de Jos | Jicarean Gheorghe Daniel - Com. Blandiana nr.265, Str. Principala/Jicarean Gheorghe Daniel - Com. Blandiana nr.265, Str. Principala | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-10-11 | N/A | N/A |  |  |  |  | TN | 50 | Tower | N/A | SVF | OK | SVF | 2000-08-10 | 2000-09-13 | YesV | 2000-09-19 | Mugur | 2000-10-05 | 2000-09-22 |  |  |  |  | 2000-06-28 |  | 2000-07-21 | 2000-08-11 |  |  |  | 2000-10-20 | ICOM | SVF | 2000-09-27 | 2000-09-27 | 2000-10-24 | 2000-11-01 | 2000-11-03 |  | Yes | Mihai Constantin | 2001-03-26 | 2001-03-26 | 2001-03-26 | 2001-05-15 | 2001-05-28 | K 739 494 | 70 | 0 | 49 | K 739 494 | 240 | 0 | 49 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 65 | 65 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 130 | ML 15 E 1+0 | Timisoara | MW | 243 | 1.2 | 47 | 60 | 15/84 |  | 4x2/8 | 4U-1 |  |  |  | RBS | [9 empty] | 1 | TM002 | VLAICU_2 | 63 | 1.2 | 47 | 60 | 15/89 | [6 empty] | 9 | SVF | 2000-10-20 | 238 | 2000-10-13 | 2000-10-17 | 2000-10-20 | DINCA | OK | 2001-03-26 | PENDING ITEMS |  |  | 30N01 Orastie-Baneasa |  | 2000-12-22 | Cristian CROITOR | Cosmorom | [32 empty] | 235 | Vintu de Jos | Alba | [7 empty] | 2 |  |  | 2
Phase_2 | CS | TM002 | VLAICU_2 | Road Deva-Sebes(5) | TM003 Orastie_RTC | Banat | 45 55 09.9 | 23 18 05 | 45 55 09.9 | 23 18 07.4 | Com Geoagiu, Sat Aurel Vlaicu | Mara Sabin - Cugir, Str. Constructorilor nr.10 Sc.A Ap.8/Culda Liviu - 058/ 754 015 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-10-11 | N/A | N/A |  |  |  |  | TN | 50 | Tower | N/A | SVF | OK | SVF | 2000-08-10 | 2000-09-13 | YesV | 2000-09-19 | Mugur | 2001-03-14 | 2000-09-22 |  |  |  | 2000-07-06 | OK |  | 2000-08-04 | 2000-08-15 |  |  |  | 2000-10-20 | ICOM | SVF | 2000-09-27 | 2000-09-27 | 2000-10-24 | 2000-10-29 | 2000-11-01 |  | Yes | Mihai Constantin | 2001-03-23 | 2001-03-26 | 2001-03-26 | 2001-05-15 | 2001-05-28 | K 739 494 | 80 | 0 | 49 | K 739 494 | 230 | 0 | 49 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 70 | 70 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 140 | ML 15 E 1+0 | Timisoara | MW | 224 | 1.2 | 47/1.2 | 60 | 15/89 |  | 4x2/8 | 4U-1 |  |  |  | RBS | [9 empty] | 1 | TM003 | ORASTIE_RTC | 43 | 1.2 | 28.2/1.2 | 32 | 15/84 | [6 empty] | 9 | SVF | 2000-10-20 | 239 | 2000-10-16 | 2000-10-17 | 2000-10-20 | DINCA | OK | 2001-03-06 |  | 2001-05-03 | 2001-05-11 | 30N01 Orastie-Baneasa |  | 2000-12-22 | Cristian CROITOR | Cosmorom | [32 empty] | 203 | Vlaicu 2 | Alba | [7 empty] | 2 |  |  | 2
Phase_2 | CS | TM003 | ORASTIE_RTC | Road Deva-Sebes(5) | TM003 Orastie_RTC | Banat | 45 50 20 | 23 11 29 | 45 50 20 | 23 11 29 | Str. Armatei, nr.2 | Romtelecom/ | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-09-19 | N/A | N/A |  |  |  | 4.8 | B | 16.8 | 12m new pylonet | Room | SVF | OK | PROFIL | 2000-08-18 | 2000-09-09 | YesV | 2000-09-19 | Mugur | 2000-09-08 | 2000-09-22 |  |  |  | N/A | 2000-06-22 |  | 2000-08-01 | 2000-08-22 |  |  |  | 2000-09-15 | YRO | MOB | 2000-09-15 | 2000-09-15 | 2000-09-18 | 2000-09-19 | 2000-10-31 |  | Yes | Alexandru Toma | 2000-12-30 | 2000-12-30 | 2000-12-30 | 2001-02-13 | 2001-02-16 | K 739 494 | 30 | 0 | 28.2 | K 739 494 | 150 | 0 | 28.2 | K 739 494 | 280 | 0 | 28.2 |  |  |  |  | N/A | 34 | 34 | 7/8" | 34 | 34 | 7/8" | 34 | 34 | 7/8" |  |  |  | 0 | N/A | Timisoara | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | 4U-1 |  |  |  | Indoor Comteck | 50003 | [8 empty] | 1 | BSC31 | BSC TIMISOARA | N/A | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | 30N01 Orastie-Baneasa |  | 2000-12-22 | Cristian CROITOR | Cosmorom | [32 empty] | 236 | Orastie | Hunedoara | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | TM004 | SPIN | Road Deva-Sebes(5) | TM007 Deva_RTC | Banat | 45 49 57.3 | 23 05 39.1 | 45 49 56.8 | 23 05 47.3 | Loc Spini, jud Hunedoara | Ciolna Ioan - Loc. Spini nr.9/Ciolna Ioan - Loc. Spini nr.9 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-10-11 | N/A | N/A |  |  |  |  | TN | 30 |  | N/A | SVF | OK | EL-MONT | 2000-09-27 | 2000-10-10 | YesV | 2000-11-07 | Mugur | 2000-10-10 | 2000-11-27 |  |  |  |  | 2000-06-28 |  | 2000-09-13 | 2000-09-20 |  |  |  | 2000-10-20 | ICOM | SVF | 2000-10-13 | 2000-10-13 | 2000-10-24 | 2000-10-25 | 2000-10-31 |  | Yes | Theo Radoi | 2001-01-26 | 2001-01-26 | 2001-01-26 | 2001-02-08 | 2001-04-10 | K 739 494 | 80 | 0 | 29 | K 739 494 | 280 | 0 | 29 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 45 | 45 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 90 | ML 23 E 1+0 | Timisoara | MW | 286 | 0.6 | 27 | 48 | 23/58 |  | 4x2/8 | 4U-1 |  |  |  | RBS | [9 empty] | 1 | TM005 | SIMERIA_RTC | 105 | 0.6 | 45 | 50 | 23/56 | [6 empty] | 9 | SVF | 2000-10-20 | 306 | 2000-10-13 | 2000-10-17 | 2000-10-20 | DINCA | OK | 2001-01-26 |  | 2001-02-05 | 2001-02-06 | 30N02 Baneasa-Deva |  | OK | Cristian CROITOR | Cosmorom | [32 empty] | 222 | Spini | Hunedoara | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | TM005 | SIMERIA_RTC | Road Deva-Sebes(5) | TM007 Deva_RTC | Banat | 45 50 53 | 23 00 55.6 | 45 50 53 | 23 00 55.6 | Str. Avram Iancu nr.21, RTC Simeria | Romtelecom/ | 2202 | M | C+C+ | 2/2 | 2202 | [6 empty] | 2000-10-11 | N/A | N/A |  |  |  |  | TN | 45 |  | Room | SVF | OK | EL-MONT | 2000-09-04 | 2000-10-04 | YesV | 2000-10-12 | Mugur | 2000-10-06 | 2000-10-13 |  |  |  |  | 2000-06-28 |  | 2000-07-21 | 2000-11-29 |  |  |  | 2000-10-20 | ICOM | SVF | 2000-10-12 | 2000-10-12 | 2000-10-24 | 2000-10-25 | 2000-10-31 |  | Yes | Theo Radoi | 2001-01-26 | 2001-01-26 | 2001-01-26 | 2001-03-02 | 2001-04-10 | K 739 494 | 70 | 0 | 37 | K 739 494 | 170 | 0 | 37 | K 739 494 | 280 | 0 | 37 |  |  |  |  | N/A | 47 | 47 | 7/8" | 47 | 47 | 7/8" | N/A | N/A | N/A |  |  |  | 188 | ML 15 E 1+0 | Timisoara | MW | 293 | 0.6 | 45/1.2 | 60 | 15/84 |  | 4x2/8 | 4U-1 |  |  |  | Indoor Comteck | [9 empty] | 1 | TM006 | IULIU MANIU | 113 | 0.6 | 33/0.6 | 15 | 15/89 | [6 empty] | 9 | SVF | 2000-10-20 | 320 | 2000-10-16 | 2000-10-25 | 2000-10-31 | DINCA | OK | 2001-01-26 |  | 2001-02-05 | 2001-02-06 | 30N02 Baneasa-Deva |  | OK | Cristian CROITOR | Cosmorom | [32 empty] | 194 | Simeria | Hunedoara | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | TM006 | IULIU MANIU | Deva(3) | TM007 Deva_RTC | Banat | 45 52 50 | 22 54 10 | 44 52 55 | 22 54 13 | B-dul. Iuliu Maniu Bl.L4 Sc.A |  | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-09-19 | N/A | N/A |  |  |  | 28 | B | 30.8 | T3m+T3m | Room | SVF | OK | TEHNOROB | 2000-08-14 | 2000-08-21 | YesV | 2000-09-04 | Mugur | 2000-08-30 |  |  |  |  | OK | 2000-05-13 |  | 2000-05-25 | 2000-06-22 |  |  |  | 2000-09-05 | YRO | Interactive | 2000-08-30 | 2000-08-30 | 2000-09-05 | 2000-09-06 | 2000-09-06 |  | Yes | Alexandru Toma | 2000-12-30 | 2000-12-30 | 2000-12-30 | 2001-02-19 | 2001-04-10 | K 739 494 | 20 | 0 | 32.6 | K 739 494 | 160 | 0 | 32.6 | K 739 494 | 260 | 0 | 32.6 |  |  |  |  | N/A | 15 | 15 | 7/8" | 6 | 6 | 7/8" | 6 | 6 | 7/8" |  |  |  | 39 | ML 23 E 1+0 | Timisoara | MW | 148.02 | 0.6 | 33.8 | 15 | 23/56 |  | 4x2/8 | 4U-1+2U-3 |  |  |  | Indoor Comteck | [9 empty] | 1 | TM007 | DEVA_RTC | 333 | 0.6 | 37 | 20 | 23/58 | [6 empty] | 10 | INTERACTIVE | 2000-10-20 | 303 | 2000-10-13 | 2000-10-14 | 2000-10-17 | DINCA | OK | 2000-12-30 |  | 2001-02-21 | 2001-03-02 | 30N01 Baneasa-Deva |  | OK | Cristian CROITOR | Cosmorom | CSFT1802-DONOR | TM235 | [30 empty] | 240 | Deva | Hunedoara | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | TM007 | DEVA_RTC | Deva(3) | TM007 Deva_RTC | Banat | 45 52 03 | 22 54 52 | 45 52 19.7 | 22 54 32.1 | DEVA RTC Central | Romtelecom/ | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-10-20 | N/A | N/A |  |  |  | 20 | B | 25 | 17m existing pylonet | N/A | SVF | OK | TEHNOROB | 2000-10-05 | 2000-10-09 | YesV | 2000-10-12 | Mugur | 2000-10-12 | 2000-10-13 |  |  |  | N/A | 2000-09-18 |  | 2000-09-19 | 2000-10-09 |  |  |  | 2000-10-20 | ICOM | Interactive | 2000-10-16 | 2000-10-16 | 2000-10-23 | 2000-10-25 | 2000-10-26 |  | Yes | Alexandru Toma | 2000-12-30 | 2000-12-29 | 2000-12-29 | 2001-04-17 | 2001-04-23 | K 739 494 | 0 | 0 | 39 | K 739 494 | 120 | 0 | 42 | K 739 494 | 240 | 0 | 32 |  |  |  |  | N/A | 22 | 22 | 7/8" | 25 | 25 | 7/8" | 15 | 15 | 7/8" |  |  |  | 124 | N/A | Timisoara | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | 2U-3 |  |  |  | Indoor Comteck | 50007 | [8 empty] | 1 | BSC31 | BSC TIMISOARA | N/A | N/A | N/A | N/A | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | 30N01 Baneasa-Deva |  | 22.12.2000 | Cristian CROITOR | Cosmorom | [32 empty] | 216 | Deva | Hunedoara | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | TM010 | MINTIA | Road Arad-Deva(13+3) | TM007 Deva_RTC | Banat | 45 54 59 | 22 51 03.2 | 45 54 52.9 | 22 51 34.9 | Loc Mintia, jud Hunedoara | Pascu Maria - Str. Principala nr.1, Mintia/Pascu Maria - Str. Principala nr.1, Mintia | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-11-17 | N/A | N/A |  |  |  | 0 | TN | 50 |  | N/A | SVF | OK | IMSAT | 2000-10-17 | 2000-12-18 | YesV | 2001-01-22 | Mugur | 2001-02-26 | 2001-01-23 |  |  |  |  | 2000-06-28 |  | 2000-09-11 | 2000-11-03 |  |  |  | 2000-12-18 | ICOM | SVF | 2000-12-18 | 2000-12-18 | 2000-12-19 | 2001-01-18 | 2001-01-19 |  | Prov | Alexandru Toma | 2001-04-05 | 2001-04-05 | 2001-04-05 |  |  | K 739 494 | 140 | 0 | 49 | K 739 494 | 260 | 0 | 49 | N/A | 350 | 0 | 49 |  |  |  |  | N/A | 70 | 70 | 1 1/4" | 70 | 70 | 1 1/4" | 70 | 70 | 1 1/4" |  |  |  | 420 | ML 15 E 1+0 | Timisoara | MW | 121 | 1.2 | 47/1.2 | 68 | 15/89 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [9 empty] | 1 | TM005 | SIMERIA_RTC | 301 | 1.2 | 45/1.2 | 50 | 15/84 | [6 empty] | 20* | SVF | 2001-01-24 | 577 | 2001-03-19 | 2001-03-20 | 2001-03-24 | DINCA | OK | 2001-04-05 |  | 2001-05-10 | 2001-05-25 | 30N02 Baneasa-Deva |  | OK | Cristian CROITOR | Cosmorom | [32 empty] | 206 | Mintia | Hunedoara | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | TM013 | BURJUC | Road Arad-Deva(13+3) | YM145 Ilia_RTC | Banat | 45 58 42.4 | 22 26 48.1 | 45 58 45.1 | 22 26 54.6? | Dealul Varful Magurii - extravilan com. Burjuc | Primaria Burjuc - 631 218/Maris Eugenia - primaria Burhuc, 092/ 463 547 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-10-20 | N/A | N/A |  |  |  |  | TN | 40 | Tower | N/A | SVF | OK | ISAF | 2000-09-11 | 2000-11-30 | YesV | Respins | Mugur | 2001-01-09 | [5 empty] | 2000-07-25 |  | 2000-08-21 | 2000-09-27 |  |  |  | 2000-12-15 | ICOM | SVF | 2000-12-14 | 2000-12-15 | 2000-12-19 | 2001-01-10 | 2001-01-13 |  | Yes | Alexandru Toma | 2001-04-06 | 2001-04-06 | 2001-04-06 |  |  | K 739 494 | 120 | 0 | 39 | K 739 494 | 320 | 0 | 39 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+1 | Timisoara | MW | 144 | 15/89 | 37/0.6 | 50 | 15/89 | YES | 4x2/8 | 4U-1 | 4U-1 |  |  | TMR 9000 | [9 empty] | 1 | TM146 | GRIND | 324 | 0.6 | 47.5 | 65 | 15/84 | [6 empty] | 43* | VECTOR | 2001-03-15 | 727 | 2001-03-19 | 2001-03-19 | 2001-03-24 | DINCA | OK | 2001-04-06 |  | 2001-05-21 | 2001-05-25 | 30N02 Ilia-Timisoara |  | 2001-03-31 | Cristian CROITOR | [33 empty] | 408 | Burjuc | Hunedoara | [5 empty] | 1 | 1 | 2 | 1 |  | 2
Phase_2 | CS | TM014 | CAPRIOARA | Road Arad-Deva(13+3) | YM145 Ilia_RTC | Banat | 45 59 12.1 | 22 17 47.4 | 45 59 17.7 | 22 17 52.2 | Sat Caprioara | Ardelean Sofia - sat Caprioara nr.22 com. Savirsin/Ardelean Sofia - sat Caprioara nr.22 com. Savirsin | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-10-11 | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | SVF | OK | SVF | 2000-08-03 | 2000-09-25 | YesV | 2000-09-27 | Mugur | 2001-02-05 | 2000-09-29 |  |  |  | 2000-06-29 | 2000-06-20 |  | 2000-07-18 | 2000-08-02 |  |  |  | 2000-10-20 | ICOM | Interactive | 2000-10-10 | 2000-10-10 | 2000-10-23 | 2000-10-26 | 2000-10-27 |  | Yes | Alexandru Toma | 2001-04-06 | 2001-04-06 | 2001-04-06 | 2001-06-19 | 2001-07-11 | K 739 494 | 70 | 0 | 49.5 | K 739 494 | 300 | 0 | 49.5 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 70 | 70 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 140 | ML 38 E 1+0 | Timisoara | MW | 41 | 0.6 | 39 | 55 | 38/18 |  | 4x2/8 | 4U-1 |  |  |  | RBS | [9 empty] | 1 | TM111 | TOC_DRTV | 221 | 0.6 | 19 | 28 | 38/14 | [6 empty] | 10 | INTERACTIVE | 2000-10-20 | 309 | 2000-10-13 | 2000-10-14 | 2000-10-27 | IVAN | OK | 2001-04-06 |  | 2001-05-03 | 2001-05-11 | 30N01 Ilia-Timisoara |  | 2001-03-31 | Cristian CROITOR | CATALINA CIOCAN | [32 empty] | 160 | Caprioara | Arad | [7 empty] | 2 |  |  | 2
Phase_2 | CS | TM015 | VARADIA | Road Arad-Deva(13+3) | YM145 Ilia_RTC | Banat | 46 00 28 | 22 10 26.4 | 46 00 32 | 22 10 28 | Extravilan loc. Varadia De Mures | Primaria Varadia de Mures - 057/ 417 101/Primarul_ 057/ 417 230 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-10-13 | N/A | N/A |  |  |  |  | TN | 40 |  | N/A | SVF | OK | SVF | 2000-08-15 | 2000-09-29 | YesV | 2000-10-11 | Mugur | 2000-10-24 | 2000-10-13 |  |  |  |  | 2000-06-22 |  | 2000-08-27 | 2000-09-08 |  |  |  | 2000-10-20 | ICOM | Interactive | 2000-10-12 | 2000-10-12 | 2000-10-23 | 2000-10-27 | 2000-10-30 |  | Yes | Alexandru Toma | 2001-04-06 | 2001-04-06 | 2001-04-06 |  |  | K 739 494 | 100 | 0 | 39 | K 739 494 | 290 | 0 | 39 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+1 | Timisoara | MW | 99 | 1.2 | 37/1.2 | 50 | 15/84 | YES | 4x2/8 | 4U-1 |  |  |  | RBS | [9 empty] | 1 | TM013 | BURJUC | 278 | 1.2 | 37/1.2 | 50 | 15/89 | [6 empty] | 8* | SVF | 2000-12-15 | 469 | 2000-12-18 | 2001-01-30 | 2001-02-13 | PAUN | OK | 2001-04-06 |  | 2001-05-17 | 2001-05-25 | 30N02 Ilia-Timisoara |  | 2001-03-31 | Cristian CROITOR | Cosmorom | [32 empty] | 240 | Varadia de Mures | Arad | [5 empty] | 1 | 1 | 2 | 1 | 1 | 2
Phase_2 | CS | TM016 | LALASINT | Road Arad-Deva(13+3) | YM145 Ilia_RTC | Banat | 46 03 35.5 | 22 00 50.6 | 46 03 40.9 | 22 01 00.2 | Loc. Lalasint | Nu a avut contract de inchiriere in DDE/ | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-12-11 | N/A | N/A |  |  |  |  | TN | 40 |  | N/A | SVF | OK | SVF | 2000-11-08 | 2000-12-15 | YesV | 2001-01-23 | Mugur | 2001-03-08 | [5 empty] | 2000-06-22 |  | 2000-10-06 | 2000-11-14 |  |  |  | 2000-12-14 | ICOM | SVF | 2000-12-14 | 2000-12-14 | 2000-12-19 | 2001-01-18 | 2001-01-22 |  | Yes | Alexandru Toma | 2001-04-07 | 2001-04-07 | 2001-04-07 |  |  | K 739 494 | 110 | 0 | 39 | K 739 494 | 340 | 0 | 39 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Timisoara | MW | 115 | 1.2 | 37/1.2 | 60 | 15/89 |  | 4x2/8 | 4U-1 |  |  |  | RBS | [9 empty] | 1 | TM015 | VARADIA | 295 | 1.2 | 37/1.2 | 50 | 15/84 | [6 empty] | 7* | SVF | 2000-12-14 | 464 | 2000-12-18 | 2001-01-30 | 2001-02-06 | IVAN | OK | 2001-04-07 |  | 2001-05-03 | 2001-05-11 | 30N02 Ilia-Timisoara |  | 2001-03-31 | Cristian CROITOR | Cosmorom | [32 empty] | 358 | Lalasint | Arad | [7 empty] | 2 |  |  | 2
Phase_2 | CS | TM017 | BARZAVA | Road Arad-Deva(13+3) | YM145 Ilia_RTC | Banat | 46 06 21.2 | 21 59 34.3 | 46 06 17.7 | 21 59 37.2 | Comuna Birzava nr.84 | Posta Ghe. - Barzava nr.84, 095/ 636 308/Posta Ghe. - Barzava nr.84, 095/ 636 308 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-10-20 | N/A | N/A |  |  |  |  | TN | 40 | Tower | N/A | SVF | OK | VECTOR | 2000-10-25 | 2000-11-24 | YesV | 2000-11-29 | Mugur | 2001-01-19 | 2000-12-13 |  |  |  | 2000-06-07 | 2000-06-22 |  | 2000-07-28 | 2000-08-15 |  |  |  | 2000-12-14 | ICOM | SVF | 2000-11-10 | 2000-11-10 | 2001-01-04 | 2001-01-18 | 2001-01-19 |  | Yes | Alexandru Toma | 2001-04-07 | 2001-04-07 | 2001-04-07 |  |  | K 739 494 | 120 | 0 | 39 | K 739 494 | 300 | 0 | 39 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 55 | 55 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 110 | ML 23 E 1+0 | Timisoara | MW | 162 | 1.2 | 32/0.6 | 48 | 23/56 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [9 empty] | 1 | TM016 | LALASINT | 342 | 1.2 | 37/1.2 | 60 | 23/58 | [6 empty] | 7* | SVF | 2000-12-14 | 461 | 2000-12-18 | 2001-01-30 | 2001-02-06 | IVAN | OK | 2001-04-07 |  | 2001-05-03 | 2001-05-11 | 30N02 Ilia-Timisoara |  | 2001-03-31 | Cristian CROITOR | Petrica BURGHIU | [32 empty] | 155 | Birzava | Arad | [7 empty] | 2 |  |  | 2
Phase_2 | CS | TM018 | CHELMAC | Road Arad-Deva(13+3) | YM145 Ilia_RTC | Banat | 46 05 05 | 21 52 45 | 46 05 03.1 | 21 52 52.7 | Com. Conop, sat Chelmac | Primaria Conop/Moldovan Petru (primar) - loc. Odvos, 094/ 361 672 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-10-13 | N/A | N/A |  |  |  |  | TN | 50 | Tower | N/A | SVF | OK | DUAL | 2000-09-01 | 2000-10-20 | YesV | 2000-11-02 | Mugur | 2001-01-09 | 2000-11-15 |  |  |  |  | 2000-06-22 |  | 2000-08-05 | 2000-08-15 |  |  |  | 2000-10-20 | ICOM | Interactive | 2000-10-16 | 2000-10-16 | 2000-10-23 | 2000-10-27 | 2000-10-30 |  | Yes | Alexandru Toma | 2001-04-08 | 2001-04-08 | 2001-04-08 | 2001-06-15 | 2001-07-11 | K 739 494 | 75 | 0 | 49.5 | K 739 494 | 290 | 0 | 49.5 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 70 | 70 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 140 | ML 15 E 1+0 | Timisoara | MW | 75 | 0.6 | 47/1.2 | 65 | 15/89 |  | 4x2/8 | 4U-1 |  |  |  | RBS | [9 empty] | 1 | TM017 | BARZAVA | 255 | 0.6 | 39/1.2 | 55 | 15/84 | [6 empty] | 7* | SVF | 2000-12-14 | 407 | 2000-12-18 | 2001-01-30 | 2001-02-06 | IVAN | OK | 2001-04-08 |  | 2001-05-03 | 2001-05-11 | 30N02 Ilia-Timisoara |  | 2001-03-31 | Cristian CROITOR | CATALINA CIOCAN | [32 empty] | 139 | Chelmac | Arad | [7 empty] | 2 |  |  | 2
Phase_2 | CS | TM019 | MILOVA | Road Arad-Deva(13+3) | YM145 Ilia_RTC | Banat | 46 05 27 | 21 48 26.3 | 46 05 24.7 | 21 48 32.9 | Com. Milova | Primaria Conop/Moldovan Petrica - primaria Conop, 094/ 361 372 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-10-13 | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | SVF | OK | DUAL | 2000-09-14 | 2000-10-23 | YesV | 2000-11-02 | Mugur | 2001-01-09 | 2000-11-10 |  |  |  |  | 2000-06-22 |  | 2000-08-22 | 2000-09-11 |  |  |  | 2000-10-20 | ICOM | Interactive | 2000-10-16 | 2000-10-16 | 2000-10-23 | 2000-10-27 | 2000-10-30 |  | Yes | Alexandru Toma | 2001-04-08 | 2001-04-08 | 2001-04-08 | 2001-06-15 | 2001-07-11 | K 739 494 | 80 | 0 | 49 | K 739 494 | 300 | 0 | 49 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 70 | 70 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 140 | ML 23 E 1+0 | Timisoara | MW | 96 | 0.6 | 47 | 70 | 23/56 |  | 4x2/8 | 4U-1 |  |  |  | RBS | [9 empty] | 1 | TM018 | CHELMAC | 277 | 0.6 | 47 | 65 | 23/58 | [6 empty] | 10 | INTERACTIVE | 2000-10-20 | 315 | 2000-10-14 | 2000-10-14 | 2000-10-30 | PAUN | OK | 2001-04-08 |  | 2001-05-03 | 2001-05-11 | 30N02 Ilia-Timisoara |  | 2001-03-31 | Cristian CROITOR | Cosmorom | [32 empty] | 142 | Milova | Arad | [7 empty] | 2 |  |  | 2
Phase_2 | CS | TM021 | LIPOVA_RTC(OPTIMIZARE) | Road Arad-Deva(13+3) | TM025 Arad-DRTv_RTC | Banat | 46 05 28.1 | 21 41 39.7 | 46 05 28.1 | 21 41 39.7 | Str. Nicolae Balcescu, Sediul Romtelecom | Romtelecom/ | 2202 | M | C+C+ | 2/2 | 2202 | FEEDER(+6m) | N/A | N/A | N/A | N/A | N/A | 2000-10-11 | N/A | N/A |  |  |  | 8 | B | 12 | 12m new pylon | Room | SVF | OK | DUAL | 2000-08-20 | 2000-09-15 | YesV | 2000-09-21 | Mugur | 2000-09-22 | 2000-09-26 |  |  | 2001-06-19 | N/A | 2000-06-22 |  | 2000-07-20 | 2000-08-15 |  |  |  | 2001-06-26 | ICOM |  |  | 2000-09-27 | 2000-10-04 | 2000-10-09 | 2000-10-12 |  | Yes | Alexandru Toma | 2001-03-07 | 2001-03-07 | 2001-03-07 | 2001-06-15 | 2001-07-11 | K 739 494 | 60 | 0 | 21.5 | K 739 494 | 300 | 0 | 21.5 | N/A | N/A | N/A | N/A |  |  |  |  | N/A | 30 | 30 | 7/8" | 30 | 30 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 23 E 1+0 | Timisoara | MW | 285 | 0.6 | 25 | 45 | 23/58 |  | 4x2/8 | 2U-3 |  |  |  | N/A | [9 empty] | 1 | TM023 | PAULIS | 106 | 0.6 | 47 | 70 | 23/56 | [6 empty] | 10 | SVF | 2000-10-03 | 254 | 2000-10-04 | 2000-10-04 | 2000-10-12 | DINCA | OK | 2001-03-07 | PENDING ITEMS |  |  | 30N01 Arad-Timisoara |  | 2001-03-05 | Cristian CROITOR | Cosmorom | [23 empty] | 2000-10-03 | YRO | SVF | [6 empty] | 135 | Lipova | Arad | [7 empty] | 2 |  |  | 2
Phase_2 | CS | TM023 | PAULIS | Road Arad-Deva(13+3) | TM025 Arad-DRTv_RTC | Banat | 46 06 30.3 | 21 36 22.6 | 46 06 30 | 21 36 22.6 | Paulis nr.682 | Brad Ioan - Paulis nr.705/Brad Dorel - 461 232 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-09-19 | N/A | N/A |  |  |  |  | TN | 50 | 50m new tower | N/A | SVF | OK | ORION | 2000-08-03 | 2000-09-04 | YesV | 2000-09-07 | Mugur | 2000-09-04 | 2000-12-08 |  |  |  |  | 2000-06-20 |  | 2000-07-18 | 2000-08-02 |  |  |  | 2000-08-29 | YRO | ORION | 2000-08-29 | 2000-08-29 | 2000-08-30 | 2000-08-30 | 2000-08-31 |  | Yes | Alexandru Bucur | 2001-03-07 | 2001-03-07 | 2001-03-07 |  |  | K 739 494 | 110 | 0 | 49 | K 739 494 | 300 | 0 | 49 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 70 | 70 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 140 | ML 15 E 1+0 | Timisoara | MW | 292 | 1.2 | 47 | 70 | 15/84 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [9 empty] | 1 | TM024 | MINDRULOC | 111 | 1.2 | 47 | 60 | 15/89 | [6 empty] | 5 | ORION | 2000-08-29 | 158 | 2000-08-30 | 2000-08-30 | 2000-08-31 | DINCA | OK | 2001-03-07 | PENDING ITEMS |  |  | 30N01 Arad-Timisoara |  | 2001-03-05 | Cristian CROITOR | Cosmorom | [32 empty] | 144 | Paulis | Arad | [7 empty] | 2 |  |  | 2
Phase_2 | CS | TM024 | MINDRULOC | Road Arad-Deva(13+3) | TM025 Arad-DRTv_RTC | Banat | 45 08 58 | 21 27 31 | 46 08 39 | 21 27 39 | Mindruloc tarlaua 24 poz. 1 parcela 881 poz.1 | Valentin Gheorghe - loc. Mindruloc nr.317, 216 057/Volentir Gheorghe - loc. Mindruloc nr.317, 216 057 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-09-19 | N/A | N/A |  |  |  |  | TN | 50 | 50m new tower | N/A | SVF | OK | ORION | 2000-08-03 | 2000-08-28 | YesV | 2000-08-31 | Mugur | 2000-09-04 | 2000-09-06 |  |  |  |  | 2000-07-25 |  | 2000-07-25 | 2000-08-02 |  |  |  | 2000-08-29 | YRO | ORION | 2000-08-29 | 2000-08-29 | 2000-08-30 | 2000-08-30 | 2000-08-31 |  | Yes | Alexandru Bucur | 2001-03-07 | 2001-03-07 | 2001-03-07 |  |  | K 739 494 | 110 | 0 | 49 | K 739 494 | 290 | 0 | 49 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 70 | 70 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 140 | ML 15 E 1+0 | Timisoara | MW | 287 | 0.6 | 47/1.2 | 60 | 15/89 |  |  | 2U-3 |  |  |  | RBS | [9 empty] | 1 | TM175 | MICALACA | 107 | 0.6 | 26 | 27 | 15/84 | [6 empty] | 5 | ORION | 2000-08-29 | N/A | 2000-08-30 | 2000-08-30 | 2000-08-31 | DINCA | OK | 2001-03-07 | PENDING ITEMS |  |  | 30N01 Arad-Timisoara |  | 2001-03-05 | Cristian CROITOR | Cosmorom | [32 empty] | 116 | Mindruloc | Arad | [7 empty] | 2 |  |  | 2
Phase_2 | CS | TM025 | ARAD_RTC_DRTV | Arad(9+1) | TM025 Arad-DRTv_RTC | Banat | 46 10 47 | 21 19 12 | 46 10 47 | 21 19 12 | B-dul Revolutiei | Romtelecom/ | 2202 | M/E | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-07-06 | N/A | N/A |  |  |  | 15 | TN | 50 | Existent | Room | DIEKAT | OK | DIEKAT | 2000-06-14 | 2000-06-26 | YesV | 2000-06-29 | Mugur | 2000-07-03 | 2000-07-11 |  |  |  | N/A | 2000-05-14 |  | 2000-05-23 | 2000-06-22 |  |  |  | 2000-07-06 | YRO | Interactive | 2000-07-06 | 2000-07-06 | 2000-07-07 | 2000-07-08 | 2000-07-18 |  | Yes | Constantin Mihai | 2000-08-15 | 2000-08-12 | 2000-08-12 | 2000-08-24 | 2000-09-05 | K 739 494 | 0 | 0 | 30 | K 739 494 | 140 | #N/A | 30 | K 739 494 | 250 | 0 | 30 |  |  |  |  | N/A | 37 | 37 | 7/8" | 29 | 29 | 7/8" | 33 | 33 | 7/8" |  |  |  | 198 | N/A | Timisoara | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | 4U-1(TMR9202) |  |  |  | TMR 9202 | 50025 | [9 empty] | BSC31 | BSC TIMISOARA |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | 30N01 Arad-Dr.Taberei |  | OK | Cristian CROITOR | #N/A | [32 empty] | 110 | Arad | Arad | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | TM026 | CALEA RADNEI | Arad(9+1) | TM025 Arad-DRTv_RTC | Banat | 46 10 44 | 21 20 54 | 46 10 44.9 | 21 20 54.2 | Calea radnei Bl.108A | Asociatie de locatari - Ignea Nicolae, adm., Bl. 108A, Et.6, Ap.21, tel: 057/ 262 018/Frumusache Ioan - calea Radnei Bl.108A Et.8 Ap.25, tel: 057/ 261 151 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-07-06 | 2000-07-07 | N/A |  |  |  | 27.5 | B | 30.5 | C5m+C5m | N/A | DIEKAT | OK | DIEKAT | 2000-06-14 | 2000-06-29 | YesV | 2000-06-30 | Mugur | 2000-06-30 | 2000-07-11 |  |  |  | 2000-05-19 | 2000-05-14 |  | 2000-06-01 | 2000-06-22 |  |  |  | 2000-07-06 | YRO | Interactive | 2000-07-05 | 2000-07-06 | 2000-07-07 | 2000-07-08 | 2000-07-19 |  | Yes | Constantin Mihai | 2000-08-15 | 2000-08-12 | 2000-08-12 | 2000-08-24 | 2000-09-05 | K 739 494 | 0 | 0 | 34.5 | K 739 494 | 120 | 0 | 34.5 | K 739 494 | 240 | 0 | 34.5 |  |  |  |  | N/A | 12 | 12 | 7/8" | 22 | 22 | 7/8" | 22 | 22 | 7/8" |  |  |  | 112 | ML 38 E 1+1 | Timisoara | MW | 272 | 0.3 | 34.5 | 20 | 38/17 | YES | 4x2/8 | 4U-1 |  |  |  | RBS | [9 empty] | 1 | TM025 | ARAD_RTC_DRTV | 92 | 0.3 | 33 | 35 | 38/13 | [6 empty] | 1 | INTERACTIVE | 2000-07-06 | 732 | 2000-07-08 | 2000-07-08 | 2000-07-18 | IVAN | OK | 10-Aug-00 / 11-Jul-01 | Link dublat ulterior si acceptat | 2000-08-23 | 2000-09-05 | 30N02 Arad-Dr.Taberei |  | OK | Cristian CROITOR | CATALINA CIOCAN | [32 empty] | 112 | Arad | Arad | [5 empty] | 1 | 1 | 2 | 1 | 1 | 2
Phase_2 | CS | TM028 | TEATRU DE STAT | Arad(9+1) | TM025 Arad-DRTv_RTC | Banat | 46 10 17 | 21 18 57 | 46 10 17 | 21 18 57 | B-dul. Republicii nr.103 | Teatrul de Stat - B-dul. Republicii nr.103/Dir. Ec. Enescu, tel: 057/ 280 018/ 280 016 | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-07-06 | N/A | N/A |  |  |  | 15 | B | 33 | C2m+C3m | Room | DIEKAT | OK | DIEKAT | 2000-06-14 | 2000-07-07 | YesV | 2000-07-12 | Mugur | 2000-07-03 | 2000-07-21 |  |  |  | 2000-05-22 | 2000-05-14 |  | 2000-06-20 | 2000-06-28 |  |  |  | 2000-07-06 | YRO | Interactive | 2000-07-06 | 2000-07-06 | 2000-07-07 | 2000-07-08 | 2000-07-24 |  | Yes | Constantin Mihai | 2000-08-15 | 2000-08-12 | 2000-08-12 | 2000-08-24 | 2000-09-05 | K 739 494 | 20 | 0 | 33 | K 739 494 | 130 | 0 | 33 | K 739 494 | 240 | 0 | 33 |  |  |  |  | N/A | 37 | 37 | 7/8'' | 44 | 44 | 7/8'' | 44 | 44 | 7/8'' |  |  |  | 250 | ML 38 E 1+0 | Timisoara | MW | 20 | 0.3 | 34 | 85 | 38/17 |  | 4x2/8 | 4U-1(TMR9202) |  |  |  | TMR 9202 | [10 empty] | TM025 | ARAD_RTC_DRTV | 200 | 0.3 | 33 | 31 | 38/13 | [6 empty] | 1 | INTERACTIVE | 2000-07-06 | 34 | 2000-07-08 | 2000-07-08 | 2000-07-24 | IVAN | OK | 2000-08-12 |  | 2000-08-25 | 2000-09-05 | 30N01 Arad-Dr.Taberei |  | OK | Cristian CROITOR | Cosmorom | [32 empty] | 111 | Arad | Arad | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | TM029 | FALEZA SUD | Arad(9+1) | TM025 Arad-DRTv_RTC | Banat | 46 09 50 | 21 17 32 | 46 09 48 | 21 17 30 | Str. Faleza de sud Bl.38 Ap.15 | Asociatie de locatari - Str. Faleza de Sud Bl.38 Ap.15/ | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-07-06 | 2000-07-07 | N/A |  |  |  | 16.2 | B | 16.2 | Pylonet 6m | N/A | DIEKAT | OK | DIEKAT | 2000-06-14 | 2000-06-26 | YesV | 2000-06-30 | Mugur | 2000-07-03 | 2000-07-11 |  |  |  | 2000-05-22 | 2000-05-14 |  | 2000-05-25 | 2000-06-21 |  |  |  | 2000-07-06 | YRO | Interactive | 2000-07-06 | 2000-07-06 | 2000-07-07 | 2000-07-08 | 2000-07-24 |  | Yes | Constantin Mihai | 2000-08-15 | 2000-09-05 | 2000-09-05 | 2000-09-18 | 2000-09-21 | K 739 494 | 20 | 0 | 20.7 | K 739 494 | 140 | 0 | 20.7 | K 739 494 | 240 | 0 | 20.7 |  |  |  |  | N/A | 15 | 15 | 7/8" | 15 | 15 | 7/8" | 15 | 15 | 7/8" |  |  |  | 90 | ML 38 E 1+0 | Timisoara | MW | 65 | 0.3 | 22 | 15 | 38/13 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [9 empty] | 1 | TM028 | TEATRU DE STAT | 246 | 0.3 | 34 | 85 | 38/17 | [6 empty] | 1 | INTERACTIVE | 2000-07-06 | 35 | 2000-07-08 | 2000-07-08 | 2000-07-24 | IVAN | OK | 2000-09-05 |  | 2000-09-15 | 2000-09-25 | 30N04 Arad-Dr.Taberei |  | OK | Cristian CROITOR | Cosmorom | [32 empty] | 109 | Arad | Arad | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | TM031 | AUREL VLAICU_1 | Arad(9+1) | TM094 Arad_RTC4 | Banat | 46 11 43 | 21 18 04 | 46 11 42.9 | 21 18 03.5 | Calea Aurel vlaicu Bl.Z 26a | Asociatie de proprietari, tel: 057/ 242 711/ | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-07-06 | N/A | N/A |  |  |  | 27 | B | 27 | Catarg existent | Room | DIEKAT | OK | DIEKAT | 2000-06-14 | 2000-07-07 | YesV | 2000-07-12 | Mugur | 2000-07-03 | 2000-07-21 |  |  |  | 2000-05-22 | 2000-05-14 |  | 2000-06-01 | 2000-06-22 |  |  |  | 2000-07-06 | YRO | Interactive | 2000-07-05 | 2000-07-06 | 2000-07-07 | 2000-07-08 | 2000-07-14 |  | Yes | Constantin Mihai | 2000-08-15 | 2000-08-12 | 2000-08-12 | 2000-08-24 | 2000-09-07 | K 739 494 | 0 | 0 | 34 | K 739 494 | 130 | #N/A | 34 | K 739 494 | 250 | 0 | 34 |  |  |  |  | N/A | 10 | 10 | 7/8" | 16 | 16 | 7/8" | 16 | 16 | 7/8" |  |  |  | 84 |  | Timisoara | MW | CABLU | [10 empty] | TMR 9202 | 50031 | [9 empty] | TM094 | ARAD_RTC4 | CABLU | [23 empty] | 30N03 Arad RTC4-Dr.Taberei |  | OK | Cristian CROITOR | #N/A | [32 empty] | 108 | Arad | Arad | [7 empty] | 2 |  |  | 2
Phase_2 | CS | TM032 | AUREL VLAICU_2 | Arad(9+1) | TM094 Arad_RTC4 | Banat | 46 12 06 | 21 17 30 | 46 12 05.5 | 21 17 30.8 | Calea Aurel Vlaicu bl. A 1/3, nr.210, jud. Arad | Asociatia de proprietari - Podoaba Mihai - adm. - Bl.A1/3 et.2 Ap.10, tel: 057/248 429/ 280 692/Vanciu Valentin - Calea Aurel Vlaicu Bl.A1/3 Et.6, tel:057/ 243 141 | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-07-06 | N/A | N/A |  |  |  | 31.7 | B | 31.7 | C3.5m+c3.5m | Room | DIEKAT | OK | DIEKAT | 2000-06-14 | 2000-06-29 | YesV | 2000-06-30 | Mugur | 2000-07-03 | 2000-07-11 |  |  |  | 2000-05-22 | 2000-05-14 |  | 2000-06-01 | 2000-06-22 |  |  |  | 2000-07-06 | YRO | Interactive | 2000-07-05 | 2000-07-05 | 2000-07-07 | 2000-07-08 | 2000-07-14 |  | Yes | Constantin Mihai | 2000-08-15 | 2000-08-12 | 2000-08-12 | 2000-08-24 | 2000-09-05 | K 739 494 | 0 | 0 | 37 | K 739 494 | 130 | #N/A | 35 | K 739 494 | 260 | 0 | 37 |  |  |  |  | N/A | 11 | 11 | 7/8" | 26 | 26 | 7/8" | 26 | 26 | 7/8" |  |  |  | 126 | ML 38 E 1+0 | Timisoara | MW | 134.2 | 0.3 | 34 | 25 | 38/17 |  | 4x2/8 | 4U-1(TMR9202) |  |  |  | TMR 9202 | [10 empty] | TM031 | AUREL VLAICU_1 | 314.25 | 0.3 | 34 | 15 | 38/13 | [6 empty] | 1 | INTERACTIVE | 2000-07-06 | 37/36 | 2000-07-06 | 2000-07-08 | 2000-07-16 | IVAN | OK | 2000-08-12 |  | 2000-08-23 | 2000-09-05 | 30N03 Arad RTC4-Dr.Taberei |  | OK | Cristian CROITOR | #N/A | [32 empty] | 108 | Arad | Arad | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | TM033 | PIATA GARII | Arad(9+1) | TM025 Arad-DRTv_RTC | Banat | 46 11 23 | 21 19 23 | 46 11 22.6 | 21 19 20.6 | Bl. L, Piata Garii | Asociatia de proprietari/Mihai Roblasca - Str. Piata garii Bl. L, tel: 057/234 769 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-07-06 | 2000-07-07 | N/A |  |  |  | 14.8 | B | 16 | Pylonet 9m | N/A | DIEKAT | OK | DIEKAT | 2000-06-14 | 2000-06-26 | YesV | 2000-06-29 | Mugur | 2000-07-03 | 2000-07-11 |  |  |  | 2000-05-19 | 2000-05-14 |  | 2000-05-25 | 2000-06-22 |  |  |  | 2000-07-06 | YRO | Interactive | 2000-07-05 | 2000-07-05 | 2000-07-07 | 2000-07-08 | 2000-07-16 |  | Yes | Constantin Mihai | 2000-08-15 | 2000-08-11 | 2000-08-11 | 2000-08-24 | 2000-09-05 | K 739 494 | 30 | 0 | 33.3 | K 739 494 | 140 | 0 | 33.3 | K 739 494 | 270 | 0 | 33.3 |  |  |  |  | N/A | 14 | 14 | 7/8" | 14 | 14 | 7/8" | 14 | 14 | 7/8" |  |  |  | 84 | ML 38 E 1+0 | Timisoara | MW | 121.11 | 0.3 | 21 | 14.5 | 38/13 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [10 empty] | TM026 | CALEA RADNEI | 301 | 0.3 | 33.5 | 12 | 38/17 | [6 empty] | 1 | INTERACTIVE | 2000-07-06 | 33 | 2000-07-08 | 2000-07-08 | 2000-07-16 | IVAN | OK | 2000-08-11 |  | 2000-08-23 | 2000-09-05 | 30N02 Arad-Dr.Taberei |  | OK | Cristian CROITOR | Cosmorom | [32 empty] | 110 | Arad | Arad | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | TM040 | FERMA 8 | Road Arad-Nadlac(4) | TM043 Nadlac_RTC | Banat | 46 11 55 | 21 08 38 | 46 11 35.7 | 21 08 50.2 | DN Pecica-Arad Km 9+850m | Tomoioaga Gheorghe - DN Pecica-Pecica, Km 9+850m, 094/ 611 684/Tomimpex SRL - 057/ 468 021 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-08-16 | N/A | N/A |  |  |  |  | TN | 50 | Tower | N/A | DIEKAT | OK | VECTOR | 2000-08-10 | 2000-09-15 | YesV | 2000-09-28 | Mugur | 2001-01-19 | 2000-09-29 |  |  |  |  | 2000-06-21 |  | 2000-07-20 | 2000-08-11 |  |  |  | 2000-10-20 | ICOM | MOB | 2000-10-09 | 2000-10-09 | 2000-10-23 | 2000-10-27 | 2000-10-30 |  | Yes | Constantin Mihai | 2001-03-17 | 2001-03-21 | 2001-03-21 | 2001-05-15 | 2001-05-28 | K 739 494 | 60 | 0 | 49 | K 739 494 | 260 | 0 | 49 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 65 | 65 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 130 | ML 23 E 1+0 | Timisoara | MW | 255 | 0.6 | 47 | 65 | 23/58 |  | 4x2/8 | 4U-1 |  |  |  | RBS | [9 empty] | 1 | TM041 | PECICA | 75.31 | 0.6 | 47 | 55 | 23/56 | [6 empty] | 9 | MOBILCOM | 2000-10-20 | 307 | 2000-10-13 | 2000-10-14 | 2000-10-30 | IVAN | OK | 2001-03-21 |  | 2001-04-11 | 2001-04-17 | 30N01 Nadlac-Dr.Taberei |  | OK | Cristian CROITOR | Cosmorom | [32 empty] | 102 | PECICA | Arad | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | TM041 | PECICA | Road Arad-Nadlac(4) | TM043 Nadlac_RTC | Banat | 46 10 19 | 20 59 16 | 46 10 19.5 | 20 59 14.8 | Sos. Arad-Nadlac Km 29 | SC Agro Vest - Sos. Arad-Nadlac Km 29/Ing. Mihet Mihai, tel: 057/ 468 129; 057/ 468 297 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-08-16 | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | DIEKAT | OK | VECTOR | 2000-06-20 | 2000-07-31 | YesV | 2000-08-09 | Mugur | 2000-09-15 | 2000-08-14 |  |  |  | 2000-05-19 | 2000-06-21 |  | 2000-05-23 | 2000-07-04 |  |  |  | 2000-10-20 | ICOM | MOB | 2000-08-23 |  | 2000-10-23 | 2000-10-27 | 2000-10-30 |  | Yes | Alexandru Toma | 2001-03-17 | 2001-03-17 | 2001-03-17 | 2001-05-28 | 2001-06-19 | K 739 494 | 80 | 0 | 48 | K 739 494 | 220 | 0 | 48 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 61 | 61 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 122 | ML 15 E 1+0 | Timisoara | MW | 257.56 | 0.6c | 47/0.6 | 55 | 15/84h |  | 4x2/8 | 4U-1 |  |  |  | RBS | [9 empty] | 1 | TM042 | SEITIN | 77.46 | 0.6c | 47/0.6 | 55 | 15/89h | [6 empty] | 7* | SVF | 2000-12-14 | 324 | 2001-02-21 | 2001-02-22 | 2001-03-01 | PAUN | OK | 2001-03-17 |  | 2001-05-03 | 2001-05-11 | 30N01 Nadlac-Dr.Taberei |  | OK | Cristian CROITOR | Cosmorom | [32 empty] | 111 | PECICA | Arad | [7 empty] | 2 |  |  | 2
Phase_2 | CS | TM042 | SEITIN | Road Arad-Nadlac(4) | TM043 Nadlac_RTC | Banat | 46 08 54 | 20 50 43 | 46 08 55.2 | 20 50 40.9 | E68 Sos. Nadlac-Pecica km7 | Mocris Gheorghe - Str. Revolutiei nr.37 com. Seitin, tel: 057/ 415 114/ | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-08-16 | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | DIEKAT | OK | VECTOR | 2000-11-08 | 2000-12-13 | YesV | 2001-02-06 | Mugur | 2001-01-19 | 2001-02-07 |  |  |  | 2000-05-23 | 2000-06-21 |  | 2000-06-09 | 2000-07-04 |  |  |  | 2000-12-14 | ICOM | SVF | 2000-10-09 | 2000-12-18 | 2000-12-19 | 2001-01-18 | 2001-01-19 |  | Yes | Alexandru Toma | 2001-03-17 | 2001-03-17 | 2001-03-17 | 2001-05-15 | 2001-05-28 | K 739 494 | 80 | 0 | 48 | K 739 494 | 290 | 0 | 48 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 23 E 1+0 | Timisoara | MW | 282.29 | 1.2 | 47/0.6 | 55 | 23/58 |  | 4x2/8 | 4U-1 | 4U-1 |  |  | RBS | [9 empty] | 1 | TM043 | NADLAC_RTC | 102 | 0.6 | 22.5 | 50 | 23/56 | [6 empty] | 7* | SVF | 2000-12-14 | 459 | 2000-12-18 | 2001-02-22 | 2001-03-01 | RADU | OK | 2001-03-17 | Pending |  |  | 30N01 Nadlac-Dr.Taberei |  | OK | Cristian CROITOR | Cosmorom | [32 empty] | 100 | SEITIN | Arad | [7 empty] | 2 |  |  | 2
Phase_2 | CS | TM043 | NADLAC_RTC | Road Arad-Nadlac(4) | TM043 Nadlac_RTC | Banat | 46 09 47 | 20 44 52 | 46 09 47 | 20 44 52 | RTC Nadlac, jud. Arad | Romtelecom/ | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-07-06 | N/A | N/A |  |  |  | 10.5 | B | 10.5 | Pilonet 12m | Room | DIEKAT | OK | VECTOR | 2000-06-19 | 2000-07-03 | YesV | 2000-07-11 | Mugur | 2000-07-03 | 2000-09-04 |  |  |  | N/A | 2000-06-21 |  | 2000-06-09 | 2000-06-22 |  |  |  | 2000-07-06 | YRO | Interactive | 2000-07-05 | 2000-07-05 | 2000-07-07 | 2000-07-08 | 2000-07-24 |  | Yes | Constantin Mihai | 2000-09-10 | 2000-09-05 | 2000-09-05 | 2000-09-21 | 2000-09-26 | K 739 494 | 30 | 0 | 10 | K 739 494 | 150 | 0 | 10 | K 739 494 | 270 | 0 | 10 |  |  |  |  | N/A | 36 | 36 | 7/8" | 36 | 36 | 7/8" | 36 | 36 | 7/8" |  |  |  | 216 | N/A | Timisoara | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | 4U-1(TMR9202) |  |  |  | TMR 9202 | 50043 | [8 empty] | 1 | BSC31 | BSC TIMISOARA | N/A | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | 30N01 Nadlac-Dr.Taberei |  | OK | Cristian CROITOR | Cosmorom | [32 empty] | 85 | Nadlac | Arad | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | TM044 | SAGU | Road Arad-Timisoara(4) | TM053 Central_RTC | Banat | 46 05 29.5 | 21 18 01.4 | 46 05 32 | 21 18 03 | Nod hidro Valea Viilor | Iancu- Dir. IAS Sagu, 094/ 556 812/Dl. Iancu Gheorghe - 094/ 556 812 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-09-04 | N/A | N/A |  |  |  |  | TN | 50 | 50m new tower | N/A | SVF | OK | SVF | 2000-08-03 | 2000-08-28 | YesV | 2000-08-31 | Mugur | 2000-08-30 | 2000-09-04 |  |  |  |  | 2000-07-24 |  | 2000-07-24 | 2000-08-02 |  |  |  | 2000-08-30 | YRO | SVF | 2000-08-30 | 2000-08-30 | 2000-08-31 | 2000-08-31 | 2000-09-07 |  | Yes | Alexandru Bucur | 2001-03-11 | 2001-03-11 | 2001-03-11 | 2001-04-17 | 2001-04-23 | K 739 494 | 10 | 0 | 49.5 | K 739 494 | 210 | 0 | 49.5 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 65 | 65 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 130 | ML 15 E 1+0 | Timisoara | MW | 218 | 1.2 | 47.5 | 65 | 15/84 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [9 empty] | 1 | TM045 | VINGA | 38 | 1.2 | 47/1.2 | 66 | 15/89 | [6 empty] | 7 | SVF | 2000-08-31 | 162 | 2000-08-31 | 2000-08-31 | 2000-09-06 | DINCA | OK | 2001-03-11 | PENDING ITEMS |  |  | 30N06 Timisoara Centru-Dr.Taberei |  | OK | Cristian CROITOR | Cosmorom | [32 empty] | 141 | Sagu | Arad | [7 empty] | 2 |  |  | 2
Phase_2 | CS | TM045 | VINGA | Road Arad-Timisoara(4) | TM053 Central_RTC | Banat | 45 59 57.3 | 21 11 45.3 | 45 59 58 | 21 11 44 | Extravilan loc. Vinga Tarlaua 210, parcela 1426/2/1/1 | Smoc Nicolae - Loc. Vinga nr.91, 057/ 460 454/Smoc Nicolae - Loc. Vinga nr.91, 057/ 460 454 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-09-04 | N/A | N/A |  |  |  |  | TN | 50 | 50m new tower | N/A | SVF | OK | SVF | 2000-08-03 | 2000-08-28 | YesV | 2000-08-31 | Mugur | 2000-08-30 | 2000-09-04 |  |  |  | 2000-06-29 | 2000-06-20 |  | 2000-07-18 | 2000-08-02 |  |  |  | 2000-08-30 | YRO | SVF | 2000-08-30 | 2000-08-30 | 2000-08-31 | 2000-08-31 | 2000-09-07 |  | Yes | Alexandru Bucur | 2001-03-11 | 2001-03-11 | 2001-03-11 | 2001-04-17 | 2001-04-23 | K 739 494 | 45 | 0 | 49 | K 739 494 | 180 | 0 | 49 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 70 | 70 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 140 | ML 15 E 1+0 | Timisoara | MW | 174 | 0.6 | 47 | 66 | 15/89 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [9 empty] | 1 | TM046 | CORNESTI | 354 | 0.6 | 37 | 47 | 15/84 | [6 empty] | 9 | MOBILCOM | 2000-10-20 | 308 | 2000-10-24 | 2000-08-31 | 2000-09-06 | DINCA | OK | 2001-03-11 | PENDING ITEMS |  |  | 30N06 Timisoara Centru-Dr.Taberei |  | OK | Cristian CROITOR | Cosmorom | [32 empty] | 120 | Vinga | Arad | [7 empty] | 2 |  |  | 2
Phase_2 | CS | TM046 | CORNESTI | Road Arad-Timisoara(4) | TM053 Central_RTC | Banat | 45 54 47.5 | 21 12 31.4 | 45 54 49 | 21 12 36 | Com. Ortisoara, sat Cornesti | Hiris Petru - Com. Ortosoara, sat Cornesti nr.56, 094/ 838 017/Hiris Petru - Com. Ortosoara, sat Cornesti nr.56, 094/ 838 017 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-10-11 | N/A | N/A |  |  |  |  | TN | 40 | 50m new tower | N/A | SVF | OK | VECTOR | 2000-08-03 | 2000-09-08 | YesV | 2000-09-20 | Mugur | 2001-01-19 | 2000-09-22 |  |  |  |  | 2000-06-22 |  | 2000-07-21 | 2000-08-01 |  |  |  | 2000-10-20 | ICOM | MOB | 2000-09-27 | 2000-09-27 | 2000-10-23 | 2000-10-27 | 2000-10-30 |  | Yes | Alexandru Bucur | 2001-03-04 | 2001-03-04 | 2001-03-04 | 2001-05-15 | 2001-05-25 | K 739 494 | 0 | 0 | 40 | K 739 494 | 180 | 0 | 40 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Timisoara | MW | 183 | 1.2 | 37/1.2 | 47 | 15/84 |  | 4x2/8 | 4U-1 |  |  |  | RBS | [9 empty] | 1 | TM047 | AGRO | 4 | 1.2 | 37/1.2 | 50 | 15/89 | [6 empty] | 19* | SVF | 2001-01-24 | 535 | 2001-01-26 | 2000-08-31 | 2000-09-06 | DINCA | OK | 2001-03-04 | PENDING ITEMS |  |  | 30N06 Timisoara Centru-Dr.Taberei |  | OK | Cristian CROITOR | COSMOROM | [32 empty] | 138 | Cornesti | Timis | [7 empty] | 2 |  |  | 2
Phase_2 | CS | TM047 | AGRO | Road Arad-Timisoara(4) | TM053 Central_RTC | Banat | 45 48 31.1 | 21 11 54.3 | 45 48 31.3 | 21 11 56.8 | Extravilan loc. Covaci | Andreica Victor/Otves Carol - 094/ 771 493 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-10-20 | N/A | N/A |  |  |  |  | TN | 40 |  | N/A | SVF | OK | VECTOR | 2000-09-12 | 2000-10-14 | YesV | 2001-04-20 | Mugur | 2001-01-19 | 2001-04-25 |  |  |  | 2000-07-06 | 2000-06-22 |  | 2000-08-27 | 2000-09-08 |  |  |  | 2000-10-23 | ICOM | MOB | 2000-10-23 | 2000-10-23 | 2000-10-23 | 2000-10-25 | 2000-10-30 |  | Yes | Alexandru Bucur | 2001-03-04 | 2001-03-04 | 2001-03-04 |  |  | K 739 494 | 0 | 0 | 39 | K 739 494 | 170 | #N/A | 39 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 23 E 1+1 | Timisoara | MW | 166 | 0.6 | 37 | 50 | 23/58 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [9 empty] | 1 | TM050 | CIRCUMVALATIUNII | 346 | 0.6 | 36 | 20 | 23/56 | [6 empty] | 10 | MOBILCOM | 2000-10-23 | 323 | 2000-10-23 | 2000-08-31 | 2000-09-06 | DINCA | OK | 2001-03-04 | PENDING ITEMS |  |  | 30N06 Timisoara Centru-Dr.Taberei |  | OK | Cristian CROITOR | #N/A | [32 empty] | 97 | Covaci | Timis | [7 empty] | 2 |  |  | 2
Phase_2 | CS | TM048 | IALOMITEI | Timisoara(14+1) | TM053 Central_RTC | Banat | 45 46 09 | 21 14 08 | 45 46 09 | 21 14 18 | Str. Ialomitei nr.19 | PRESTIM SA - Str. Ialomitei nr.19/D-na. Brenar - Str. Ialomitei nr.19, tel:056/ 211417 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-08-16 | Yes | N/A |  |  |  | 12 | B | 13.5 | T6m+T6m | N/A | SVF | OK | SVF | 2000-07-20 | 2000-07-31 | YesV | 2000-08-09 | Mugur | 2000-08-17 | 2000-08-14 |  |  |  | 2000-05-29 | 2000-05-12 |  | 2000-07-14 | 2000-07-24 |  |  |  | 2000-08-18 | YRO | MOB | 2000-08-18 | 2000-08-18 | 2000-08-21 | 2000-08-22 | 2000-08-23 |  | Yes | Alexandru Bucur | 2001-03-10 | 2001-03-10 | 2001-03-10 | 2001-04-17 | 2001-05-15 | K 739 494 | 0 | 0 | 17 | K 739 494 | 120 | 0 | 16.5 | K 739 494 | 240 | 0 | 17 |  |  |  |  | N/A | 15 | 15 | 7/8'' | 13 | 13 | 7/8'' | 15 | 15 | 7/8'' |  |  |  | 86 | ML 38 E 1+0 | Timisoara | MW | 175 | 0.3 | 17.5 | 13 | 38/18 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [9 empty] | 1 | TM052 | TACHE IONESCU | 358 | 0.3 | 37.35/0.3 | 11 | 38/14 | [6 empty] | 1 | MOBILCOM | 2000-07-06 | 138 | 2000-08-21 | 2000-08-22 | 2000-08-23 | DINCA | OK | 2001-03-10 | PENDING ITEMS |  |  | 30N02 Centru-Timisoara |  | OK | Cristian CROITOR | Cosmorom | [32 empty] | 87 | Timisoara | Timis | [7 empty] | 2 |  |  | 2
Phase_2 | CS | TM049 | NORD_RTC | Timisoara(14+1) | TM049 Nord_RTC | Banat | 45 45 54 | 21 13 26 | 45 45 54 | 21 13 26 | Str. Teiului nr.7 | Romtelecom/ | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-06-14 | N/A | N/A |  |  |  |  | B | 15 | Existing tower 18m | Room | SVF | OK | SVF | 2000-06-02 | 2000-06-11 | YesV | 2000-06-13 | Mugur | 2000-08-01 | 2000-06-16 |  |  |  | N/A | 2000-05-12 |  | 2000-06-02 | 2000-06-12 |  |  |  | 2000-06-15 | YRO | MOB | 2000-06-15 | 2000-06-15 | 2000-06-19 | 2000-06-20 | 2000-06-23 |  | Yes | Constantin Mihai | 2000-08-14 | 2000-08-17 | 2000-08-17 | 2000-08-24 | 2000-09-05 | K 739 494 | 0 | 0 | 32 | K 739 494 | 120 | 0 | 32 | K 739 494 | 240 | 0 | 32 |  |  |  |  | N/A | 32 | 32 | 7/8" | 32 | 32 | 7/8" | 32 | 32 | 7/8" |  |  |  | 160 | N/A | Timisoara | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | [12 empty] | 200/ |  |  | BSC31 | BSC TIMISOARA |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | 30N01 Nord-Dr.Taberei |  | OK | Cristian CROITOR | Cosmorom | [32 empty] | 86 | Timisoara | Timis | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | TM050 | CIRCUMVALATIUNII | Timisoara(14+1) | TM053 Central_RTC | Banat | 45 45 26 | 21 12 59 | 45 45 26 | 21 12 59 | Str. Cicumvalatiunii nr.21 bl.I1 | Asociatie de proprietari/Gomana Gheorghe - Str. Cicumvalatiunii nr.21 bl.I1, tel: 056/ 146 714 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-06-21 | 2000-07-07 | N/A |  |  |  | 34.5 | B | 33 | T4.5m+T4.5m | N/A | SVF | OK | SVF | 2000-06-15 | 2000-06-29 | YesV | 2000-06-30 | Mugur | 2000-07-03 | 2000-07-11 |  |  |  | 2000-06-01 | 2000-05-12 |  | 2000-06-07 | 2000-06-22 |  |  |  | 2000-07-07 | YRO | MOB | 2000-07-05 | 2000-07-05 | 2000-07-07 | 2000-07-11 | 2000-07-17 |  | Yes | Constantin Mihai | 2000-08-14 | 2000-08-18 | 2000-08-18 | 2000-08-24 | 2000-09-05 | K 739 494 | 25 | 0 | 34.5 | K 739 494 | 120 | 0 | 38 | K 739 494 | 240 | 0 | 38.3 |  |  |  |  | N/A | 19 | 19 | 7/8" | 31 | 31 | 7/8" | 32 | 32 | 7/8" |  |  |  | 164 | ML 38 E 1+1 | Timisoara | MW | 118 | 0.3 | 36 | 18 | 38/14 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [9 empty] | 1 | TM053 | CENTRAL_RTC | 298 | 0.3 | 30 | 50 | 38/18 | [6 empty] | 2 | MOBILCOM | 2000-07-07 | 26 | 2000-07-05 | 2000-07-11 | 2000-07-24 | IVAN | OK | 2000-08-18 |  | 2000-08-23 | 2000-09-05 | 30N06 Timisoara Centru-Dr.Taberei |  | OK | Cristian CROITOR | CATALINA CIOCAN | [32 empty] | 85 | Timisoara | Timis | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | TM051 | SIMION BARNUTIU | Timisoara(14+1) | TM053 Central_RTC | Banat | 45 45 54 | 21 15 35 | 45 45 54 | 21 15 33 | Str. Simion Barnutiu nr.56 Sc.A | Asociatie de proprietari/Fam. Hotico, tel: 092/379 823 | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-07-18 | N/A | N/A |  |  |  | 25.6 | B | 29.15 | 2xSuport zid | Room | SVF | OK | SVF | 2000-08-14 | 2000-08-25 | YesV | 2000-09-01 | Mugur | 2000-09-06 | 2000-09-04 |  |  |  | 2000-06-01 | 2000-05-12 |  | 2000-06-21 | 2000-08-01 |  |  |  | 2000-08-22 | YRO | MOB | 2000-08-22 | 2000-08-22 | 2000-08-23 | 2000-08-24 | 2000-08-29 |  | Yes | Alexandru Bucur | 2001-03-10 | 2001-03-10 | 2001-03-10 | 2001-04-17 | 2001-04-23 | K 739 494 | 0 | 0 | 31 | K 739 494 | 120 | 0 | 31.2 | K 739 494 | 240 | 0 | 31.3 |  |  |  |  | N/A | 31 | 31 | 7/8" | 31 | 31 | 7/8" | 25 | 25 | 7/8" |  |  |  | 174 | ML 38 E 1+0 | Timisoara | MW | 249 | 0.3 | 34.1 | 25 | 38/18 |  | 4x2/8 | 2U-3 | [13 empty] | 1 | TM052 | TACHE IONESCU | 65 | 0/3 | 46.35 | 20 | 38/14 | [6 empty] | 6 | MOBILCOM | 2000-08-22 | 137 | 2000-08-22 | 2000-08-24 | 2000-08-29 | DINCA | OK | 2001-03-10 | PENDING ITEMS |  |  | 30N02 Centru-Timisoara |  | OK | Cristian CROITOR | Cosmorom | [32 empty] | 87 | Timisoara | Timis | [7 empty] | 2 |  |  | 2
Phase_2 | CS | TM052 | TACHE IONESCU | Timisoara(14+1) | TM053 Central_RTC | Banat | 45 45 32 | 21 14 12 | 45 45 26 | 21 14 10 | Str. Tache Ionescu bl.39 | Asociatie de proprietari/Cristescu Petru - 056/ 202 848 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-08-16 | Yes | N/A |  |  |  | 34.33 | B | 34.33 | 12m new pylonet | N/A | SVF | OK | SVF | 2000-11-14 | 2001-01-15 | YesV | 2001-02-14 | Mugur | 2001-03-08 | 2001-03-06 |  |  |  |  | 2000-09-22 |  | 2000-11-07 | 2000-11-24 |  |  |  | 2001-02-01 | ICOM | SVF | 2001-01-30 | 2001-01-30 | 2001-02-06 | 2001-02-09 | 2001-02-13 |  | Prov | Alexandru Bucur | 2001-03-10 | 2001-03-10 | 2001-03-10 | 2001-05-17 | 2001-05-25 | K 739 494 | 0 | 0 | 42.35 | K 739 494 | 120 | 0 | 42.35 | K 739 494 | 240 | 0 | 42.35 |  |  |  |  | N/A | 16 | 16 | 7/8" | 16 | 16 | 7/8" | 16 | 16 | 7/8" |  |  |  | 108 | ML 38 E 1+1 | Timisoara | MW | 214 | 0.3 | 46.35 | 20 | 38/14 |  | 4x2/8 | 4U-1 |  |  |  | RBS | [9 empty] | 1 | TM053 | CENTRAL_RTC | 29 | 0.3 | 30 | 50 | 38/18 | [6 empty] | 30*/1 | MOBILCOM | 21.02.01-6.07.00 | 141 | 2000-08-21 | 2001-02-20 | 2001-02-26 | DINCA | OK | 2001-03-10 | PENDING ITEMS |  |  | 30N01Centru-Timisoara |  | OK | SORIN UNTARU | SORIN UNTARU | [32 empty] | 85 | Timisoara | Timis | [7 empty] | 2 |  |  | 2
Phase_2 | CS | TM053 | CENTRAL_RTC | Timisoara(14+1) | TM053 Central_RTC | Banat | 45 45 06 | 21 13 51 | 45 45 06 | 21 13 51 | Romtelecom Central Timisoara | Romtelecom/ | 2202 | M/E | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-06-14 | N/A | N/A |  |  |  | 21.5 | B | 21.5 | Existing pylon 9m | Room | SVF | OK | SVF | 2000-06-02 | 2000-06-11 | YesV | 2000-06-13 | Mugur | 2000-06-09 | 2000-06-16 |  |  |  | N/A | 2000-05-12 |  | 2000-05-25 | 2000-06-12 |  |  |  | 2000-06-15 | YRO | MOB | 2000-06-13 | 2000-06-13 | 2000-06-19 | 2000-06-20 | 2000-06-23 |  | Yes | Constantin Mihai | 2000-08-15 | 2000-08-18 | 2000-08-18 | 2000-08-24 | 2000-09-05 | K 739 494 | 0 | 0 | 32 | K 739 494 | 120 | 0 | 32 | K 739 494 | 240 | 0 | 32 |  |  |  |  | N/A | 50 | 50 | 1 1/4" | 50 | 50 | 1 1/4" | 50 | 50 | 1 1/4" |  |  |  | 250 | N/A | Timisoara | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | 4U-1(TMR9202) |  |  |  | TMR 9202 | 50053 | [8 empty] | 1 | BSC31 | BSC TIMISOARA |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | 30N02 Timisoara Centru-Dr.Taberei |  | OK | Cristian CROITOR | CATALINA CIOCAN | [32 empty] | 85 | Timisoara | Timis | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | TM054 | IULIU MANIU | Timisoara(14+1) | TM095 Resita_RTC3 | Banat | 45 44 21 | 21 12 34 | 45 44 25 | 21 12 37 | Str. Iuliu Maniu Bl.1B | Asociatie de proprietari/Pavel Viorel - B-dul. Iuliu Maniu Bl.1B Ap.28, tel: 056/ 155 391 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-08-02 | 2000-08-02 | N/A |  |  |  | 25.2 | B | 27.3 | T4m+T4m | N/A | SVF | OK | ARGOS | 2000-06-25 | 2000-07-15 | YesV | 2000-07-26 | Mugur | 2000-08-01 | 2000-08-03 |  |  |  | 2000-05-29 | 2000-05-12 |  | 2000-06-05 | 2000-06-22 |  |  |  | 2000-08-01 | YRO | MOB | 2000-08-01 | 2000-08-01 | 2000-08-02 | 2000-08-03 | 2000-08-07 |  | Yes | Constantin Mihai | 2000-08-15 | 2000-08-17 | 2000-08-17 | 2000-08-24 | 2000-09-05 | K 739 494 | 20 | 0 | 28.7 | K 739 494 | 140 | 0 | 31.8 | K 739 494 | 240 | 0 | 28.5 |  |  |  |  | N/A | 19 | 19 | 7/8" | 30 | 30 | 7/8" | 19 | 19 | 7/8" |  |  |  | 136 | N/A | Timisoara | CABLU | CABLU | N/A | N/A | N/A | N/A |  | N/A | 4U-1 |  |  |  | RBS | 50054 | [9 empty] | TM095 | RESITA_RTC3 | CABLU | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 30N04 TM Resita-Dr.Taberei |  | OK | Cristian CROITOR | Cosmorom | [32 empty] | 84 | Timisoara | Timis | [7 empty] | 2 |  |  | 2
Phase_2 | CS | TM056 | STEFAN CEL MARE | Timisoara(14+1) | TM053 Central_RTC | Banat | 45 45 04 | 21 15 11 | 45 45 10 | 21 15 09 | Str. Stefan cel Mare Bl.C12 | Asociatie de proprietari/Tucanov Jiva - Str. Stefan Cel Mare, tel: 056/ 206 684 | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-07-06 | N/A | N/A |  |  |  | 26 | B | 28.3 | T4.5m+T4.5m | Room | SVF | OK | SVF | 2000-06-14 | 2000-06-29 | YesV | 2000-06-30 | Mugur | 2000-07-03 | 2000-07-11 |  |  |  | 2000-05-29 | 2000-05-12 |  | 2000-06-20 | 2000-06-28 |  |  |  | 2000-07-07 | YRO | MOB | 2000-07-05 | 2000-07-05 | 2000-07-07 | 2000-07-11 | 2000-07-16 |  | Yes | Constantin Mihai | 2000-08-15 | 2000-08-17 | 2000-08-17 | 2000-08-24 | 2000-09-05 | K 739 494 | 0 | 0 | 30 | K 739 494 | 120 | 0 | 30 | K 739 494 | 240 | 0 | 30 |  |  |  |  | N/A | 18 | 18 | 7/8" | 18 | 18 | 7/8" | 17 | 17 | 7/8" |  |  |  | 106 | ML 38 E 1+0 | Timisoara | MW | 240 | 0.3 | 30.2 | 16 | 38/17 |  | 4x2/8 | 4U-1(TMR9202) |  |  |  | TMR 9202 | [9 empty] | 1 | TM057 | SPORTIVILOR | 59 | 0.3 | 41 | 27 | 38/13 | [6 empty] | 2 | MOBILCOM | 2000-07-07 | 27 | 2000-07-06 | 2000-07-11 | 2000-07-16 | IVAN | OK | 2000-08-18 |  | 2000-08-23 | 2000-09-05 | 30N02 Timisoara Centru-Dr.Taberei |  | OK | Cristian CROITOR | Cosmorom | [32 empty] | 86 | Timisoara | Timis | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | TM057 | SPORTIVILOR | Timisoara(14+1) | TM053 Central_RTC | Banat | 45 44 44 | 21 14 22 | 45 44 46 | 21 14 25 | Str. Sportivilor nr.6 | Asociatie de proprietari/Frazler Josif - Ap.32, 056/ 195 143 | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-07-18 | N/A | N/A |  |  |  | 31.9 | B | 37.2 | C3m+T6m | Room | SVF | OK | SVF | 2000-07-10 | 2000-07-25 | YesV | 2000-07-26 | Mugur | 2000-07-28 | 2000-08-03 |  |  |  | 2000-06-01 | 2000-05-20 |  | 2000-06-21 | 2000-07-06 |  |  |  | 2000-08-01 | YRO | MOB | 2000-08-01 | 2000-08-01 | 2000-08-02 | 2000-08-03 | 2000-08-10 |  | Yes | Constantin Mihai | 2000-08-16 | 2000-08-17 | 2000-08-17 | 2000-08-24 | 2000-09-05 | K 739 494 | 0 | 0 | 40 | K 739 494 | 120 | 0 | 40 | K 739 494 | 240 | 0 | 36.5 |  |  |  |  | N/A | 26 | 26 | 7/8" | 26 | 26 | 7/8" | 15 | 15 | 7/8" |  |  |  | 134 | ML 38 E 1+0 | Timisoara | MW | 315 | 0.3 | 37.5 | 16 | 38/14 |  | 4x2/8 | 2U-3 | [14 empty] | TM053 | CENTRAL_RTC | 135 | 0.3 | 30 | 50 | 38/18 | [6 empty] | 1 | MOBILCOM | 2000-06-15 | 89 | 2000-08-01 | 2000-08-03 | 2000-08-10 | IVAN | OK | 2000-08-18 |  | 2000-08-23 | 2000-09-05 | 30N03 Timisoara Centru-Dr.Taberei |  | OK | Cristian CROITOR | Cosmorom | [32 empty] | 85 | Timisoara | Timis | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | TM059 | CALEA SAGULUI | Timisoara(14+1) | TM095 Resita_RTC3 | Banat | 45 43 50 | 21 12 28 | 45 43 52 | 21 12 30 | CALEA Sagului nr.45-47, Sc.A-B | Asociatie de proprietari/Modek Adam - 056/ 151 583 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-06-14 | 2000-06-15 | N/A |  |  |  | 35.65 | B | 33 | C3m+C3m+C3m | N/A | SVF | OK | SVF | 2000-06-07 | 2000-06-21 | YesV | 2000-06-29 | Mugur | 2000-06-30 | 2000-07-11 |  |  |  | 2000-06-01 | 2000-05-12 |  | 2000-06-07 | 2000-06-12 |  |  |  | 2000-06-15 | YRO | MOB | 2000-06-13 | 2000-06-13 | 2000-06-19 | 2000-06-20 | 2000-06-24 |  | Yes | Constantin Mihai | 2000-08-16 | 2000-08-18 | 2000-08-18 | 2000-08-24 | 2000-09-05 | K 739 494 | 0 | 0 | 37 | K 739 494 | 120 | 0 | 37.2 | K 739 494 | 250 | 0 | 37.2 |  |  |  |  | N/A | 15 | 15 | 7/8" | 18 | 18 | 7/8" | 15 | 15 | 7/8" |  |  |  | 81 | ML 38 E 1+0 | Timisoara | MW | 7 | 0.3 | 37 | 15 | 38/18 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [9 empty] | 1 | TM054 | IULIU MANIU | 188 | 0.3 | 32.7 | 30 | 38/14 | [6 empty] | 1 / 3 | MOBILCOM | 19.06.00-1.08.00 | 1987-11-01 | 19.06.00-1.08.00 | 2000-06-23 | 2000-06-23 | DINCA | OK | 2000-08-18 |  | 2000-08-23 | 2000-09-05 | 30N05 TM Resita-Dr.Taberei |  | OK | Cristian CROITOR | CATALINA CIOCAN | [32 empty] | 84 | Timisoara | Timis | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | TM060 | DIMBOVITA | Timisoara(14+1) | TM095 Resita_RTC3 | Banat | 45 44 19 | 21 11 50 | 45 44 22 | 21 11 52 | B-dul. Dimbovita nr.84 Bl.T3 | Asociatie de proprietari/Musat Calin - B-dul. Dimbovita nr.84 bl. T3, tel: 056/ 217 422 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-08-16 | Yes | N/A |  |  |  | 31.35 | B | 33 | T3m+T3m | N/A | SVF | OK | ARGOS | 2000-06-25 | 2000-07-31 | YesV | 2000-08-09 | Mugur | 2000-08-17 | 2000-08-14 |  |  |  | 2000-05-29 | 2000-05-12 |  | 2000-06-12 | 2000-06-22 |  |  |  | 2000-08-18 | YRO | MOB | 2000-08-18 | 2000-08-18 | 2000-08-21 | 2000-08-22 | 2000-08-23 |  | Yes | Constantin Mihai | 2000-09-10 | 2000-09-01 | 2000-09-01 | 2000-09-18 | 2000-09-21 | K 739 494 | 0 | 0 | 33.6 | K 739 494 | 120 | 0 | 33.5 | K 739 494 | 240 | 0 | 33.4 |  |  |  |  | N/A | 12 | 12 | 7/8" | 23 | 23 | 7/8" | 12 | 12 | 7/8" |  |  |  | 94 | ML 38 E 1+0 | Timisoara | MW | 86 | 0.3 | 34.2 | 24 | 38/18 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [10 empty] | TM054 | IULIU MANIU | 266 | 0.3 | 29.5 | 19 | 38/14 | [6 empty] | 5 / 3 | MOBILCOM | 18.08.00-1.08.00 | 133 / 87 | 18.08.00-1.08.00 | 2000-08-22 | 2000-08-23 | IVAN | OK | 2000-09-01 |  | 2000-09-15 | 2000-09-25 | 30N04 TM Resita-Dr.Taberei |  | OK | Cristian CROITOR | Cosmorom | [32 empty] | 83 | Timisoara | Timis | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | TM062 | GIROCULUI | Timisoara(14+1) | TM062 Girocului_RTC | Banat | 45 44 02 | 21 14 15 | 45 44 02 | 21 14 15 | Str. Girocului, Oficiul Romtelecom nr.4 |  | 2202 | M/E | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-06-14 | N/A | N/A |  |  |  | 20 | B | 20 | T4m+T4m | N/A | SVF | OK | SVF | 2000-06-02 | 2000-06-11 | YesV | 2000-06-13 | Mugur | 2000-06-09 | 2000-06-16 |  |  |  | N/A | 2000-05-12 |  | 2000-05-22 | 2000-06-12 |  |  |  | 2000-06-15 | YRO | MOB | 2000-06-13 | 13.06.2000 | 2000-06-19 | 2000-06-20 | 2000-06-23 |  | Yes | Constantin Mihai | 2000-08-16 | 2000-08-18 | 2000-08-18 | 2000-08-24 | 2000-09-05 | K 739 494 | 0 | 0 | 23 | K 739 494 | 120 | 0 | 23 | K 739 494 | 240 | 0 | 23 |  |  |  |  | N/A | 20 | 20 | 7/8" | 32 | 32 | 7/8" | 20 | 20 | 7/8" |  |  |  | 52 | N/A | Timisoara | FO | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | [7 empty] | 25/ |  |  | BSC31 | BSC TIMISOARA | N/A | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | 30N01 Girocului-Nord/30N01 Nord-Dr.Taberei |  | OK | Cristian CROITOR | Cosmorom | [32 empty] | 86 | Timisoara | Timis | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | TM064 | CALEA BUZIASULUI | Timisoara(14+1) | TM053 Central_RTC | Banat | 45 43 52 | 21 15 41 | 45 43 55.9 | 21 15 36 | CALEA Buziasului Bl.A1a | Asociatie de proprietari/Preda Mihai - 223 168 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-07-18 | Yes | N/A |  |  |  | 19 | B | 19 | 15m new pylonet | N/A | SVF | OK | ARGOS | 2000-11-09 | 2000-12-06 | YesV | 2001-02-06 | Mugur | 2000-12-08 | 2001-02-07 |  |  |  |  | 2000-10-14 |  | 2000-11-06 | 2000-11-15 |  |  |  | 2000-12-18 | ICOM | TRY | 2000-12-08 | 2000-12-13 | 2000-12-14 | 2000-12-15 | 2000-12-18 |  | Yes | Alexandru Bucur | 2001-03-05 | 2001-03-05 | 2001-03-05 | 2001-04-24 | 2001-05-03 | K 739 494 | 0 | 0 | 24 | K 739 494 | 120 | 0 | 29.21 | K 739 494 | 240 | 0 | 24 |  |  |  |  | N/A | 17 | 17 | 7/8" | 22 | 22 | 7/8" | 17 | 17 | 7/8" |  |  |  | 112 | ML 38 E 1+0 | Timisoara | MW | 345 | 0.3 | 21.5/0.3 | 14.5 | 38/14 |  | 4x2/8 | 4U-1 |  |  |  | RBS | [9 empty] | 1 | TM056 | STEFAN CEL MARE | 163 | 0.3 | 30.2 | 17 | 38/18 | [6 empty] | 17*/2 | TRYLON | 11.01.00-7.07.00 | 437 | 2001-01-11 | 2001-01-12 | 2001-01-17 | IVAN | OK | 2001-03-05 | PENDING ITEMS |  |  | 30N03 Timisoara Centru-Dr.Taberei |  | OK | SORIN UNTARU | SORIN UNTARU | [32 empty] | 88 | Timisoara | Timis | [7 empty] | 2 |  |  | 2
Phase_2 | CS | TM065 | STEAUA | Timisoara(14+1) | TM095 Resita_RTC3 | Banat | 45 43 17 | 21 12 14 | 45 43 18 | 21 12 17 | Str. Islaz nr.96 Bl.50 Sc.B | Asociatie de proprietari/Fam. Iorga - Ap. 10 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-07-18 | 2000-08-02 | N/A |  |  |  | 15.1 | B | 13.5 | T6m+T6m | N/A | SVF | OK | ARGOS | 2000-06-25 | 2000-07-15 | YesV | 2000-07-26 | Mugur | 2000-08-01 | 2000-08-03 |  |  |  | 2000-06-01 | 2000-10-14 |  | 2000-06-07 | 2000-06-22 |  |  |  | 2000-08-01 | YRO | MOB | 2000-08-01 | 2000-08-01 | 2000-08-02 | 2000-08-03 | 2000-08-08 |  | Yes | Alexandru Bucur | 2000-08-16 | 2000-08-18 | 2000-08-18 | 2000-08-24 | 2000-09-05 | K 739 494 | 0 | 0 | 20 | K 739 494 | 120 | 0 | 20 | K 739 494 | 240 | 0 | 20 |  |  |  |  | N/A | 21 | 21 | 7/8" | 24 | 24 | 7/8" | 21 | 21 | 7/8" |  |  |  | 132 | ML 38 E 1+0 | Timisoara | MW | 16 | 0.3 | 20 | 28 | 38/14 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [9 empty] | 1 | TM059 | CALEA SAGULUI | 80 | 0.3 | 36.35 | 18 | 38/18 | [6 empty] | 3 / 1 | MOBILCOM | 1.08.00-15.06.00 | 88 | 2000-08-01 | 2000-08-03 | 2000-08-08 | IVAN | OK | 2000-08-18 |  | 2000-08-23 | 2000-09-05 | 30N05 TM Resita-Dr.Taberei |  | OK | Cristian CROITOR | Cosmorom | [32 empty] | 85 | Timisoara | Timis | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | TM066 | SAG | Road Timisoara-Stamora(4) | TM095 Resita_RTC3 | Banat | 45 38 48 | 21 10 33 | 45 38 50 | 21 10 35 | SC SPORT SAG, loc. SAG, jud. TIMIS | SC Sport SAG/Gradinaru Nicolae | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-07-06 | N/A | N/A |  |  |  |  | TN | 50 | New 50m tower | N/A | SVF | OK | SVF | 2000-06-02 | 2000-06-29 | YesV | 2000-06-29 | Mugur | 2000-08-01 | 2000-06-29 |  |  |  | 2000-06-09 | 2000-05-25 |  | 2000-06-21 | 2000-06-22 |  |  |  | 2000-07-07 | YRO | MOB | 2000-06-30 | 2000-06-30 | 2000-07-07 | 2000-07-11 | 2000-07-14 |  | Yes | Constantin Mihai | 2000-09-10 | 2000-09-04 | 2000-09-04 | 2000-09-21 | 2000-09-26 | K 739 494 | 0 | 0 | 49.5 | K 739 494 | 180 | 0 | 49.5 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 70 | 70 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 140 | ML 23 E 1+0 | Timisoara | MW | 15 | 0.6 |  | 70 | 23/58 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [9 empty] | 1 | TM065 | STEAUA | 195 | 0.6 |  |  | 23/56 | [6 empty] | 2 / 3 | MOBILCOM | 7.07.00-1.08.00 | 134 | 2000-08-18 | 2000-07-11 | 2000-07-16 | IVAN | OK | 2000-09-03 |  |  |  | 30N05 TM Resita-Dr.Taberei |  | OK | Cristian CROITOR | Cosmorom | [32 empty] | 85 | Sag | Timis | [7 empty] | 2 |  |  | 2
Phase_2 | CS | TM067 | JEBEL | Road Timisoara-Stamora(4) | TM095 Resita_RTC3 | Banat | 45 33 46 | 21 11 55 | 45 33 51 | 21 12 00 | Siloz Jebel | SC Cerealcom SA - Str. N. Titulescu nr.32 Timisoara, tel: 193 429/ 198 128/Berci Petru - 056/193 429 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-07-18 | Yes | N/A |  |  |  | 32 | B | 32 | T6m | N/A | SVF | OK | SVF | 2000-07-20 | 2000-07-31 | YesV | 2000-08-09 | Mugur | 2000-08-17 | 2000-08-14 |  |  |  | 2000-06-01 | 2000-05-25 |  | 2000-06-30 | 2000-07-18 |  |  |  | 2000-08-18 | YRO | MOB | 2000-08-18 | 2000-08-18 | 2000-08-21 | 2000-08-22 | 2000-08-30 |  | Yes | Constantin Mihai | 2000-09-04 | 2000-09-07 | 2000-09-07 | 2000-10-04 | 2000-10-13 | K 739 494 | 0 | 0 | 36.7 | K 739 494 | 160 | 0 | 36.7 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 21 | 21 | 7/8" | 21 | 21 | 7/8" | N/A | N/A | N/A |  |  |  | 84 | ML 23 E 1+0 | Timisoara | MW | 349 | 0.6 | 37.3 | 22 | 23/56 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [10 empty] | TM066 | SAG | 169 | 0.6 | 47 | 67 | 23/58 | [6 empty] | 5 / 2 | MOBILCOM | 18.08.00-7.07.00 | 135 | 2000-08-18 | 2000-08-22 | 2000-08-30 | AUREL | OK | 2000-09-05 |  | 2000-09-15 | 2000-09-25 | 30N04 TM Resita-Dr.Taberei |  | OK | Cristian CROITOR | Cosmorom | [32 empty] | 89 | Jebel | Timis | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | TM069 | DETA | Road Timisoara-Stamora(4) | TM069 Deta_RTC | Banat | 45 21 31.68 | 21 15 25.1 | 45 23 28 | 21 13 24 | Drumul Nadlac-Stamora |  | 2202 | M | C+C+ | 2/2 | 2202 | [6 empty] | 2000-06-14 | N/A | N/A |  |  |  |  | B | 15 | Pilonet 18m | Room | SVF | OK | SVF | 2000-06-02 | 2000-06-11 | YesV | 2000-06-13 | Mugur | 2000-08-01 | 2000-06-13 |  |  |  | N/A | 2000-05-25 |  | 2000-05-22 | 2000-06-12 |  |  |  | 2000-06-15 | YRO | MOB | 2000-06-13 | 13.06.2000 | 2000-06-19 | 2000-06-20 | 2000-06-24 |  | Yes | Constantin Mihai | 2000-09-10 | 2000-09-01 | 2000-09-01 | 2000-09-21 | 2000-10-04 | K 739 494 | 0 | 0 | 31 | K 739 494 | 180 | 0 | 31 | N/A | N/A | N/A | N/A |  |  |  |  | N/A | 50 | 50 | 1 1/4" | 50 | 50 | 1 1/4" | N/A | N/A | N/A |  |  |  | 50 | N/A | Timisoara | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | 4U-1(TMR9202) |  |  |  | TMR 9202 | 50069 | [8 empty] | 1 | BSC31 | BSC TIMISOARA |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | 30N01 Deta-Dr.Taberei |  | OK | Cristian CROITOR | Cosmorom | [32 empty] | 92 | Deta | Timis | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | TM070 | STAMORA GERMANA | Road Timisoara-Stamora(4) | TM069 Deta_RTC | Banat | 45 17 05 | 21 15 16 | 45 17 07 | 21 15 21 | Ferma de berbecuti Stamora Germana, jud. Timis | Ferma de berbecuti/Dir. Gen. Tota - 270 882/ 175 | 2202 | M | C+C+ | 2/2 | 2202 | [6 empty] | 2000-07-26 | N/A | N/A |  |  |  |  | TN | 50 | New 50m tower | Room | SVF | OK | SVF | 2000-06-02 | 2000-06-29 | YesV | 2000-06-29 | Mugur | 2000-08-01 | 2000-06-29 |  |  |  | 2000-06-09 | 2000-05-25 |  | 2000-06-21 | 2000-06-26 |  |  |  | 2000-07-07 | YRO | MOB | 2000-06-30 | 2000-06-30 | 2000-07-07 | 2000-07-11 | 2000-07-16 |  | Yes | Constantin Mihai | 2000-09-10 | 2000-09-07 | 2000-09-07 | 2000-09-21 | 2000-09-26 | K 739 494 | 0 | 0 | 49.5 | K 739 494 | 180 | 0 | 49.5 | N/A | N/A | N/A | N/A |  |  |  |  | N/A | 70 | 70 | 1 1/4" | 70 | 70 | 1 1/4" | N/A | N/A | N/A |  |  |  | 140 | ML 15 E 1+0 | Timisoara | MW | 348 | 0.6 | 47 | 67 | 15/89 |  | 4x2/8 | 4U-1(TMR9202) |  |  |  | TMR 9202 | [9 empty] | 1 | TM069 | DETA | 168 | 0.6 | 33 | 52 | 15/84 | [6 empty] | 1 | MOBILCOM | 2000-06-15 | 10 | 2001-06-19 | 2000-07-11 | 2000-07-16 | IVAN | OK | 2000-09-01 |  | 2000-09-25 | 2000-10-03 | 30N01 Deta-Dr.Taberei |  | OK | Cristian CROITOR | Cosmorom | [32 empty] | 100 | Stamora Germana | Timis | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | TM071 | LUGOJ_RTC | Lugoj(5) | TM071 Lugoj_RTC | Banat | 45 41 16 | 21 54 18 | 45 41 16 | 21 54 18 | Romtelecom Lugoj | Romtelecom/ | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-08-02 | N/A | N/A |  |  |  | 18 | B | 18 | C3.5m+C3.5m+C3.5m | Room | SVF | OK | TEHNOROB | 2000-06-20 | 2000-07-19 | YesV | 2000-07-25 | Mugur | 2000-08-01 | 2000-08-03 |  |  |  | N/A | 2000-05-20 |  | 2000-06-09 | 2000-06-27 |  |  |  | 2000-08-01 | YRO | MOB | 2000-08-01 | 2000-08-01 | 2000-08-02 | 2000-08-03 | 2000-08-11 |  | Yes | Constantin Mihai | 2000-09-10 | 2000-08-31 | 2000-08-31 | 2000-09-18 | 2000-09-21 | K 739 494 | 30 | 0 | 19.5 | K 739 494 | 150 | 0 | 20 | K 739 494 | 270 | 0 | 20 |  |  |  |  | N/A | 21 | 21 | 7/8" | 55 | 55 | 1 1/4" | 14 | 14 | 7/8" |  |  |  | 180 | N/A | Timisoara | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | 4U-1(TMR9202) |  |  |  | TMR 9202 | 50071 | 2001-04-25 | [8 empty] | BSC31 | BSC TIMISOARA |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | 30N03 Lugoj-Timisoara |  | OK | Cristian CROITOR | Cosmorom | [32 empty] | 121 | Lugoj | Timis | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | TM072 | NICOLAE BALCESCU | Lugoj(5) | TM071 Lugoj_RTC | Banat | 45 40 51 | 21 54 15 | 45 40 56 | 21 54 20 | Str. N. Balcescu nr.22 | Asociatie de proprietari/Mincic Traian - 056/354 018 | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-08-09 | N/A | N/A |  |  |  | 34.45 | B | 31 | C3m+C4m | Room | SVF | OK | TEHNOROB | 2000-07-03 | 2000-07-19 | YesV | 2000-07-25 | Mugur | 2000-08-04 | 2000-09-06 |  |  |  | 2000-06-01 | 2000-05-20 |  | 2000-06-12 | 2000-07-19 |  |  |  | 2000-08-18 | YRO | MOB | 2000-08-18 | 2000-08-18 | 2000-08-21 | 2000-08-22 | 2000-08-29 |  | Yes | Constantin Mihai | 2000-09-10 | 2000-09-02 | 2000-09-02 | 2000-09-21 | 2000-10-04 | K 739 494 | 30 | 0 | 37.2 | K 739 494 | 150 | 0 | 37.4 | K 739 494 | 290 | 0 | 37.2 |  |  |  |  | N/A | 25 | 25 | 7/8" | 10 | 10 | 7/8" | 10 | 10 | 7/8" |  |  |  | 90 | ML 38 E 1+0 | Timisoara | MW | 4 | 0.3 | 38 | 26 | 38/17 |  | 4x2/8 | 2U-3 |  |  |  | N/A | [10 empty] | TM071 | LUGOJ_RTC | 185 | 0.3 | 21 | 56 | 38/13 | [6 empty] | 3 | MOBILCOM | 2000-08-01 | 132 | 2000-08-18 | 2000-08-22 | 2000-08-29 | VLAD | OK | 2000-09-02 |  | 2000-09-15 | 2000-09-25 |  |  | OK | Cristian CROITOR | Cosmorom | [32 empty] | 122 | Lugoj | Timis | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | TM073 | CEAHLAULUI | Lugoj(5) | TM071 Lugoj_RTC | Banat | 45 41 48 | 21 53 52 | 45 41 36.8 | 21 54 27.4 | Str.Ceahlaului, Bl.45,Lugoj | Dl. Corne Marius, str. Cehlaului, nr.27, bl. 45, sc.C, et.4, ap.17/Corne Marius-093 389 987 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-12-11 | Yes | N/A |  |  |  | 14.4 | B | 14.4 | T4.5m+T4.5m | N/A | SVF | OK | TEHNOROB | 2000-11-14 | 2000-11-25 | YesV | 2000-11-28 | Mugur | 2001-02-23 | 2000-12-07 |  |  |  |  | 2000-10-11 |  | 2000-11-07 | 2000-11-24 |  |  |  | 2000-11-27 | ICOM | DIEKAT | 2000-11-27 | 2000-11-27 | 2000-11-28 | 2000-11-29 | 2000-11-29 |  | Yes | Theo Radoi | 2001-03-14 | 2001-03-14 | 2001-03-14 | 2001-04-17 | 2001-05-15 | K 739 494 | 80 | 0 | 18 | K 739 494 | 190 | 0 | 17.9 | K 739 494 | 310 | 0 | 18 |  |  |  |  | N/A | 15 | 15 | 7/8" | 15 | 15 | 7/8" | 18 | 18 | 7/8" |  |  |  | 96 | ML 38 E 1+0 | Timisoara | MW | 75 | 0.3 | 31.4 | 18 | 38/13 |  | 4x2/8 | 4U-1 |  |  |  | RBS | XC50154 | [8 empty] | 1 | TM154 | LUGOJ-BORDER | 255 | 0.3 | 47.5 | 70 | 38/17 | [6 empty] | 8* | SVF | 2000-12-15 | 482 | 2000-12-18 | 2001-01-30 | 2001-02-15 | VLAD | OK | 2001-03-14 | PENDING ITEMS | 2001-07-12 |  | 30N01 Lugoj-Timisoara |  | 2001-02-26 | Cristian CROITOR | CATALINA CIOCAN | [32 empty] | 119 | Lugoj | Timis | [7 empty] | 2 |  |  | 2
Phase_2 | CS | TM074 | LIBERTATII_RTC | Resita(3) | TM076 Cuza | Banat | 45 17 26 | 21 53 39 | 45 17 26 | 21 53 39 | Bd. Libertatii | Romtelecom/ | 2202 | M | C+C+ | 2/2 | 2202 | [6 empty] | 2000-07-26 | N/A | N/A |  |  |  | 15.5 | B | 15.5 | T4m | Room | DIEKAT | OK | VECTOR | 2000-06-14 | 2000-06-29 | YesV | 2000-06-30 | Mugur | 2000-07-03 | 2000-07-11 |  |  |  | N/A | 2000-05-12 |  | 2000-05-26 | 2000-06-22 |  |  |  | 2000-07-07 | YRO | MOB | 2000-07-06 | 2000-07-06 | 2000-07-07 | 2000-07-11 | 2000-07-23 |  | Yes | Constantin Mihai | 2000-08-30 | 2000-08-29 | 2000-08-29 | 2000-09-21 | 2000-10-04 | K 739 494 | 60 | 0 | 18 | K 739 494 | 240 | 0 | 18 | N/A | N/A | N/A | N/A |  |  |  |  | N/A | 21 | 21 | 7/8" | 21 | 21 | 7/8" | N/A | N/A | N/A |  |  |  | 84 | N/A | Timisoara | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | [5 empty] | N/A | [6 empty] | 110/8p indoor |  |  | TM076 | A.I. CUZA |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | 30N02 Resita-Timisoara | Se muta capatul Fluxului din BSC031 in TM075 | OK | Cristian CROITOR | Cosmorom | [32 empty] | 233 | Resita | Caras Severin | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | TM075 | RESITA_RTC | Resita(3) | TM075 Resita_RTC | Banat | 45 19 32 | 21 52 32 | 45 19 32 | 21 52 32 | Romtelecom Resita - Bd. Republicii nr.17 | Romtelecom/ | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-07-06 | N/A | N/A |  |  |  | 27 | B | 27 | T4.5m+T4.5m | Room | DIEKAT | OK | VECTOR | 2000-06-15 | 2000-07-03 | YesV | 2000-07-10 | Mugur | 2000-07-03 | 2000-07-21 |  |  |  | N/A | 2000-05-12 |  | 2000-05-26 | 2000-06-22 |  |  |  | 2000-07-07 | YRO | MOB | 2000-07-05 | 2000-07-05 | 2000-07-07 | 2000-07-11 | 2000-07-23 |  | Yes | Constantin Mihai | 2000-08-30 | 2000-08-29 | 2000-08-29 | 2000-09-18 | 2000-09-21 | K 739 494 | 0 | 0 | 30 | K 739 494 | 140 | 0 | 30 | K 739 494 | 260 | 0 | 30 |  |  |  |  | N/A | 20 | 20 | 7/8" | 20 | 20 | 7/8" | 20 | 20 | 7/8" |  |  |  | 120 | N/A | Timisoara | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | [5 empty] | N/A | [6 empty] | 160/8p indoor |  |  | BSC31 | BSC TIMISOARA | N/A | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | 30N01 Resita-Timisoara |  | OK | Cristian CROITOR | Cosmorom | [32 empty] | 239 | Resita | Caras Severin | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | TM076 | AL. I. CUZA | Resita(3) | TM076 Cuza | Banat | 45 17 34 | 21 52 57 | 45 17 33.9 | 21 52 56.9 | Str. Alex. Ioan Cuza nr.4 Bl.4, Resita | Asociatie de locatari/Rosculescu Gheorghe - Str. Alex. Ioan Cuza nr.4 Bl.4 Et.1 Ap.1, tel: 055/ 211 751 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-08-09 | Yes | N/A |  |  |  | 27.4 | B | 30.4 | T4.5m+T4.5m | N/A | DIEKAT | OK | VECTOR | 2000-07-06 | 2000-07-21 | YesV | 2000-07-25 | Mugur | 2000-08-04 | 2000-08-03 |  |  |  | 2000-05-23 | 2000-05-12 |  | 2000-06-06 | 2000-07-03 |  |  |  | 2000-08-07 | YRO | MOB | 2000-08-07 | 2000-08-03 | 2000-08-08 | 2000-08-09 | 2000-08-14 |  | Yes | Theo Radoi | 2000-10-12 | 2000-10-11 | 2000-10-11 | 2000-10-25 | 2000-11-09 | K 739 494 | 35 | 0 | 32 | K 739 494 | 140 | #N/A | 32 | K 739 494 | 260 | 0 | 32 |  |  |  |  | N/A | 30 | 30 | 7/8" | 30 | 30 | 7/8" | 30 | 30 | 7/8" |  |  |  | 180 | N/A | Timisoara | HDSL | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | RBS | N/A | [9 empty] | BSC31 | BSC TIMISOARA |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | NDSL+30N02 Resita-Timisoara | Se muta capatul Fluxului din BSC031 in TM075 | 2000-12-29 | Cristian CROITOR | #N/A | [32 empty] | 242 | Resita | Caras Severin | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | TM078 | CARANSEBES_RTC | Caransebes(1) | TM078 Caransebes_RTC | Oltenia | 45 24 46 | 22 13 06 | 45 24 46 | 22 13 06 | Romtelecom Caransebes, jud Caras Severin |  | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-06-21 | N/A | N/A |  |  |  | 13.95 | B | 14 | Pylonet 12m | Room | SVF | OK | VECTOR | 2000-06-20 | 2000-07-03 | YesV | 2000-07-10 | Mugur | 2000-07-03 | 2000-07-21 |  |  |  | N/A | 2000-05-20 |  | 2000-05-25 | 2000-06-23 |  |  |  | 2000-07-07 | YRO | MOB | 2000-07-05 | 2000-07-05 | 2000-07-07 | 2000-07-11 | 2000-07-16 |  | Yes | Constantin Mihai | 2000-08-30 | 2000-08-30 | 2000-08-30 | 2000-09-18 | 2000-09-21 | K 739 494 | 30 | 0 | 25 | K 739 494 | 150 | 0 | 25 | K 739 494 | 270 | 0 | 25 |  |  |  |  | N/A | 30 | 30 | 7/8" | 30 | 30 | 7/8" | 30 | 30 | 7/8" |  |  |  | 180 | N/A | Timisoara | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | 4U-1 |  |  |  | Indoor Comteck | 50078 | [6 empty] | 36.5/ |  | 1 | BSC31 | BSC TIMISOARA | N/A | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | 30N01 Caransebes-Resita | Se va muta de pe fluxul cu TM075 | OK | Cristian CROITOR | CATALINA CIOCAN | [32 empty] | 231 | Caransebes | Caras Severin | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | TM081 | ORADEA_1 | Oradea(9) | TM082 Oradea_2_RTC | Banat | 47 03 27 | 21 55 33 | 47 03 28.1 | 21 55 34.8 | Str. Tudor Vladimirescu nr.1 | Asociatie de locatari/Radulescu Lucian - 059/ 435 552 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-07-18 | 2000-07-24 | N/A |  |  |  | 19 | B | 41 | T4.5m+T4.5m+T4.5m | N/A | PROTELCO | OK | EL-MONT | 2000-06-20 | 2000-07-03 | YesV | 2000-07-11 | Doru | 2000-07-06 | 2000-07-26 |  |  |  | OK | 2000-05-15 |  | 2000-06-07 | 2000-06-27 |  |  |  | 2000-07-24 | YRO | Interactive | 2000-07-12 | 2000-07-13 | 2000-07-25 | 2000-06-27 | 2000-07-01 |  | Yes | Ionut Grigorescu | 2000-08-23 | 2000-08-24 | 2000-08-24 | 2000-09-12 | 2000-09-21 | K 739 494 | 100 | 0 | 44 | K 739 494 | 220 | 0 | 44 | K 739 494 | 340 | 0 | 44 |  |  |  |  | N/A | 9 | 9 | 7/8" | 15 | 15 | 7/8" | 15 | 15 | 7/8" |  |  |  | 78 | ML 23 E 1+0 | Oradea | MW | 128 | 0.6 | 43.5 | 7.5 | 23/58 |  | 4x2/8 | 4U-1 |  |  |  | RBS | [9 empty] | 1 | TM083 | ORADEA_3 | 306 | 0.6 | 36.3 | 20 | 23/56 | [6 empty] | 2 | INTERACTIVE | 2000-07-24 | 71 | 2000-07-21 | 2000-06-27 | 2000-07-01 | PITURCESCU | OK | 2000-08-23 |  | 2000-09-12 | 2000-09-25 |  |  | OK | George IFRIM | Cosmorom | [32 empty] | 120 | Oradea | Bihor | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | TM082 | ORADEA_2 | Oradea(9) | TM082 Oradea_2_RTC | Banat | 47 02 28 | 21 56 34 | 47 02 28.4 | 21 56 34.5 | Str. Dimitrie Cantemir nr.1 | Romtelecom Bihor, Str. Roman Ciorogariu nr.12tel: 059/404110/Marcusiu dan - Str. Dimitrie cantemir nr.2, tel: 059/ 121 500 | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-07-18 | N/A | N/A |  |  |  | 19 | B | 19 | New pylon 15m | Room | PROTELCO | OK | EL-MONT | 2000-06-20 | 2000-07-09 | YesV | 2000-07-11 | Doru | 2000-07-13 | 2000-09-04 |  |  |  | N/A | 2000-05-15 |  | 2000-05-26 | 2000-06-27 |  |  |  | 2000-07-24 | YRO | Interactive | 2000-07-18 | 2000-07-18 | 2000-07-25 | 2000-07-27 | 2000-07-29 |  | Yes | Ionut Grigorescu | 2000-08-23 | 2000-08-23 | 2000-08-23 | 2000-09-12 | 2000-09-21 | K 739 494 | 100 | 0 | 32 | K 739 494 | 220 | 0 | 32 | K 739 494 | 340 | 0 | 32 |  |  |  |  | N/A | 36 | 36 | 7/8" | 36 | 36 | 7/8" | 36 | 36 | 7/8" |  |  |  | 216 | N/A | Oradea | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | 4U-1(TMR9202) |  |  |  | TMR 9202 | [7 empty] | 35/Indoor |  | 1 | BSC32 | BSC ORADEA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PITURCESCU | OK | N/A |  | N/A | N/A |  |  | OK | George IFRIM | Cosmorom | [32 empty] | 127 | Oradea | Bihor | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | TM083 | ORADEA_3 | Oradea(9) | TM082 Oradea_2_RTC | Banat | 47 03 04 | 21 56 20 | 47 02 56.8 | 21 56 21.7 | Aleea D. Dimitrie Cantemir nr.2 Bl.A1 | Asociatie de proprietari/Vrabiuta Gheorghe - 059/411 986 | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-07-18 | N/A | N/A |  |  |  | 35.3 | B | 35.3 | C3m+C3m+C3m | Room | PROTELCO | OK | EL-MONT | 2000-06-20 | 2000-07-03 | YesV | 2000-07-11 | Doru | 2000-07-06 | 2000-07-26 |  |  |  | OK | 2000-05-15 |  | 2000-06-07 | 2000-06-22 |  |  |  | 2000-07-24 | YRO | Interactive | 2000-07-12 | 2000-07-12 | 2000-07-25 | 2000-07-27 | 2000-07-31 |  | Yes | Ionut Grigorescu | 2000-08-23 | 2000-08-23 | 2000-08-23 | 2000-09-12 | 2000-09-21 | K 739 494 | 100 | 0 | 36.5 | K 739 494 | 220 | 0 | 36.5 | K 739 494 | 340 | 0 | 36.5 |  |  |  |  | N/A | 8 | 8 | 7/8" | 13 | 13 | 7/8" | 21 | 21 | 7/8" |  |  |  | 84 | ML 23 E 1+1 | Oradea | MW | 165 | 0.6 | 36.3 | 12 | 23/56 | YES | 4x2/8 | 4U-1 | 4U-1 |  |  | Indoor Comteck | [9 empty] | 1 | TM082 | ORADEA_2 | 345 | 0.6 | 31.5 | 35 | 23/58 | [6 empty] | 2/7 | INTERACTIVE/SVF | 7/24/00/12/14/00 | 70/440 | 7/21/00/1/29/01 | 2000-06-27 | 2000-07-31 | PITURCESCU | OK | 2000-08-24 | Sunt livrate 2 4U-1 si doar 1 este facturata. | 2000-09-12 | 2000-09-25 |  |  | OK | George IFRIM | Cosmorom | [32 empty] | 122 | Oradea | Bihor | [5 empty] | 1 | 1 | 2 | 1 | 1 | 2
Phase_2 | CS | TM084 | ORADEA_5 | Oradea(9) | TM082 Oradea_2_RTC | Banat | 47 04 02 | 21 55 35 | 47 04 02 | 21 55 46 | Bd. Dacia nr.2 Bl.A2 nr.4 | Asociatie de proprietari nr.135/Boros Gheorghe - 059/ 164 631 | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-07-18 | N/A | N/A |  |  |  | 33 | B | 33 | C3m+C3m+C3m | Room | PROTELCO | OK | EL-MONT | 2000-06-20 | 2000-07-07 | YesV | 2000-07-11 | Doru | 2000-07-13 | 2000-07-26 |  |  |  | OK | 2000-05-15 |  | 2000-06-08 | 2000-07-06 |  |  |  | 2000-07-24 | YRO | Interactive | 2000-07-18 | 2000-07-18 | 2000-07-25 | 2000-07-27 | 2000-07-31 |  | Yes | Ionut Grigorescu | 2000-08-24 | 2000-08-24 | 2000-08-24 | 2000-09-12 | 2000-09-21 | K 739 494 | 100 | 0 | 37.2 | K 739 494 | 220 | 0 | 37.2 | K 739 494 | 340 | 0 | 37.2 |  |  |  |  | N/A | 21 | 21 | 7/8" | 16 | 16 | 7/8" | 10 | 10 | 7/8" |  |  |  | 94 | ML 23 E 1+0 | Oradea | MW | 192 | 0.6 | 36.7 | 20 | 23/56 |  | 4x2/8 | 2U-3 |  |  |  | N/A | [10 empty] | TM081 | ORADEA_1 | 12 | 0.6 | 43.5 | 14 | 23/58 | [6 empty] | 2 | INTERACTIVE | 2001-07-24 | 72 | 2000-07-21 | 2000-06-27 | 2000-07-31 | PITURCESCU | OK | 2000-08-24 |  | 2000-09-12 | 2000-09-25 |  |  | OK | George IFRIM | Cosmorom | [32 empty] | 122 | Oradea | Bihor | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | TM085 | ORADEA_7 | Oradea(9) | TM082 Oradea_2_RTC | Banat | 47 04 44 | 21 55 05 | 47 04 45.9 | 21 55 07.5 | Str. Transilvaniei nr.22 Bl.K2 Sc.B | Asociatie de proprietari bloc Transilvaniei 12/Veres Emil - Et.2 Ap.47, 059/ 144 159 | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-07-18 | N/A | N/A |  |  |  | 29 | B | 29 | C3m+C3m+C3m | Room | PROTELCO | OK | EL-MONT | 2000-06-20 | 2000-06-30 | YesV | 2000-07-01 | Doru | 2000-07-03 | 2000-07-04 |  |  |  | OK | 2000-05-15 |  | 2000-06-08 | 2000-06-22 |  |  |  | 2000-07-24 | YRO | Interactive | 2000-07-12 | 2000-07-12 | 2000-07-25 | 2000-07-27 | 2000-07-31 |  | Yes | Ionut Grigorescu | 2000-08-24 | 2000-08-24 | 2000-08-24 | 2000-09-12 | 2000-09-21 | K 739 494 | 100 | 0 | 33.7 | K 739 494 | 220 | 0 | 33.7 | K 739 494 | 340 | 0 | 33.7 |  |  |  |  | N/A | 8 | 8 | 7/8" | 15 | 15 | 7/8" | 20 | 20 | 7/8" |  |  |  | 0 | ML 23 E 1+0 | Oradea | MW | 149 | 0.6 | 33.2 | 8 | 23/58 |  | 4x2/8 | 2U-3 |  |  |  | N/A | [10 empty] | TM084 | ORADEA_5 | 329 | 0.6 | 36.7 | 9 | 23/56 | [6 empty] | 2 | INTERACTIVE | 2001-07-24 | 73 | 2000-07-21 | 2000-06-27 | 2000-07-31 | PITURCESCU | OK | 2000-08-24 |  | 2000-09-12 | 2000-09-25 |  |  | OK | George IFRIM | Cosmorom | [32 empty] | 123 | Oradea | Bihor | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | TM086 | ORADEA_8 | Oradea(9) | TM082 Oradea_2_RTC | Banat | 47 01 58 | 21 57 01 | 47 01 48.8 | 21 57 18.6 | Str. Nufarului nr.78 Bl.AN 78 | Asociatia de locatari nr.430/Lincar Ioan - Str. Nufarului nr.78 Bl.AN78 | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-08-16 | N/A | N/A |  |  |  | 30 | B | 35 | C3m+C3m | Room | PROTELCO | OK | EL-MONT | 2000-08-10 | 2000-08-25 | YesV | 2000-09-01 | Doru | 2000-08-16 | 2000-09-04 |  |  |  |  | 2000-05-15 |  | 2000-07-21 | 2000-08-02 |  |  |  | 2000-08-16 | YRO | Interactive | 2000-08-16 | 2000-08-16 | 2000-08-18 | 2000-08-18 | 2000-08-20 |  | Yes | Ionut Grigorescu | 2000-08-29 | 2000-08-29 | 2000-08-29 | 2000-09-12 | 2000-09-21 | K 739 494 | 20 | 0 | 32.6 | K 739 494 | 100 | 0 | 32.6 | K 739 494 | 300 | 0 | 32.6 |  |  |  |  | N/A | 11 | 11 | 7/8" | 11 | 11 | 7/8" | 14 | 14 | 7/8" |  |  |  | 72 | ML 23 E 1+0 | Oradea | MW | 322 | 0.6 | 32.3 | 8 | 23/56 |  | 4x2/8 | 2U-3 |  |  |  | N/A | [10 empty] | TM082 | ORADEA_2 | 151 | 0.6 | 31.5 | 35 | 23/58 | [6 empty] | 2 | INTERACTIVE | 2001-07-24 | 123 | 2000-08-16 | 2000-08-18 | 2000-08-20 | PITURCESCU | OK | 2000-08-29 |  | 2000-09-12 | 2000-09-25 |  |  | OK | George IFRIM | Cosmorom | [32 empty] | 138 | Oradea | Bihor | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | TM087 | SALONTA_RTC | Road Arad-Oradea(10) | TM087 Salonta_RTC | Banat | 46 48 07 | 21 39 33 | 46 48 07.2 | 21 39 32.7 | Str. Republicii nr.2A | Romtelecom Bihor - Str. Roman Ciorogariu nr.12, Oradea, 059/ 404 110/Ing. Cotaru Silvia - sef centru, Str. Samuil Vulcan nr.2, tel: 059/ 466 765, 094/ 910 176 | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-08-16 | N/A | N/A |  |  |  | 7 | TE | 35 | Existing 35m tower | Room | PROTELCO | OK | ESROM | 2000-06-24 | 2000-07-07 | YesV | 2000-07-11 | Doru | 2000-07-14 | 2000-07-26 |  |  |  | N/A | 2000-05-10 |  | 2000-06-05 | 2000-06-26 |  |  |  | 2000-08-02 | YRO | Interactive | 2000-07-18 | 2000-07-18 | 2000-08-03 | 2000-08-04 | 2000-08-08 |  | Yes | Alexandru Toma | 2001-01-10 | 2001-01-10 | 2001-01-10 |  |  | K 739 494 | 40 | 0 | 33.5 | K 739 494 | 150 | 0 | 32.5 | K 739 494 | 225 | 0 | 33.5 |  |  |  |  | N/A | 41 | 41 | 7/8" | 41 | 41 | 7/8" | 41 | 41 | 7/8" |  |  |  | 246 | N/A | Oradea | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | 4U-1 |  |  |  | Indoor Comteck | XC50087 | 2001-04-04 | YES |  |  |  |  | 35/Indoor |  | 1 | BSC32 | BSC ORADEA | N/A | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | RADU | OK | N/A |  | N/A | N/A | 30N01 |  | 23.11.2000 | Bogdan CRAIU | Cosmorom | [32 empty] | 94 | Salonta | Bihor | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | TM088 | BAILE FELIX | Oradea(9) | TM082 Oradea_2_RTC | Banat | 46 59 27 | 21 58 45 | 46 59 31.4 | 21 58 53.6 | Hotel Somes | Romtelecom - Hotel Somes/Tor Gavril, 094/ 520 939 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-07-18 | 2000-07-24 | N/A |  |  |  | 49 | B | 49 | C2m+C2m+C2m | N/A | PROTELCO | OK | EL-MONT | 2000-06-20 | 2000-06-28 | YesV | 2000-06-30 | Doru | 2000-07-03 | 2000-08-21 |  |  |  | 2000-06-01 | 2000-05-15 |  | 2000-06-05 | 2000-06-14 |  |  |  | 2000-07-24 | YRO | Interactive | 2000-07-12 | 2000-07-12 | 2000-07-25 | 2000-07-27 | 2000-07-31 |  | Yes | Alexandru Bucur | 2000-09-10 | 2000-09-11 | 2000-09-11 | 2000-09-21 | 2000-09-26 | K 739 494 | 165 | 0 | 50.5 | K 739 494 | 255 | 0 | 50.5 | K 739 494 | 345 | 0 | 50.5 |  |  |  |  | N/A | 9 | 9 | 7/8" | 15 | 15 | 7/8" | 15 | 15 | 7/8" |  |  |  | 78 | ML 23 E 1+0 | Oradea | MW | 331.62 | 0.6 | 50.5 | 14 | 23/58 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [10 empty] | TM086 | ORADEA_8 | 155 | 0.6 | 32.3 | 12 | 23/56 | [6 empty] | 4 | INTERACTIVE | 2000-08-16 | 68 | 2000-07-21 | 2000-07-27 | 2000-07-31 | PITURCESCU | OK | 2000-08-29 |  | 2000-09-12 | 2000-09-25 |  |  | OK | George IFRIM | Petrica BURGHIU | [32 empty] | 182 | Baile Felix | Oradea | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | TM089 | MARGHITA_RTC | Road Oradea-Satu Mare(16+3) | YM096 Valea lui Mihai | Banat | 47 20 49 | 22 20 21 | 47 20 49 | 22 20 21.4 | Str. Eroilor nr.4 | Romtelecom/Dl. Bit | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-07-25 | N/A | N/A |  |  |  | 6 | TE | 35 | 35m existed tower | Room | PROTELCO | OK | ESROM | 2000-06-23 | 2000-07-19 | YesV | 2000-07-27 | Doru | 2000-07-19 | 2000-08-03 |  |  |  | N/A | 2000-05-12 |  | 2000-06-01 | 2000-06-22 |  |  |  | 2000-08-21 | YRO | Interactive | 2000-07-20 | 2000-08-21 | 2000-08-22 | 2000-08-23 | 2000-08-30 | PAUN | Yes | Ion Soare | 2001-06-15 | 2001-06-15 | 2001-06-15 | 2001-06-19 | 2001-07-11 | K 739 494 | 40 | 0 | 33.5 | K 739 494 | 135 | 0 | 33.5 | K 739 494 | 270 | 0 | 33.5 |  |  |  |  | N/A | 70 | 70 | 1 1/4" | 70 | 70 | 1 1/4" | 70 | 70 | 1.25 | N/A | N/A | N/A | 510 | ML 15 E 1+0 | Oradea | MW | 257 | 0.6 | 33/1.2 | 70 | 15/84 |  | 4X2/8 | 4U-1(TMR9202) |  |  |  | TMR 9202 | [7 empty] | /2 perechi |  | 1 | TM206 | CUBULCUT_RTC | 77 | 0.6 | 33 | 40 | 15/89 | [6 empty] | 71 | VECTOR | 2001-05-24 | 953 | 2001-05-28 | 2001-05-28 | 2001-06-11 |  |  |  |  | 2001-07-12 |  | 30N01 |  | 2001-03-07 | George IFRIM | Cosmorom | [32 empty] | 140 | Marghita | Bihor | [7 empty] | 2 |  |  | 2
Phase_2 | CS | TM090 | BEIUS_RTC | Road Oradea-Brad(11+1) | TM090 Beius_RTC | Transilvania | 46 40 00 | 22 20 57 | 46 40 01.5 | 22 20 58.1 | Piata Samuil Vulcan nr.2 | Romtelecom - Str. Roman Ciorogariu nr.12059/ 404 110/Pantis Gheorghe - Piata samuil Vulcan nr.2, tel: 059/ 321 777 (092/ 468 684) | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-07-25 | 2000-08-02 | N/A |  |  |  | 0 | TE | 36 | Existing 36m tower | N/A | PROTELCO | OK | ESROM | 2000-06-24 | 2000-07-19 | YesV | 2000-07-27 | Doru | 2000-07-19 | 2000-08-03 |  |  |  | N/A | 2000-05-14 |  | 2000-06-05 | 2000-06-27 |  |  |  | 2000-08-02 | YRO | Interactive | 2000-07-20 | 2000-07-20 | 2000-08-03 | 2000-08-04 | 2000-08-07 |  | Yes | Alexandru Bucur | 2001-01-09 | 2001-01-09 | 2001-01-09 | 2001-04-17 | 2001-05-03 | K 739 494 | 45 | 0 | 34.5 | K 739 494 | 135 | 0 | 34.5 | K 739 494 | 300 | 0 | 34.5 |  |  |  |  | N/A | 41 | 41 | 7/8" | 41 | 41 | 7/8" | 41 | 41 | 7/8" |  |  |  | 246 | N/A | Oradea | FO | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | RBS | 50090 | [6 empty] | 62/Indoor |  |  | BSC32 | BSC ORADEA | N/A | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PITURCESCU | OK | N/A |  | N/A | N/A | 30N01 Beius-Oradea |  | 2000-12-29 | George IFRIM | Petrica BURGHIU | [32 empty] | 192 | Beius | Bihor | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | TM091 | ALESD_RTC | Road Oradea-Cluj(13) | TM091 Alesd_RTC | Transilvania | 47 03 34 | 22 23 53 | 47 03 34.7 | 22 23 53.5 | Str. Bobilna nr.4Bis - Terasa bloc tehnic | Romtelecom Bihor - Str. Roman Ciorogariu nr.12, 059/ 404 110/Ing. Dejeu Nela - sef centru, 059/ 341 450, 094/156 034, Str. Bobalna nr.4 Bis, Alesd | MAXITE | M | 1 | 2 | 2PBC | [6 empty] | 2000-07-25 | N/A | N/A |  |  |  | 5 | B | 10 | Pilon 15m | Room | PROTELCO | OK | ESROM | 2000-06-25 | 2000-07-19 | YesV | 2000-07-27 | Doru | 2000-07-19 | 2000-08-03 |  |  |  | N/A | 2000-08-18 |  | 2000-06-05 | 2000-06-26 |  |  |  | 2000-08-02 | YRO | Interactive | 2000-07-21 | 2000-07-21 | 2000-08-03 | 2000-08-04 | 2000-08-08 |  | Yes | Alexandru Toma | 2001-01-09 | 2001-01-09 | 2001-01-09 |  |  | AAU | 100 | 0 | 23 | AAU | 280 | #N/A | 23 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 42 | 42 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 84 | N/A | Oradea | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A |  |  |  | N/A | [7 empty] | 22/ |  |  | BSC32 | BSC ORADEA | N/A | N/A | N/A | N/A | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PITURCESCU | OK | N/A |  | N/A | N/A |  |  | 2000-11-23 | George IFRIM | #N/A | [32 empty] | 230 | Alesd | Bihor | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | TM092 | STEI_RTC | Road Oradea-Brad(11+1) | TM092 Stei_RTC | Transilvania | 46 32 03 | 22 27 27 | 46 32 03 | 22 27 26.1 | Str. George Enescu nr.3 | Romtelecom Bihor - Str. Roman Ciorogariu nr.12, tel: 059/ 404 110/Mladin Vasile - Str. George Enescu nr.3, tel: 059/ 330 300 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-07-25 | N/A | N/A |  |  |  | 0 | TE | 35 | Existing 35m tower | N/A | PROTELCO | OK | ESROM | 2000-06-23 | 2000-07-19 | YesV | 2000-07-27 | Doru | 2000-07-19 | 2000-08-03 |  |  |  | N/A | 2000-05-14 |  | 2000-06-01 | 2000-06-26 |  |  |  | 2000-08-02 | YRO | Interactive | 2000-07-20 | 2000-07-20 | 2000-08-03 | 2000-08-04 | 2000-08-08 |  | Yes | Alexandru Toma | 2001-01-10 | 2001-01-10 | 2001-01-10 | 2001-04-17 | 2001-05-03 | K 739 494 | 150 | 0 | 33.5 | K 739 494 | 350 | 0 | 33.5 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 41 | 41 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 82 | N/A | Oradea | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | 4U-1 |  |  |  | RBS | 500092 | 2001-05-17 | [5 empty] | 30/ |  |  | BSC32 | BSC ORADEA | N/A | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PITURCESCU | OK | N/A |  | N/A | N/A | 30N01 |  | 2000-12-27 | George IFRIM | Cosmorom | [32 empty] | 253 | Stei | Bihor | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | TM093 | BORS | Oradea(9) | TM082 Oradea_2_RTC | Banat | 47 06 44 | 21 58 45 | 47 06 54 | 21 48 15 | DN1 E60 | Primaria comunei Bors, tel: 059/ 316 155; fax: 059/ 417 291/Dl. Primar Batori Geza, 094/ 772 686 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-08-02 | N/A | N/A |  |  |  |  | TN | 40 | New 40m tower | N/A | PROTELCO | OK | EL-MONT | 2000-06-22 | 2000-07-21 | YesV | 2000-07-26 | Doru | OK-DORU | 2000-08-03 |  |  |  | 2000-06-01 | 2000-05-15 |  | 2000-06-05 | 2000-06-20 |  |  |  | 2000-07-24 | YRO | Interactive | 2000-07-20 | 2000-07-20 | 2000-07-25 | 2000-07-27 | 2000-07-29 |  | Yes | Ionut Grigorescu | 2000-08-25 | 2000-08-25 | 2000-08-25 | 2000-09-12 | 2000-09-21 | K 739 494 | 130 | 0 | 38 | K 739 494 | 310 | 0 | 38 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 51 | 51 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 102 | ML 15 E 1+0 | Oradea | MW | 114 | 1.2 | 37.5 | 50 | 15/84 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [10 empty] | TM085 | ORADEA_7 | 294 | 1.2 | 33.5 | 20 | 15/89 | [6 empty] | 2 | INTERACTIVE | 2001-07-24 | 74 | 2000-07-27 | 2000-07-27 | 2000-07-29 | PITURCESCU | OK | 2000-08-25 |  | 2000-09-12 | 2000-09-25 |  |  | OK | George IFRIM | Petrica BURGHIU | [32 empty] | 103 | Bors | Bihor | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | TM | TM094 | ARAD_RTC4 | Arad(9+1) | TM094 Arad_RTC4 | Banat | 46 11 48 | 21 18 10 | 46 11 48 | 21 18 10 | Romtelecom Arad |  | N/A | N/A | N/A | N/A | N/A | [7 empty] | N/A | N/A | [21 empty] | N/A | OK |  | OK | OK |  |  |  | NA | YRO | YRO | N/A | N/A | 2000-07-08 | N/A | N/A |  |  | N/A | 2000-09-10 | 2000-09-10 | 2000-09-10 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | #N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A | Timisoara | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | [15 empty] | BSC31 | BSC TIMISOARA | N/A | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | 30N03 Arad RTC4-Dr.Taberei |  | OK | George IFRIM | #N/A | [32 empty] | 108 | Arad | Arad | [7 empty] | Site Near=Insertion Point
Phase_2 | TM | TM095 | RESITA_RTC3 | Timisoara(14+1) | TM095 Resita_RTC3 | Banat | 45 44 25 | 21 12 25 | 45 44 25 | 21 12 25 | Romtelecom Timisoara |  | N/A | N/A | N/A | N/A | N/A | [7 empty] | N/A | N/A | [21 empty] | N/A | 2000-10-14 |  | OK | OK |  |  |  | NA | YRO | YRO | N/A | N/A | 2000-07-31 | N/A | N/A |  |  | N/A | 2000-09-10 | 2000-09-10 | 2000-09-10 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A | Timisoara | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | [15 empty] | BSC31 | BSC TIMISOARA | N/A | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A |  | OK | George IFRIM | Cosmorom | [32 empty] | 84 | [9 empty] | Site Near=Insertion Point
Phase_2 | CS | TM096 | VALEA LUI MIHAI | Road Oradea-Satu Mare(16+3) | YM096 Valea lui Mihai | Banat | 47 30 44 | 22 07 57 | 47 30 34.4 | 22 09 16.3 | Valea lui Mihai | Faff Maria - str. Izvorului, nr.20, 059/ 355 250/Faff Maria - str. Izvorului, nr.20, 059/ 355 250 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | N/A |  |  |  |  | 0 | TN | 50 |  | N/A | PROTELCO | OK | SVF | 2001-02-02 | 2001-03-07 | YesV | 2001-03-23 | Doru | 2001-04-06 | 2001-03-29 |  |  |  |  | 2000-07-05 |  | 2000-12-15 | 2001-01-16 |  |  |  | 2001-03-13 | ICOM | SVF | 2001-03-13 | 2001-03-13 | 2001-03-14 | 2001-03-19 | 2001-03-23 |  | Yes | Theo Radoi | 2001-04-11 | 2001-04-11 | 2001-04-11 |  |  | K 739 494 | 55 | 0 | 48.5 | K 739 494 | 165 | 0 | 48.5 | K 739 494 | 275 | 0 | 48.5 |  |  |  |  | N/A | 59 | 59 | 1 1/4" | 59 | 59 | 1 1/4" | 59 | 59 | 1 1/4" | N/A | N/A | N/A | 354 | ML 38 E 1+1 | Oradea | MW | 112 | 0.3 | 47/0.3 | 53 | 38/14 | YES | 4X2/8 | 4U-1 |  |  |  | RBS | [9 empty] | 1 | YM096 | VALEA LUI MIHAI_RTC | 292 | 0.3 |  |  | 38/18 | [6 empty] | 41* | SVF | 2001-03-13 | 712 | 2001-03-14 | 2001-03-14 | 2001-03-23 | VLAD | OK | 2001-04-11 |  | 2001-05-21 | 2001-05-25 | 30N01 |  | 2001-03-07 | Petrica BURGHIU | Cosmorom | [32 empty] | 130 | Valea lui Mihai | Bihor | [5 empty] | 1 | 1 | 2 | 1 | 1 | 2
Phase_2 | CS | TM097 | ROSIORI | Road Oradea-Satu Mare(16+3) | YM096 Valea lui Mihai | Banat | 47 15 42 | 21 57 11 | 47 15 43.8 | 21 57 17.2 | Rosiori, com. Diosig | SC Eco Kapa SA - 059/ 434 791/Vasile Marian - 092/ 460 879 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-09-19 | N/A | N/A |  |  |  |  | TN | 50 | Tower | N/A | PROTELCO | OK | SVF | 2000-08-01 | 2000-08-31 | YesV | 2000-08-31 | Doru | 2000-08-30 | 2000-09-04 |  |  |  | 2000-07-19 | 2000-07-05 |  | 2000-07-28 | 2000-08-21 |  |  |  | 2000-09-05 | YRO | Interactive | 2000-08-30 | 2000-08-30 | 2000-09-05 | 2000-09-06 | 2000-09-08 |  | Yes | Theo Radoi | 2001-04-12 | 2001-04-12 | 2001-04-12 | 2001-06-19 | 2001-07-11 | K 739 494 | 50 | 0 | 48 | K 739 494 | 200 | 0 | 48 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 130 | ML 23 E 1+0 | Oradea | MW | 56 | 0.6 | 47.5 | 65 | 23/56 |  | 4X2/8 | 2U-3 |  |  |  | RBS | [9 empty] | 1 | TM098 | DIOSIG | 236 | 0.6 | 47.5 | 65 | 23/58 | [6 empty] | 6 | INTERACTIVE | 2000-09-05 | 170 | 2000-09-06 | 2000-09-06 | 2000-09-08 | DINCA | OK | 2001-04-12 |  | 2001-05-03 | 2001-05-11 | 30N02 |  | 2001-03-07 | George IFRIM | Cosmorom | [32 empty] | 110 | Rosiori | Bihor | [7 empty] | 2 |  |  | 2
Phase_2 | CS | TM098 | DIOSIG | Road Oradea-Satu Mare(16+3) | YM096 Valea lui Mihai | Banat | 47 17 44 | 22 01 48 | 47 17 44.1 | 22 01 51 | Com. Diosig, Dealul Mic | Teleki Gheza - Com. Diosig, Str. Livezilor nr.58/Teleki Gheza - Com. Diosig, Str. Livezilor nr.58, 059/ 350 574 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-09-19 | N/A | N/A |  |  |  |  | TN | 50 | Tower | N/A | PROTELCO | OK | SVF | 2000-08-01 | 2000-08-31 | YesV | 2000-08-31 | Doru | 2000-08-30 | 2000-09-04 |  |  |  | 2000-07-20 | 2000-07-05 |  | 2000-07-28 | 2000-08-21 |  |  |  | 2000-09-05 | YRO | Interactive | 2000-08-30 | 2000-08-30 | 2000-09-05 | 2000-09-06 | 2000-09-08 |  | Yes | Theo Radoi | 2001-04-12 | 2001-04-12 | 2001-04-12 |  |  | K 739 494 | 45 | 0 | 48 | K 739 494 | 236 | 0 | 48 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 65 | 65 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 130 | ML 23 E 1+0 | Oradea | MW | 43 | 1.2 | 47.5/0.6 | 65 | 23/58 |  | 4X2/8 | 2U-3 |  |  |  | RBS | [9 empty] | 1 | TM109 | SACUIENI | 225 | 1.2 | 41.5/1.2 | 50 | 23/56 | [6 empty] | 47* | SVF | 2001-03-26 | 755 | 2001-03-06 | 2001-03-06 | 2001-03-27 | DINCA | OK | 2001-04-11 |  | 2001-05-03 | 2001-05-11 | 30N02 |  | 2001-03-07 | George IFRIM | Cosmorom | [32 empty] | 161 | Diosig | Bihor | [7 empty] | 2 |  |  | 2
Phase_2 | CS | TM099 | CHISINEU CRIS_RTC | Road Arad-Oradea(10) | TM099 Chisineu Cris_RTC | Banat | 46 31 19 | 21 30 59 | 46 31 20.1 | 21 30 58.9 | Str. Infratirii nr.60 | DTC Arad - Str. 30 Decembrie nr.1, 057/ 204 610/Czeczi Iosif - 057/ 520 040, 057/ 523 006 | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-10-13 | N/A | N/A |  |  |  | 5 | B | 15.25 | 18m new pylonet | Room | PROTELCO | OK | ISAF | 2000-09-15 | 2000-10-10 | YesV | 2000-10-19 | Doru | 2000-11-15 | 2000-10-24 |  |  |  | N/A | 2000-07-19 |  | 2000-07-28 | 2000-09-19 |  |  |  | 2000-10-20 | ICOM | MOB | 2000-10-12 | 2000-10-12 | 2000-10-23 | 2000-10-29 | 2000-10-31 |  | Yes | Alexandru Bucur | 2001-03-06 | 2001-03-06 | 2001-03-06 | 2001-04-17 | 2001-04-23 | K 739 494 | 0 | 0 | 31 | K 739 494 | 200 | 0 | 31.75 | K 739 494 | 290 | 0 | 31.75 |  |  |  |  | N/A | 35 | 35 | 7/8" | 35 | 35 | 7/8'' | 35 | 35 | 7/8'' |  |  |  | 210 | N/A | Timisoara | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | 4U-1 |  |  |  | Indoor Comteck | 50099 | [6 empty] | 30 2p outdoor/ |  | 1 | BSC31 | BSC TIMISOARA |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | 30N01 Chisineu Cris-Timisoara |  | 2001-03-05 | Bogdan CRAIU | CATALINA CIOCAN | [32 empty] | 94 | Chisineu Cris | Arad | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | TM100 | ZIMANDU NOU | Road Arad-Oradea(10) | TM101 Curtici_RTC | Banat | 46 17 00 | 21 23 34 | 46 17 00.4 | 21 23 35.8 | Com. Zimandu Nou, DN 79 (langa turn RTC- in spatele bisericii Penticostale) | Cons. Local Zimandu Nou - 057/ 217 140; 057/ 217 141, Zimandu Nou nr. 248/Dl. Primar Kovacs Andrei | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-10-20 | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | PROTELCO | OK | ISAF | 2000-10-02 | 2000-11-30 | YesV | 2000-12-08 | Doru | 2001-01-09 | 2000-12-13 |  |  |  | 2000-07-26 | 2000-07-19 |  | 2000-09-13 | 2000-09-27 |  |  |  | 2000-12-14 | ICOM | SVF | 2000-12-14 | 2000-12-14 | 2001-01-04 | 2001-01-10 | 2001-01-13 |  | Yes | Alexandru Bucur | 2001-03-09 | 2001-03-09 | 2001-03-09 |  |  | K 739 494 | 20 | 0 | 48 | K 739 494 | 210 | 0 | 48 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Timisoara | MW | 314 | 0.6 | 35/1.2 | 45 | 15/84 |  | 4x2/8 | 4U-1 |  |  |  | RBS | XC50101 | [8 empty] | 1 | TM101 | CURTICI_RTC | 134 | 0.6 | 26/0.6 | 50 | 15/89 | TM102 | 195 | 1.2 | 47.5 |  | 15/89 | 7* | SVF | 2000-12-14 | 325 | 2000-12-15 | 2001-01-30 | 2001-02-06 | RADU | OK | 2001-03-09 | PENDING ITEMS |  |  | 30N01 Curtici-Timisoara |  | 2001-03-05 | Bogdan CRAIU | [33 empty] | 112 | Zimandu Nou | Arad | [7 empty] | 2 |  |  | 2
Phase_2 | CS | TM101 | CURTICI_RTC | Road Arad-Oradea(10) | TM101 Curtici_RTC | Banat | 46 20 22 | 21 18 30 | 46 20 21.9 | 21 18 32.6 | Str. Revolutiei nr. 4-6 | RTC Arad, B-dul Revolutiei nr.4-6, Dronca Petre tel.057-204.766/Ardelean Florica, Sef Centru, te.057-464.000 | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [6 empty] | 2000-10-20 | N/A | N/A |  |  |  | 3 | B | 10.8 | 18m new pylonet | Room | PROTELCO | OK | ISAF | 2000-09-06 | 2000-10-27 | YesV | 2000-11-17 | Doru | 2000-10-27 | 2000-11-22 |  |  |  | N/A | 2000-07-19 |  | 2000-08-01 | 2000-08-22 |  |  |  | 2000-11-23 | ICOM | MOB | 2000-10-31 | 2000-10-31 | 2000-11-24 | 2000-12-11 | 2000-12-15 |  | Yes | Alexandru Bucur | 2001-03-06 | 2001-03-06 | 2001-03-06 |  |  | K 739 494 | 75 | 0 | 27.3 | K 739 494 | 180 | 0 | 27.3 | K 739 494 | 300 | 0 | 27.3 |  |  |  |  | N/A | 50 | 50 | 1 1/4" | 50 | 50 | 1 1/4" | 50 | 50 | 1 1/4" |  |  |  | 300 | N/A | Timisoara | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | 2U-3 |  |  |  |  | XC50101 | [6 empty] | 30 2 p indoor/ |  | 1 | BSC32 | BSC ORADEA |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | 30N01 Curtici-Timisoara |  | 2001-03-05 | Bogdan CRAIU | Cosmorom | [32 empty] | 112 | Curtici | Arad | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | TM102 | SIMAND | Road Arad-Oradea(10) | TM099 Chisineu Cris_RTC | Banat | 46 25 39 | 21 27 07 | 46 25 31.9 | 21 27 06.7 | Sat Simand, com. Simand | D-na. Per Elena - sat Simand nr.535 - 094/337 112, 094/ 337 112/D-na. Per Elena - sat Simand nr.535 - 094/337 112, 094/ 337 112 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-10-20 | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | PROTELCO | OK | ISAF | 2000-11-15 | 2000-11-30 | YesV | 2000-12-08 | Doru | 2001-01-09 | 2000-12-13 |  |  |  |  | 2000-07-07 |  | 2000-11-13 | 2000-12-21 |  |  |  | 2000-12-14 | ICOM | SVF | 2000-12-14 | 2000-12-14 | 2001-01-04 | 2001-01-11 | 2001-01-14 |  | Yes | Mihai Constantin | 2001-03-21 | 2001-03-21 | 2001-03-21 |  |  | K 739 494 | 30 | 0 | 48 | K 739 494 | 200 | 0 | 48 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Timisoara | MW | 25 | 1.2 | 47.5/1.2 | 59 | 15/89 |  | 4x2/8 | 4U-1 |  |  |  | RBS | [9 empty] | 1 | TM099 | CHISINEU CRIS_RTC | 205 | 1.2 | 30/1.2 | 34 | 15/84 | TM100 | 16 | 1.2 | 47 |  | 15/84 | 7* | SVF | 2000-12-14 | 327 | 2000-12-18 | 2001-01-30 | 2001-02-13 | RADU | OK | 2001-03-21 | PENDING ITEMS |  |  | 30N01 Chisineu Cris-Timisoara |  | 2001-03-05 | Bogdan CRAIU | Cosmorom | [32 empty] | 102 | Simand | Arad | [7 empty] | 2 |  |  | 2
Phase_2 | CS | TM103 | ZERIND | Road Arad-Oradea(10) | TM099 Chisineu Cris_RTC | Banat | 46 31 19 | 21 30 59 | 46 36 45.1 | 21 31 16.3 | Com. Zerind, langa ferma Zerind | Consiliul loca Zerind - str. Principala 2991/Primar Ozsvar Zoltan | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-10-20 | N/A | N/A |  |  |  |  | TN | 40 |  | N/A | PROTELCO | OK | ISAF | 2000-10-02 | 2000-11-17 | YesV | 2000-11-29 | Doru | 2001-01-09 | 2001-02-07 |  |  |  |  | 2000-08-05 |  | 2000-08-21 | 2000-09-07 |  |  |  | 2000-10-25 | ICOM | MOB | 2000-10-25 | 2000-10-25 | 2000-10-25 | 2000-12-06 | 2000-12-07 |  | Yes | Alexandru Bucur | 2001-03-09 | 2001-03-09 | 2001-03-09 |  |  | K 739 494 | 10 | 0 | 38 | K 739 494 | 180 | 0 | 38 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 50 | 50 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 100 | ML 15 E 1+0 | Timisoara | MW | 180 | 0.6 | 37.5/0.6 | 50 | 15/89 |  | 4x2/8 | 4U-1 |  |  |  | RBS | [9 empty] | 1 | TM099 | CHISINEU CRIS_RTC | 2 | 0.6 | 26.4/0.6 | 34 | 15/84 | [6 empty] | 7* | SVF | 2000-12-14 | 328 | 2000-12-18 | 2001-01-30 | 2001-02-13 | RADU | OK | 2001-03-09 | PENDING ITEMS |  |  | 30N01 Chisineu Cris-Timisoara |  | 2001-03-05 | Bogdan CRAIU | [33 empty] | 92 | Zerind | Arad | [7 empty] | 2 |  |  | 2
Phase_2 | CS | TM104 | CIUMEGHIU | Road Arad-Oradea(10) | TM087 Salonta_RTC | Banat | 46 43 49 | 21 34 35 | 46 43 44.9 | 21 34 33.8 | Com. Ciumeghiu DN 79 |  | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-10-20 | N/A | N/A |  |  |  |  | TN | 40 |  | N/A | PROTELCO | OK | ISAF | 2000-10-02 | 2000-11-23 | YesV | 2000-11-29 | Doru | 2001-01-09 | 2001-02-07 |  |  |  | 2000-07-26 | 2000-08-05 |  | 2000-09-11 | 2000-09-27 |  |  |  | 2000-11-23 | ICOM | MOB | 2000-10-25 | 2000-10-25 | 2000-11-24 | 2000-12-01 | 2000-12-05 |  | Yes | Constantin Mihai | 2001-03-27 | 2001-03-28 | 2001-03-28 | 2001-05-15 | 2001-05-28 | K 739 494 | 40 | 0 | 38 | K 739 494 | 220 | 0 | 38 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 50 | 50 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 100 | ML 15 E 1+0 | Oradea | MW | 38 | 0.6 | 37.5/0.6 | 50 | 15/89 |  | 4X2/8 | 2U-3 |  |  |  | RBS | XC50087 | [8 empty] | 1 | TM087 | SALONTA_RTC | 218 | 0.6 | 33/0.6 | 50 | 15/84 | [6 empty] | 13 | MOBILCOM | 2000-11-23 | 403 | 2000-11-24 | 2000-11-25 | 2001-03-27 | AUREL | OK | 2001-03-28 | Nu este trimis la COSMOROM |  |  | 30N01 |  | 23.11.2000 | Bogdan CRAIU | CATALINA CIOCAN | [32 empty] | 93 | Ciumeghiu | Bihor | [7 empty] | 2 |  |  | 2
Phase_2 | CS | TM106 | GEPIU | Road Arad-Oradea(10) | TM082 Oradea_2_RTC | Banat | 45 56 01 | 21 48 07 | 46 56 01.3 | 21 48 06.6 | Com. Cefa, sat Gepiu, fost CAP | Bunta Nicolaie - Oradea, str. Transilvaniei nr.8 Bl.U2 Sc.A Ap.19, 059/ 350 574/Bunta Nicolaie - Centrala Sacadat, casa Mester (se cere Bunta) | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-09-19 | N/A | N/A |  |  |  |  | TN | 50 | Tower | N/A | PROTELCO | OK | SVF | 2000-09-01 | 2000-08-31 | YesV | 2000-08-31 | Doru | 2000-08-30 | 2000-09-04 |  |  |  |  | 2000-07-07 |  | 2000-07-28 | 2000-08-25 |  |  |  | 2000-09-05 | YRO | Interactive | 2000-08-30 | 2000-08-30 | 2000-09-05 | 2000-09-06 | 2000-09-08 |  | Yes | Theo Radoi | 2001-01-25 | 2001-01-25 | 2001-01-25 | 2001-03-27 | 2001-04-10 | K 739 494 | 45 | 0 | 48 | K 739 494 | 215 | 0 | 48 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 65 | 65 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 130 | ML 15 E 1+0 | Oradea | MW | 43 | 0.6 | 47.5/1.2 | 65 | 15/84 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [9 empty] | 1 | TM107 | NOJORID | 222 | 0.6 | 37.5/0.6 | 55 | 15/89 | [6 empty] | 15 | INTERACTIVE | 2000-10-04 | 389 | 2000-11-21 | 2000-11-22 | 2000-11-30 | DINCA | OK | 2001-01-25 |  | 2001-02-05 | 2001-02-06 |  |  | OK | Bogdan CRAIU | Cosmorom | [32 empty] | 111 | Gepiu | Mures | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | TM107 | NOJORID | Road Arad-Oradea(10) | TM082 Oradea_2_RTC | Banat | 46 59 54.6 | 21 53 20.1 | 46 59 54.6 | 21 53 20.1 | Com. Nojorid, sat Nojorid nr.362 | Cartis Gheorghe - com. Nojorid, sat Nojorid nr.362/Cartis Alexandru - Com. Nojorid, sat Nojorid nr.362, 059/ 144 159 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-09-19 | N/A | N/A |  |  |  |  | TN | 40 | Tower | N/A | PROTELCO | OK | SVF | 2000-09-01 | 2000-09-13 | YesV | 2000-09-20 | Doru | 2000-09-15 | 2000-09-22 |  |  |  |  | 2000-08-05 |  | 2000-08-22 | 2000-09-07 |  |  |  | 2000-09-15 | YRO | MOB | 2000-09-15 | 2000-09-15 | 2000-09-18 | 2000-09-19 | 2000-09-20 |  | Yes | Theo Radoi | 2001-01-23 | 2001-01-23 | 2001-01-23 | 2001-03-15 | 2001-04-10 | K 739 494 | 15 | 0 | 38 | K 739 494 | 230 | 0 | 38 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 55 | 55 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 110 | ML 23 E 1+0 | Oradea | MW | 25 | 0.6 | 37.5 | 55 | 23/56 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [9 empty] | 1 | TM081 | ORADEA_1 | 206 | 0.6 |  | 55 | 23/58 | [6 empty] | 8 | MOBILCOM | 2000-09-15 | 208 | 2000-09-16 | 2000-09-16 | 2000-09-20 | DINCA | OK | 2001-01-24 |  | 2001-02-05 | 2001-02-06 |  |  | OK | Bogdan CRAIU | Cosmorom | [32 empty] | 151 | Nojorid | Bihor | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | TM108 | BIHARIA | Road Oradea-Satu Mare(16+3) | YM096 Valea lui Mihai | Banat | 47 09 11 | 21 55 10 | 47 10 12.3 | 21 55 19.3 | Com. Biharia | Dorobont Sandor - 094/ 574 917/Dorobont Sandor - 094/ 574 917 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-09-19 | N/A | N/A |  |  |  |  | TN | 40 | Tower | N/A | PROTELCO | OK | SVF | 2000-09-01 | 2000-09-13 | YesV | 2000-09-20 | Doru | 2000-09-15 | 2000-09-22 |  |  |  |  | 2000-07-07 |  | 2000-08-21 | 2000-09-07 |  |  |  | 2000-09-15 | YRO | MOB | 2000-09-15 | 2000-09-15 | 2000-09-18 | 2000-09-19 | 2000-09-20 |  | Yes | Theo Radoi | 2001-04-12 | 2001-04-12 | 2001-04-12 |  |  | K 739 494 | 5 | 0 | 38 | K 739 494 | 200 | 0 | 38 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 50 | 50 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 100 | ML 15 E 1+0 | Oradea | MW | 13 | 1.2 | 37.5 | 50 | 15/89 |  | 4X2/8 | 2U-3 |  |  |  | RBS | [9 empty] | 1 | TM097 | ROSIORI | 193 | 1.2 | 47 | 65 | 15/84 | [6 empty] | 8 | MOBILCOM | 2000-09-15 | 206 | 2000-09-16 | 2000-09-16 | 2000-09-20 | DINCA | OK | 2001-04-12 | Pending |  |  | 30N02 |  | 2001-03-07 | George IFRIM | Petrica BURGHIU | [32 empty] | 120 | Biharia | Bihor | [7 empty] | 2 |  |  | 2
Phase_2 | CS | TM109 | SACUIENI | Road Oradea-Satu Mare(16+3) | YM096 Valea lui Mihai | Banat | 47 21 04 | 22 06 23 | 47 21 21.8 | 22 07 11.6 | Extravilan Sacuieni parcela nr.616 | Szamos Ileana str. Morii nr.84/Zsamos Ileana str. Morii nr.84 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-10-20 | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | PROTELCO | OK | SVF | 2000-12-08 | 2001-02-12 | YesV | 2001-02-14 | Doru | 2001-03-23 | 2001-02-26 |  |  |  |  | 2000-11-05 |  | 2000-11-27 | 2001-01-11 |  |  |  | 2001-03-26 | ICOM | SVF | 2001-02-13 | 2001-02-13 | 2001-03-27 | 2001-03-27 | 2001-04-02 |  | Yes | Theo Radoi | 2001-04-11 | 2001-04-11 | 2001-04-11 |  |  | K 739 494 | 30 | 0 | 48 | K 739 494 | 230 | 0 | 48 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+1 | Oradea | MW | 31 | 0.6 | 42.75/0.6 | 50 | 15/84 | YES | 4X2/8 | 4U-1 |  |  |  | RBS | [9 empty] | 1 | TM110 | ADONI | 209 | 0.6 | 42.5/0.6 | 70 | 15/89 | [6 empty] | 47* | SVF | 2001-03-26 | 756 | 2001-03-27 | 2001-03-27 | 2001-04-03 | VLAD | OK | 2001-04-11 |  | 2001-05-17 | 2001-05-25 | 30N02 |  | 2001-03-07 | Petrica BURGHIU | Cosmorom | [32 empty] | 120 | Sacuieni | Bihor | [5 empty] | 1 | 1 | 2 | 1 | 1 | 2
Phase_2 | CS | TM110 | ADONI | Road Oradea-Satu Mare(16+3) | YM096 Valea lui Mihai | Banat | 47 25 32 | 22 10 54 | 47 25 43.9 | 22 10 42.7 | Sat Adoni, str. Dealului, com. Tarcea | Consiliul local Tarcea/Primar Lucaci Alexandru - 095/ 638 658 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-10-19 | N/A | N/A |  |  |  |  | TN | 55 |  | N/A | PROTELCO | OK | ESROM | 2000-09-11 | 2000-10-15 | YesV | 2000-11-16 | Doru | 2001-02-05 | 2000-11-22 |  |  |  |  | 2000-08-05 |  | 2000-08-21 | 2000-11-15 |  |  |  | 2000-10-23 | ICOM | MOB | 2000-10-23 | 2000-10-23 | 2000-10-23 | 2000-12-01 | 2000-12-04 |  | Yes | Theo Radoi | 2001-04-11 | 2001-04-11 | 2001-04-11 |  |  | K 739 494 | 210 | 0 | 55 | K 739 494 | 350 | #N/A | 55 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 70 | 70 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 140 | ML 15 E 1+1 | Oradea | MW | 347 | 0.6 | 42.5/0.6 | 70 | 15/89 | YES | 4X2/8 | 4U-1 |  |  |  | RBS | [9 empty] | 1 | TM096 | VALEA LUI MIHAI | 164 | 0.6 | 47/0.6 | 53 | 15/84 | [6 empty] | 41* | SVF | 2001-03-13 | 713 | 2001-03-14 | 2001-03-14 | 2001-04-03 | VLAD | OK | 2001-04-11 |  | 2001-05-17 | 2001-05-25 | 30N02 |  | 2001-03-07 | Petrica BURGHIU | #N/A | [32 empty] | 117 | Adoni | Bihor | [5 empty] | 1 |  | 2 | 1 | 1 | 2
Phase_2 | TM | TM111 | TOC_DRTV | Road Arad-Deva(13+3) | YM145 Ilia_RTC | Banat | 46 00 29.4 | 22 19 24.9 | 46 00 29.4 | 22 19 24.9 | Pilon DRTV Toc | DRTV/ | N/A | N/A | N/A | N/A | N/A | [7 empty] | N/A | N/A |  |  |  | N/A | TE | 25 | Tower | N/A | SVF | OK | ISAF | 2000-10-02 | 2000-10-12 | YesV | 2000-10-19 | Mugur | 2000-10-10 | 2000-10-24 |  |  |  | N/A | 2000-07-05 |  | 2000-07-24 | 2000-08-21 |  |  |  | 2000-10-20 | ICOM | Interactive | N/A | N/A | 2000-10-23 | N/A | N/A |  | Yes | N/A | 2001-04-06 | 2001-04-06 | 2001-04-06 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | ML 15 E 1+0 | Timisoara | MW | 109 | 0.6 | 19/1.2 | 28 | 15/84 |  | 4x2/8 | 4U-1 |  |  |  | TMR 9000 | [9 empty] | 1 | TM013 | BURJUC | 289 | 0.6 | 37/1.2 | 50 | 15/89 | [6 empty] | 8* | SVF | 2000-12-15 | 470 | 2000-12-18 | 2001-01-30 | 2001-02-06 | IVAN | OK | 2001-04-06 |  | 2001-05-03 | 2001-05-11 | N/A |  | 2001-03-31 | Cristian CROITOR | Cosmorom | [32 empty] | 161 | Toc | Arad | [7 empty] | 2 |  |  | 2
Phase_2 | TM | TM112 | NUCET | Road Arad-Deva(13+3) | TM112 Nucet_RTC | Banat | 45 52 20.6 | 22 51 41.9 | 45 52 20.6 | 22 51 41.9 | Turn DRTV Deva Nucet | DRTV/Betea Miron, tel. 094/783023 sau 054/204283 | N/A | N/A | N/A | N/A | N/A | [12 empty] | N/A | TE | 118 | Tower | N/A/TMR9000 | SVF | OK | TEHNOROB | 2000-09-01 | 2000-09-08 | YesV | 2000-09-19 | Mugur | 2000-09-15 | 2000-09-22 |  |  |  | 2000-05-22 | 2000-07-26 |  | 2000-07-27 | 2001-02-28 | [6 empty] | N/A | N/A |  |  |  |  | Yes | N/A | 2001-05-15 | 2001-05-15 | 2001-05-15 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A | Timisoara | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | 4U-1 |  |  |  | TMR 9000 | 50112 | 2001-05-14 | [5 empty] | 100/16p outdoor |  |  | BSC31 | BSC TIMISOARA |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A |  | 2001-02-26 | Cristian CROITOR | Cosmorom | [32 empty] | 640 | Nucet (Deva) | Hunedoara | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | TM114 | TOPA DE CRIS | Road Oradea-Cluj(13) | TM091 Alesd_RTC | Transilvania | 47 00 00.3 | 22 31 25.1 | 47 00 00.5 | 22 31 28.1 | Intravilan com. Vadu Crisului | Garz Trifon, Topa de Cris, com. Vadu Crisului nr.88/Garz Trifon, Topa de Cris nr.88 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-11-17 | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | IMSAT | OK | ORION | 2000-10-26 | 2001-08-05 | in exec |  | Andrei | [6 empty] | 2000-08-18 |  | 1900-04-13 | 2000-11-02 | [14 empty] | RBS 2101 |  |  |  |  | K 739 494 | 100 | 0 | 48.3 | K 739 494 | 320 | 0 | 48.3 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Oradea | MW | 305 | 1.2 | 47/1.2 | 58 | [7 empty] | RBS | [10 empty] | TM091 | ALESD_RTC | 125 | 0.6 | 25/0.6 | [23 empty] | 2000-11-23 | Bogdan CRAIU | Cosmorom | [32 empty] | 272 | Vadu Crisului | Bihor | [7 empty] | 2 |  |  | 2
Phase_2 | CS | TM115 | OSORHEI | Road Oradea-Cluj(13) | TM082 Oradea_2_RTC | Banat | 47 02 54.9 | 22 02 35.1 | 47 03 00.5 | 22 02 33.5 | Intravilan com. Osorhei | Primaria Osorhei/ | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-11-17 | N/A | N/A |  |  |  |  | TN | 40 |  | N/A | IMSAT | OK | ESROM | 2000-10-16 | 2000-12-08 | YesV | 2000-12-19 | Andrei | 2001-01-17 | 2000-12-20 |  |  |  |  | 2000-08-18 |  | 2000-10-06 | 2000-10-30 |  |  |  | 2000-12-11 | ICOM | TRY | 2000-12-08 | 2000-12-13 | 2000-12-14 | 2000-12-15 | 2000-12-20 |  | Yes | Theo Radoi | 2001-01-24 | 2001-01-24 | 2001-01-24 | 2001-04-26 | 2001-05-03 | K 739 494 | 80 | 0 | 38.25 | K 739 494 | 250 | 0 | 38.25 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 50 | 50 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 100 | ML 15 E 1+0 | Oradea | MW | 271 | 0.6 | 37.5/0.6 | 48 | 15/84 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [9 empty] | 1 | TM082 | ORADEA_2 |  | 0.6 |  | 40 | 15/89 | [6 empty] | 4* | TRYLON | 2000-12-11 | 439 | 2000-11-12 | 2000-11-13 | 2000-12-20 | PITURCESCU | OK | 2001-01-24 |  | 2001-02-05 | 2001-02-06 |  |  | OK | Bogdan CRAIU | Cosmorom | [32 empty] | 144 | Osorhei | Bihor | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | TM116 | UILEACU DE CRIS | Road Oradea-Cluj(13) | TM082 Oradea_2_RTC | Banat | 47 04 55.8 | 22 12 05.2 | 47 04 56.4 | 22 12 02.1 | Intravilan parcela Barat-Domb, com. Tileaid, sat Uileacu de Cris | Varga Ferenc, sat Uileacu de Cris nr.232, jud. Bihor/Varga Ferenc, sat Uileacu de Cris nr.232 | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | IMSAT | OK | ESROM | 2000-11-20 | 2001-06-21 | YesV | 2001-07-03 | Andrei |  | 2001-06-12 |  |  |  |  | 2000-08-18 |  | 2000-11-09 | 2000-12-05 | [6 empty] | 2001-07-11 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 103 | 0 | 48.3 | K 739 494 | 247 | 0 | 48.3 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 120 | ML 15 E 1+0 | Oradea | MW | 253 |  | 47 | 60 | [7 empty] | RBS | [10 empty] | TM115 | OSORHEI | 70 | 1.2 | 37.3/1.2 | 48 | [22 empty] | OK | Bogdan CRAIU | Cosmorom | [32 empty] | 181 | Uileacu de Cris | Bihor | [7 empty] | 2 |  |  | 2
Phase_2 | CS | TM117 | TOPLET | Road Herculane-Caransebes(9+1) | TM155 Baile Herculane_RTC | Banat | 44 47 59.5 | 22 23 09.7 | 44 48 01.9 | 22 23 15.6 | Extravilan loc. Toplet, Dealul Iorgovan | Primaria Toplet - 055/ 560 266/Ciocu - Primaria Toplet, 055/ 560 266 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-12-11 | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | SVF | OK | COMARK | 2000-11-06 | 2001-01-26 | YesV | 2001-06-18 | Andrei | 2001-02-02 | 2001-06-22 |  |  |  |  | 2000-09-25 |  | 2000-10-26 | 2000-11-13 | [6 empty] | 2001-02-01 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 10 | 0 | 49 | K 739 494 | 160 | 0 | 49 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | 70 | 70 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 140 | ML 23 E 1+0 | Timisoara | MW | 8 | 0.6 | 22/0.6 | 45 | [7 empty] | RBS | [10 empty] | TM118 | PECINISCA | 187 | 1.2 | 21 | 36 | [23 empty] | SORIN UNTARU | Cosmorom | [32 empty] | 110 | Toplet | Caras Severin | [7 empty] | 2 |  |  | 2
Phase_2 | CS | TM118 | PECINISCA | Road Herculane-Caransebes(9+1) | TM155 Baile Herculane_RTC | Banat | 44 44 31.1 | 22 24 32.3 | 44 50 57.5 | 22 23 45 | Extravilan Baile Herculane | Primaria orasului Baile Herculane, str. Mihai Eminescu 10/Primar Popovici Ion | 2101 | M | C+ | 2 | 2101 | [13 empty] | TN | 40 |  | N/A | SVF | OK | DUAL | 2001-05-11 | 2001-07-27 | in exec |  | Adi | [8 empty] | 2001-05-10 | OK | [14 empty] | RBS 2101 |  |  |  |  | K 739 494 | 190 | 0 | 39.5 | K 739 494 | 345 | 0 | 39.5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | 55 | 55 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 110 | ML 23 E 1+1 | Timisoara | MW | 13 | 1.2 | 21 | 36 | [7 empty] | RBS | [10 empty] | TM119 | HOTEL DIANA | 193 |  | 40 | 12 | [23 empty] | SORIN UNTARU | Cosmorom | [33 empty] | Herculane | Herculane | [6 empty] | 1 | 2 |  | 1 | 2
Phase_2 | CS | TM119 | HOTEL DIANA | Road Herculane-Caransebes(9+1) | TM155 Baile Herculane_RTC | Banat | 44 52 49.7 | 22 24 58.1 | 44 52 49.7 | 22 24 58.1 | Hotel Diana | SC HERCULES SA - str. Izvorului nr.97, 055/ 560 444/Cristescu Ilie - hotel Diana, 055/ 560 443 | 2101 | M | C+ | 2 | 2101 | [7 empty] | YES |  |  |  |  | 39 | B | 43 | 4xC2m+2xC3m | N/A | DUAL | OK | DUAL | 2001-01-19 | 2001-02-20 | YesV | 2001-03-05 | Andrei | 2001-02-23 | 2001-03-14 |  |  |  |  | 2000-11-23 |  | 2000-12-18 | 2001-02-01 | [6 empty] | 2001-02-21 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 15 | 0 | 40 | K 739 494 | 210 | 0 | 40 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | 10 | 10 | 7/8" | 15 | 15 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A | 50 | ML 38 E 1+1 | Timisoara | MW | 274 |  | 40 | 15 | [7 empty] | RBS | [10 empty] | TM155 | BAILE HERCULANE_RTC | 80 | 0.3 | 19.2/0.3 | 28 | [23 empty] | SORIN UNTARU | Cosmorom | [32 empty] | 148 | Herculane | Caras Severin | [6 empty] | 1 | 2 |  | 1 | 2
Phase_2 | CS | TM121 | CORNEA | Road Herculane-Caransebes(9+1) | TM155 Baile Herculane_RTC | Banat | 45 02 36.1 | 22 18 40.7 | 45 02 37.4 | 22 18 43.2 | Extravilan loc. Cornea | Sadovan Gheorghe - Cornea nr.250/Sadovan Gheorghe - Cornea nr.250 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-12-11 | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | SVF | OK | SVF | 2001-02-14 | 2001-03-12 | YesV | 2001-03-27 | Andrei | 2001-05-07 | 2001-03-29 |  |  |  |  | 2000-09-26 |  | 2000-11-07 | 2000-11-24 | [6 empty] | 2001-03-13 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 170 | 0 | 49.5 | K 739 494 | 355 | 0 | 49.5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | 60 | 60 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 120 | ML 15 E 1+0 | Timisoara | MW | 121 | 1.2 | 40/1.2 | [8 empty] | RBS | [10 empty] | TM118 | PECINISCA | 343 | 1.2 | 37 | 52 | [23 empty] | SORIN UNTARU | COSMOROM | [32 empty] | 391 | Cornea | Caras Severin | [7 empty] | 2 |  |  | 2
Phase_2 | CS | TM122 | DOMASNEA | Road Herculane-Caransebes(9+1) | TM155 Baile Herculane_RTC | Banat | 45 06 04.6 | 22 19 04.4 | 45 06 05.5 | 22 19 10.1 | Com. Domasnea | Galescu Petru si Ciortan Ana - Resita, B-dul. Revolutiei Decembrie nr.23/Fiat Iancu (vecin) - Luncavita, 095/ 864 003 | MUTAT | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | SVF | OK | SVF | 2000-11-06 | 2000-12-22 | YesV | 2001-01-25 | Andrei | 2001-01-17 | 2001-02-13 |  |  |  |  | 2000-09-27 |  | 2000-11-13 | 2000-11-30 |  |  |  | 2000-12-28 | ICOM | SVF | 2000-12-27 | 2001-01-10 | 2001-01-11 | 2001-01-12 | 2001-01-22 |  | Yes |  | 2101 MOVED TO CJ124 |  |  |  |  | K 739 494 | 190 | 0 | 50 | K 739 494 | 350 | 0 | 50 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | 70 | 70 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 140 | ML 23 E 1+0 | Timisoara | MW | 184 |  | 44 | 55 | [7 empty] | N/A | [10 empty] | TM121 | CORNEA | 4 |  | 45.7 | 70 | [23 empty] | SORIN UNTARU | Cosmorom | [32 empty] | 576 | Domasnea | Timis | [7 empty] | 2 |  |  | 2
Phase_2 | CS | TM123 | ARMENIS | Road Herculane-Caransebes(9+1) | TM155 Baile Herculane_RTC | Banat | 45 11 11.4 | 22 18 29.5 | 45 11 12.7 | 22 18 35.4 | Extravilan loc. Rusca | Blaj Gheorghe - loc. Rusca nr.340/Blaj Gheorghe - loc. Rusca nr.340 | MUTAT | M | C+ | 2 | 2101 | [6 empty] | 2000-12-11 | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | SVF | OK | SVF | 2000-11-15 | 2000-12-05 | YesV | 2000-12-07 | Andrei | 2001-01-09 | 2000-12-13 |  |  |  |  | 2000-09-27 |  | 2000-11-07 | 2000-11-23 |  |  |  | 2000-12-07 | ICOM | MOB | 2000-12-07 | 2000-12-10 | 2000-12-11 | 2000-12-12 | 2000-12-21 |  | Yes |  | 2101 MOVED TO CJ125 |  |  |  |  | K 739 494 | 190 | 0 | 50 | K 739 494 | 350 | #N/A | 50 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | 70 | 70 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 140 | ML 15 E 1+0 | Timisoara | MW | 178 |  | 48 | 60 | [7 empty] | N/A | [10 empty] | TM122 | DOMASNEA | 357 |  | 48 | 60 | [23 empty] | SORIN UNTARU | #N/A | [32 empty] | 382 | Rusca | Caras Severin | [7 empty] | 2 |  |  | 2
Phase_2 | CS | TM124 | SADOVA | Road Herculane-Caransebes(9+1) | TM078 Caransebes_RTC | Oltenia | 45 14 26.2 | 22 18 20.4 | 45 14 26 | 22 18 20 | Com. Slatina Timis, sat Sadova Veche | Primaria Slatina - Timis/Motolan Martin (primar) - primaria Slatina-Timis, 094/ 537 824 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-12-11 | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | SVF | OK | SVF | 2000-11-03 | 2000-11-17 | YesV | 2000-11-28 | Andrei | 2000-12-11 | 2000-12-07 |  |  |  |  | 2000-09-26 |  | 2000-10-26 | 2000-11-13 |  |  |  | 2000-11-17 | ICOM | SVF | 2000-11-17 | 2000-11-17 | 2000-11-20 | 2000-11-21 | 2000-11-23 |  | Yes | Alexandru Toma | 2001-03-15 | 2001-03-15 | 2001-03-15 |  |  | K 739 494 | 195 | 0 | 49 | K 739 494 | 325 | 0 | 49 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 70 | 70 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 140 | ML 15 E 1+0 | Timisoara | MW | 342 | 1.2 | 47/1.2 | 65 | 15/84 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [9 empty] | 1 | TM125 | VALEA TIMISULUI | 162 | 1.2 | 47/1.2 | 70 | 15/89 | [6 empty] | 1* | MOBILCOM | 2000-12-07 | 433 | 2000-12-08 | 2000-12-09 | 2000-12-15 | IVAN | OK | 2001-03-15 | PENDING ITEMS |  |  | 30N01 Caransebes-Timisoara |  | 2001-02-26 | SORIN UNTARU | Cosmorom | [32 empty] | 331 | Sadova Veche | Caras Severin | [7 empty] | 2 |  |  | 2
Phase_2 | CS | TM125 | VALEA TIMISULUI | Road Herculane-Caransebes(9+1) | TM078 Caransebes_RTC | Oltenia | 45 20 39.6 | 22 15 29.8 | 45 20 43.3 | 22 15 38.6 | Extravilan loc. Valea Timisului, zona pod rau Bolvasuita | Primaria Buchin - 055/ 511 678/Gheorghe Coila - 055/ 511 678 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-11-17 | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | SVF | OK | SVF | 2000-11-08 | 2000-12-05 | YesV | 2000-12-07 | Andrei | 2001-01-09 | 2000-12-13 |  |  |  |  | 2000-09-28 |  | 2000-10-26 | 2000-11-03 |  |  |  | 2000-12-07 | ICOM | MOB | 2000-12-07 | 2000-12-10 | 2000-12-11 | 2000-12-12 | 2000-12-20 |  | Yes | Alexandru Toma | 2001-03-15 | 2001-03-15 | 2001-03-15 |  |  | K 739 494 | 160 | 0 | 49.5 | K 739 494 | 335 | 0 | 49.5 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 70 | 70 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 140 | ML 15 E 1+1 | Timisoara | MW | 337 | 0.6 | 47/0.6 | 70 | 15/89 |  | 4x2/8 | 4U-1+2U-3 |  |  |  | N/A | [9 empty] | 1 | TM078 | CARANSEBES_RTC | 157 | 0.6 | 26 | 35 | 15/84 | [6 empty] | 1* | MOBILCOM | 2000-12-07 | 431 | 2000-12-08 | 2000-12-09 | 2000-12-20 | IVAN | OK | 2001-03-15 |  | 2001-05-03 | 2001-05-11 | 30N01 Caransebes-Timisoara |  | 2001-02-26 | SORIN UNTARU | Cosmorom | [32 empty] | 231 | Valea Timisului | Caras Severin | [6 empty] | 1 | 2 |  |  | 2
Phase_2 | CS | TM126 | JUPA | Road Caransebes-Lugoj(4) | TM078 Caransebes_RTC | Oltenia | 45 27 33.3 | 22 11 13.7 | 45 27 55.5 | 22 11 21.1 | Com. Jupa | Golici Nicolae/Golici Nicolae | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-11-17 | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | SVF | OK | SVF | 2000-11-03 | 2000-11-17 | YesV | 2000-11-28 | Andrei | 2000-12-13 | 2000-12-07 |  |  |  |  | 2000-09-20 |  | 2000-10-25 | 2000-11-03 |  |  |  | 2000-11-17 | ICOM | SVF | 2000-11-17 | 2000-11-17 | 2000-11-20 | 2000-11-21 | 2000-11-22 |  | Yes | Alexandru Toma | 2001-03-16 | 2001-03-16 | 2001-03-16 |  |  | K 739 494 | 200 | 0 | 49.5 | K 739 494 | 340 | 0 | 49.5 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 70 | 70 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 140 | ML 15 E 1+0 | Timisoara | MW | 157 | 0.6 | 48/0.6 | 64 | 15/89 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [9 empty] | 1 | TM125 | VALEA TIMISULUI | 337 | 1.2 | 45/1.2 |  | 15/84 | [6 empty] | 1* | MOBILCOM | 2000-12-07 | 432 | 2000-11-20 | 2000-11-20 | 2000-11-23 | OK | OK | 2001-03-16 |  | 2001-05-03 | 2001-05-11 | 30N01 Caransebes-Timisoara |  | 2001-02-26 | SORIN UNTARU | Cosmorom | [32 empty] | 223 | Jupa | Caras Severin | [7 empty] | 2 |  |  | 2
Phase_2 | CS | TM127 | DAICOVICIU | Road Caransebes-Lugoj(4) | TM078 Caransebes_RTC | Oltenia | 45 32 41 | 22 08 51 | 45 32 56 | 22 09 03 | Constantin Daicoviciu nr.118 | Sarbu Ioan - Constantin Daicoviciu nr.68/Sarbu Ioan - Constantin Daicoviciu nr.68 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-12-11 | N/A | N/A |  |  |  |  | TN | 50 | tower | N/A | SVF | OK | SVF | 2000-11-06 | 2000-11-27 | YesV | 2000-11-28 | Andrei | 2000-11-28 | 2000-12-08 |  |  |  |  | 2000-09-27 |  | 2000-10-26 | 2000-11-13 |  |  |  | 2000-11-17 | ICOM | SVF | 2000-11-17 | 2000-11-17 | 2000-11-20 | 2000-11-24 | 2000-11-25 |  | Yes | Alexandru Toma | 2001-03-16 | 2001-03-16 | 2001-03-16 |  |  | K 739 494 | 180 | 0 | 50 | K 739 494 | 325 | 0 | 50 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 70 | 70 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 140 | ML 15 E 1+0 | Timisoara | MW | 161 | 0.6 | 50/1.2 | 70 | 15/84 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [9 empty] | 1 | TM126 | JUPA | 342 | 0.6 | 47/1.2 | 65 | 15/89 | [6 empty] | N/A | SVF | N/A | 379 | 2000-11-17 | 2000-11-20 | 2000-11-25 | IVAN | OK | 2001-03-16 |  | 2001-07-12 |  | 30N01 Caransebes-Timisoara |  | 2001-02-26 | SORIN UNTARU | Cosmorom | [32 empty] | 160 | Constantin Daicoviciu | Timis | [7 empty] | 2 |  |  | 2
Phase_2 | CS | TM128 | JENA | Road Caransebes-Lugoj(4) | TM071 Lugoj_RTC | Banat | 45 36 32 | 22 03 12 | 45 36 10.6 | 22 04 34.4 | Com. Jena |  | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  | 0 | TN | 50 |  | N/A | SVF | OK | SVF | 2000-11-29 | 2000-12-15 | YesV | 2001-01-09 | Andrei | 2001-01-09 | 2001-01-10 |  |  |  | 2000-10-24 | OK |  | 2000-11-22 | 2000-11-30 |  |  |  | 2000-12-14 | ICOM | SVF | 2000-12-14 | 2000-12-15 | 2000-12-19 | 2001-01-12 | 2001-01-15 |  | Yes | Alexandru Toma | 2001-04-28 | 2001-04-27 | 2001-04-27 | 2001-05-23 | 2001-05-31 | K 739 494 | 125 | 0 | 49 | K 739 494 | 300 | 0 | 49 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 70 | 70 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 140 | ML 23 E 1+0 | Timisoara | MW | 296 | 1.2 | 48 | 68 | 23/58 |  | 4x2/8 | 4U-1 |  |  |  | RBS | XC50071 | [8 empty] | 1 | TM129 | TAPIA | 116 | 1.2 | 26.5 | 47 | 23/56 | [6 empty] | 7* | SVF | 2000-12-14 | 462 | 2000-12-18 | 2000-11-20 | 2001-01-15 | IVAN | OK | 2001-04-27 |  | 2001-05-21 | 2001-05-25 | 30N02 Lugoj-Timisoara |  | OK | SORIN UNTARU | Cosmorom | [32 empty] | 155 | Com. Jena | Timis | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | TM129 | TAPIA | Road Caransebes-Lugoj(4) | TM071 Lugoj_RTC | Banat | 45 39 02 | 21 58 03 | 45 39 02.3 | 21 58 03 | SC EDIL 2000 ITALIA extravilan, loc. Lugojel | SC EDIL 2000 ITALIA - loc. Lugojel/Vanagolli Giorgio - loc. Tipari nr.115, 094/ 692 203 | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  | 0 | TN | 50 |  | N/A | SVF | OK | SVF | 2000-11-15 | 2000-12-08 | YesV | 2001-01-09 | Andrei | 2001-01-11 | 2001-01-10 |  |  |  |  | OK |  | 2000-11-13 | 2000-11-30 |  |  |  | 2000-12-11 | ICOM | TRY | 2000-12-08 | 2000-12-08 | 2001-01-08 | 2001-01-09 | 2001-01-11 |  | Yes | Alexandru Toma | 2001-04-28 | 2001-04-28 | 2001-04-28 | 2001-06-19 | 2001-07-11 | K 739 494 | 120 | 0 | 49.5 | K 739 494 | 300 | 0 | 49.5 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 70 | 70 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 140 | ML 15 E 1+0 | Timisoara | MW | 308 | 1.2 | 26 | 47 | 15/84 |  | 4x2/8 | 2U-3 |  |  |  | RBS | XC50071 | [8 empty] | 1 | TM072 | NICOLAE BALCESCU | 126 | 1.2 |  | 30 | 15/89 | [6 empty] | 4* | TRYLON | 2000-12-11 | 438 | 2000-12-11 | 2000-12-13 | 2001-01-11 | IVAN | OK | 2001-04-27 | PENDING ITEMS |  |  | 30N02 Lugoj-Timisoara |  | OK | SORIN UNTARU | Cosmorom | [32 empty] | 135 | Lugojel | Timis | [7 empty] | 2 |  |  | 2
Phase_2 | CS | TM131 | BELINT | Road Lugoj-Timisoara(4) | TM071 Lugoj_RTC | Banat | 45 44 55.2 | 21 46 21.9 | 45 44 56.2 | 21 46 38.9 | Belint nr.222 | Bulcu Brandusa - Belint nr.245, 056/ 327 109/Danila Dragos - Belint, 056/ 327 164 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-12-11 | N/A | N/A |  |  |  | 0 | TN | 50 |  | N/A | SVF | OK | EL-MONT | 2000-11-06 | 2000-12-05 | YesV | 2000-12-07 | Andrei | 2000-11-28 | 2000-12-13 |  |  |  |  | 2000-09-26 |  | 2000-11-03 | 2000-11-23 |  |  |  | 2000-12-14 | ICOM | SVF | 2000-12-14 | 2000-12-14 | 2001-01-04 | 2001-01-18 | 2001-01-22 |  | Yes | Constantin Mihai | 2001-03-25 | 2001-03-25 | 2001-03-25 |  |  | K 739 494 | 100 | 0 | 49 | K 739 494 | 300 | 0 | 49 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 70 | 70 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 140 | ML 15 E 1+0 | Timisoara | MW | 122 | 0.6 | 47 | 68 | 15/89 |  | 4x2/8 | 2U-3 |  |  |  | RBS | XC50071 | [8 empty] | 1 | TM156 | TINERETII | 303 | 0.6 | 19 | 19 | 15/84 | [6 empty] | 31* | SVF | 2001-02-26 | 671 | 2001-02-27 | 2001-02-27 | 2001-03-05 | IVAN | OK | 2001-03-25 | PENDING ITEMS |  |  | 30N02 Lugoj-Timisoara |  | 2/26/2001(Conectare locala) | SORIN UNTARU | Cosmorom | [32 empty] | 107 | Belint | Timis | [7 empty] | 2 |  |  | 2
Phase_2 | CS | TM132 | TOPOLOVATU MARE | Road Lugoj-Timisoara(4) | TM071 Lugoj_RTC | Banat | 45 46 09.1 | 21 37 49.6 | 45 46 09.1 | 21 37 49.1 | SC CEREALCOM TIMIS SA | SC CEREALCOM TIMIS/Popa Laurentiu - Topolavatu Mare, Siloz, 056/ 193 429 sau 056/332018 | 2101 | M | C+ | 2 | 2101 | [7 empty] | YES |  |  |  |  | 45 | S | 45 | T6m+T6m | N/A | SVF | OK | EL-MONT | 2001-03-01 | 2001-03-27 | YesV | 2001-04-05 | Adi | 2001-04-17 | 2001-04-10 | Cosmorom |  |  |  | 2000-09-27 |  | 2001-02-20 | 2001-03-14 | [6 empty] | 2001-03-29 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 70 | 0 | 50.3 | K 739 494 | 290 | 0 | 50.3 | N/A | N/A | N/A | N/A |  |  |  |  | N/A | 17 | 17 | 7/8" | 14 | 14 | 7/8" | N/A | N/A | N/A |  |  |  | 62 | ML 15 E 1+0 | Timisoara | MW | 102 | 1.2 | 48/1.2 | 15 |  |  |  | 2U-3 |  |  |  | RBS | [10 empty] | TM131 | BELINT | 282 |  | 47 | 68 | [20 empty] | 30N03 Lugoj-Timisoara |  | 2/26/2001(Conectare locala) | SORIN UNTARU | Cosmorom | [32 empty] | 109 | Topolovatu Mare | Timis | [7 empty] | 2 |  |  | 2
Phase_2 | CS | TM134 | IZVIN | Road Lugoj-Timisoara(4) | TM053 Central_RTC | Banat | 45 47 52.9 | 21 27 18.1 | 45 47 52.9 | 21 27 18.1 | Izvin, com. Recas, nr.163 | Draguescu Calin, Izvin nr.163/Draguescu Calin, Izvin nr.163 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-12-11 | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | SVF | OK | TEHNOROB | 2000-11-14 | 2000-12-15 | YesV | 2001-01-09 | Andrei |  | 2001-01-10 |  |  |  |  | 2000-09-27 |  | 2000-11-07 | 2000-11-24 |  |  |  | 2000-12-14 | ICOM | SVF | 2000-12-14 | 2000-12-14 | 2000-12-19 | 2001-01-11 | 2001-01-15 |  | Yes | Theo Radoi | 2001-03-15 | 2001-03-15 | 2001-03-15 |  |  | K 739 494 | 90 | 0 | 49 | K 739 494 | 245 | 0 | 49 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 70 | 70 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 140 | ML 15 E 1+0 | Timisoara | MW | 258 | 0.6 | 47 | 65 | 15/89 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [10 empty] | TM135 | GHIRODA | 78 | 0.6 | 47 | 67 | 15/84 | [6 empty] | 32* | SVF | 2001-02-27 | 674 | 2001-02-27 | 2001-02-27 | 2001-03-05 | DINCA | OK | 2001-03-15 |  |  |  | 30N01Centru-Timisoara |  | OK | SORIN UNTARU | Cosmorom | [32 empty] | 100 | Izvin | Timis | [7 empty] | 2 |  |  | 2
Phase_2 | CS | TM135 | GHIRODA | Road Lugoj-Timisoara(4) | TM053 Central_RTC | Banat | 45 46 30.6 | 21 17 59.7 | 45 46 28.6 | 21 18 31.8 | Cimitir Ghiroda, judetul Timis | Parorhia Ortodoxa Romana, comuna Giroda Veche str. Victoria nr. 51, jud. Timis/Parintele Mermeje , Biserica Ghiroda | 2102 | M | C+C+C+ | 2/2/2 | N/A | [12 empty] | 0 | TN | 50 |  |  | SVF | OK | SVF | 2001-02-12 | 2001-02-24 | YesV | 2001-03-06 | Andrei | 2001-03-15 | 2001-03-14 |  |  |  |  | 2000-09-27 |  | 2001-01-30 | 2001-02-20 |  |  |  | 2001-02-27 | ICOM | SVF | 2001-02-27 | 2001-02-27 | 2001-02-28 | 2001-02-03 | 2001-03-06 |  | Yes | Theo Radoi | 2001-03-15 | 2001-03-15 | 2001-03-15 | 2001-06-29 | 2001-07-11 | K 739 494 | 5 | 0 | 49.5 | K 739 494 | 85 | 0 | 49.5 | K 739 494 | 240 | 0 | 49.5 |  |  |  |  | N/A | 70 | 70 | 1 1/4" | 70 | 70 | 1 1/4" | 70 | 70 | 1 1/4" |  |  |  | 420 | ML 23 E 1+0 | Timisoara | MW | 248 | 0.6 | 47 | 67 | 23/58 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [10 empty] | TM052 | TACHE IONESCU | 109 | 0.6 | 37.35 | 11 | 23/56 | [6 empty] | 32* | SVF | 2001-02-27 | 675 | 2001-02-27 | 2001-02-27 | 2001-03-05 | DINCA | OK | 2001-03-15 |  |  |  | 30N01Centru-Timisoara |  | OK | SORIN UNTARU | Cosmorom | [32 empty] | 93 | Ghironda | Timis | [7 empty] | 2 |  |  | 2
Phase_2 | CS | TM145 | ILIA | Road Arad-Deva(13+3) | YM145 Ilia_RTC | Banat | 45 56 20 | 22 39 40 | 45 56 20.1 | 22 39 40.3 | Moara din com. Ilia | SC CETATE DEVA SA - Moara din comuna Ilia, 054/ 214 225/Dir. Nita Adriana - Moara din Com. Ilia | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-12-11 | Yes | N/A |  |  |  | 40 | B | 40 | T6m+T6m | N/A | SVF | OK | ESROM | 2000-11-14 | 2000-12-30 | YesV | 2001-02-21 | Andrei | 2001-02-05 | 2001-02-28 |  |  |  |  | 2000-09-20 |  | 2000-11-07 | 2000-12-11 |  |  |  | 2001-02-01 | ICOM | CAMUSAT | 2001-01-26 | 2001-01-26 | 2001-02-06 | 2001-02-08 | 2001-02-12 |  | Yes | Alexandru Toma | 2001-04-04 | 2001-04-04 | 2001-04-04 | 2001-04-27 | 2001-05-31 | K 739 494 | 115 | 0 | 45 | K 739 494 | 225 | 0 | 45 | K 739 494 | 285 | 0 | 45 |  |  |  |  | N/A | 20 | 20 | 7/8" | 20 | 20 | 7/8" | 20 | 20 | 7/8" |  |  |  | 120 | ML 38 E 1+1 | Timisoara | MW | 205 | 0.3 | 43.5/0.3 | 18.5 | 38/18 | YES | 4x2/8 | 4U-1 |  |  |  | RBS | [9 empty] | 1 | YM145 | ILIA_RTC | 25 | 0.3 | 9.4/9.8/0.3 | 12 | 38/14 | [6 empty] | 51* | YRO | 2001-03-27 | 764 | 2001-03-27 | 2001-03-26 | 2001-04-04 | DINCA | OK | 2001-04-04 |  | 2001-05-03 | 2001-05-11 | 30N01 Ilia-Timisoara |  | 2001-03-31 | SORIN UNTARU | SORIN UNTARU | [32 empty] | 183 | Ilia | Timis | [6 empty] | 1 | 2 |  | 1 | 2
Phase_2 | CS | TM146 | GRIND | Road Lugoj-Deva(9) | YM145 Ilia_RTC | Banat | 45 54 09 | 22 30 57 | 45 54 43.2 | 22 31 04.6 | Extravilan Grind | Primaria Lapugiu de Jos - 092/ 523 001/Primar Pogan - 092/ 523 001 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | N/A |  |  |  |  | 0 | TN | 50 |  | N/A | SVF | OK | IMSAT | 2000-11-14 | 2001-03-12 | YesV | 2001-05-24 | Andrei | 2001-04-06 | [5 empty] | 2000-09-21 |  | 2000-11-07 | 2000-12-11 |  |  |  | 2001-03-15 | ICOM | VECTOR | 2001-03-13 | 2001-03-13 | 2001-03-19 | 2001-03-21 | 2001-03-23 |  | Yes | Alexandru Toma | 2001-04-04 | 2001-04-04 | 2001-04-04 | 2001-05-23 | 2001-05-31 | K 739 494 | 95 | 0 | 49 | K 739 494 | 240 | 0 | 49 | K 739 494 | 335 | 0 | 49 |  |  |  |  | N/A | 60 | 60 | 1 1/4" | 60 | 60 | 11/4" | 60 | 60 | 11/4" |  |  |  | 360 | ML 15 E 1+1 | Timisoara | MW | 75 | 0.6 | 47.5 | 65 | 15/84 | YES | 4x2/8 | 4U-1 |  |  |  | TMR 9000 | [9 empty] | 1 | TM145 | ILIA | 255 | 0.6 | 43.5 | 18.5 | 15/89 | [6 empty] | 43* | VECTOR | 2001-03-15 | 726 | 2001-03-19 | 2001-03-19 | 2001-03-23 | DINCA | OK | 2001-04-04 |  | 2001-05-21 | 2001-05-25 | 30N01 Ilia-Timisoara |  | 2001-03-31 | SORIN UNTARU | SORIN UNTARU | [32 empty] | 240 | Grind | Timis | [5 empty] | 1 | 1 | 2 | 1 | 1 | 2
Phase_2 | CS | TM147 | OHABA | Road Lugoj-Deva(9) | YM145 Ilia_RTC | Banat | 45 53 15 | 22 27 31 | 45 53 15.9 | 22 27 47.7 | Extravilan Ohaba | Primaria Lapugiu de Jos - 092/ 523 000/Primar Pogan - 092/ 523 000 | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | SVF | OK | ESROM | 2000-11-20 | 2001-05-09 | YesV | 2001-05-17 | Adi |  | 2001-05-23 |  |  |  |  | 2000-09-20 |  | 2000-11-29 | 2000-11-30 | [6 empty] | 2001-05-10 | 2001-05-10 |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 50 | 0 | 49 | K 739 494 | 260 | 0 | 49 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 70 | 70 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 140 | ML 23 E 1+0 | Timisoara | MW | 58 | 0.6 | 47.5/0.6 | 65 | [7 empty] | RBS | XC50145 | [9 empty] | TM146 | GRIND | 237 |  | 47.5 | 65 | [20 empty] | new04 |  | 2001-03-31 | SORIN UNTARU | SORIN UNTARU | [32 empty] | 240 | Ohaba | Timis | [7 empty] | 2 |  |  | 2
Phase_2 | CS | TM148 | COSEVITA_DRTV | Road Lugoj-Deva(9) | YM145 Ilia_RTC | Banat | 45 52 42.7 | 22 23 22.7 | 45 52 42.7 | 22 23 22.7 | DN 68A, Cosevita, statia DRTv | DRTv/ | 2202 | M | C+C+ | 2/2 | 2202 | [12 empty] | 0 | TE | 35 | 18m new tower |  | SVF | OK | SVF | 2001-07-09 | 2001-08-17 | in exec |  | Adi | [5 empty] | N/A | 2000-09-20 |  | 2000-10-31 | 2001-02-05 | [14 empty] | CTR |  |  |  |  | K 739 494 | 75 | 0 | 53.7 | K 739 494 | 250 | 0 | 53.7 | N/A | N/A | N/A | N/A |  |  |  |  | N/A | 76 | 76 | 1 1/4" | 72.5 | 72.5 | 1 1/4" | N/A | N/A | N/A |  |  |  | 297 | ML 23 E 1+0 | Timisoara | MW | 80 | 1.2 | 44/1.2 | 75 | [8 empty] | XC50145 | [9 empty] | TM147 | OHABA | 260 | 0.6 | 47.5/0.6 | 65 | [20 empty] | new04 |  | 2001-03-31 | SORIN UNTARU | SORIN UNTARU | [32 empty] | 317 | Cosevita | Timis | [7 empty] | 2 |  |  | 2
Phase_2 | CS | TM150 | FAGET | Road Lugoj-Deva(9) | TM071 Lugoj_RTC | Banat | 45 51 09 | 22 10 17 | 45 51 09 | 22 10 17 | Com. Faget | Primaria Faget- 056/ 320 641/D-na. Ing. Liliana Zamfirescu si d-na. Secretar Sita Valentin - com. Faget, 056/ 320 641, 056/ 320 494 | MUTAT | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  | 0 | B | 43.25 | T4.5m+T4.5m | N/A | SVF | OK | SVF | 2000-11-14 | 2000-12-13 | YesV | 2001-01-26 | Andrei | 2001-03-08 | [5 empty] | 2000-10-24 |  | 2000-11-15 | 2001-11-30 |  |  |  | 2000-12-14 | ICOM | SVF | 2000-12-14 | 2000-12-15 | 2000-12-19 | 2001-01-10 | 2001-01-13 |  | Yes |  | 2101 MOVED TO TM159 |  |  |  |  | K 739 494 | 85 | 0 | 46.15 | K 739 494 | 240 | 0 | 46.15 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 44 | 44 | 1 1/4" | 44 | 44 | 1 1/4" | N/A | N/A | N/A |  |  |  | 176 | ML 15 E 1+0 | Timisoara | MW | 224 |  | 44 | 55 | [7 empty] | N/A | XC50154 | [9 empty] | TM154 | LUGOJ-BORDER | 44 | 1.2 | 47.5/1.2 | 60 | [20 empty] | 30N01 Lugoj-Timisoara |  | 2001-02-26 | SORIN UNTARU | SORIN UNTARU | [32 empty] | 155 | Faget | Timis | [7 empty] | 2 |  |  | 2
Phase_2 | CS | TM152 | SACENI | Road Lugoj-Deva(9) | TM071 Lugoj_RTC | Banat | 45 46 04 | 22 02 34 | 45 46 06.7 | 22 02 39.4 | Loc.Traian Vuia | Primaria com. Traian Vuia - 054/ 325 632, 054/ 325 613/Primar Borboni Iosif, Com Traian Vuia nr18 | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  | 0 | TN | 50 |  | N/A | SVF | OK | SVF | 2000-11-14 | 2001-01-08 | YesV | 2001-02-06 | Andrei | 2001-01-09 | 2001-02-07 |  |  |  |  | 2000-09-20 |  | 2000-11-13 | 2000-12-11 | [6 empty] | 2001-01-26 |  |  |  |  | GATA-2101 |  |  | RBS 2101 |  |  |  |  | K 739 494 | 30 | 0 | 49.5 | K 739 494 | 225 | 0 | 49.5 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 70 | 70 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 140 | ML 15 E 1+0 | Timisoara | MW | 47 | 1.2 | 47/1.2 | 68 | [7 empty] | RBS | XC50154 | [9 empty] | TM150 | FAGET | 227 | 1.2 | 44/1.2 | [21 empty] | 30N01 Lugoj-Timisoara |  | 2/26/2001(Conectare locala) | SORIN UNTARU | SORIN UNTARU | [32 empty] | 172 | Saceni | Timis | [7 empty] | 2 |  |  | 2
Phase_2 | CS | TM153 | ANA LUGOJANA | Road Lugoj-Deva(9) | TM071 Lugoj_RTC | Banat | 45 43 05 | 21 59 42 | 45 43 12.8 | 21 59 47.1 | Extravilan Lugoj(Hanul Turistic) | Primaria/Primar Matescu, P-ta Victoriei, jud. Timis, tel 056/350393 | 2101 | M | C+ | 2 | 2101 | [12 empty] | 0 | TN | 50 |  | N/A | SVF | OK | SVF | 2001-04-09 | 2001-04-30 | YesV | 2001-03-28 | Adi | 2001-05-07 | 2001-05-30 |  |  |  |  | 2000-09-22 |  | 2001-03-14 | 2001-04-18 | [6 empty] | 2001-04-20 | 2001-04-20 |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 20 | 0 | 49.5 | K 739 494 | 250 | #N/A | 49.5 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 65 | 65 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 130 | ML 23 E 1+0 | Timisoara | MW | 236 |  | 47.7 | 63 | [7 empty] | RBS | XC50154 | [9 empty] | TM154 | LUGOJ-BORDER | 56 |  | 47.5 | 70 | [20 empty] | 30N01 Lugoj-Timisoara |  | 2/26/2001(Conectare locala) | SORIN UNTARU | SORIN UNTARU | [32 empty] | 202 | Lugoj | Timis | [7 empty] | 2 |  |  | 2
Phase_2 | CS | TM154 | LUGOJ-BORDER | Road Lugoj-Deva(9) | TM071 Lugoj_RTC | Banat | 45 42 07.8 | 21 55 27.4 | 45 42 07.8 | 21 55 27.4 | Extravilan Lugoj | Stoita Constantin - Str. Cotu Mic bl.11, ap.1, parter, Lugoj, 056/ 358 522/Stoita Constantin - Str. Cotu Mic bl.11, ap.1, parter, Lugoj, 056/ 358 522 | 2101 | M | C+ | 2 | 2101 | [6 empty] | 2000-12-11 | N/A | N/A |  |  |  | 0 | TN | 50 |  | N/A | SVF | OK | SVF | 2000-11-13 | 2000-12-22 | YesV | 2001-02-06 | Andrei | 2001-01-11 | 2001-02-07 |  |  |  |  | 2000-09-22 |  | 2000-11-07 | 2000-11-27 |  |  |  | 2000-12-15 | ICOM | SVF | 2000-12-14 | 2000-12-15 | 2000-12-19 | 2001-01-11 | 2001-01-15 |  | Yes | Constantin Mihai | 2001-03-25 | 2001-03-25 | 2001-03-25 | 2001-04-19 | 2001-04-23 | K 739 494 | 25 | 0 | 49.5 | K 739 494 | 275 | 0 | 49.5 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 70 | 70 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 140 | ML 23 E 1+0 | Timisoara | MW | 258 | 0.6 | 47.5 | 70 | 23/56 |  | 4x2/8 | 4U-1 |  |  |  | RBS | XC50154 | [8 empty] | 1 | TM156 | TINERETII | 78 | 0.6 | 19 | 19 | 23/58 | [6 empty] | 19* | SVF | 2001-01-24 | 529 | 2001-01-11 | 2001-01-11 | 2001-03-22 | VLAD | OK | 2001-03-26 |  |  |  | 30N01 Lugoj-Timisoara |  | 2001-02-26 | SORIN UNTARU | SORIN UNTARU | [32 empty] | 135 | Lugoj | Timis | [7 empty] | 2 |  |  | 2
Phase_2 | TM | TM155 | BAILE HERCULANE_RTC | Road Herculane-Caransebes(9+1) | TM155 Baile Herculane_RTC | Banat | 44 52 49.5 | 22 24 44.3 | 44 52 49.5 | 22 24 44.3 | RTC Baile Herculane | Romtelecom/ | N/A | N/A | N/A | N/A | N/A | [12 empty] | 12 | B | 16.2 | T3m | Room | SVF | OK | SVF | 2000-10-26 | 2000-11-10 | YesV | 2000-11-17 | Andrei | 2000-11-28 | 2000-11-22 |  |  |  | N/A | 2000-09-24 |  | 2000-10-05 | 2000-10-24 | [6 empty] | N/A | N/A |  |  |  |  | Yes |  | RBS 2101 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Timisoara | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | [12 empty] | 56/ |  |  | BSC31 | BSC TIMISOARA | N/A | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A |  |  |  | SORIN UNTARU | N/A | [32 empty] | 161 | Baile Herculane | Caras Severin | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | TM156 | TINERETII | Lugoj(5) | TM071 Lugoj_RTC | Oltenia | 45 41 38.0 | 21 53 38.9 | 45 41 33 | 21 53 48 | Str.Cotul Mic,Bl.13 | Asociatie de locatari/ADI,Bl.13,ap.13-092 285 303 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | Yes | N/A |  |  |  |  | B | 15 | T6m+T6m+T6m | N/A | SVF | OK | SVF | 2000-11-20 | 2000-12-05 | YesV | 2000-12-07 | Andrei | 2001-01-09 | 2000-12-13 |  |  |  |  | 2000-10-11 |  | 2000-11-15 | 2000-11-29 |  |  |  | 2000-12-04 | ICOM | SVF | 2000-12-04 | 2000-12-04 | 2000-12-04 | 2000-12-06 | 2000-12-08 |  | Yes | Theo Radoi | 2001-03-14 | 2001-03-14 | 2001-03-14 | 2001-04-17 | 2001-05-15 | K 739 494 | 85 | 0 | 20.2 | K 739 494 | 185 | 0 | 20.2 | K 739 494 | 305 | 0 | 20.2 |  |  |  |  | N/A | 18 | 18 | 7/8" | 19 | 19 | 7/8" | 21 | 21 | 7/8" |  |  |  | 120 | ML 23 E 1+1 | Timisoara | MW | 129 | 0.6 | 19 | 16 | 23/58 | YES | 4x2/8 | 4U-1 | 4U-1 |  |  | TMR 9000 | [9 empty] | 1 | TM071 | LUGOJ_RTC | 309 | 0.6 |  |  | 23/56 | [6 empty] | 19* | SVF | 2001-01-24 | 530 | 2001-01-26 | 2001-01-30 | 2001-02-08 | VLAD | OK | 2001-03-14 |  |  |  | 30N03 Lugoj-Timisoara |  | OK | SORIN UNTARU | SORIN UNTARU | [32 empty] | 119 | Lugoj | Timis | [6 empty] | 1 | 2 |  | 1 | 2
Phase_2 | CS | TM157 | ST.O.IOSIF | Lugoj(5) | TM071 Lugoj_RTC | Oltenia | 45 41 06.3 | 21 53 39.6 | 45 41 06.3 | 21 53 39.6 | Str.St.O.Iosif, nr.4 | S.C.URBAN S.A. str. Timisoriii bl.151/S.C.URBAN S.A.-056 356 020 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [6 empty] | 2000-12-11 | Yes | N/A |  |  |  | 14.25 | B | 14.25 | T4m+T4m+T4m | N/A | SVF | OK | SVF | 2000-11-14 | 2000-12-05 | YesV | 2000-12-07 | Andrei | 2001-07-06 | 2000-12-13 |  |  |  |  | 2000-10-11 |  | 2000-11-07 | 2000-11-23 |  |  |  | 2000-12-04 | ICOM | SVF | 2000-12-04 | 2000-12-04 | 2000-12-04 | 2000-12-06 | 2000-12-08 |  | Yes | Theo Radoi | 2001-03-14 | 2001-03-14 | 2001-03-14 | 2001-05-17 | 2001-05-25 | K 739 494 | 70 | 0 | 18.25 | K 739 494 | 190 | 0 | 18.25 | K 739 494 | 300 | 0 | 18.25 |  |  |  |  | N/A | 27 | 27 | 7/8" | 18 | 18 | 7/8" | 13 | 13 | 7/8" |  |  |  | 116 | ML 23 E 1+0 | Timisoara | MW | 359 | 0.6 | 16.75 | 25 | 23/56 |  | 4x2/8 | 4U-1 |  |  |  | RBS | XC50071 | [8 empty] | 1 | TM156 | TINERETII | 179 | 0.6 | 17.5 | 17 | 23/58 | [6 empty] | 19* | SVF | 2001-01-24 | 531 | 2001-01-26 | 2001-01-30 | 2001-02-06 | VLAD | OK | 2001-03-14 | PENDING ITEMS | 2001-07-12 |  | 30N02 Lugoj-Timisoara |  | 2001-02-26 | SORIN UNTARU | SORIN UNTARU | [32 empty] | 120 | Lugoj | Timis | [7 empty] | 2 |  |  | 2
Phase_2 | CS | TM158 | CRISTUR | Road Hunedoara-Santuhalm(1) | TM112 Nucet_RTC | Oltenia | 45 49 28 | 22 56 29 | 45 49 26.2 | 22 56 36.4 | Com. Cristur | David Romulus com. Cristur,Str. Principala nr.58-tel 054/671617/David Romulus com. Cristur,Str. Principala nr.58-tel 054/671617 | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | SVF | OK | ALMO | 2000-12-21 | 2001-05-14 | YesV | 2001-06-19 | Adi |  | 2001-06-22 |  |  |  |  | 2000-10-20 |  | 2000-12-18 | 2001-01-19 | [6 empty] | 2001-05-15 | 2001-05-15 |  |  |  | GATA-2101 |  |  | RBS 2101 |  |  |  |  | K 739 494 | 20 | 0 | 49.5 | K 739 494 | 215 | 0 | 49.5 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 70 | 70 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 140 | ML 15 E 1+0 | Timisoara | MW | 311 |  | 47 | 67 | [7 empty] | RBS | XC50112 | [9 empty] | TM112 | NUCET | 131 | 0.6 | 62/0.6 | 69 | [20 empty] | 30N02 Nucet-Timisoara |  | 2001-02-26 | Marius LUNGU | SORIN UNTARU | [32 empty] | 211 | Cristur | Hunedoara | [7 empty] | 2 |  |  | 2
Phase_2 | CS | TM159 | PINILOR | Hunedoara(3) | TM112 Nucet_RTC | Oltenia | 45 45 11 | 22 55 06 | 45 45 06 | 22 55 19 | Str. Pinilor, bl. 38, nr.2 | Asociatie de locatari/Guzgan Grigore, str. Pinilor, bl. 38, nr2, Hunedoarea, tel. 054/712492 | 2101 | M | C+ | 2 | 2101 | [7 empty] | Yes | N/A |  |  |  | 35.7 | B | 35.7 | T4.5m+T6m | N/A | SVF | OK | ALMO | 2000-12-11 | 2001-01-10 | YesV | 2001-02-22 | Marin | 2001-02-02 | 2001-02-28 |  |  |  |  | 2000-10-18 |  | 2000-11-19 | 2001-01-03 |  |  |  | 2001-04-04 | ICOM | SVF | 2001-01-26 | 2001-01-26 | 2001-04-05 | 2001-04-09 | 2001-04-11 |  | Yes | Alexandru Toma | 2001-05-15 | 2001-05-15 | 2001-05-15 | 2001-06-05 | 2001-06-19 | K 739 494 | 0 | 0 | 37.2 | K 739 494 | 240 | 0 | 35.8 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 31 | 31 | 7/8" | 12 | 12 | 7/8" | N/A | N/A | N/A |  |  |  | 86 | ML 15 E 1+0 | Timisoara | MW | 341 | 1.2 | 34 | 11 | 15/89 |  | 4x2/8 | 4U-1 |  |  |  | RBS | [9 empty] | 1 | TM112 | NUCET | 161.4 | 1.2 | 50/1.2 | 57 | 15/84 | [6 empty] | 54* | SVF | 2001-04-04 | 828 | 2001-04-05 | 2001-04-06 | 2001-04-10 | DINCA | OK | 2001-05-15 | PENDING ITEMS |  |  | 30N01 Nucet Timisoara |  | 2001-02-26 | Mona ARDELEANU | Cosmorom | [32 empty] | 305 | Hunedoara | Hunedoara | [7 empty] | 2 |  | 1 | 2
Phase_2 | CS | TM160 | DACIA | Hunedoara(3) | TM112 Nucet_RTC | Oltenia | 45 46 15 | 22 54 45 | 45 46 10 | 22 55 00 | DBd. Dacia nr.24, bl. 38, sc. C,D | Asociatia de propietari a blocului 38, bd. Dacia nr 24/Sulu Virgil, Bd. Dacia nr. 24, bl.38, tel. 054/742116, 093/768688 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | YES | N/A |  |  |  | 26.6 | B | 30.05 | S6m+S6m |  | SVF | OK | SETRACO | 2001-02-13 | 2001-03-03 | YesV | 2001-03-22 | Marin | 2001-03-06 | 2001-03-29 |  |  |  |  | 2000-11-23 |  | 2001-01-25 | 2001-02-28 |  |  |  | 2001-03-26 | ICOM | SVF | 2001-03-13 | 2001-03-13 | 2001-03-27 | 2001-03-27 | 2001-04-02 |  | Yes | Alexandru Toma | 2001-05-15 | 2001-05-15 | 2001-05-15 | 2001-06-06 | 2001-06-19 | K 739 494 | 355 | 0 | 34 | K 739 494 | 155 | 0 | 33.8 | K 739 494 | 255 | 0 | 34 |  |  |  |  | N/A | 22 | 22 | 7/8" | 22 | 22 | 7/8" | 22 | 22 | 7/8" |  |  |  | 132 | ML 23 E 1+0 | Timisoara | MW | 166 | 0.6 | 32 | 21 | 23/56 |  | 4x2/8 | 2U-3 |  |  |  | RBS | XC50112 | [8 empty] | 1 | TM159 | PINILOR | 346 | 0.6 | 33.5 | 29 | 23/58 | [6 empty] | 59* | SVF | 2001-04-18 | 855 | 2001-04-18 | 2001-04-18 | 2001-04-26 | DINCA | OK | 2001-05-15 | PENDING ITEMS |  |  | 30N01 Nucet Timisoara |  | 2001-02-26 | Marius LUNGU | Cosmorom | [32 empty] | 238 | Hunedoara | Hunedoara | [7 empty] | 2 |  |  | 2
Phase_2 | CS | TM161 | CENTRAL | Hunedoara(3) | TM112 Nucet_RTC | Oltenia | 45 45 35 | 22 54 30 | 45 45 29 | 22 54 30.8 | Bl. Dacia, nr.13, bl. A1-3, sc.B | Asociatia de locatari nr.8, B-ul Corvin nr.4 tel. 054/671617/Tutelea Nicolae, tel. 054/714281 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | YES |  |  |  |  | 30 | B | 30 | T4,5m+T4,5m | N/A | SVF | OK | SETRACO | 2001-02-13 | 2001-03-03 | YesV | 2001-03-22 | Marin | 2001-03-06 | 2001-03-29 |  |  |  |  | 2000-07-05 |  | 2000-12-22 | 2001-02-28 |  |  |  | 2001-03-26 | ICOM | SVF | 2001-03-13 | 2001-03-13 | 2001-03-27 | 2001-03-27 | 2001-04-02 |  | Yes | Alexandru Toma | 2001-05-15 | 2001-05-15 | 2001-05-15 | 2001-05-25 | 2001-06-19 | K 739 494 | 15 | 0 | 34 | K 739 494 | 135 | 0 | 33.8 | K 739 494 | 255 | 0 | 35.5 |  |  |  |  | N/A | 15 | 15 | 7/8" | 15 | 15 | 7/8" | 21 | 21 | 7/8" |  |  |  | 102 | ML 23 E 1+0 | Timisoara | MW | 130 | 0.6 | 32 | 15 | 23/56 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [9 empty] | 1 | TM159 | PINILOR | 310 | 0.6 | 35 | 29 | 23/58 | [6 empty] | 59* | SVF | 2001-04-18 | 856 | 2001-04-18 | 2001-04-18 | 2001-04-26 | DINCA | OK | 2001-05-15 | PENDING ITEMS |  |  | 30N01 Nucet Timisoara |  | 2001-02-26 | Marius LUNGU | CATALINA CIOCAN | [32 empty] | 240 | Hunedoara | Hunedoara | [7 empty] | 2 |  |  | 2
Phase_2 | CS | TM162 | URICANI_RTC | Bazinul Petrosani(20) | TM162 Uricani_RTC | Banat | 45 19 50.1 | 23 07 15.3 | 45 19 50.1 | 23 07 15.3 | Oficiul Comercial Romtelecom Uricani, jud. Hunedoara | Romtelecom/Gheorghe Emilian - 094/ 876 059 | 2202 | M | C+C+ | 2/2 | 2202 | [12 empty] | 5 | B | 15 | C4m+C4m | Room | SVF | OK | ALMO | 2000-12-21 | 2001-02-28 | YesV | 2001-03-28 | Marin | 2001-03-15 | 2001-05-04 |  |  |  | N/A | OK |  | 2000-12-08 | 2001-01-19 |  |  |  | 2001-03-01 | ICOM | TRY | 2001-02-21 | 2001-02-21 | 2001-03-02 | 2001-03-04 | 2001-03-06 |  | Yes |  | 2Mb/s |  |  |  |  | K 739 494 | 65 | 0 | 19.5 | K 739 494 | 240 | 0 | 19.5 | N/A | N/A | N/A | N/A |  |  |  |  | N/A | 30 | 30 | 7/8" | 39 | 39 | 7/8" | N/A | N/A | N/A |  |  |  | 138 | N/A | Timisoara | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | [12 empty] | 26/outdoor |  |  | BSC31 | BSC TIMISOARA |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A |  |  | Negatie RTC(nu este FO)/1Martie | SORIN UNTARU | SORIN UNTARU | [32 empty] | 742 | Uricani | Hunedoara | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | TM163 | LUPENI 1 | Bazinul Petrosani(20) | TM170 Petrosani_RTC | Banat | 45 20 58 | 23 11 59 | 45 20 49.8 | 23 11 43.3 | B-ul Pacii, nr. 9, Localitatea Lupeni, jud. Hunedoara | Asociatia de locatari a bl.4 sc.3 din B-ul Pacii nr. 9/Rusu Dorina , tel. 054/561042 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [12 empty] | 28 | B | 28 | T4m+T4m |  | SVF | OK | SVF | 2001-03-08 | 2001-03-27 | YesV | 2001-04-20 | Adi | 2001-04-20 | 2001-04-25 |  |  |  | 2000-11-24 | 2000-11-09 |  | 2001-02-28 | 2001-03-14 |  |  |  | 2001-03-27 | ICOM | SVF | 2001-03-27 | 2001-03-27 | 2001-03-27 | 2001-04-02 | 2001-04-04 |  | Yes |  | PARANG HUB |  |  |  |  | K 739 494 | 5 | 0 | 31.1 | K 739 494 | 125 | 0 | 31.2 | K 739 494 | 245 | 0 | 31.2 |  |  |  |  | N/A | 13 | 13 | 7/8" | 17 | 17 | 7/8" | 13 | 13 | 7/8" |  |  |  | 86 | ML 38 E 1+0 | Timisoara | MW | 43 |  | 30.1 | 16 | [7 empty] | RBS | [10 empty] | TM164 | LUPENI_2 | 223 | [26 empty] | Marius LUNGU | Cosmorom | [32 empty] | 909 | Hunedoara | Hunedoara | [7 empty] | 2 |  |  | 2
Phase_2 | CS | TM164 | LUPENI_2 | Bazinul Petrosani(20) | TM170 Petrosani_RTC | Banat | 45 21 30 | 23 12 42 | 4521 33 | 23 12 40 | Put IM Lupeni | Put IM Lupeni/D-nul. Pavelonescu | 2102 | M | C+C+C+ | 2/2/2 | N/A | [12 empty] | 15 | B | 15 | S4m+S4m+T4m | N/A | SVF |  | SVF | 2001-08-05 | 2001-08-30 | CTR |  | Adi | [6 empty] | 2000-12-12 |  | 2000-12-14 | [15 empty] | CTR |  |  |  |  | K 739 494 | 115 | 0 | 20.3 | K 739 494 | 235 | 0 | 20.3 | K 739 494 | 355 | 0 | 20.3 |  |  |  |  | N/A | 20 | 20 | 7/8" | 20 | 20 | 7/8" | 16 | 16 | 7/8" |  |  |  | 112 | ML 15 E 1+0 | Timisoara | MW | 82 | [10 empty] | RBS | [10 empty] | TM174 | PARANG_HUB | [27 empty] | SORIN UNTARU | SORIN UNTARU | [32 empty] | 698 | Lupeni | Hunedoara | [7 empty] | 2 |  |  | 2
Phase_2 | CS | TM165 | VULCAN_1 | Bazinul Petrosani(20) | TM170 Petrosani_RTC | Banat | 45 22 26 | 23 17 13 | 45 22 27 | 23 17 18 | Str. Dorobanti, Bl. 62, sc.3 | Asociatia de locatari/D-nul. Popescu - str. Dorobanti, | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | Yes | N/A |  |  |  | 15 | B | 15 | T-6m+T-6m | N/A | SVF | OK | SVF | 2001-02-13 | 2001-02-14 | YesV | 2001-03-14 | Marin | 2001-02-26 | 2001-03-19 |  |  |  |  | 2000-11-01 |  | 2000-12-14 | 2001-01-25 |  |  |  | 2001-02-15 | ICOM | TRY | 2001-02-15 | 2001-02-15 | 2001-02-15 | 2001-02-16 | 2001-02-23 |  | Yes |  | PARANG HUB |  |  |  |  | K 739 494 | 115 | 0 | 20.3 | K 739 494 | 235 | 0 | 20.3 | K 739 494 | 355 | 0 | 20.3 |  |  |  |  | N/A | 20 | 20 | 7/8" | 20 | 20 | 7/8" | 16 | 16 | 7/8" |  |  |  | 112 | ML 38 E 1+0 | Timisoara | MW | 71 |  | 17.8 | 12 | [7 empty] | RBS | [10 empty] | TM166 | VULCAN_2 | 251 |  | 31.1 | 20 | [23 empty] | SORIN UNTARU | SORIN UNTARU | [32 empty] | 603 | Vulcan | Hunedoara | [7 empty] | 2 |  |  | 2
Phase_2 | CS | TM166 | VULCAN_2 | Bazinul Petrosani(20) | TM170 Petrosani_RTC | Banat | 45 22 37 | 23 17 59 | 45 22 37.2 | 23 17 59.4 | Bd. N. Titulescu nr.67, Bl. D10, Sc. 1 | Asociatie de locatari/Petcu Sorin,Str. N. Titulescu, Bl. D10, Sc.1,ap. 13, jud. Hunedoara | 2101 | M | C+ | 2 | 2101 | [7 empty] | Yes | N/A |  |  |  | 25 | B | 25 | T4.5m+T3m | N/A | SVF | OK | SVF | 2001-02-13 | 2001-02-14 | YesV | 2001-02-22 | Marin | 2001-02-26 | 2001-02-28 |  |  |  |  | 2000-11-09 |  | 2000-12-18 | 2001-02-12 | [6 empty] | 2001-02-15 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 80 | 0 | 31.8 | K 739 494 | 270 | 0 | 30 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 20 | 20 | 7/8" | 20 | 20 | 7/8" | N/A | N/A | N/A |  |  |  | 80 | ML 15 E 1+0 | Timisoara | MW | 87 |  | 30 | 20 | [7 empty] | RBS | [10 empty] | TM174 | PARANG_HUB | [27 empty] | SORIN UNTARU | SORIN UNTARU | [32 empty] | 593 | Hunedoara | Hunedoara | [7 empty] | 2 |  |  | 2
Phase_2 | CS | TM167 | ANINOASA INTERSECTIE | Bazinul Petrosani(20) | TM170 Petrosani_RTC | Banat | 45 22 34 | 23 20 07 | 45 22 26.1 | 23 21 52.3 | Loc. Aninoasa, jud. Hunedoara | Miroi Traian, str. Danutoni, nr350, Aninoasa/Miroi Traian, str. Danutoni, nr350, Aninoasa | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | N/A | N/A |  |  |  | 0 | TN | 30 |  |  | SVF | OK | SVF | 2001-04-09 | 2001-04-29 | YesV | 2001-05-16 | Adi |  | 2001-05-23 |  |  |  |  | 2001-02-07 |  | 2001-03-27 | 2001-04-10 |  |  |  | 2001-05-07 | ICOM | SVF | 2001-05-03 | 2001-05-03 | 2001-05-08 | 2001-05-10 | 2001-05-14 |  |  |  | PARANG HUB |  |  |  |  | K 739 494 | 25 | 0 | 29.5 | K 739 494 | 145 | #N/A | 29.5 | K 739 494 | 270 | 0 | 29.5 |  |  |  |  | N/A | 38 | 38 | 7/8" | 38 | 38 | 7/8" | 38 | 38 | 7/8" |  |  |  | 228 | ML 15 E 1+0 | Timisoara | MW | 80 |  | 27.8 | 37 | [7 empty] | RBS | [10 empty] | TM174 | PARANG_HUB | [27 empty] | SORIN UNTARU | Cosmorom | [32 empty] | 605 | Aninoasa | Hunedoara | [7 empty] | 2 |  |  | 2
Phase_2 | CS | TM170 | PETROSANI_RTC | Bazinul Petrosani(20) | TM170 Petrosani_RTC | Banat | 45 25 4.7 | 23 22 17.8 | 45 25 4.7 | 23 22 17.8 | Str. 1 Decembrie, nr. 86 | Romtelecom/Dl. Mamara Vasile, tel. 054/204611 | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [7 empty] | N/A | N/A |  |  |  | 7.4 | B | 19 | new pilonet 9m | Room | SVF | OK | TEHNOROB | 2000-12-21 | 2001-01-25 | YesV | 2001-03-22 | Marin | 2001-01-29 | 2001-03-29 |  |  |  | N/A | 2000-11-20 |  | 2000-12-08 | 2001-01-19 |  |  |  | 2001-02-01 | ICOM | CAMUSAT | 2001-01-30 | 2001-01-30 | 2001-02-06 | 2001-02-08 | 2001-02-12 |  | Yes | Alexandru Toma | 2001-03-31 | 2001-03-31 | 2001-03-31 | 2001-04-10 | 2001-04-23 | K 739 494 | 120 | 0 | 29 | K 739 494 | 220 | 0 | 29 | K 739 494 | 340 | 0 | 29 |  |  |  |  | N/A | 33 | 33 | 7/8" | 33 | 33 | 7/8" | 33 | 33 | 7/8" |  |  |  | 198 | N/A | Timisoara | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | [5 empty] | 50170 | [9 empty] | BSC31 | BSC TIMISOARA | N/A | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | 30N02 Petrosani-Timisoara |  | 2001-03-26 | SORIN UNTARU | SORIN UNTARU | [32 empty] | 599 | Petrosani | Hunedoara | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | TM171 | INTRARE PETRILA | Bazinul Petrosani(20) | TM170 Petrosani_RTC | Banat | 45 26 32 | 23 22 02 |  |  |  |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [17 empty] | SVF |  | ROMPSAR | 2001-07-10 | 2001-08-15 | CTR |  | Adi | [24 empty] | CTR | [13 empty] | 0 | 0 | 0 | [17 empty] | 0 | ML 15 E 1+0 | Timisoara | MW | [11 empty] | RBS | [10 empty] | TM174 | PARANG_HUB | [27 empty] | SORIN UNTARU | SORIN UNTARU | [32 empty] | 652 | [9 empty] | 2 |  |  | 2
Phase_2 | CS | TM172 | PETRILA | Bazinul Petrosani(20) | TM170 Petrosani_RTC | Banat | 45 26 45.3 | 23 22 54.5 | 45 26 45.3 | 23 22 54.5 | Str. Republicii, nr. 55, sc.5 | Asociatia de locatari din str. Republicii, nr. 55, sc.5, Petrila , jud. Hunedoara/D-na Viorica Amelian | 2101 | M | C+ | 2 | 2101 | [7 empty] | YES |  |  |  |  | 15 | B | 15 | T-6m | N/A | SVF | OK | VECTOR | 2001-02-26 | 2001-03-10 | YesV | 2001-03-27 | Marin | 2001-04-20 | 2001-03-29 |  |  |  |  | 2000-11-01 |  | 2000-12-14 | 2001-02-28 | [6 empty] | 2001-03-13 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 45 | 0 | 20.2 | K 739 494 | 255 | 0 | 20.3 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 12 | 12 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 24 |  | Timisoara | MW | 250 |  | 17 | 10 | [7 empty] | RBS | [10 empty] | TM171 | INTRARE PETRILA | [27 empty] | SORIN UNTARU | SORIN UNTARU | [32 empty] | 679 | Petrila | Hunedoara | [7 empty] | 2 |  |  | 2
Phase_2 | CSH | TM173 | PARANG | Bazinul Petrosani(20) | TM170 Petrosani_RTC | Banat | [28 empty] | SVF* |  | ROMPSAR* |  |  |  |  | Adi | [24 empty] | PARANG HUB | [33 empty] | 0 |  | Timisoara | MW | [22 empty] | TM170 | PETROSANI_RTC | [26 empty] | 0 | SORIN UNTARU | SORIN UNTARU | [42 empty] | Site Near=Insertion Point
Phase_2 | TM | TM174 | PARANG_HUB | Bazinul Petrosani(20) | TM170 Petrosani_RTC | Banat | 45 23 03.4 | 23 28 38.9 | 45 23 05.6 | 23 28 34 | Petrosani, Vf. Parang |  | N/A | N/A | N/A | N/A | N/A | [12 empty] | N/A | TE | 25 |  | N/A | SVF | OK | FIBEC | 2001-08-05 | 2001-09-10 | DL |  | Adi | [5 empty] | 2001-02-06 | [18 empty] | PARANG HUB |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | ML 15 E 1+1 | Timisoara | MW | [22 empty] | TM170 | PETROSANI_RTC | 115 | 1.2 | 23.6/1.2 | 26 | [23 empty] | SORIN UNTARU | N/A | [42 empty] | 2 |  | 1 | 2
Phase_2 | CS | TM175 | MICALACA | Arad(9+1) | TM025 Arad-DRTv_RTC | Banat | 46 10 16.9 | 21 21 13.6 | 46 10 16.9 | 21 21 13.6 | Str. Voinicilor nr.39 bl.510 | Asociatie de locatari/Pres. Asociatie d-na. Sofica Sofron - ap.8 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | YES |  |  |  |  | 20.7 | B | 23.55 | T4.5m+T4.5m | N/A | TRANSDAT | OK | ARGOS | 2001-01-18 | 2001-02-25 | YesV | 2001-03-27 | Marin | 2001-03-15 | 2001-03-29 |  |  |  |  | 2000-11-24 |  | 2000-12-18 | 2001-01-19 |  |  |  | 2001-02-28 | ICOM | Interactive | 2001-02-28 | 2001-02-28 | 2001-03-01 | 2001-03-02 | 2001-03-06 |  | Yes | Theo Radoi | 2001-03-12 | 2001-03-16 | 2001-03-16 | 2001-04-24 | 2001-05-03 | K 739 494 | 15 | 0 | 26.7 | K 739 494 | 135 | 0 | 26.7 | K 739 494 | 256 | 0 | 26.6 |  |  |  |  | N/A | 27 | 27 | 7/8" | 28 | 28 | 7/8" | 17.5 | 17.5 | 7/8" |  |  |  | 145 | ML 38 E 1+0 | Timisoara | MW | 336 | 0.3 | 26.2 | 27 | 38/14 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [9 empty] | 1 | TM026 | CALEA RADNEI | 156 | 0.3 | 33/0.3 | 30 | 38/18 | [6 empty] | 33* | INTERACTIVE | 2001-02-28 | 680 | 2001-03-01 | 2001-03-01 | 2001-03-05 | DINCA | OK | 2001-03-16 |  | 2001-07-12 |  | 30N01 Arad-Timisoara |  | 2001-03-05 | SORIN UNTARU | SORIN UNTARU | [32 empty] | 112 | Arad | Arad | [7 empty] | 2 |  |  | 2
Phase_2 | CS | TM176 | CALEA TIMISOAREI | Arad(9+1) | TM025 Arad-DRTv_RTC | Banat | 46 08 14.3 | 21 19 11.8 | 46 08 14.3 | 21 19 11.8 | Str. Calea Timisoarei bl.212 | SC SUPERSEM ARAS SA/Dir. D-na. Adina Opret - 094/ 791 094, 057/ 287 861 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | YES |  |  |  |  | 14.75 | B | 14.75 | 12m new pylonet | N/A | TRANSDAT | OK | ARGOS | 2001-01-18 | 2001-02-25 | YesV | 2001-03-27 | Marin | 2001-03-15 | 2001-03-29 |  |  |  |  | 2000-11-24 |  | 2000-12-04 | 2001-02-28 |  |  |  | 2001-02-28 | ICOM | Interactive | 2001-02-28 | 2001-02-28 | 2001-03-01 | 2001-03-02 | 2001-03-06 |  | Yes | Alexandru Toma | 2001-03-16 | 2001-03-16 | 2001-03-16 | 2001-04-24 | 2001-05-15 | K 739 494 | 0 | 0 | 25.35 | K 739 494 | 120 | 0 | 25.35 | K 739 494 | 240 | 0 | 25.35 |  |  |  |  | N/A | 18.5 | 19 | 7/8" | 19 | 19 | 7/8" | 19 | 19 | 7/8" |  |  |  | 114 | ML 23 E 1+0 | Timisoara | MW | 324 | 0.6 | 24.65/0.6 | 18.5 | 23/58 |  | 4x2/8 | 2U-3 |  |  |  | RBS | [9 empty] | 1 | TM029 | FALEZA SUD | 144 | 0.6 | 22 | 20 | 23/56 | [6 empty] | 33* | INTERACTIVE | 2001-02-28 | 679 | 2001-03-01 | 2001-03-01 | 2001-03-05 | DINCA | OK | 2001-03-16 |  | 2001-04-11 | 2001-04-17 | 30N04 Arad-Dr.Taberei |  | OK | SORIN UNTARU | SORIN UNTARU | [32 empty] | 116 | Arad | Arad | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | TM177 | HIDISELU | Road Oradea-Brad(11+1) | TM090 Beius_RTC | Transilvania | 46 55 57.19 | 22 03 01.01 | 46 56 05.9 | 24 03 08.9 | Sat Hidiselu De Sus , jud. Bihor | Primaria Com. Hidiselu De Sus/Primar Bucureanu Petre, tel. 094/772693, secretar Pasca Florea | 2102 | M | C+C+C+ | 2/2/2 | N/A | [12 empty] | 0 | TN | 50m/6mp |  | N/A | TRANSDAT | OK | VECTOR | 2001-03-26 | 2001-06-08 | YesV | 2001-07-03 | Marin | 2001-07-06 | 2001-06-12 |  |  |  |  | 2000-11-22 |  | 2001-04-18 | OK |  |  |  | 2001-06-14 | ICOM | TRY | 2001-06-13 | 2001-06-13 | 2001-06-15 | 2001-06-19 | 2001-06-29 | VLAD | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 100 | 0 | 48.5 | K 739 494 | 190 | 0 | 48.5 | K 739 494 | 320 | 0 | 48.5 |  |  |  |  | N/A | 61 | 61 | 1 1/4" | 60 | 60 | 1 1/4" | 60 | 60 | 1 1/4" |  |  |  | 362 | ML 23 E 1+0 | Oradea | MW | 126 |  | 47.5 | 60 | 23/58 |  | 4X2/8 | 2U-3 |  |  |  | RBS | [10 empty] | TM178 | DRAGESTI | 306 |  | 47 | 58.5 | 23/56 | [6 empty] | 75* | TRYLON | 2001-06-14 | 1003 | 2001-07-07 | [8 empty] | 30N02 Beius-Oradea |  | 2001-06-30 | Cristian CROITOR | Cosmorom | [32 empty] | 206 | Hidiselul de Sus | Bihor | [7 empty] | 2 |  |  | 2
Phase_2 | CS | TM178 | DRAGESTI | Road Oradea-Brad(11+1) | TM090 Beius_RTC | Transilvania | 46 53 56.28 | 22 07 26.09 | 46 53 56.3 | 22 07 26.1 | Comuna Dragesti, sat Dicanesti | Primaria Comunei Dragesti, nr. 65, loc. Dragesti/Primar Judea Moise, com. Dragesti, tel. 096/556650 | 2101 | M | C+ | 2 | 2101 | [6 empty] | N/A | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | TRANSDAT | OK | SVF | 2001-03-26 | 2001-04-27 | YesV | 2001-05-28 | Marin | 2001-07-06 | 2001-05-30 |  |  |  |  | 2001-05-07 |  | 2001-02-28 | 2001-03-14 |  |  |  | 2001-05-24 | ICOM | DIEKAT | 2001-05-03 | 2001-05-03 | 2001-05-28 | 2001-05-29 | 2001-05-31 | VLAD | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 150 | 0 | 48.45 | K 739 494 | 340 | 0 | 48.45 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 61 | 61 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 122 | ML 15 E 1+0 | Oradea | MW | [7 empty] | 2U-3 |  |  |  | RBS | [10 empty] | TM180 | SAUCANI | 335 | 1.2 | 41.5 | 52 | [20 empty] | 30N02 Beius-Oradea |  | 2001-06-30 | Cristi Croitor | Cosmorom | [32 empty] | 286 | Dragesti | Bihor | [7 empty] | missing |  |  | 2
Phase_2 | CS | TM179 | SAMBATA | Road Oradea-Brad(11+1) | TM090 Beius_RTC | Transilvania | 46 48 23.8 | 22 11 34.8 | 46 48 23.8 | 22 11 34.8 | Loc. Sambata (DN76), nr.77 | Stefan Eleonora - loc. Sambata, nr. 79, jud. Bihor/Stefan Eleonora - loc. Sambata, nr. 79, jud. Bihor | 2102 | M | C+C+C+ | 2/2/2 | N/A | [12 empty] | 0 | TN | 50 |  | N/A | TRANSDAT | OK | IMSAT | 2001-02-15 | 2001-04-05 | YesV | 2001-04-25 | Marin | 2001-05-07 | 2001-05-03 |  |  |  |  | 2001-05-07 |  | 2001-02-05 | 2001-02-20 |  |  |  | 2001-04-10 | ICOM | TRY | 2001-04-10 | 2001-04-11 | 2001-04-11 | 2001-06-19 | 2001-06-29 | VLAD | Prov |  | CW TM180 |  |  |  |  | K 739 494 | 60 | 0 | 48.45 | K 739 494 | 180 | 0 | 48.45 | K 739 494 | 340 | 0 | 48.45 |  |  |  |  | N/A | 61 | 61 | 1 1/4" | 60 | 60 | 1 1/4" | 59.5 | 59.5 | 1 1/4" |  |  |  | 0 | ML 15 E 1+0 | Oradea | MW | 333 | 0.6 | 47/1.2 | 57 | 15/89 |  | 4X2/8 | 2U-3 |  |  |  | RBS | [10 empty] | TM178 | DRAGESTI | 153 | 0.6 | 47 | 60 | 15/84 | [6 empty] | 71* | DIEKAT | 2001-05-24 | 962 | 2001-05-28 | 2001-06-25 | 2001-06-28 | VLAD | 2001-06-29 |  |  |  |  | 30N01 Beius-Oradea |  | 2000-12-29 | Cristian CROITOR | CATALINA CIOCAN | [32 empty] | 150 | Sambata | Bihor | [7 empty] | 2 |  |  | 2
Phase_2 | CS | TM180 | SAUCANI | Road Oradea-Brad(11+1) | TM090 Beius_RTC | Transilvania | 46 43 50 | 22 14 39 | 46 43 58.6 | 22 15 05.2 | Comuna Rabagani, sat Saucani, nr.243 | Tau Teodor, sat Rabagani, nr.243/Tau Teodor, sat Rabagani, nr.243 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [12 empty] | 0 | TN | 50 |  | N/A | TRANSDAT | OK | DUAL | 2001-05-11 | 2001-07-30 | in exec |  | Marin | [5 empty] | 2000-11-24 | 2000-11-22 |  | 2001-06-01 | OK | [14 empty] | CW NOT READY |  |  |  |  | K 739 494 | 150 | 0 | 48.45 | K 739 494 | 250 | 0 | 48.45 | K 739 494 | 320 | 0 | 48.45 |  |  |  |  | N/A | 59.5 | 59.5 | 1 1/4" | 59.5 | 59.5 | 1 1/4" | 59.5 | 59.5 | 1 1/4" |  |  |  | 177 | ML 15 E 1+0 | Oradea | MW | 131 | 0.6 | 48 | 60 | [7 empty] | RBS | [10 empty] | TM090 | BEIUS_RTC | 312 | 0.6 | 32/0.6 | [21 empty] | 30N02 Beius-Oradea |  | 2000-12-29 | Cristi Croitor | Cosmorom | [32 empty] | 239 | [9 empty] | 2 |  |  | 2
Phase_2 | CS | TM181 | SUDRUGIU | Road Oradea-Brad(11+1) | TM092 Stei_RTC | Transilvania | 46 35 51.4 | 22 25 54.4 | 46 35 51.04 | 22 25 54.04 | Localitatea Sudrugiu | Dan Nicolaie, Stei, str. Independentei, nr.34, ap.11/Dan Nicolaie, Stei, str. Independentei, nr.34, ap.11 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [12 empty] | 0 | TN | 50 |  | N/A | TRANSDAT | OK | AXA | 2001-04-10 | 2001-05-14 | YesV | 2001-05-17 | Adi | 2001-06-06 | 2001-05-23 |  |  |  |  | 2001-05-07 |  | 2001-02-20 | 2001-03-14 |  |  |  | 2001-05-16 | ICOM | Interactive | 2001-05-16 | 2001-05-16 | 2001-05-17 | 2001-05-19 | 2001-05-23 | PAUN | Yes |  | POWER |  |  |  |  | K 739 494 | 80 | 0 | 48.45 | K 739 494 | 165 | 0 | 48.45 | K 739 494 | 335 | 0 | 48.45 |  |  |  |  | N/A | 59.5 | 59.5 | 1 1/4" | 61 | 61 | 1 1/4" | 59.5 | 59.5 | 1 1/4" |  |  |  | 360 | ML 15 E 1+0 | Oradea | MW | 164 | 0.6 | 47.5/0.6 | 60 | 15/89 |  | 4X2/8 | 2U-3 |  |  |  | RBS | [10 empty] | TM092 | STEI_RTC | 345 | 0.6 | 35/0.6 | 45 | 15/84 | [6 empty] | 69* | INTERACTIVE | 2001-05-16 | 932 | 2001-05-17 | 2001-05-17 | 2001-05-23 | [6 empty] | 30N01 |  | OK | Cristi CROITOR | Cosmorom | [32 empty] | 231 | Localitatea Sudrugiu | Bihor | [7 empty] | 2 |  |  | 2
Phase_2 | CS | TM182 | VASCAU_RTC | Road Oradea-Brad(11+1) | TM182 Vascau_RTC | Transilvania | 46 28 08.4 | 22 28 49.1 | 46 28 08.4 | 22 28 49.1 | Romtelecom Vascau | Romtelecom/ | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | N/A | N/A |  |  |  | 0 | TE | 27 |  | N/A | TRANSDAT | OK | TEHNOROB | 2000-12-15 | 2001-01-25 | YesV | 2001-02-15 | Adi |  | 2001-02-26 |  |  |  | N/A | 2000-11-22 |  | 2000-11-29 | 2000-12-15 |  |  |  | 2001-02-01 | ICOM | TRY | 2001-02-01 | 2001-02-01 | 2001-02-05 | 2001-02-08 | 2001-02-09 | VLAD | Prov | Bogdan Bogodai | 2001-04-12 | 2001-04-12 | 2001-04-12 | 2001-06-05 | 2001-06-19 | K 739 494 | 0 | 0 | 25 | K 739 494 | 140 | 0 | 25 | K 739 494 | 250 | 0 | 25 |  |  |  |  | N/A | 34 | 34 | 7/8" | 36 | 35.5 | 7/8" | 35 | 35 | 7/8" |  |  |  | 210 | N/A | Oradea | FO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [9 empty] | BSC32 | BSC ORADEA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 30N01 |  | 2001-03-30 | Cristian CROITOR | Cosmorom | [32 empty] | 308 | Vascau | Bihor | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | TM184 | DEALUL SOROC | Road Oradea-Brad(11+1) | XM184 Halmagiu_RTC | Transilvania | 46 17 55.22 | 22 32 14.92 | 46 16 50.8 | 22 34 46.7 | Dealul Soroc (La Lupina) | Primaria Halmagiu/Viceprimar Nicula Cornel, tel. 094/391913 | MAXITE | M | 1 | 2 | 2PBC | [7 empty] | N/A | N/A |  |  |  |  | TN | 50 |  | N/A/TMR9000 | TRANSDAT | OK | ORION | 2001-02-12 | 2001-03-23 | YesV | 2001-04-06 | Adi | 2001-04-06 | 2001-04-10 |  |  |  |  | 2001-05-07 |  | 2001-01-16 | 2001-02-20 |  |  |  | 2001-04-03 | ICOM | ORION | 2001-03-29 | 2001-03-30 | 2001-04-04 | 2001-04-05 | 2001-04-09 |  | Yes |  | CW XM184 |  |  |  |  | AAU | 140 | 0 | 48.3 | AAU | 330 | 0 | 48.3 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 58 | 58 | 1/2" | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 116 | ML 38 E 1+0 | Timisoara | MW | 136 | 0.3 | 26/0.3 | 35 | [7 empty] | N/A | XC50101 | [9 empty] | XM184 | HALMAGIU_RTC | 316 | 0.3 | 10 | 20 | [20 empty] | 30N01 Halmagiu-Curtici/30N01 Curtici-Timisoara |  | 2001-06-28 | Florin BELEA | Cosmorom | [32 empty] | 328 | Comuna Halmagiu | Arad | [7 empty] | 2 |  |  | 2
Phase_2 | CS | TM187 | BRAD_BLOC | Road Oradea-Brad(11+1) | TM112 Nucet_RTC | Transilvania | 46 07 40.9 | 22 47 33.3 | 46 07 40.9 | 22 47 33.3 | Bd. Republicii, bl.19, Brad | Asociatia de locatari nr.9/Administrator Toma Ion | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [12 empty] | 13.6 | B | 19 | S6m | Room | PROTELCO | OK | DUAL | 2001-05-11 | 2001-06-05 | YesV | Respins | Adi | [6 empty] | OK |  | OK | 2001-06-06 |  |  |  | 2001-06-06 | ICOM | TRY | 2001-06-06 | 2001-06-06 | 2001-06-07 | 2001-06-12 | 2001-06-13 | PAUN | Yes | Alexandru Toma | 2001-07-11 | 2001-07-11 |  |  |  | K 739 494 | 100 | 0 | 23 | K 739 494 | 190 | 0 | 23 | K 739 494 | 320 | 0 | 23 |  |  |  |  | N/A | 30 | 30 | 7/8" | 30 | 30 | 7/8" | 30 | 30 | 7/8" |  |  |  | 180 | N/A | Timisoara | HDSL | N/A | N/A | N/A | N/A | N/A |  | N/A | [5 empty] | XC50112 | [6 empty] | 40/outdoor |  |  | TM112 | NUCET |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | 30N01 Brad-Nucet/30N02 Nucet-Timisoara |  | 2001-06-28 | Florin BELEA | Petrica BURGHIU | [32 empty] | 281 | Brad | Hunedoara | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | TM189 | VATA_RTC(OPTIMIZARE) | Road Oradea-Brad(11+1) | TM189 VATA_RTC | Transilvania | 46 10 37.21 | 22 35 50 | 46 10 37.21 | 22 35 50 | Romtelecom, Vata Bai | Romtelecom/ | 2102 | M | C+C+C+ | 2/2/2 | N/A | ANTENNA MOVED(14m) | N/A | N/A | N/A | N/A | N/A |  | Yes | N/A |  |  |  | 10 | B | 10 | 15m new pylonet | N/A | SVF | OK | ALMO | 2000-12-01 | 2000-12-30 | YesV | 2001-01-30 | Marin |  | 2001-02-01 |  |  | 2001-06-07 | N/A | OK |  | 2000-11-23 | 2000-12-07 |  |  |  | 2000-12-18 | ICOM | SVF | 2000-12-18 | 2000-12-18 | 2000-12-19 | 2000-12-20 | 2000-12-28 | RADU | Yes | Alexandru Toma | 2000-12-30 | 2000-12-29 | 2000-12-29 | 2001-01-16 | 2001-01-26 | K 739 494 | 60 | 0 | 21 | K 739 494 | 250 | 0 | 21 | K 739 494 | 340 | 0 | 21 |  |  |  |  | N/A | 16 | 16 | 7/8" | 16 | 16 | 7/8" | 16 | 16 | 7/8" |  |  |  | 96 | N/A | Oradea | FO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [6 empty] | 100/outdoor |  |  | BSC32 | BSC ORADEA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | OK |  | 2001-12-27 | Cosmorom | Cosmorom | [32 empty] | 240 | Vata de Jos | Hunedoara | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | TM190 | ORADEA_9 | Oradea(9) | TM082 Oradea_2_RTC | Banat | 47 04 04.6 | 21 54 16.8 | 47 04 04.5 | 21 54 16.8 | Str. Cazaban , nr. 51, bl. CARPO I | Asociatia de locatari CARPO I, str. 51/Lazar Stefan sau Balog Mircea, tel. 059/458895 si 059/417607 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | Yes | N/A |  |  |  | 35 | B | 35 | C3m+C3m | N/A | PROTELCO | OK | ROMPSAR | 2001-01-12 | 2001-02-05 | YesV | 2001-02-14 | Andrei | 2001-03-08 | 2001-02-26 |  |  |  |  | 2000-12-06 |  | 2000-12-18 | 2001-01-11 |  |  |  | 2001-02-09 | ICOM | Interactive | 2001-02-07 | 2001-02-07 | 2001-02-12 | 2001-02-13 | 2001-02-16 |  | Yes | Constantin Mihai | 2001-03-28 | 2001-03-22 | 2001-03-22 | 2001-04-10 | 2001-04-23 | K 739 494 | 70 | 0 | 37 | K 739 494 | 180 | 0 | 37 | K 739 494 | 340 | 0 | 36.8 |  |  |  |  | N/A | 30 | 30 | 7/8" | 30 | 30 | 7/8" | 10 | 10 | 7/8" |  |  |  | 140 | ML 38 E 1+0 | Oradea | MW | 125 | 0.3 | 36.5 | 30 | 38/14 |  | 4x2/8 | 4U-1 |  |  |  | RBS | [9 empty] | 1 | TM081 | ORADEA_1 |  | 0.3 |  | 60 | 38/18 | [6 empty] | 25* | INTERACTIVE | 2001-02-09 | 616 | 2001-02-09 | 2001-02-12 | 2001-02-16 | RADU | OK | 2001-03-21 |  | 2001-04-11 | 2001-04-17 |  |  | 2001-02-16 | Marius LUNGU | Cosmorom | [32 empty] | 118 | Oradea | Bihor | [5 empty] | 1 |  | 2 | 1 |  | 2
Phase_2 | CS | TM191 | TINCA_RTC | Road Arad-Oradea(10) | TM087 Salonta_RTC | Banat | 46 46 26.9 | 21 55 48.7 | 46 46 26.9 | 21 55 48.7 | Romtelecom, Str. Armatei Romane nr.8 | Romtelecom/ | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | N/A | N/A |  |  |  | 0 | TE | 29 |  | N/A | PROTELCO | OK | MULTISERV | 2001-01-15 | 2001-01-28 | YesV | 2001-02-14 | Andrei | 2001-02-26 | 2001-02-26 |  |  |  | N/A | 2000-12-06 |  | 2000-12-18 | 2001-01-19 |  |  |  | 2001-02-01 | ICOM | TRY | 2001-02-01 | 2001-02-01 | 2001-02-05 | 2001-02-11 | 2001-02-12 |  | Yes | Mircea Mihut | 2001-05-15 | 2001-05-15 | 2001-05-15 |  |  | K 739 494 | 85 | 0 | 26 | K 739 494 | 180 | 0 | 26 | K 739 494 | 335 | 0 | 26 |  |  |  |  | N/A | 38.5 | 38.5 | 7/8" | 37 | 37 | 7/8" | 39 | 39 | 7/8" |  |  |  | 229 | N/A | Oradea | RR | RR |  |  |  | N/A |  | N/A | N/A |  |  |  | N/A | XC50087 | [6 empty] | 37/outdoor |  |  | TM087 | SALONTA_RTC | RR |  |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | 30N01 |  | 23.11.2000 | Marius LUNGU | Cosmorom | [32 empty] | 123 | Tinca | Bihor | [7 empty] | 2 |  |  | 2
Phase_2 | CS | TM193 | CALAN_RTC | Bazinul Petrosani(20) | TM197 Hateg_RTC | Transilvania | 45 43 54.4 | 23 01 31.7 | 45 43 54.4 | 23 01 31.7 | Romtelecom, Str. Independentei 14A | Romtelecom/Oltean Viorel tel. 054/204580 | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [7 empty] | N/A | N/A |  |  |  | 5.4 | B | 9.5 | 6m new pylonet | room | SVF | OK | ALMO | 2000-12-21 | 2001-02-08 | YesV | 2001-03-28 | Marin | 2001-03-15 | 2001-05-04 |  |  |  | N/A |  |  | 2000-12-08 | 2001-01-19 |  |  |  | 2001-02-14 | ICOM | SVF | 2001-02-13 | 2001-02-13 | 2001-02-19 | 2001-03-06 | 2001-03-12 |  | Yes |  | RBS 2101 TM194 |  |  |  |  | K 739 494 | 90 | 0 | 19.5 | K 739 494 | 210 | 0 | 19.5 | K 739 494 | 330 | 0 | 19.5 |  |  |  |  | N/A | 31 | 31 | 7/8" | 31 | 31 | 7/8" | 31 | 31 | 7/8" |  |  |  | 186 | ML 38 E 1+0 | Timisoara | MW | 232 |  | 15.4 | 27 | [15 empty] | 100/outdoor |  |  | TM194 | STREI | 52 |  | 48 | 68 | [23 empty] | SORIN UNTARU | SORIN UNTARU | [32 empty] | 243 | Calan | Hunedoara | [7 empty] | 2 |  |  | 2
Phase_2 | CS | TM194 | STREI | Bazinul Petrosani(20) | TM197 Hateg_RTC | Transilvania | 45 42 47 | 22 59 28 | 45 43 03.4 | 22 59 24.1 | Sat Strei, nr. 17, Calan | Danescu Ioan , sat Strei, nr.17, Calan Jud. Hunedoara/Danescu Ioan , sat Strei, nr.17, Calan Jud. Hunedoara | 2101 | M | C+ | 2 | 2101 | [13 empty] | TN | 50 |  | N/A | SVF | OK | SVF | 2001-03-08 | 2001-04-05 | YesV | 2001-04-20 | Adi |  | 2001-04-25 |  |  |  |  | 2000-11-25 |  | 2001-02-28 | 2001-03-14 | [6 empty] | 2001-04-09 |  |  |  |  | GATA-2101 |  |  | RBS 2101 |  |  |  |  | K 739 494 | 170 | 0 | 49.5 | K 739 494 | 330 | 0 | 49.5 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 70 | 70 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 140 | ML 15 E 1+0 | Timisoara | MW | 187 |  | 47.7 | 68 | [18 empty] | TM196 | BURSUC | 7 | 1.2 | 47 | 60 | [23 empty] | SORIN UNTARU | SORIN UNTARU | [32 empty] | 263 | Strei | Hunedoara | [6 empty] | 1 | 2 |  |  | 2
Phase_2 | CS | TM196 | BURSUC | Bazinul Petrosani(20) | TM197 Hateg_RTC | Banat | 45 37 01.8 | 22 58 26.4 | 45 37 04 | 22 58 36.2 | Extravilan Loc Bursuc | Regia Nationala a Padurilor/Primaria Com. Bursuc, tel. 054/77756 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [12 empty] | 0 | TN | 50 |  | N/A | SVF | OK | FIBEC | 2001-06-01 | 2001-07-27 | in exec |  | Adi | [8 empty] | 2001-05-23 | 2001-06-01 | [14 empty] | CW NOT READY |  |  |  |  | K 739 494 | 35 | 0 | 49.5 | K 739 494 | 170 | 0 | 49.5 | K 739 494 | 260 | 0 | 49.5 |  |  |  |  | N/A | 65 | 65 | 1 1/4" | 65 | 65 | 1 1/4" | 65 | 65 | 1 1/4" |  |  |  | 390 | ML 38 E 1+0 | Timisoara | MW | 247 | 0.6 | 45.5 | 60 | [7 empty] | RBS | [10 empty] | TM197 | HATEG_RTC | 67 | 0.3 | 17.2/0.3 | 40 | [23 empty] | SORIN UNTARU | SORIN UNTARU | [32 empty] | 399 | Hunedoara | Hunedoara | [6 empty] | 1 | 2 |  | 1 | 2
Phase_2 | CS | TM197 | HATEG_RTC | Bazinul Petrosani(20) | TM197 Hateg_RTC | Transilvania | 45 36 35.8 | 22 56 59.3 | 45 36 35.8 | 22 56 59.3 | Romtelecom, localitatea Hateg | Romtelecom/Dl. Mihutescu Ion - 054/ 204575; 054/ 77055 | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [12 empty] | 5.4 | B | 9.5 | 12m new pylonet | Room | SVF | OK | ALMO | 2000-12-21 | 2001-03-17 | YesV | 2001-04-06 | Marin | 2001-04-06 | 2001-04-10 |  |  |  | N/A | 2000-11-20 |  | 2000-12-08 | 2001-03-01 |  |  |  | 2001-03-26 | ICOM | SVF | 2001-03-19 | 2001-03-19 | 2001-03-27 | 2001-04-02 | 2001-04-04 | VLAD | Yes | Cristian Strambeanu | 2001-07-03 | 2001-07-03 |  |  |  | K 739 494 | 20 | 0 | 20.6 | K 739 494 | 140 | 0 | 20.6 | K 739 494 | 240 | 0 | 20.6 |  |  |  |  | N/A | 39 | 39 | 7/8'' | 39 | 39 | 7/8'' | 39 | 39 | 7/8'' |  |  |  | 234 | N/A | Timisoara | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | [5 empty] | 50197 | [6 empty] | 10/8p outdoor | 10m/8p/outdoor |  | BSC31 | BSC TIMISOARA | N/A | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | 30N01 |  |  | SORIN UNTARU | SORIN UNTARU | [32 empty] | 320 | Hateg | Hunedoara | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | TM199 | PUI | Bazinul Petrosani(20) | TM197 Hateg_RTC | Banat | 45 31 22 | 23 02 37 | 45 31 21.3 | 23 02 42 | Com. Pui, langa Balastiera dintre satele Puisor si Galati | Primaria com Pui/Primar Stoica Victor Tiberiu | 2101 | M | C+ | 2 | 2101 | [13 empty] | TN | 50/6mp |  | N/A | SVF | OK | SVF | 2001-03-08 | 2001-04-05 | YesV | 2001-05-30 | Adi | 2001-07-06 | [7 empty] | 2001-03-14 | 2001-04-09 | [6 empty] | 2001-04-09 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 120 | 0 | 49.5 | K 739 494 | 290 | 0 | 49.5 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 65 | 65 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 130 | ML 23 E 1+0 | Timisoara | MW | 259 | [10 empty] | RBS | [10 empty] | ZM198 | SALASU DE SUS_RTC | [27 empty] | SORIN UNTARU | SORIN UNTARU | [32 empty] | 402 | Pui | Hunedoara | [7 empty] | 2 |  |  | missing
Phase_2 | CS | TM200 | BARU | Bazinul Petrosani(20) | TM197 Hateg_RTC | Banat | 45 28 39 | 23 10 06 | 45 28 40.1 | 23 10 13.1 | Extravilan comuna Baru | Primaria Com. Baru, jud. Hunedoara/Primar Popescu Marcu | 2101 | M | C+ | 2 | 2101 | [13 empty] | TN | 50 |  | N/A | SVF | OK | EL-MONT | 2001-03-21 | 2001-04-25 | YesV | 2001-06-01 | Adi |  | 2001-06-06 |  |  |  |  | 2000-11-01 |  | 2001-03-16 | 2001-03-27 | [6 empty] | 2001-05-03 | 2001-05-03 |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 115 | 0 | 49.5 | K 739 494 | 300 | 0 | 49.5 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 65 | 65 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 130 | ML 15 E 1+0 | Timisoara | MW | 297 |  | 48 | 60 | [7 empty] | RBS | [10 empty] | TM199 | PUI | 116 | 1.2 | 46/1.2 | 67 | [23 empty] | SORIN UNTARU | SORIN UNTARU | [32 empty] | 543 | Baru | Hunedoara | [7 empty] | 2 |  |  | 2
Phase_2 | CS | TM202 | PESTENITA | Bazinul Petrosani(20) | TM197 Hateg_RTC | Banat | 45 33 02 | 22 51 17 | 45 33 01.4 | 22 51 19.3 | Extravilan Pestenita | Braila Ioan , sat Cirnesti, comuna Totesti/Primaria Com. Samizegetusa, jud. Hunedoara, tel. 054/762210 | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | SVF | OK | SVF | 2001-03-01 | 2001-05-10 | YesV | 2001-05-17 | Adi | 2001-07-06 | 2001-05-23 |  |  |  |  | 2000-11-09 |  | 2001-02-12 | 2001-03-01 | [6 empty] | 2001-05-17 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 30 | 0 | 49.5 | K 739 494 | 240 | 0 | 49.5 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 70 | 70 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 140 | ML 15 E 1+0 | Timisoara | MW | 52 |  | 47.7 | 68 | [7 empty] | RBS | [10 empty] | TM196 | BURSUC | 232 | 1.2 | 21.5 | 30 | [23 empty] | SORIN UNTARU | Cosmorom | [32 empty] | 401 | Hunedoara | Hunedoara | [7 empty] | 2 |  |  | 2
Phase_2 | CS | TM203 | ZEICANI | Bazinul Petrosani(20) | TM197 Hateg_RTC | Banat | 45 30 12 | 22 43 59 | 45 30 15.1 | 22 44 10.4 | Extravilan com.Zeicani | Ianc Susana, comuna Sarmizegatusa, sat Zeicani/Ianc Susana, comuna Sarmizegatusa, sat Zeicani, tel. 056/762210 Zicon Virgil | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  |  | TN | 50 |  | N/A | SVF | OK | ORION | 2001-02-16 | 2001-04-03 | YesV | 2001-04-05 | Adi |  | 2001-04-10 |  |  |  |  | 2001-01-03 |  | 2001-01-26 | 2001-02-26 | [6 empty] | 2001-04-09 |  |  |  |  | GATA-2101 | Yes |  | RBS 2101 |  |  |  |  | K 739 494 | 65 | 0 | 49.5 | K 739 494 | 270 | 0 | 49.5 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 70 | 70 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 140 | ML 15 E 1+0 | Timisoara | MW | 61 |  | 47 | 67 | [7 empty] | RBS | [10 empty] | TM202 | PESTENITA | 241 |  | 47.7 | 68 | [23 empty] | SORIN UNTARU | [33 empty] | 583 | Hunedoara | Hunedoara | [7 empty] | 2 |  |  | 2
Phase_2 | CS | TM205 | ROSCANI | Road Arad-Deva(13+3) | YM145 Ilia_RTC | Banat | 45 51 57 | 22 33 24 | 45 51 57 | 22 33 29 | Comuna Roscani( in spatele Romtelecom Roscani) | Primaria Doba, Piata Victoriei nr.1/Ing. Suiga Vasile, tel. 054/283101 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | N/A |  |  |  |  | 0 | TN | 50 |  | N/A | SVF | OK | VECTOR | 2001-02-15 | 2001-03-15 | YesV | 2001-03-28 | Marin | 2001-05-07 | 2001-05-04 |  |  |  |  | Iulie 2000 |  | 2001-02-05 | 2001-02-28 |  |  |  | 2001-03-15 | ICOM | VECTOR | 2001-03-13 | 2001-03-13 | 2001-03-19 | 2001-03-21 | 2001-03-23 | RADU | Yes | Mircea Mihut | 2001-05-14 | 2001-05-14 | 2001-06-14 |  |  | K 739 494 | 10 | 0 | 49 | K 739 494 | 150 | 0 | 49 | K 739 494 | 270 | 0 | 49 |  |  |  |  | N/A | 60 | 60 | 1 1/4" | 60 | 60 | 1 1/4" | 60 | 60 | 1 1/4" |  |  |  | 360 | N/A | Timisoara | FO | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | RBS | XC50145 | [6 empty] | 50/8p outdoor |  |  | YM145 | ILIA_RTC |  | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | 30N03 Ilia-Timisoara |  | 2001-05-14 | SORIN UNTARU | Cosmorom | [32 empty] | 240 | Hunedoara | Hunedoara | [7 empty] | Site Near=Insertion Point
Phase_2 | CS | TM206 | CUBULCUT_RTC | Road Oradea-Satu Mare(16+3) | YM096 Valea lui Mihai | Banat | 47 19 28 | 22 11 29.7 | 47 19 28 | 22 11 29.7 | Romtelecom, Sat Cubulcut, com Sacuieni | Romtelecom/ | 2101 | M | C+ | 2 | 2101 | [7 empty] | N/A | N/A |  |  |  | 0 | TE | 32 |  | N/A | PROTELCO | OK | MULTISERV | 2001-01-15 | 2001-01-26 | YesV | 2001-04-09 | Andrei | 2001-04-17 | 2001-04-10 |  |  |  | N/A | 2000-12-06 |  | 2000-12-13 | 2001-01-15 |  |  |  | 2001-05-24 | ICOM | VECTOR | 2001-02-01 | 2001-02-01 | 2001-05-25 | 2001-06-10 | 2001-06-13 | PAUN | Yes | Ion Soare | 2001-06-15 | 2001-06-15 | 2001-06-15 |  |  | K 739 494 | 170 | 0 | 31.5 | K 739 494 | 320 | 0 | 31.5 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 40 | 40 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 80 | ML 23 E 1+0 | Oradea | MW | 303 | 0.6 | 30 | 40 | 23/58 |  | 4X2/8 | 2U-3 |  |  |  | RBS | [9 empty] | 1 | TM109 | SACUIENI | 123 | 0.6 | 48.5/0.6 | 60 | 23/56 | [6 empty] | 71* | VECTOR | 2001-05-24 | 956 | 2001-05-28 | 2001-05-28 | 2001-06-11 |  |  |  |  | 2001-07-12 |  | 30N01 |  | 2001-03-07 | Marius LUNGU | Cosmorom | [32 empty] | 201 | Cubulcut | Bihor | [7 empty] | 2 |  |  | 2
Phase_3 | CS | TM207 | BECICHERECU | Road Timisoara-Sannicolau(4) | TM053 Central_RTC | Transilvania | 45 50 33.20 | 21 01 18.80 | 45 49 58.2 | 21 02 28.4 | Extravilan Becicherecu-Biled | Primaria Becicherecu Mic | 2101 | M | C+ | 2 | 2101 | [7 empty] | YES |  |  |  |  | 0 | TN | 50 |  | N/A | SVF | OK | SVF | 2001-08-01 | 2001-08-30 |  |  | Adi |  |  | 2001-04-26 |  |  | N/A | 2001-07-12 |  | 2001-07-09 | [15 empty] | RBS 2101 |  |  |  |  | K 739 494 | 110 | 0 | 49 | K 739 494 | 310 | 0 | 49 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | 65 | 65 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 130 | ML 15 E 1+1 (PS) | Timisoara | MW | 105 | 1.2 | 45 | 60 | [18 empty] | TM047 | AFRO | 285 | [26 empty] | Petrica BURGHIU | Andrei Dumitrescu | [32 empty] | 88.5 | Becicheru-Biled | Timis | [7 empty] | missing |  |  | missing
Phase_3 | CS | TM208 | SANDRA | Road Timisoara-Sannicolau(4) | TM053 Central_RTC | Transilvania | 45 55 35.10 | 20 53 21.30 |  |  |  |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | YES |  |  |  |  | 0 | TN | 50 |  |  | SVF |  | @ | 2001-08-01 | 2001-09-10 |  |  | Adi |  |  | 2001-04-26 |  |  |  | 2001-07-12 | [17 empty] | CTR | [35 empty] | Timisoara | MW | 132 | [21 empty] | TM207 | BECICHERECU | 312 | 1.2 | 35 | 50 | [23 empty] | Petrica BURGHIU | Andrei Dumitrescu | [42 empty] | 3 |  |  | 3
Phase_3 | CS | TM209 | LOVRIN | Road Timisoara-Sannicolau(4) | TM053 Central_RTC | Transilvania | 45 58 05.60 | 20 45 39.8 | 45 57 55.5 | 28 47 17.9 | Ferma3 SCA Lovrin | SCA Lovrin | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | YES |  |  |  |  | 0 | TE | 31 | C6m+C6m | N/A | SVF | OK | SVF | 2001-07-12 | 2001-07-17 | in exec |  | Adi |  |  | 2001-04-26 |  |  | N/A | 2001-07-12 |  | 2001-06-08 | 2001-06-13 | [14 empty] | CW NOT STARTED |  |  |  |  | K 739 494 | 65 | 0 | 36.4 | K 739 494 | 240 | 0 | 36.4 | K 739 494 | 310 | 0 | 36.4 |  |  |  |  | N/A | 55 | 55 | 1 1/4" | 55 | 55 | 1 1/4" | 55 | 55 | 1 1/4" |  |  |  | 330 |  | Timisoara | MW | 115 | 0.6 | 33.6 | 54 | [18 empty] | TM208 | SANDRA | 295 | [26 empty] | Petrica BURGHIU | Andrei Dumitrescu | [33 empty] | Lovrin | Timis | [7 empty] | 3 |  |  | 3
Phase_3 | CS | TM210 | SANNICOLAU_RTC | Road Timisoara-Sannicolau(4) | TM053 Central_RTC | Transilvania | 46 04 15 | 20 37 24 | 46 04 14.8 | 20 37 24.6 | Sediul Romtelecom , Piata 30 Decembrie | Romtelecom | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [12 empty] | 5 | TE | 41 |  | Room/Rack19" | SVF |  | SVF | 2001-06-15 | 2001-06-30 | Yes |  | Adi |  |  | 2001-04-26 |  |  | N/A | 2001-07-12 |  | 2001-06-08 | 2001-06-13 |  |  | 1113 | 2001-07-16 | ICOM | ELECTROTRADE | 2001-07-13 | 2001-07-16 | 2001-07-17 | [5 empty] | CTR |  |  |  |  | K 739 494 | 130 | 0 | 40 | K 739 494 | 205 | 0 | 40 | K 739 494 | 340 | 0 | 40 |  |  |  |  | N/A | 45 | 45 | 7/8" | 45 | 45 | 7/8'' | 45 | 45 | 7/8'' |  |  |  | 270 |  | Timisoara | MW | 137 | 1.2 | 33 | 38 | [18 empty] | TM209 | LOVRIN | 317 | 1.2 | 33.6 | 54 | [23 empty] | Petrica BURGHIU | Andrei Dumitrescu | [33 empty] | Sannicolau Mare | Timis | [7 empty] | 3 |  |  | 3
Phase_3 | CS | TM211 | TEREMIA MARE | Road Timisoara-Jimbolia(5) | TM053 Central_RTC | Transilvania | 45 56 03.3 | 20 31 29 | 45 56 03.5 | 20 37 29 | Intravilan loc. Teramia Mare | Primaria Teramia Mare | 2101 | M | C+ | 2 | 2101 | [7 empty] | YES |  |  |  |  | 0 | TE | 31 | T6m | N/A | SVF | OK | SVF | 2001-07-12 | 2001-08-15 | in exec |  | Adi |  |  | 2001-04-26 |  |  | N/A | 2001-07-12 |  | 2001-07-09 | [15 empty] | RBS 2101 |  |  |  |  | K 739 494 | 30 | 0 | 36.4 | K 739 494 | 120 | 0 | 36.4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | 55 | 55 | 1 1/4" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 110 | ML 15 E 1+0 | Timisoara | MW | 120 | 0.6 | 34.4 | 55 | [18 empty] | TM212 | COMLOSU MARE | 300 | 0.6 | 36.5 | 45 | [23 empty] | Petrica BURGHIU | Andrei Dumitrescu | [33 empty] | Teramia Mare | Timis | [7 empty] | 3 |  |  | 3
Phase_3 | CS | TM212 | COMLOSU MARE | Road Timisoara-Jimbolia(5) | TM053 Central_RTC | Transilvania | 45 53 26 | 20 37 54 | 45 53 43.3 | 20 37 56.1 | Intravilan loc. Comlosu Mare | Pribac Anica, oras Jimbolia, bl. 4I, ap2 | 2101 | M | C+ | 2 | 2101 | [7 empty] | YES |  |  |  |  | 0 | TN | 40 |  | N/A | SVF | OK | SVF | 2001-06-20 | 2001-06-26 | YesV |  | Adi |  |  | 2001-04-26 |  |  | N/A | 2001-07-12 |  |  | 2001-06-11 | [6 empty] | 2001-07-13 |  |  |  |  | GATA-2101 |  |  | RBS 2101 |  |  |  |  | K 739 494 | 145 | 0 | 39.5 | K 739 494 | 290 | 0 | 39.5 | N/A | N/A | N/A | N/A |  |  |  |  | Yes | 55 | 55 | 7/8" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 110 | ML 15 E 1+0 | Timisoara | MW | 148 | 1.2 | 37.6 | 47 | [7 empty] | N/A | [10 empty] | TM213 | JIMBOLIA_RTC | 328 | 1.2 | 41.8 | 55 | [23 empty] | Petrica BURGHIU | Andrei Dumitrescu | [32 empty] | 82.2 | Comlosu Mare | Timis | [7 empty] | 3 |  |  | 3
Phase_3 | CS | TM213 | JIMBOLIA_RTC | Road Timisoara-Jimbolia(5) | TM053 Central_RTC | Transilvania | 45 47 41.20 | 20 43 03.9 | 45 47 41.3 | 20 43 03.5 | Sediul Romtelecom , Jimbolia, str. Republicii, 35 | Romtelecom | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [12 empty] | 5 | TE | 52.5 |  | Room/Rack19" | SVF |  | SVF | 2001-06-15 | 2001-06-30 | YesV |  | Adi |  |  | 2001-04-26 |  |  | N/A | 2001-07-12 |  | 2001-06-08 | 2001-06-13 | [6 empty] | 2001-07-13 | [7 empty] | CTR |  |  |  |  | K 739 494 | 90 | 0 | 51 | K 739 494 | 190 | 0 | 50.8 | K 739 494 | 320 | 0 | 51 |  |  |  |  | N/A | 65 | 65 | 1 1/4" | 65 | 65 | 1 1/4" | 65 | 65 | 1 1/4" |  |  |  | 390 | ML 15 E 1+0 | Timisoara | MW | 94 | 1.2 | 41.8 | 55 | [15 empty] | 16/indoor |  |  | TM214 | CARPINIS | 274 | [26 empty] | Petrica BURGHIU | Andrei Dumitrescu | [33 empty] | Jimbolia | Timis | [7 empty] | 3 |  |  | 3
Phase_3 | CS | TM214 | CARPINIS | Road Timisoara-Jimbolia(5) | TM053 Central_RTC | Transilvania | 45 47 10.80 | 20 53 34.5 |  |  |  |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | YES | [5 empty] | S |  |  |  | SVF |  | @ | 2001-08-01 | 2001-09-10 |  |  | Adi |  |  | 2001-04-26 |  |  |  | 2001-07-12 | [17 empty] | CTR | [34 empty] | ML 15 E 1+0 | Timisoara | MW | [22 empty] | TM207 | BECICHERECU | 238 | 0.6 | 35 | 50 | [23 empty] | Petrica BURGHIU | Andrei Dumitrescu | [42 empty] | missing |  |  | missing
Phase_3 | CS | TM215 | TIMISOARA_VEST | Road Timisoara-Jimbolia(5) | TM053 Central_RTC | Transilvania | 45 45 42.3 | 21 11 06.7 | 45 45 42.5 | 21 11 07.8 | Sediul Romtelecom , str. Pelinului, nr.6-8 | Romtelecom | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | YES |  |  |  |  | 0 | TN | 50 |  | N/A/TMR9000 | SVF* |  | SVF* |  |  |  |  | Adi* | [5 empty] | N/A | 2001-07-12 |  | 2001-06-08 | [15 empty] | CTR |  |  |  |  | K 739 494 | 100 | 0 | 45 | K 739 494 | 170 | 0 | 45 | K 739 494 | 270 | 0 | 65 |  |  |  |  | N/A | 45 | 45 | 1 1/4" | 45 | 45 | 1 1/4" | 65 | 65 | 1 1/4" |  |  |  | 310 |  | Timisoara | MW | 305 | 1.2 | 35 | 50 | [18 empty] | TM207 | BECICHERECU | 125 | [26 empty] | Petrica BURGHIU | Andrei Dumitrescu | [32 empty] | 85.4 | Timisoara | Timis | [7 empty] | 3 |  |  | 3
Phase_3 | CS | TM216 | CONSTANTIN CEL MARE | Timisoara | TM053 Central_RTC | Banat | 45 46 37.9 | 21 14 15.1 | 45 46 37..4 | 21 14 15.4 | Str Ion Ionescu de la Brad, bl. A32 | Iancu Teodora, bl. A32, ap.2, tel. 056/212213 | 2102 | M | C+C+C+ | 2/2/2 | N/A | [7 empty] | YES |  |  |  |  | 14.4 | B | 14.4 | new pylonet 6m | N/A | SVF | OK | SVF | 2001-07-05 | 2001-08-15 | in exec |  | Adi |  |  | 2001-05-04 |  |  | N/A | 2001-05-15 |  |  | 2001-06-11 | [14 empty] | CW NOT STARTED |  |  |  |  | K 739 494 | 0 | 0 | 20 | K 739 494 | 120 | 0 | 20 | K 739 494 | 240 | 0 | 20 |  |  |  |  | N/A | 18 | 18 | 7/8" | 18 | 18 | 7/8" | 18 | 18 | 7/8" |  |  |  | 108 | ML 38 E 1+0 | Timisoara | MW | 128 | 0.3 | 18.4 | 17 | [18 empty] | TM051 | SIMON BARNUTIU | [27 empty] | Florin BALEA | Andrei DUMITRESCU | [33 empty] | Timisoara | Timis | [7 empty] | 3 |  |  | missing
Phase_3 | CS | TM217 | ISIM | Timis county | TM062 Girocului_RTC | Oltenia | 45 44 39.2 | 21 13 31.2 |  |  |  |  | 2101 | M | C+ | 2 | 2101 | [17 empty] | DUAL |  | @ | 2001-08-15 | 2001-08-30 |  |  | Adi |  |  | 2001-06-19 | [57 empty] | Timisoara | MW | [22 empty] | TM062 | GIROCULUI | [27 empty] | Florin BELEA | Andrei Dumitrescu | [42 empty] | missing |  |  | missing
Phase_3 | CS | TM218 | H. TIMISOARA | Timis county | TM062 Girocului_RTC | Oltenia | 45 45 17 | 21 13 31.6 |  |  |  |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [17 empty] | DUAL |  | @ | 2001-08-15 | 2001-08-30 |  |  | Adi |  |  | 2001-06-19 | [57 empty] | Timisoara | MW | [22 empty] | TM217 | ISIM | [27 empty] | Florin BELEA | Andrei Dumitrescu | [42 empty] | missing |  |  | missing
Phase_3 | CS | TM219 | CHEVERESU MARE | Timis county | TM071 Lugoj_RTC | Oltenia | 45 39 55.5 | 21 28 44.5 |  |  |  |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [17 empty] | DUAL |  | @ | 2001-08-15 | 2001-09-20 |  |  | Adi |  |  | 2001-06-19 | [57 empty] | Timisoara | MW | [22 empty] | TM220 | BUZIAS | [27 empty] | Florin BELEA | Andrei Dumitrescu | [42 empty] | missing |  |  | missing
Phase_3 | CS | TM220 | BUZIAS | Timis county | TM071 Lugoj_RTC | Oltenia | 45 39 08.9 | 21 36 31.9 |  |  |  |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [17 empty] | DUAL |  | @ | 2001-08-15 | 2001-08-30 |  |  | Adi |  |  | 2001-06-19 | [57 empty] | Timisoara | MW | [22 empty] | TM132 | TOPOLOVATU MARE | [27 empty] | Florin BELEA | Andrei Dumitrescu | [42 empty] | missing |  |  | missing
Phase_3 | CS | TM221 | LUGOJ WATER TOWER | Lugoj(5) | TM071 Lugoj_RTC | Oltenia | 45 40 55 | 21 51 53.5 |  |  |  |  | 2101 | M | C+ | 2 | 2101 | [17 empty] | ROMPSAR |  | @ | 2001-08-15 | 2001-08-30 |  |  | Adi |  |  | 2001-06-19 | [57 empty] | Timisoara | MW | [22 empty] | TM071 | LUGOJ_RTC | [27 empty] | Florin BELEA | Andrei Dumitrescu | [42 empty] | missing |  |  | missing
Phase_3 | CS | TM222 | ABATOR | Road Lugoj-Soceni(3) | TM071 Lugoj_RTC | Oltenia | 45 36 50 | 21 52 49.9 |  |  |  |  | 2101 | M | C+ | 2 | 2101 | [17 empty] | ROMPSAR |  | @ | 2001-08-15 | 2001-09-20 |  |  | Adi |  |  | 2001-06-19 | [57 empty] | Timisoara | MW | [22 empty] | TM221 | LUGOJ WATER TOWER | [27 empty] | Florin BELEA | Andrei Dumitrescu | [42 empty] | missing |  |  | missing
Phase_3 | CS | TM223 | FARLIUG | Road Lugoj-Soceni(3) | TM071 Lugoj_RTC | Oltenia | 45 31 05.1 | 21 52 16.5 |  |  |  |  | 2101 | M | C+ | 2 | 2101 | [17 empty] | ROMPSAR |  | @ | 2001-08-15 | 2001-08-30 | Replaning |  | Adi |  |  | 2001-06-19 | [57 empty] | Timisoara | MW | [22 empty] | TM222 | ABATOR | [27 empty] | Florin BELEA | Andrei Dumitrescu | [42 empty] | missing |  |  | missing
Phase_3 | CS | TM224 | SOCENI | Road Lugoj-Soceni(3) | TM078 Caransebes_RTC | Oltenia | 45 23 35.9 | 21 57 05.1 |  |  |  |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [17 empty] | ROMPSAR |  | @ | 2001-08-15 | 2001-09-20 |  |  | Adi |  |  | 2001-06-19 | [57 empty] | Timisoara | MW | [22 empty] | TM226 | CORNUTEL | [27 empty] | Florin BELEA | Andrei Dumitrescu | [42 empty] | missing |  |  | missing
Phase_3 | CS | TM225 | RESITA_METEO | Resita | TM075 Resita_RTC | Oltenia | 45 18 51.7 | 21 53 11.8 |  |  |  |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [17 empty] | DIEKAT |  | @ | 2001-08-15 | 2001-09-20 |  |  | Adi |  |  | 2001-07-19 | 2001-07-05 |  |  | 2001-07-05 |  |  |  |  | 2001-07-05 | [47 empty] | ML 38 E 1+0* | Timisoara | MW | [22 empty] | TM075 | RESITA_RTC | [27 empty] | Florin BELEA | Andrei Dumitrescu | [42 empty] | missing |  |  | missing
Phase_3 | CS | TM226 | CORNUTEL | Road Caransebes-Resita | TM078 Caransebes_RTC | Oltenia | 45 25 56.3 | 22 06 27.4 |  |  |  |  | 2101 | M | C+ | 2 | 2101 | [17 empty] | DIEKAT |  | @ | 2001-08-15 | 2001-09-20 |  |  | Adi |  |  | 2001-06-19 | [57 empty] | Timisoara | MW | [22 empty] | TM126 | JUPA | [27 empty] | Florin BELEA | Andrei Dumitrescu | [42 empty] | missing |  |  | missing
Phase_3 | CS | TM227 | IAZ | Road Caransebes-Hateg(3) | TM078 Caransebes_RTC | Oltenia | 45 28 17.1 | 22 13 47.5 |  |  |  |  | 2101 | M | C+ | 2 | 2101 | [17 empty] | DIEKAT |  | @ | 2001-08-15 | 2001-09-20 |  |  | Adi |  |  | 2001-06-19 | [57 empty] | Timisoara | MW | [22 empty] | TM126 | JUPA | [27 empty] | Florin BELEA | Andrei Dumitrescu | [42 empty] | missing |  |  | missing
Phase_3 | CS | TM228 | OTELU ROSU | Road Caransebes-Hateg(3) | TM078 Caransebes_RTC | Oltenia | 45 31 16.7 | 22 22 19.5 |  |  |  |  | MAXITE | M | 1 | 2 | 2PBC | [17 empty] | DIEKAT |  | @ | 2001-08-15 | 2001-09-20 |  |  | Adi |  |  | 2001-06-19 | [57 empty] | Timisoara | MW | [22 empty] | TM227 | IAZ | [27 empty] | Florin BELEA | Andrei Dumitrescu | [42 empty] | missing |  |  | missing
Phase_3 | CS | TM229 | VAMA MARGA | Road Caransebes-Hateg(3) | YM229 Vama Marga_RTC | Oltenia | 45 30 26.6 | 22 30 22.3 |  |  |  |  | MAXITE | M | 1 | 2 | 2PBC | [17 empty] | DIEKAT |  | @ | 2001-08-15 | 2001-08-30 |  |  | Adi |  |  | 2001-06-19 | 2001-07-05 |  |  | 2001-07-05 |  |  |  |  | 2001-07-05 | [47 empty] | ML 15 E 1+0* | Timisoara | MW | [22 empty] | TM228 | OTELU ROSU | [27 empty] | Florin BELEA | Andrei Dumitrescu | [42 empty] | missing |  |  | missing
Phase_3 | CS | TM230 | SILOZ BIRDA | Timis county | TM069 Deta_RTC | Oltenia | 45 26 03.9 | 21 18 55.8 |  |  |  |  | 2101 | M | C+ | 2 | 2101 | [17 empty] | DUAL |  | @ | 2001-08-15 | 2001-09-20 |  |  | Adi |  |  | 2001-06-19 | [57 empty] | Timisoara | MW | [22 empty] | TM069 | DETA | [27 empty] | Florin BELEA | Andrei Dumitrescu | [42 empty] | missing |  |  | missing
Phase_3 | CS | TM231 | MAURENI | Timis county | TM069 Deta_RTC | Oltenia | 45 24 12.1 | 21 31 08.2 |  |  |  |  | 2101 | M | C+ | 2 | 2101 | [17 empty] | DUAL |  | @ | 2001-08-15 | 2001-09-20 |  |  | Adi |  |  | 2001-06-19 | [57 empty] | Timisoara | MW | [22 empty] | TM230 | SILOZ BIRDA | [27 empty] | Florin BELEA | Andrei Dumitrescu | [42 empty] | missing |  |  | missing
Phase_3 | CS | TM232 | BOCSA_1 | Timis county | YM232 Bocsa_1_RTC | Oltenia | 45 22 17.7 | 21 41 37.3 |  |  |  |  | 2101 | M | C+ | 2 | 2101 | [17 empty] | DUAL |  | @ | 2001-08-15 | 2001-09-20 |  |  | Adi |  |  | 2001-06-19 | [57 empty] | Timisoara | MW | [22 empty] | YM232 | BOCSA_1 | [24 empty] | new01 Bocsa-Resita_RTC |  |  | Florin BELEA | Andrei Dumitrescu | [42 empty] | missing |  |  | missing
Phase_3 | CS | TM233 | BOCSA_2 | Timis county | YM232 Bocsa_1_RTC | Oltenia | 45 22 37.2 | 21 46 39.9 |  |  |  |  | MAXITE | M | 1 | 2 | 2PBC | [17 empty] | DUAL |  | @ | 2001-08-15 | 2001-09-20 |  |  | Adi |  |  | 2001-06-19 | [57 empty] | Timisoara | MW | [22 empty] | TM232 | BOCSA_1 | [24 empty] | new01 Bocsa-Resita_RTC |  |  | Florin BELEA | Andrei Dumitrescu | [42 empty] | missing |  |  | missing
Phase_3 | CS | TM234 | DEVA_3 | Deva(3) | TM007 Deva_RTC | Banat | 45 51 54.2 | 22 54 20.3 |  |  |  |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [17 empty] | SVF |  | @ | 2001-08-15 | 2001-08-30 |  |  | Adi |  |  | 2001-06-25 |  |  |  | 2001-06-25 | [53 empty] | Timisoara | MW | [22 empty] | TM007 | DEVA_RTC | [24 empty] | new03 Deva-Timisoara |  |  | Florin BELEA | Andrei DUMITRESCU
Phase_3 | RS | TM235 | DEVA_4 | Deva(3) | TM007 Deva_RTC | Banat | 45 53 37 | 22 54 19.2 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | [17 empty] | DUAL |  | @ | 2001-08-15 | 2001-09-20 |  |  | Adi |  |  | 2001-07-05 | [56 empty] | N/A | Timisoara | RF | [22 empty] | TM006 | IULIU MANIU | [28 empty] | Andrei Dumitrescu | CSFT1802-REMOTE | TM006
Phase_3 | CS | TM236 | SEMENIC_DRTV | Caras Severin county | TM075 Resita_RTC | Oltenia | 45 10 55.9 | 22 03 15.6 |  |  |  |  | MAXITE | M | 1 | 2 | 2PBC | [17 empty] | DIEKAT |  | @ | 2001-08-15 | 2001-08-30 |  |  | Adi |  |  | 2001-06-19 | 2001-07-05 |  |  | 2001-07-06 |  |  |  |  | 2001-07-05 | [48 empty] | Timisoara | MW | [22 empty] | TM225 | RESITA_METEO | [27 empty] | Florin BELEA | Andrei Dumitrescu | [42 empty] | missing |  |  | missing
Phase_3 | CS | TM238 | CARASOVA | Caras Severin county | TM075 Resita_RTC | Oltenia | 45 11 47.2 | 21 51 08.5 |  |  |  |  | MAXITE | M | 1 | 2 | 2PBC | [17 empty] | DIEKAT |  | @ | 2001-08-15 | 2001-09-20 |  |  | Adi |  |  | 2001-06-19 | [57 empty] | Timisoara | MW | [22 empty] | TM236 | SEMENIC_DRTV | [27 empty] | Florin BELEA | Andrei Dumitrescu | [42 empty] | missing |  |  | missing
Phase_3 | CS | TM239 | ANINA_DRTV | Road Herculane-Anina | YM239 Anina_RTC | Oltenia | 45 05 05.2 | 21 51 36.3 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | [17 empty] | DIEKAT |  | @ | 2001-08-15 | 2001-08-30 |  |  | Adi |  |  | 2001-06-19 | [57 empty] | Timisoara | MW | [22 empty] | YM239 | ANINA_RTC | [27 empty] | Florin BELEA | Andrei Dumitrescu | [42 empty] | missing |  |  | missing
Phase_3 | CS | TM240 | GLOBUL CRAIOVEI | Road Herculane-Caransebes(9+1) | TM155 Baile Herculane_RTC | Banat | 44 59 12.7 | 22 15 10.3 |  |  |  |  | MAXITE | M | 1 | 2 | 2PBC | [17 empty] | DIEKAT |  | @ | 2001-08-15 | 2001-09-20 |  |  | Adi |  |  | 2001-06-19 | [57 empty] | Timisoara | MW | [22 empty] | TM122 | DOMASNEA | [27 empty] | Florin BELEA | Andrei Dumitrescu | [42 empty] | missing |  |  | missing
Phase_3 | CS | TM241 | BOZOVICI | Road Herculane-Anina | YM241 Bozovici_RTC | Oltenia | 44 55 41.6 | 22 01 13.9 |  |  |  |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [17 empty] | DIEKAT |  | @ | 2001-08-15 | 2001-09-20 |  |  | Adi |  |  | 2001-06-19 | 2001-07-05 |  |  | 2001-07-11 |  |  |  |  | 2001-07-05 | [47 empty] | ML 38 E 1+0 | Timisoara | MW | [22 empty] | YM241 | BOZOVICI_RTC | [27 empty] | Florin BELEA | Andrei Dumitrescu | [42 empty] | missing |  |  | missing
Phase_3 | CS | TM242 | ORAVITA | Road Oravita-Stamora Germana | YM242 Oravita_RTC | Oltenia | 45 01 47.7 | 21 41 30.8 |  |  |  |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [17 empty] | DIEKAT |  | @ | 2001-08-15 | 2001-09-20 |  |  | Adi |  |  | 2001-07-19 | [57 empty] | Timisoara | MW | [22 empty] | YM242 | ORAVITA_RTC | [27 empty] | Florin BELEA | Andrei Dumitrescu | [42 empty] | missing |  |  | missing
Phase_3 | CS | TM243 | GRADINARI | Road Oravita-Stamora Germana | YM242 Oravita_RTC | Oltenia | 45 07 26.5 | 21 35 03.6 |  |  |  |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [17 empty] | DIEKAT |  | @ | 2001-08-15 | 2001-09-20 |  |  | Adi |  |  | 2001-06-19 | [57 empty] | Timisoara | MW | [22 empty] | TM242 | ORAVITA | [27 empty] | Florin BELEA | Andrei Dumitrescu | [42 empty] | missing |  |  | missing
Phase_3 | CS | TM244 | POPAS CARAS-TIMIS | Road Oravita-Stamora Germana | YM242 Oravita_RTC | Oltenia | 45 12 03.2 | 21 31 12.2 |  |  |  |  | 2101 | M | C+ | 2 | 2101 | [17 empty] | DIEKAT |  | @ | 2001-08-15 | 2001-09-20 |  |  | Adi |  |  | 2001-06-19 | [57 empty] | Timisoara | MW | [22 empty] | TM243 | GRADINARI | [27 empty] | Florin BELEA | Andrei Dumitrescu | [42 empty] | missing |  |  | missing
Phase_3 | CS | TM245 | JAMU MARE | Road Oravita-Stamora Germana | TM069 Deta_RTC | Oltenia | 45 15 22.9 | 21 24 10.1 |  |  |  |  | 2101 | M | C+ | 2 | 2101 | [17 empty] | DIEKAT |  | @ | 2001-08-15 | 2001-09-20 |  |  | Adi |  |  | 2001-06-19 | [57 empty] | Timisoara | MW | [22 empty] | TM070 | STAMORA GERMANA | [27 empty] | Florin BELEA | Andrei Dumitrescu | [42 empty] | missing |  |  | missing
Phase_3 | CS | TM247 | NICOLINT | Road Oravita-Stamora Germana | YM242 Oravita_RTC | Oltenia | 44 56 10.4 | 21 34 03.3 |  |  |  |  | 2101 | M | C+ | 2 | 2101 | [17 empty] | DIEKAT* | [6 empty] | Adi* |  |  | 2001-06-19 | [57 empty] | Timisoara | MW | [22 empty] | TM242 | ORAVITA | [27 empty] | Florin BELEA | Andrei Dumitrescu | [42 empty] | missing |  |  | missing
Phase_3 | CS | TM248 | PIPIRIG | Caransebes | TM078 Caransebes_RTC | Oltenia | 45 25 19.9 | 22 13 20.1 |  |  |  |  | MAXITE | M | 1 | 2 | 2PBC | [17 empty] | SVF |  | @ | 2001-09-01 | 2001-09-30 |  |  | Adi |  |  | 2001-07-10 | [8 empty] | 2001-07-10 | [47 empty] | ML 38 E 1+0* | Timisoara | MW | [22 empty] | TM250 | INTERSECTIE | [27 empty] | Sorin UNTARU | Sorin UNTARU
Phase_3 | CS | TM249 | EUROFIAT | Caransebes | TM078 Caransebes_RTC | Oltenia | 45 24 13.2 | 22 13 38.9 |  |  |  |  | 2202 | M | C+C+C+ | 2/2/2 | 2202 | [17 empty] | SVF |  | @ | 2001-09-01 | 2001-09-30 |  |  | Adi |  |  | 2001-07-10 | [8 empty] | 2001-07-10 | [47 empty] | ML 23 E 1+0* | Timisoara | MW | [22 empty] | TM125 | VALEA TIMISULUI | [27 empty] | Sorin UNTARU | Sorin UNTARU
Phase_3 | CS | TM250 | INTERSECTIE | Caransebes | TM078 Caransebes_RTC | Oltenia | 45 24 59.1 | 22 11 32.6 |  |  |  |  | 2102 | M | C+C+C+ | 2/2/2 | N/A | [17 empty] | SVF |  | @ | 2001-09-01 | 2001-09-30 |  |  | Adi |  |  | 2001-07-10 | [8 empty] | 2001-07-10 | [47 empty] | ML 38 E 1+0* | Timisoara | MW | [22 empty] | TM249 | EUROFIAT | [27 empty] | Sorin UNTARU | Sorin UNTARU
Phase_2 | TM | XM184 | HALMAGIU_RTC | Road Oradea-Brad(11+1) | XM184 Halmagiu_RTC | Transilvania | 46 16 07.3 | 22 35 46.6 | 46 16 07.3 | 22 35 46.6 | Romtelecom Halmagiu | Romtelecom(Colf Ioan tel. 093/088806) | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | [6 empty] | N/A | B | 15 | suport zid | Room/Rack19" | SVF | OK | SVF | 2001-05-25 | 2001-06-26 | YesV | 2001-07-03 | Adi |  | 2001-06-12 |  |  |  | 2001-05-07 | 2001-05-07 | [9 empty] | N/A | N/A | N/A | N/A | N/A |  | Yes |  | CW NOT READY |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A | Timisoara | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | [5 empty] | XC50101 | [6 empty] | 6m/indoor |  |  | BSC31 | BSC TIMISOARA | N/A | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | 30N01 Halmagiu-Curtici |  | 2001-06-28 | Florin BELEA | Cosmorom | [42 empty] | Site Near=Insertion Point
Phase_3 | CS | XV145 |  | Road Gheorghieni-Reghin | XV145 Toplita_RTC | Transilvania | [38 empty] | 2001-07-12 | [57 empty] | Brasov | [52 empty] | Petrica BURGHIU | Calin ACHIM
Phase_2 | TM | YJ096 | TEACA_RTC | Road Bistrita-Tg.Mures(4+1) | YJ096 Teaca_RTC | Transilvania | 46 54 34.1 | 24 30 23.3 | 46 54 34.1 | 24 30 23.3 |  |  | N/A | N/A | N/A | N/A | N/A | [17 empty] | PROTELCO | OK | ESROM | 2001-05-24 | 2001-06-22 | YesV | 2001-07-13 | Andrei | [5 empty] | N/A | [18 empty] | CW NOT READY |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A | Tg. Mures | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | 2U-3 | [14 empty] | BSC32 | BSC ORADEA | N/A | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A |  |  |  | SORIN UNTARU | Cosmorom | [42 empty] | Site Near=Insertion Point
Phase_3 | TM | YJ231 | BLAJ_RTC | Road Copsa Mica-Teius(3) | CJ043 Alba Iulia_RTC | Transilvania | 46 10 37 | 23 54 57.5 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | [17 empty] | DUAL |  | DUAL | 2001-07-23 | 2001-08-10 |  |  | Andrei |  |  | 2001-06-25 | 2001-07-05 |  |  | 2001-06-25 |  |  |  |  | 2001-06-25 | [47 empty] | N/A | Cluj | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | [15 empty] | CJ043 | ALBA IULIA_RTC | N/A | N/A |  |  | N/A | [10 empty] | N/A | N/A | N/A |  |  | N/A |  |  |  | new01 Blaj-Alba Iulia+ new Alba Iulia-Cluj |  |  | Florin BELEA | N/A
Phase_2 | TM | YM096 | VALEA LUI MIHAI_RTC | Road Oradea-Satu Mare(16+3) | YM096 Valea lui Mihai | Banat | 47 30 34 | 22 09 16 | 47 30 34 | 22 09 16 | Romtelecom Valea lui Mihai | Romtelecom/ | N/A | N/A | N/A | N/A | N/A | [12 empty] | N/A | B |  | Catarg existent | Room | [13 empty] | N/A | N/A |  | N/A | N/A |  |  |  | 2001-03-14 | ICOM | SVF | N/A | N/A | 2001-03-14 | N/A | N/A |  |  | N/A | 2001-04-11 | 2001-04-11 | 2001-04-11 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Oradea | FO | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 50096 | [8 empty] | 1 | BSC32 | BSC ORADEA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2001-03-07 | Cosmorom | Cosmorom | [42 empty] | Site Near=Insertion Point
Phase_2 | TM | YM145 | ILIA_RTC | Road Arad-Deva(13+3) | YM145 Ilia_RTC | Banat | 44 55 55.5 | 22 39 25.1 | 44 55 55.5 | 22 39 25.1 | Romtelecom Ilia | Romtelecom/ | N/A | N/A | N/A | N/A | N/A | [12 empty] | N/A | B | 13.3 |  | N/A | SVF | OK | SVF | 2001-03-26 | 2001-03-29 | YesV | 2001-06-06 | Andrei | 2001-04-06 | 2001-06-14 |  |  |  | N/A | 2001-03-20 |  | N/A | 2001-03-27 |  |  |  | 2001-03-27 | ICOM | ICOM | N/A | N/A | 2001-03-26 | N/A | N/A |  | Yes | N/A | 2001-04-04 | 2001-04-04 | 2001-04-04 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A | Timisoara | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | 2U-3 |  |  |  | N/A | 50145 | [6 empty] | 2/indoor |  | 1 | BSC31 | BSC TIMISOARA | N/A | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A |  | 2001-03-31 | Denis CIUCU | Cosmorom | [42 empty] | Site Near=Insertion Point
Phase_3 | TM | YM232 | BOCSA_1_RTC | Timis county | YM232 Bocsa_1_RTC | Oltenia | 45 22 38.6 | 21 43 21.4 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | [17 empty] | DUAL |  | @ | 2001-08-15 | 2001-08-30 |  |  | Adi |  |  | 2001-06-19 | [56 empty] | N/A | Timisoara | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | [5 empty] | 50232 | [9 empty] | BSC31 | BSC TIMISOARA | N/A | N/A |  |  | N/A | [10 empty] | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | new01 Bocsa-Resita_RTC |  |  | Florin BELEA | Andrei Dumitrescu | [42 empty] | Site Near=Insertion Point
Phase_3 | TM | YM239 | ANINA_RTC | Road Herculane-Anina | YM239 Anina_RTC | Oltenia | 45 05 46.6 | 21 51 23.1 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | [17 empty] | DIEKAT |  | @ | 2001-08-15 | 2001-08-30 |  |  | Adi |  |  | 2001-07-06 | [56 empty] | N/A | Timisoara | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | [15 empty] | BSC31 | BSC TIMISOARA | N/A | N/A |  |  | N/A | [10 empty] | N/A | N/A | N/A | N/A | N/A | N/A | [6 empty] | Florin BELEA | Andrei Dumitrescu | [42 empty] | Site Near=Insertion Point
Phase_3 | TM | YM241 | BOZOVICI_RTC | Road Herculane-Anina | YM241 Bozovici_RTC | Oltenia | 44 55 38.2 | 22 00 08.1 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | [17 empty] | DIEKAT |  | @ | 2001-08-15 | 2001-08-30 |  |  | Adi |  |  | 2001-07-06 |  |  |  | 2001-07-11 | [52 empty] | N/A | Timisoara | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | [15 empty] | BSC31 | BSC TIMISOARA | N/A | N/A |  |  | N/A | [10 empty] | N/A | N/A | N/A | N/A | N/A | N/A | [6 empty] | Florin BELEA | Andrei Dumitrescu | [42 empty] | Site Near=Insertion Point
Phase_3 | TM | YM242 | ORAVITA_RTC | Road Oravita-Stamora Germana | YM242 Oravita_RTC | Oltenia | 45 01 58.1 | 21 41 19 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | [17 empty] | DIEKAT |  | @ | 2001-08-15 | 2001-09-20 |  |  | Adi |  |  | 2001-07-06 | [56 empty] | N/A | Timisoara | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | [15 empty] | BSC31 | BSC TIMISOARA | N/A | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [6 empty] | Florin BELEA | Andrei Dumitrescu | [42 empty] | Site Near=Insertion Point
Phase_2 | TM | YR121 | OLANESTI_RTC | Road Rm. Valcea-Olanesti(2+1) | YR121 Olanesti_RTC | Oltenia | 44 12 13.2 | 24 14 29.4 | 44 12 13.9 | 24 14 32.4 | Aleea Castanilor nr.1, Baile Olanesti | Romtelecom/Pecingine Sorin - sef centru RTC, 050/ 710 410 | N/A | N/A | N/A | N/A | N/A | [12 empty] | N/A | B | 10.5 | C0.9m | Room | PROTELCO | OK | IMSAT | 2000-11-14 | 2001-02-05 | YesV | 2001-03-30 | Mugur | [5 empty] | N/A | N/A |  | 2000-10-16 | 2000-11-01 | [6 empty] | N/A | N/A |  |  |  |  | Yes |  | CW CR120 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A | Craiova | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | 2U-3 |  |  |  | N/A | 40121 | 2001-07-10 | YES |  |  |  |  | 7/Indoor | 10/8p indoor | 1 | BSC31 | BSC TIMISOARA | N/A | N/A | [9 empty] | N/A | SVF | N/A | N/A | N/A | 2001-07-12 | 2001-07-13 | VLAD | N/A | N/A |  | N/A | N/A | 30N01 Rm. Valcea-Craiova |  |  | Cristian CROITOR | Cosmorom | [32 empty] | 113 | Olanesti | Vacea | [7 empty] | Site Near=Insertion Point
Phase_2 | TM | YR191 | CURTEA DE ARGES_RTC | Road Pitesti-Curtea de Arges(4+1) | YR191 Curtea de Arges_RTC | Muntenia | 45 08 34.8 | 24 40 34.8 | 45 08 34.8 | 24 40 34.8 | Str. Basarabilor nr.121, Romtelecom Curtea de Arges | Romtelecom/ | N/A | N/A | N/A | N/A | N/A | [12 empty] | N/A | B | [35 empty] | CW | [13 empty] | 0 | 0 | 0 | [17 empty] | 0 | N/A | Baneasa | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | [5 empty] | 40191 | [9 empty] | BSC21 | BSC BANEASA | N/A | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | 30N01 Curtea de Arges-Baneasa |  | 2001-06-27 | Petrica BURGHIU | N/A | [42 empty] | Site Near=Insertion Point
Phase_3 | TM | YV140 | GHEORGHIENI_RTC | Road Gheorghieni-M.Ciuc | YV140 Gheorghieni_RTC | Transilvania | 46 43 23.1 | 25 35 56.3 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | [27 empty] | 2001-07-12 |  |  |  | 2001-07-13 |  |  |  |  | N/A | [47 empty] | N/A | Brasov | FO | [22 empty] | BSC12 | BSC BRASOV | [27 empty] | Petrica BURGHIU | Calin ACHIM
Phase_2 | TM | YX138 | OLTENITA_RTC | Road Bucuresti-Oltenita(4+1) | YX138 Oltenita_RTC | Muntenia | 44 05 05 | 26 38 08 | 44 05 05 | 26 38 08 | Str. Mihai Eminescu nr.8 | Romtelecom/ | N/A | N/A | N/A | N/A | N/A | [12 empty] | N/A | B | 15.5 | T4m | Room | ROMPSAR | OK | ROMPSAR | 2000-11-01 | 2000-11-24 | YesV | 2000-11-27 | Dragos | 2000-11-27 | 2000-12-07 |  |  |  | N/A | 2000-10-04 |  | 2000-10-16 | 2000-10-30 | [6 empty] | N/A | N/A |  |  |  |  | Yes |  | CTR BX120 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A | Baneasa | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | [12 empty] | 15/Indoor |  |  | BSC21 | BSC BANEASA | N/A | N/A |  |  | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A |  |  |  | Cristian CROITOR | Cosmorom | [32 empty] | 18 | Oltenita | Calarasi | [7 empty] | Site Near=Insertion Point
Phase_3 | TMH | YX226 | FOLTESTI_RTC | Road Galati-Husi | YX226 Foltesti_RTC | Moldova | 45 44 35.8 | 28 03 45.7 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | [31 empty] | 2001-07-11 |  |  |  | Nu s-a stabilit solutia de transmisiuni (11iul01) | [48 empty] | N/A | Galati | FO | [22 empty] | BSC022 | BSC GALATI | [61 empty] | 130
Phase_1 | TM | YX616 | MIHAIL KOGALNICEANU_RTC | Road Buc-Slo-Con | YX616 Mihail Kogalniceanu_RTC | Dobrogea | 44 21 54.3 | 28 27 42.4 | 44 21 54.3 | 28 27 42.4 | Str. Calugareni, bl. TV 2, sc. B, com. Mihail Kogalniceanu, jud. Cta. + Posta Koigalniceanu | Private+Romtelecom/Fasie Constantin, 258561 | N/A | N/A | N/A | N/A | N/A | [8 empty] | N/A |  |  |  | N/A | B | 12 | T6m | ROOM | DIEKAT | OK | DIEKAT | OK | 2000-02-01 | YesV | OK | AUREL | OK | OK |  |  |  | 1999-12-09 | 1999-12-20 |  | 1999-12-20 | OK |  |  |  | N/A | ETR | N/A | N/A | N/A | N/A | N/A | N/A |  | Yes | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 0 | N/A | Constanta | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | 4U-1 |  |  | N/A | Indoor Comteck | 30616 | Phase_1 | [6 empty] | 2 perechi/50m | 1 | BSC13 | BSC CONSTANTA | N/A | N/A |  |  | N/A | [6 empty] | OK | OK | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A |  | OK | DAN | DAN | [32 empty] | 95 | Mihail Kogalniceanu | Constanta | [7 empty] | Site Near=Insertion Point
Phase_1 | TM | YX751 | CERNAVODA_RTC | Road Buc-Fet-Con | YX751 Cernavoda_RTC | Dobrogea | 44 20 31.4 | 28 02 16.0 | 44 20 31.4 | 28 02 16.0 | Romtelecom CERNAVODA, str. Rasaritului no 14 | Romtelecom/ | N/A | N/A | N/A | N/A | N/A | [8 empty] | N/A |  |  |  | N/A | B | 14.5 | C2m | ROOM | EL-MONT | OK | EL-MONT | OK | 2000-02-01 | YesV | OK | DRAGOS | OK | OK |  |  |  | OK | 1999-12-09 |  | 1999-12-09 | 1999-12-16 |  |  |  | 00:0009 | ETR | N/A | N/A | N/A | N/A | N/A | N/A |  | Yes | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 0 | N/A | Constanta | FO | N/A | N/A | N/A | N/A | N/A |  | N/A |  |  |  |  | Indoor Comteck | 30711 | Phase_1 | [7 empty] | 1 | BSC13 | BSC CONSTANTA |  | N/A |  |  | N/A | [6 empty] | OK | OK | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A |  | OK | SORIN UNTARU | SORIN UNTARU | [32 empty] | 75 | Cernavoda | Constanta | [7 empty] | Site Near=Insertion Point
Phase_3 | TM | YX829 | MAHMUDIA_RTC | Tulcea(5+1) | YX829 Mahmudia_RTC | Dobrogea | 45 10 35.7 | 28 48 25 | 45 10 35.7 | 28 48 25 | Sediul Romtelecom, str. Mahmudia | Romtelecom, dl. Cadar Aldan, tel. 092795504 | N/A | N/A | N/A | N/A | N/A | [6 empty] | N/A | N/A | N/A |  |  |  | N/A | B | 16 | S4m | Room/Rack19" | SVF | OK | CRIS-CORI | 2001-07-12 | 2001-07-25 | in exec |  | Bogdan |  |  | 2001-05-16 |  |  | N/A | 2001-05-16 |  | 2001-06-08 | 2001-06-14 |  |  | N/A |  |  |  | N/A |  | N/A | [10 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A | Galati | FO | N/A | N/A | N/A | N/A | N/A |  | N/A | [12 empty] | 12/indoor |  |  | BSC22 | BSC GALATI |  | N/A |  |  | N/A | [10 empty] | N/A | N/A | N/A |  |  | N/A | [6 empty] | Petrica BURGHIU | Tiberiu LICA | [33 empty] | Tulcea | Tulcea | [7 empty] | Site Near=Insertion Point
Phase_2 | TM | ZJ250 | RUSII MUNTI | Road Deda-Reghin(1+1) | CJ034 Reghin_RTC | Transilvania | 46 54 52 | 24 49 59.4 | 46 54 52 | 24 49 59.4 | Rusii Munti | Romtelecom/ | N/A | N/A | N/A | N/A | N/A | [12 empty] | 0 | TE | 45 |  |  | SVF | OK | SVF | 2001-07-01 | 2001-07-30 | in exec |  | Andrei |  |  |  | 2001-06-14 |  |  | 2001-07-13 | [17 empty] | CW |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | ML 15 E 1+0 | Tg. Mures | MW | 215 | 1.2 | 45/1.2 | [19 empty] | CJ034 | REGHIN_RTC | 35 | 31/1.2 | ML 15 E | [21 empty] | N/A |  | 2001-05-15 | Petrica BURGHIU | Cosmorom | [42 empty] | 2 |  |  | 2
Phase_2 | TM | ZM198 | SALASU DE SUS_RTC | Bazinul Petrosani(20) | TM197 Hateg_RTC | Transilvania | 45 30 39 | 22 57 14 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | [17 empty] | SVF | OK | SVF | 2001-07-10 | 2001-07-30 | in exec |  | Adi |  |  | 2001-06-20 | [56 empty] | ML 15 E 1+0 | Timisoara | MW | [22 empty] | TM196 | BURSUC | [27 empty] | SORIN UNTARU | N/A | [32 empty] | 500 | [9 empty] | missing |  |  | missing
Phase_2 | TM | ZR117 | COZIA_DRTV | Road Rm. Valcea-Sibiu(3+1) | CR116 Calimanesti_RTC | Oltenia | 45 19 02.9 | 24 20 30.7 | 45 19 04.7 | 24 20 22.3 | DRTv Cozia | Societatea Nationala de Radiocomunicatii - Calea Victoriei nr.31, sector 1, Bucuresti/Sef serviciu tehnic - Ing. I. Bunceanu, 01/ 400 16 57 | N/A | N/A | N/A | N/A | N/A | [12 empty] | N/A | TE | 70 |  | Room | PROTELCO | OK | IMSAT | 2000-12-13 | 2001-01-31 | YesV | 2001-03-28 | Mugur | 2001-04-06 | 2001-05-04 |  |  |  | N/A | 2001-07-16 |  | 2000-11-29 | 2000-12-12 |  |  |  | 2001-02-22 | ICOM | SVF | N/A | N/A | N/A | N/A | N/A |  | Yes |  | RBS 2101 CR115 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | ML 15 E 1+1 (PS) | Craiova | MW | 181 | 1.2 | 20 | 49 | 15/89h |  | 4x2/8 | 4U-1(TMR9202) |  |  |  | TMR 9202 | [10 empty] | CR116 | CALIMANESTI_RTC | 2 | 1.2 | 30/0.6 | 40 | 15/84h | [6 empty] | 20* | SVF | 2001-01-24 | 609 | 2001-02-21 | [8 empty] | N/A |  | N/A | Cristian CROITOR | COSMOROM | [32 empty] | 1598 | Cozia | Valcea | [7 empty] | 2 |  |  | 2
Phase_3 | TM | ZV001 | CRISTIANU_DRTV | Poiana Brasov | BV001 Brasov_CTA | Muntenia | 45 34 21 | 25 33 43 | 45 34 21 | 25 33 43 |  |  | N/A | N/A | N/A | N/A | N/A | [12 empty] | N/A | [18 empty] | 2001-05-22 | [22 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | ML 38 E 1+0 | Brasov | MW | [22 empty] | BV505 | POSTAVARU | [27 empty] | Cosmorom | N/A | [42 empty] | missing |  |  | missing
Phase_3 | TM | ZX052 | MANGALIA_DRTV | Road Constanta-Vama Veche(5) | BX052 Mangalia_RTC | Dobrogea | 43 48 38 | 28 34 50 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | [84 empty] | ML 23 E 1+0? | Constanta | MW? | [22 empty] | BX052 | MANGALIA_RTC | [24 empty] | N/A |  |  | Dragos BICIU | Leonard BANU
E.O.S.
1306