## Sheet1
Construction Start
Construction Finish
SITE EQUIPMENT INSTALATION CHECK LIST
Site Name: | Nicolae Titulescu |  | Last Design Revision |  | Site Type: | GreenField
Site Code: | 5606 |  | Revision No
I. WO SECTION | [8 empty] | RANK | Remedy done
WO completed:
Works | [5 empty] | YES | NO | NR | Failure level | Yes / No
CABINET(S)
1.Cabinet(s) position is(are) according to the design drawings | [5 empty] | x |  |  | 3
2.Cabinet(s) is(are) fixed securely | [5 empty] | x |  |  | 3
3. All cable inlets are sealed properly | [5 empty] | x |  |  | 3
4. Cabinet(s) is(are) connected to main ground | [5 empty] | x |  |  | 4
5. AC power cable(s) for outdooor cabinet(s) or DC power cable(s) for indoor is(are) installed correctly and labelled | [5 empty] | x |  |  | 2
6. Breaker(s) supplying the cabinet(s) are of correct value and labelled | [5 empty] | x |  |  | 3
7. PCM cable from FN DDF to cabinet is properly connected and labelled | [7 empty] | x | 2
8. RRU properly installed | [5 empty] | x |  |  | 3
9. Fiber optic from RRU to BBU properly installed and labelled | [5 empty] | x |  |  | 2
FEEDER AND JUMPER CONNECTION NEAR CABINET(S)
1.Feeders and jumpers are labeled correctly | [5 empty] | x |  |  | 2
2. Jumper clamps are securely tighten | [5 empty] | x |  |  | 2
3. Jumpers are correctly installed and connected to RBS (standard length:2m) | [5 empty] | x |  |  | 2
4. Splitters are mounted in the correct position, sealed and labelled | [7 empty] | x | 3
5. Splitters' mounting brackets are tight | [7 empty] | x | 2
6. Feeders are connected and sealed properly | [5 empty] | x |  |  | 3
7. Feeder grounding kits near cabinet(s) are installed correctly | [5 empty] | x |  |  | 2
8. Feeder entry into shelter/building is sealed properly | [5 empty] | x |  |  | 3
9.Feeders are grounded corectly to ground bar before shelter/building entry | [5 empty] | x |  |  | 3
10. Feeder cable is installed correctly (distance between fixing points:0.8m -7/8"; 1m-1 1/4"; 0.6m-1/2") | [5 empty] | x |  |  | 2
FEEDER AND TOP JUMPER CONNECTION
1.Feeders and jumpers are labeled correctly | [5 empty] | x |  |  | 2
2. Jumper clamps are securely tighten | [5 empty] | x |  |  | 2
3.Jumpers are correctly installed and connected to antennas (standard length:3m) | [5 empty] | x |  |  | 2
4. Feeders are connected and sealed properly | [5 empty] | x |  |  | 3
5. Feeder grounding kits near antenna(s) are installed correctly | [5 empty] | x |  |  | 3
ANTENNA INSTALLATION
1. Antennas type, position, orientation and downtilt are correct | [5 empty] | x |  |  | 4
2. Check all antennas' integrity and if there are no antenna visible imperfections | [5 empty] | x |  |  | 3
3. TMA properly installed | [7 empty] | x | 2
MINISHELTER / BBS / PP
1.Minishelter/BBS/PP is mounted in the correct position and fixed securely | [5 empty] | x |  |  | 3
2.Minishelter/BBS/PP surface is cleaned | [5 empty] | x |  |  | 2
3. Door(s) lock and retainer are working properly | [5 empty] | x |  |  | 3
4. All cable inlets are sealed | [5 empty] | x |  |  | 3
5. Minishelter/BBS/PP is connected to main ground | [5 empty] | x |  |  | 3
6. Voltage and battery parameters are correctly set | [5 empty] | x |  |  | 2
7.Minishelter/BBS/PP is suplying current to load equipment | [5 empty] | x |  |  | 3
8. Minishelter/BBS/PP DC distribution circuit breakers are labeled | [5 empty] | x |  |  | 2
9. Heating and ventilation / air conditioning are working properly | [5 empty] | x |  |  | 3
EXTERNALL ALARMS
1. Mains alarm is connected | [5 empty] | x |  |  | 3
2.Rectifier alarm alarm is connected | [5 empty] | x |  |  | 3
3. Fuse alarm is connected | [5 empty] | x |  |  | 3
4. Voltage alarm is connected | [5 empty] | x |  |  | 3
5. Generator started alarm is connected | [7 empty] | x | 3
6. Sum alarm is connected | [7 empty] | x | 3
7.Generator major alarm is connected | [7 empty] | x | 3
8. Air conditioning alarm is connected | [7 empty] | x | 3
9. Electrica main alarm is connected | [7 empty] | x | 3
10.TMA alarm alarm is connected | [7 empty] | x | 3
11. Fire alarm is connected | [5 empty] | x |  |  | 3
12. Temperature alarm is connected | [5 empty] | x |  |  | 3
13. Door alarm is connected | [5 empty] | x |  |  | 3
14. Tower light alarm is connected | [7 empty] | x | 3
15.Dehydrator alarm is connected | [7 empty] | x | 3
16. Generator low fuel alarm is connected | [7 empty] | x | 3
SITE ENVIRONMENT
1. Site area is cleaned | [5 empty] | x |  |  | 2
Other
Final cost estimate delivered | [7 empty] | x | 1
Earthing measurement bulletin delivered | [7 empty] | x | 2
VSWR Measurement delivered | [7 empty] | x | 2
Electrical file delivered (ATR, Contract, Bon miscare contor) | [7 empty] | x | 1
Access keys delivered to SAC engineer (3 pcs) | [7 empty] | x | 1
Construction book delivered to SAC | [7 empty] | x | 1
Total Failure level 4 |  |  | Site rejected
Total Failure level 3 |  |  | To remedy within 1 day
Total Failure level 2 |  |  | To remedy within 5 days
Total Failure level 1 |  |  | To remedy within 10 days
Grand Total
OBSERVATIONS | [6 empty] | REMEDY DONE?:
SIGNATURES
|  | NAME |  |  | SIGNATURE |  | DATE
SD ENGINEER |  |  |  | MIHALACHE George
SAC CONTRACTOR |  |  |  | Radcom